A C T I O N  P L A N

FOR THE IMPLEMENTATION

OF THE NATIONAL ANTI-CORRUPTION STRATEGY

FOR THE PERIOD 2013-2018

With the adoption of the National Anti-Corruption Strategy, the Republic of Serbia decided to build a systematic legal and institutional framework as necessary preconditions for efficient fight against corruption. The National Anti-Corruption Strategy is a medium-term policy document with objectives to be implemented in the next five years. The framework for the implementation of strategic objectives will be specified in the Action Plan which will be adopted no later than three months after adoption of the Strategy. The Action Plan will ensure a systematic oversight of the implementation of the Strategy and it represents a control mechanism used for control of effectiveness of the Strategy. The Action Plan will envisage specific measures and activities for the implementation of strategic objectives, periods, responsible entities and resources required for implementation. Also, it will define indicators for the execution of measures and activities used for the monitoring of their degree of realization, as well as indicators for the evaluation of successful achievement of set objectives. Since the Strategy and Action Plan are envisaged for the period of five years, it is necessary to periodically conduct an analysis and possibly amend both documents in order to harmonize them with existing social conditions. Each chapter of the Action Plan contains tables with defined anti-corruption measures, objectives, periods, required resources and competent authorities for the implementation of measures.

Appendix:

ACA – The Anti-Corruption Agency

Council – The Anti-Corruption Council

SAI - The State Audit Institution

EU - The European Union

EC - The European Commission

INTOSAI – The International Organization of Supreme Audit Institutions

Strategy - The  National Anti-Corruption Strategy for the period 2013-2018

OLAF – The European Anti-Fraud Office

GRECO - The Group of States against Corruption

RBA – The Republic Broadcasting Agency

IFC – The Internal Financial Control

SPOOC – The Special Prosecutor's Office for Organized Crime

UNCAC - The United Nations Convention against Corruption

3.1. POLITICAL ACTIVITIES

| The Action Plan for the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1. POLITICAL ACTIVITIES |  |  |  |  |  |  |  |
| 3.1.1 | Objective | Eliminate deficiencies in the legal framework and control of the financing of political activities and political entities |  |  |  |  |  |
|  | Indicator | The number of violations and untimely actions according to the Law on the Financing Political Activities reduced by 30% by 2017 (in comparison to 2012) |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.1.1 | Amending the Law on the Financing Political Activities to clearly set out and divide responsibilities of the ACA, SAI and other authorities in the procedure of control of political activities and political entities, and to precisely determine obligations and mechanisms for transparent financing of political entities | Formulate and submit draft amendments to the law | 6 months | The ministry competent for finance and the ministry competent for justice | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) | The working group should include representatives of political entities and local self-government authorities, the Standing Conference of Towns, representatives of provincial authorities. Take into account aspects of granting loans, NGOs' activities, mechanisms of reporting to the ACA |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 9 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.1.2 | Amending the Law on the State Audit Institution so that the audit program necessarily includes audit of the parliamentary political parties at the national level | Formulate and submit draft amendments to the law | 6 months | Legislative Committee of the RS | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 9 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.1.3 | Amending the Law on Tax Procedure and Tax Administration in order to introduce an obligation for the Tax Administration director to include providers of funds and other services to political entities in the annual or extraordinary tax audit plan, in accordance with the ACA report on the financing of political activities and political entities | Formulate and submit draft amendments to the law | 6 months | The Ministry competent for finance | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 9 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.1.4 | Building capacities of the Anti-Corruption Agency for the process of control of financing of political activities | Conduct the needs analysis | 6 months | The Anti-Corruption Agency | A report on the needs analysis | Not required |  |
|  |  | Change the systematization and employ the number of qualified personnel that matches the needs in the analysis | 15 months |  | The number and structure of the qualified personnel is matching the needs analysis | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Educate employees | permanent |  | Reports on education, seminar program and evaluation, control of participants | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Provide equipment | 15 months |  | The equipment matches the needs | In accordance with the needs analysis |  |
| 3.1.1.5 | Building SAI capacities for efficient audit of the parliamentary political parties | Employ an adequate number of qualified personnel | 12 months | The Ministry competent for finance and the SAI | The number and structure of the qualified personnel matches the needs | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Educate employees | permanent |  | The employees conducting an audit are trained | In accordance with the needs analysis and training program(for each training 300.000) |  |
|  |  | Provide equipment | 24 months |  | The equipment matches the needs | In accordance with the needs analysis |  |
| 3.1.1.6 | Building capacities of all public authorities applying the Law on the Financing Political Activities and other regulations in this field, and processing cases of its infringement | Conduct an analysis on what public authorities implement the law and on their capacities | 12 months | The Anti-Corruption Agency | The needs analysis is conducted | Not required |  |
|  |  | Employ the number of qualified personnel that matches the needs in the analysis | 36 months | The public authorities from the list of the needs analysis | The number and structure of the qualified personnel matches the needs | In accordance with the needs analysis (at least 50.000 gross per employee) | The Broadcasting Law, the Law on Advertizing |
|  |  | Educate employees | permanent | The Anti-Corruption Agency | The employees applying the law are trained | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Provide equipment in accordance with the needs analysis | 36 months | The Government of the Republic of Serbia | The equipment matches the needs | In accordance with the needs analysis |  |
| 3.1.1.7. | Establishing mechanisms of continuous training and providing information to the entities obliged to act in accordance with the Law on the Financing Political Activities | Conduct an analysis of the need for training | 2 months | The Anti-Corruption Agency | The analysis of the needs for training is conducted | Not required |  |
|  |  | Develop the training program | 12 months |  | The training program is developed on the basis of the analysis | Not required |  |
|  |  | Educate | 4 years from amendments to the Law |  | All political entities obliged to submit annual financial statements received training | In accordance with the needs analysis (for each training 300.000) |  |

| The Action Plan for the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 POLITICAL ACTIVITIES |  |  |  |  |  |  |  |
| 3.1.2 | Objective | Eliminate deficiencies in the legal framework in the field of conflict of interest, and control of property and incomes of public officials. |  |  |  |  |  |
|  | Indicator | Adopted amendments to the legal framework for the conflict of interest, control of property and incomes of public officials in their content match the measures envisaged by this objective. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.2.1 | Amending the Law on the Anti-Corruption Agency in order to make a distinctions and clearly define terms of accumulation of functions (to prevent performance of several public functions that are in mutual conflict of interest) and the conflict of interest (to eliminate private interest in exercising public powers) | Develop draft amendments to the law that clearly define the term of accumulation of functions, actions for preventing performance of more than one public function, legal exceptions, the term of a public official, his/her rights and obligations, as well as the obligation of adopting a by-law containing a range of public functions. In addition, the draft should govern the term of conflict of interest, and define prohibited behavior of public officials in terms of the prohibition of conflict of a private interest with a private one | 12 months | The Anti-Corruption Agency and the Ministry competent for justice | The draft Law on Amendments to the Law on the Anti-Corruption Agency is developed | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | The bill is submitted to the National Assembly | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.2.2 | Adopting a by-law containing a range of public functions | Establish a working group for developing a by-law | 19 months | The Anti-Corruption Agency | A by-law containing a range of public functions is adopted | Not required | Mandatory involvement of the Ministry of Justice and Public Administration and NGOs |
|  |  | Adopt the by-law | 24 months |  |  |  |  |
| 3.1.2.3 | Amending the Law on the Anti-Corruption Agency in order to increase the number of the parties obliged to submit property reports, data for the control of property cards, and to authorize ACA to carry out emergency property controls | Develop draft amendments to the law in order to increase the number of parties for which a public official is obliged to submit a property report, impose the obligation of submission of documents and information on banks, financial organizations and companies, and envisage an obligation of submission of an emergency report in specific circumstances, as well as the Agency's power to carry out emergency property controls that are not part of the annual audit plan | 12 months | The Anti-Corruption Agency and the Ministry competent for justice | The draft Law on Amendments to the Law on the Anti-Corruption Agency is developed | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | The bill is submitted to the National Assembly | Not required |  |
|  |  | Adopt the law on amendments | 17 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.2.4 | Creating an efficient infrastructure for the cooperation between the ACA and competent institutions for the purposes of control of data in submitted property cards | The ACA conducts an analysis about what data are necessary for efficient control of the property and incomes of public officials and what institutions have access to such data | 6 months | ACA | An analysis of data necessary for efficient control of the property and incomes of public officials and competent institutions is conducted | Not required |  |
|  |  | Conclude memorandums of cooperation with competent institutions that have access to the required information used for determining the manner of cooperation and contact points (teams) that will be obliged to timely submit required data to the ACA | 12 months | ACA and competent institutions defined after the analysis | The memorandum of cooperation with competent institutions having access to required information is concluded | Not required |  |
|  |  | Enable for the ACA access to the Tax Administration data about UTIN to the extent necessary for the control of data about the property cards and financing of political parties | 6 months after establishment of the UTIN system | The Tax Administration | ACA has access to the UTIN database | In accordance with the needs analysis | The activity may be carried out only after establishment of the UTIN system (see 3.2.1.2) |
| 3.1.2.5 | Educating employees in the public administration/ political parties about the application of new provisions | Develop a training program | 24 months | ACA | The training program is developed | Not required |  |
|  |  | Organize and conduct training | permanent |  | Training is conducted according to the program | In accordance with the needs analysis (for each training 300.000) |  |
| 3.1.2.6 | Establishing a proactive approach to the control of property cards of public officials and reviewing conflict of interest | Establish examples of good practice of proactive actions | permanent | ACA | The number of proactive controls of property cards | Not required |  |
| 3.1.2.7 | Conducting a campaign for informing the public about the implementation of provisions | Organize and conduct campaigns | 36 months | ACA | Campaigns are organized and conducted | 5.000.000 |  |

| The Action Plan for the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 POLITICAL ACTIVITIES |  |  |  |  |  |  |  |
| 3.1.3 | Objective | Adopt an effective legal framework which shall regulate lobbying and participation of the public in the process of adoption of regulations |  |  |  |  |  |
|  | Indicator | The Law governing the lobbying process is adopted. Until the end of 2017, 70% of adopted laws, and decisions of the assemblies of the territorial autonomy and local self-government units, public hearings will be conducted in accordance with the Rules of Procedure governing organization and conducting of public hearings |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.3.1 | Establishing mechanisms which will ensure for interested parties and the public to participate in the process of adoption of a regulation at all levels, through amendments to the Law on the National Assembly, the Law on Public Administration, the Law on Local Self-Government, the Law on the Protector of Citizens and the Law on the National Bank | Conduct an analysis of the existing legal framework to determine opportunities for improving participation of the public | 6 months | The Republic Committee for Legislation | A report on conducted analysis | Not required |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law, on the basis of the conducted analysis | 9 months | The Government of the RS | A proposal of amendments to the law is submitted to the NA | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The law is adopted by the NA | Not required |  |
|  |  | Harmonize the Statute/Rules of Procedure of local self-government units | 18 months | The speakers of the assemblies of local self-government units | Statutes are harmonized | Not required |  |
|  |  | Adopt amendments to the Rules of Procedure of the Government specifying the criteria and ways of conducting public hearings | 3 months from the date of adoption of the law | The Government of the RS | A proposal of amendments to the Rules of Procedure of the Government is submitted | Not required |  |
|  |  | Adopt the Rules of Procedure for organizing and conducting public hearings | 3 months from the date of adoption of the law | The Republic Secretariat for Legislation | The Rules of Procedure are adopted | Not required |  |
| 3.1.3.2 | Adopting an effective legal framework for lobbying and access of the public to all the information about the lobbying occurring in public authorities | Formulate and submit the draft law | 12 months | The Ministry competent for public administration | The draft law is submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit the bill to the National Assembly | 15 months | The Government of the RS | The bill is submitted | Not required |  |
|  |  | Adopt the law on amendments | 20 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.3.3 | Adopting amendments to the Law on the Anti-Corruption Agency and the Rules of Procedure of the Government to determine the obligation of the Government of the RS to give proposals of laws on an opinion of the ACA, as well as to provide an opinion (if submitted within 10 days) attached to the proposed law when submitting it to the National Assembly | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the RS | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments | 20 months | The National Assembly | The law is adopted by the NA | Not required |  |
|  |  | Amend the Rules of Procedure of the Government of the RS in accordance with the Law | 21 months | The Government of the RS | Amendments to the Rules of Procedure of the Government of the RS are made | Not required |  |
| 3.1.3.4 | Conducting a campaign for informing the public about the mechanisms of participation in the process of adoption of regulations at all levels | Organize and conduct campaigns | 24 months | ACA | Campaigns are organized and conducted | 5.000.000 | Establish cooperation with the Standing Conference of Towns and Municipalities and CSO |

| The Action Plan for the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 POLITICAL ACTIVITIES |  |  |  |  |  |  |  |
| 3.1.4. | Objective | Determine clear criteria for nomination, selection and dismissal, as well as for evaluation of results of work of directors of public enterprises |  |  |  |  |  |
|  | Indicator | The analysis conducted using the method of random sampling (ACA, ACC, CSO, etc.) shows that public authorities consistently apply adopted criteria and procedures in the appointment, dismissal and evaluation of work of directors of public companies. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.4.1 | Amending the Company Law in order to clearly determine objective criteria for the appointment, dismissal and method of evaluation of work of directors at all levels of the government, and introducing mechanisms of accountability for consistent implementation | Develop draft amendments to the law to determine clear and objective criteria on the basis of which a competent ministry shall propose a candidate to the commission, as well as criteria on the basis of which the commission shall make the final selection of candidates fulfilling all the prescribed requirements. In addition, set objective criteria for the evaluation of work of directors and for their dismissal | 24 months | The Ministry competent for the economy | Draft amendments to the law are developed | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) | Considering that this is a new a law, effects of corruption can be better understood only after some time of application of the Law. For this reason, a longer period of time is left for discussion about and inclusion of experience resulting from the application of the Law. |
|  |  | Submit a proposal to the National Assembly of amendments to the law, on the basis of the conducted analysis | 26 months | The Government of the RS | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments | 28 months | The National Assembly | The law is adopted by the NA | Not required |  |

| The Action Plan for the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 POLITICAL ACTIVITIES |  |  |  |  |  |  |  |
| 3.1.5. | Objective | Adopt provincial and local anti-corruption action plans whose implementation shall be supervised by standing working bodies of the assemblies of local self-government units and autonomous province |  |  |  |  |  |
|  | Indicator | Consistent implementation of conclusions of provincial and local assemblies adopted on the basis of annual reports of standing working bodies of the assembly on the implementation of provincial and local anti-corruption action plans |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.5.1 | Developing models of the anti-corruption action plan for local self-government units and the autonomous province | Conduct an analysis of occurring forms of corruption at the local and provincial level | 6 months | The Anti-Corruption Agency | The analysis is conducted and the most common forms of corruption at the local level are defined | Not required | Consult NGOs, the Standing Conference of Towns and Municipalities, experts in this field |
|  |  | Create models of the anti-corruption action plan at the local and provincial level | 10 months | The Anti-Corruption Agency | Models of the anti-corruption action plan are developed at the local and provincial level | Not required | The models are a framework of minimum requests that can be met by all local self-government units |
| 3.1.5.2 | The assemblies of the autonomous province and local self-government units adopted the anti-corruption action plan for the autonomous provinces and local self-government units | Develop a proposal of the anti-corruption action plan for local self-government units and the provincial autonomy | 15 months | Heads of administrations of all local self-government units and the governments of the autonomous provinces | The anti-corruption action plan for local self-government units and the autonomous province is developed using the model made by the ACA | Not required | Take into account the models developed by the ACA |
|  |  | Submit a proposal of the anti-corruption plan to the assemblies of the local self-government unit and the autonomous province | 17 months | All municipal and city mayors and prime ministers of the autonomous provinces | A proposal of the anti-corruption action plan is submitted to the assemblies of local self-government unit and the autonomous province | Not required |  |
| 3.1.5.3 | Amending the Law on Local Self-Government/Rules of Procedure of the AP assembly in order to bind the assemblies of local self-government units and the autonomous province, to establish a standing working body of the assembly competent for the supervision of the implementation of the provincial and local anti-corruption action plan | Formulate and propose amendments so as to establish a standing working body of the assemblies of local self-government units and the autonomous province consisting of aldermen, or provincial deputies, so that the majority makes the representatives of the opposition, and that the sessions are open for the public | 10 months | The Ministry competent for regional development and local self-government/the speaker of the assembly of the autonomous province | A standing anti-corruption working body in the assemblies of the autonomous province and local self-government units is established | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 12 months | The Government of the RS | A proposal of amendments to the law is submitted to the National Assembly | Not required |  |
|  |  | Adopt the law on amendments | 14 months | The National Assembly | The law is adopted by the NA | Not required |  |
| 3.1.5.4 | Educating aldermen/ provincial deputies (members of the standing working body, but also other members) about anti-corruption mechanisms, methods and importance of the supervision of implementation of the provincial and local anti-corruption action plan | Develop the training program | 18 months | All municipal and city mayors and prime ministers of the autonomous provinces | The training program is developed | Not required | Establish cooperation with the ACA, Standing Conference of Towns and Municipalities and CSO |
|  |  | Organize and conduct training | permanent |  | Training is conducted according to the program | In accordance with the needs analysis (for each training 300.000) |  |
| 3.1.5.5 | Conducting a campaign for informing the citizens about the mechanisms of the provincial and local anti-corruption action plan | Organize and conduct campaigns | 24 months | All municipal and city mayors and prime ministers of the autonomous provinces | Campaigns are organized and conducted | 10.000.000 | Establish cooperation with the ACA, Standing Conference of Towns and Municipalities and CSO |

3.2. PUBLIC FINANCE

3.2.1. Public revenues

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.1.1. | Objective | Fully develop the e-Tax system and regularly update the data. |  |  |  |  |  |
|  | Indicator | The percentage of tax returns submitted by the е-Tax system. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.1.1.1 | Building Tax Administration capacities for efficient implementation of the е-Tax system | Conduct an analysis of the required number and professions of persons for efficient operation of the system | 12 months | The Ministry competent for finance | The needs analysis is conducted | Not required |  |
|  |  | Employ personnel in accordance with the needs analysis | 24 months |  | The number and structure of personnel matches the needs | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
| 3.2.1.1.2 | Professional training of employees working in the Tax Administration in using the е-Tax system | Develop a professional training program and instruction manuals | 6 months | The Tax Administration, the Ministry competent for finance | Professional training program and instruction manuals | 5.000.000 |  |
|  |  | Conduct professional training of employees | permanent |  | Professional training is organized and conducted | In accordance with the needs analysis (for each training 300.000) |  |
| 3.2.1.1.3 | Provide technical requirements for the е-Tax system | Provide technical requirements and equipment in accordance with the previously conducted needs analysis | 24 months | The Tax Administration, the Ministry competent for finance | Provision of necessary technical requirements and equipment in accordance with the previously conducted needs analysis | In accordance with the needs analysis |  |
| 3.2.1.1.4 | Conducting a campaign for informing the citizens about the existence, operation and method of use of the е-Tax system | Organize and conduct campaigns | permanent | The Tax Administration, the Ministry competent for finance | Campaigns are organized and conducted | 5.000.000 |  |
| 3.2.1.1.5 | Ensuring regular data entry and update | Control data updating, system operation and elimination of any technical deficiencies | permanent | The Tax Administration, the Ministry competent for finance | The number of controls of operability and accuracy of the е-Tax system | 60.000 monthly |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.1.2. | Objective | Establish a legal and institutional framework for the implementation of a system for a unique tax identification number for natural persons and legal entities |  |  |  |  |  |
|  | Indicator | The number of issued uniform tax identification numbers. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.1.2.1 | Adopting the law that governs the unique tax identification number system | Analyze records of persons and personal incomes and of the model of connection with UTIN | 12 months | The Ministry of Finance (MF) and Tax Administration | The analysis is conducted | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Formulate and propose a law in accordance with the analysis | 24 months | The Ministry of Finance and Economy | The draft law is submitted to the Government |  |  |
|  |  | Submit the proposed law to the NA | 26 months | The Government of the Republic of Serbia | The proposed law is submitted to the NA | Not required |  |
|  |  | Adopt the proposed law | 28 months | The National Assembly | The law is adopted | Not required |  |
| 3.2.1.2.2 | Conducting professional training of employees in new solutions of the law before its enforcement | Develop a training program and manuals | until enforcement of the law | MF and Tax Administration | A professional training program is developed | 5.000.000 |  |
|  |  | Organize and conduct training |  |  | Training is organized and conducted | In accordance with the program |  |
| 3.2.1.2.3 | Conducting a campaign for informing the citizens about the UTIN | Organize and conduct campaigns | permanent | MF and Tax Administration | Campaigns are organized and conducted | 5.000.000 |  |
| 3.2.1.2.4 | Entering provisions on the method of use of the UTIN in the law governing prohibition of conflict of interest in public administration | Develop a model of use of the UTIN for the purposes of control of property cards of administrative officers and public officials | 12 months | MF and Tax Administration, ACA | The legal framework for the use of the UTIN in the control of property cards is established | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Organize cooperation between the Tax Administration, ACA and public authorities, or holders of public authorizations. Coordinate using the measure 3.2.1.2.1 (and adoption of the Law on Conflict of Interest) |
|  |  | Formulate and propose amendments to the law | 2 months after the entry into force of the law on the UTIN | MF and Tax Administration | Draft amendments to the law are submitted to the Government |  | The period for harmonization of the Law on UTIN and the law governing prevention of conflict of interest may be subject to a change due to the time of adoption of these laws |
|  |  | Submit a proposed law on amendments to the NA | 2 months after the entry into force of the law on the UTIN | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted to the NA | Not required |  |
|  |  | Adopt the proposed law | 4 months after the entry into force of the law on the UTIN | The National Assembly | The law is adopted | Not required |  |
| 3.2.1.2.5 | Amending the Law on the Financing Political Activities in order to regulate the method of use of the UTIN in a tax audit of providers of financial and other services to political entities | Develop a model of use of the UTIN for the purposes of control of providers of financial and other services to political entities | 12 months | MF, Tax Administration, ACA | The legal framework for the use of the UTIN in the control of property cards is established | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Organize cooperation between the Tax Administration, ACA and public authorities, or holders of public authorizations. Coordinate using the measure 3.2.1.2.1. |
|  |  | Formulate and propose amendments to the law | 2 months after the entry into force of the law on the UTIN | MF and Tax Administration | Draft amendments to the law are submitted to the Government |  |  |
|  |  | Submit a proposed law on amendments to the NA | 3 months after the entry into force of the law on the UTIN | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted to the NA | Not required |  |
|  |  | Adopt the proposed law | 4 months after the entry into force of the law on the UTIN | The National Assembly | The law is adopted | Not required |  |
| 3.2.1.2.6 | Educating persons about the use of the UTIN for control of property cards and providers of services to political entities | Develop a training program and manuals | until the enforcement of the law | MF and Tax Administration, ACA, SAI | A professional training program is developed | 5.000.000 |  |
|  |  | Organize and conduct training |  |  | Training is organized and conducted | In accordance with the needs analysis (for each training 300.000) | If necessary, conduct training after the entry into force of the law |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.1.3 | Objective | Identify and eliminate any deficiencies in the legal framework for the customs system conductive to corruption |  |  |  |  |  |
|  | Indicator | Adopted amendments to the legal framework in the field of customs match in their content to the measures envisaged in this objective. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.1.3.1 | Amending the legal framework in order to eliminate detected deficiencies conductive to corruption | Develop a methodology for the analysis of effects on corruption | 2 months | ACA | The methodology is developed and accessible | Not required |  |
|  |  | Conduct an analysis of customs regulations in terms of risks of corruption | 14 months | The Customs Administration, MoI | The Ministry of Interior adopted a decision on establishing a working group; the analysis is conducted | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Formulate and submit draft amendments to the law in accordance with the analysis | 20 months | The Customs Administration, MoI | Draft amendments to the law is submitted to the Government |  |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 22 months | The Government of the RS | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt a proposal of amendments to the law | 23 months | The National Assembly | The law is adopted | Not required |  |
| 3.2.1.3.2 | Adopting and amending by-laws in accordance with the analysis and ensuring their consistent application | Review operating instructions for customs inspections at border crossings, adopt a by-law governing operation of customs offices, operation of the Sector for Customs Enforcement Control, operation of the Additional Control Department, operation of the Internal Control Department, operation of the IT Sector, adopt a by-law envisaging a precise procedure for the control of access to information | 25 months | The Customs Administration, MF | By-laws are harmonized with laws | Not required | Prescribe an obligation that every access to the system and user accounts by an administrator shall be made solely on the basis of a written order of a superior; arrange a longer period of time in which the employees who attend courses would have to spend working in the Customs Administration, as well as a provision on monetary compensation in case of breach of the obligation |
| 3.2.1.3.3. | Educating employees about new provisions of the law | Develop a training program | until the enforcement of the law | MF, Customs Administration, ACA | A training program is developed | Not required |  |
|  |  | Organize and conduct training |  |  | Training is organized and conducted | In accordance with the needs analysis (for each training 300.000) |  |
| 3.2.1.3.4 | Improving the Customs Administration information system | Provide technical equipment and qualified staff | 24 months | The Customs Administration, MoI | Technical equipment and staff meet the needs | In accordance with the needs analysis |  |
|  |  | Establish a system for the exchange of information with customs services in other countries | permanent |  | The number of countries with whom information is exchanged | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.1.4 | Objective | Establish efficient control of application of customs regulations |  |  |  |  |  |
|  | Indicator | The number of investigations at the annual level conducted by the anti-corruption control unit. The number of submitted disciplinary, misdemeanor and criminal charges at the annual level. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.1.4.1 | Forming a new Division for Customs Enforcement Control within the Internal Control Department of the Customs Administration for the purposes of anti-corruption control and provision of evidence for disciplinary, misdemeanor and criminal proceedings | Amend or adopt by-laws for systematization and organization of the Division | 9 months | The Customs Administration and MF | By-laws are adopted | Not required |  |
|  |  | Employ the necessary number of qualified personnel | 15 months | The Customs Administration and MF | Systematization act | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Develop and implement a training plan of the Division of Customs Enforcement Control | permanent | The Customs Administration and MF | The number of training sessions | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Provide necessary technical and other equipment | 20 months | The Customs Administration and MF | Adequate technical equipment is provided | In accordance with the needs analysis |  |
| 3.2.1.4.2 | Forming "mobile units" within the Division for Customs Enforcement Control within the Internal Control Department of the Customs Administration for the purposes of carrying out direct customs controls inside the customs territory of Serbia | Amend the systematization act in order to systematize posts in line with the analysis | 9 months | The Customs Administration and MF | Posts for the "mobile unit" are envisaged by the systematization | Not required |  |
|  |  | Provide necessary technical and other equipment | 20 months |  | Adequate technical equipment is provided | In accordance with the needs analysis |  |
|  |  | Conduct training in efficient control methods | permanent |  | The number of training sessions | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | The Department supervises operation and keeps records of results of monitoring "mobile units" | permanent |  | A report on work of the Department | Not required |  |
| 3.2.1.4.3 | Establishing an effective Customs Administration on-call service for reception, recording and efficient processing of reports on irregularities in work of customs officers | Establish the Customs Administration Contact Center for submitting reports on irregularities in work of customs officers | 6 months | The Customs Administration and MF | The Contact Center is established | Not required |  |
|  |  | Ensure 24-hour operative duty of the Customs Administration Contact Center and acting upon reports | 6 months | The Customs Administration | The number of reports submitted to the Contact Center | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Conduct inspection on the basis of the data from obtained reports | permanent | The Customs Administration | The number of conducted inspections on the basis of the data from reports | In accordance with the needs (per diem - 3.000; petrol, technical equipment -1.000) |  |
|  |  | Create and regularly update records on reception of reports and actions upon reports | permanent | The Customs Administration | Records are updated | Not required |  |
|  |  | Develop a program and method of conducting a campaign, ensure related materials and media coverage to inform the citizens about the Contact Center | 12 months | The Customs Administration | The campaign is conducted and campaign materials created | 5.000.000 |  |
| 3.2.1.4.4 | Building capacities of the Internal Control Department | Conduct the needs analysis | 12 months | The Customs Administration | The needs analysis is conducted | Not required |  |
|  |  | Employ qualified personnel in accordance with the needs analysis | 24 months |  | Qualified personnel is employed in the number that matches the needs analysis | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Educate personnel | permanent |  | Education is organized and carried out | In accordance with the needs analysis (for each training 300.000) |  |
| 3.2.1.4.5 | Installing video surveillance in customs offices and at border crossings in the manner that will ensure full coverage of facilities, with a centralized signal recorder in the Customs Administration and with an option to access video surveillance of any facility in real time | Adopt a by-law that would govern video surveillance of the Customs Administration and its regional organizational units and handle collected data in accordance with legal protection of personal data | 6 months | The Customs Administration and MF | The by-law regulates video surveillance | Not required |  |
|  |  | Implement the pilot project for the installation of centralized video surveillance in selected customs offices and border crossings | 2 years | The Customs Administration | The project is implemented | At least 50.000.000 |  |
|  |  | Install video surveillance in all customs offices and at all border crossings | 5 years |  | All customs offices and border crossings have video surveillance | At least 50.000.000 |  |
| 3.2.1.4.6 | Building capacities and establishing regular control of the Audit Department of the Customs Administration in administrative and misdemeanor proceedings | Conduct an analysis of the required number and structure of persons, as well as opportunities for incentives to work at these posts | 3 months | The Customs Administration | The needs analysis is conducted | Not required | Cases in which parties' requests are approved should be more often the subject of control; deviations from the order of receipt are possible only with items that due to their nature require urgency (e.g. perishable goods, goods whose import and transit is forbidden, etc.); more strict analysis and control of requests for the initiation of misdemeanor proceedings |
|  |  | Change the systematization, employ and train persons in accordance with the analysis | 12 months | The Customs Administration | Qualified personnel is employed in the number that matches the needs analysis | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Develop an annual plan with the number of controls exceeding the number in 2012 | permanent | The Customs Administration | The number of annual controls | Not required |  |

3.2.2. Public expenditures

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 ЈАВНЕ ФИНАНСИЈЕ |  |  |  |  |  |  |  |
| 3.2.2.1 | Objective | Enhance participation of the public in monitoring budget expenditures |  |  |  |  |  |
|  | Indicator | Program budgeting at all levels of the government should enable transparent budget spending. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.2.1.1 | Establishing a mechanism for transition from line item to program budgeting at all levels of the government | The Law on Budget, or a decision on the budget of local self-government units, are adopted on the basis of program budgeting | 30 months | All public authorities | Program budgeting is conducted at all levels of the government | Not required |  |
| 3.2.2.1.2 | Public disclosure of the annual report on the work of budgetary inspection submitted to the National Assembly | Publish the annual report on the website | annually | The budgetary inspection, MF | Published annual reports are accessible to the citizens | Not required |  |
| 3.2.2.1.3 | Conducting an analysis of regulations governing appropriacy of and accountability for public spending | Determine mechanisms for introduction of control of appropriacy and accountability | 12 months | The budgetary inspection, MF | The analysis is conducted | Not required | Invite the Public Procurement Office to SAI working group , etc. |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.2.2. | Objective | Consistent application of the Law on Public Procurements and keeping records on the actions of competent authorities related to the irregularities found in their reports |  |  |  |  |  |
|  | Indicator | The scope and nature of irregularities determined in reports of competent supervisory and regulatory authorities. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.2.2.1 | Updating the Public Procurement Development Strategy in the Republic of Serbia starting from current changes to the regulatory and institutional framework | Formulate and propose amendments to the Public Procurement Development Strategy | 6 months | The Public Procurement Office | The Public Procurement Development Strategy is updated | Not required |  |
| 3.2.2.2.2 | Defining criteria and mechanisms for determining appropriateness of public procurements and accountabilities | Adopt by-laws establishing clear criteria for the assessment of appropriateness | 6 months | The Public Procurement Office | The by-law is adopted | Not required |  |
| 3.2.2.2.3 | Developing a model of an internal plan for prevention of corruption in public procurements to be used by ordering parties when developing their own internal plans | Formulate and develop a model | 6 months | The Public Procurement Office | The model of internal anti-corruption plan is developed | Not required |  |
| 3.2.2.2.4 | Developing a model for adoption of internal acts of ordering parties used for precise governing of the public procurement procedure, including recording of any action taken and determining personal accountability for the appropriacy of an action; | Formulate and develop a model | 6 months | The Public Procurement Office | The model of internal acts is developed | Not required |  |
| 3.2.2.2.5 | Introducing records on actions of competent authorities related to irregularities found in the reports submitted by control and regulatory bodies | Introduce records on actions | 12 months | The Public Procurement Office | Records are kept | Not required |  |
| 3.2.2.2.6 | Regulating the procedure for recording and reporting on execution of contractual obligations of bidders | Adopt a by-law governing the procedure of recording and executing contractual obligations and prescribing a clear obligation about who shall take prescribed measures in case of default of the bidder; | 6 months | The Public Procurement Office | The by-law is adopted | Not required |  |
| 3.2.2.2.7 | Increasing transparency of public procurement procedures | Improve the Public Procurement Portal so that procurement plans and other relevant acts and information on public procurements become accessible to the public | 24 months | The Public Procurement Office | Plans for procurement and other relevant plans and information on public procurements are available to the public through the Portal; Report of the Public Procurement Office | Not required |  |
| 3.2.2.2.8 | Introducing e-procurements and e-bidding in order to reduce the influence of the "human factor" | Conduct a feasibility analysis | 12 months | The Public Procurement Office | The feasibility analysis is conducted | Experts; IT technology, information on best practices (at least 50.000.000) |  |
|  |  | Establish an electronic procurement and bidding system | 36 months |  | The electronic system is established |  |  |
| 3.2.2.2.9 | Strengthening capacities of regulatory and control bodies in the field of public procurement, particularly in the Public Procurement Office considering new powers granted by the Public Procurement Law | Conduct the needs analysis | 24 months | The Public Procurement Office, MF, SAI | Regulatory and control authorities have the capacity to efficiently carry out their competences | Not required |  |
|  |  | Employ qualified personnel in accordance with the needs analysis | 30 months |  |  | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Professional training of personnel | permanent | The Public Procurement Office, MF, SAI |  | In accordance with the needs analysis (for each training 300.000) |  |
| 3.2.2.2.10 | Implementing final decisions of the Republic Commission for Protection of Rights in the Public Procurement, in all cases | Amend regulations in order to establish clear procedures for complying with Commission's decisions | 12 months | The Public Procurement Office | The regulation is amended | Not required | The report should contain information on the number of decisions implemented |
|  |  | Monitor implementation of the decisions | permanent | Republic Commission | A report on the work of the Republic Commission | Not required |  |
| 3.2.2.2.11 | Informing on the application of new solutions in the field of public procurement | Develop and implement the education plan | 24 months | The Public Procurement Office | The amount of education provided | In accordance with the needs analysis (for each training 300.000) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.2.3 | Objective | Improve cooperation and coordination between relevant institutions in combating corruption at all levels of the government |  |  |  |  |  |
|  | Indicator | The percentage of procurement related cases that are completed within statutory time limits increases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.2.3.1 | Improving cooperation and coordination of anti-corruption activities between relevant institutions | Conclude a memorandum of cooperation between the Public Procurement Office, the Republic Commission for Protection of Rights in the Public Procurement, the Ministry of Finance and Economy, the Public Audit Institution, the Anti-Corruption Agency, the Anti-Corruption Council and the Commission for the Protection of Competition | 6 months | The Public Procurement Office, the Republic Commission for Protection of Rights in the Public Procurement, MF, SAI, ACA, ACC, and Commission for the Protection of Competition | The memorandum is concluded | Not required |  |
| 3.2.2.3.2 | Training members of the police and public prosecutor's office in public procurement for the purposes of conducting more effective investigations of criminal offenses and training judges for the purposes of more efficient judicial proceedings in cases of determining criminal responsibility in the field of public procurements, and training magistrates for the purposes of more efficient conduct of proceedings related to offenses prescribed by the Law on Public Procurement; | Develop a training program | 2 months | The Judiciary Academy (JA) of the RS | The training program contains methods, fields and way of training | Not required |  |
|  |  | Develop manuals | 2 months |  | A training manual is developed | 5.000.000 |  |
|  |  | Carry out education | permanent |  | The number of training sessions | In accordance with the needs analysis (for each training 300.000) |  |
| 3.2.2.3.4 | Introducing records on actions of magistrates courts, prosecutor's office and courts of general jurisdiction related to the irregularities found in reports submitted by the SAI and Public Procurement Office | Educate employees in the SAI and Public Procurement Office about characteristics and apparent features of corruption offenses | 15 months | The Judiciary Academy of the RS | The number of training sessions | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | The SAI and Public Procurement Office submit misdemeanor reports and submit their findings to the competent prosecutor | permanent | SAI and Public Procurement Office | The number of reports | Not required |  |
|  |  | A new register of cases of corruption offenses contains records of actions of competent authorities on the basis of findings of the SAI and Public Procurement Office | permanent (from the moment the new register is created) | The public authority that keeps the register of corruption offenses | A report on work | Not required |  |
| 3.2.2.3.5 | Establishing efficient cooperation with CSO and regulatory, control and repressive authorities in prevention and combating corruption in public procurements | Develop training programs and manuals for prevention and combating corruption in public procurements | 6 months | The Public Procurement Office, JA | A training manual is developed | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Conducting specialized seminars and workshops | 24 months | The Public Procurement Office, JA | The number of training sessions | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | A new register of cases of corruption offenses contains records of actions of competent authorities upon CSO reports | permanent | The public authority that keeps the register of corruption offenses | A report on work | Not required |  |
| 3.2.2.3.6 | Ensuring adequate personnel, technical, financial and physical conditions for the operation of regulatory and control bodies in the filed of public procurement, particularly for the operation of the Public Procurement Office, having in mind new competences granted by the Law on Public Procurement | An analysis of necessary conditions | 6 months | The Public Procurement Office | The analysis is conducted | Not required |  |
|  |  | Develop a plan for the implementation of necessary conditions | 7 months | The Public Procurement Office | The plan of implementation matches the needs analysis | Not required |  |
|  |  | Execute the implementation plan (systematization of posts, number of employees and professions is in accordance with analysis, technical equipment and space is provided) | 24 months | The Public Procurement Office and MF | A report on execution of the implementation plan | According to the implementation plan (per employee at least 50,000 gross, equipment, for each training 300.000) |  |

3.2.3 Public internal financial control, external audit and protection of EU financial interests

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.3.1 | Objective | Establish and develop a system for public internal financial control in the public sector at all levels of the government, including funds from the EU and from other international institutions and organizations. |  |  |  |  |  |
|  | Indicator | The percentage of public bodies that have an internal financial control unit that has delivered at least one report increases to 50% or above in 2017. The average number of violations found by the SAI for a public body decreases by 75% in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.1.1 | Amending the Law on Budgeting system in order to legaly strenghten the position of internal auditors and ensure functional and operational independence of the internal audit and define financial management and control principles | Formulate and submit a amendments to the law | 12 months | The Ministry competent for finance | Draft amendments to the laws are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the RS | A proposal of amendments to the law is submitted |  |  |
|  |  | Adopt amendments to the law | 20 months | The National Assembly | The law is adopted | Not required |  |
| 3.2.1.2 | Consistently applying regulations in the field of public internal financial control in the public sector | Public funds beneficiaries consistently perform their duties of adoption of plans for implementation and development of the financial management and control system, of determining the manager in charge of financial management and control, of adoption of internal acts and procedures related to financial management and control, as well as of submission of annual reports to the CHU | permanent | All public funds beneficiaries | The Consolidated Annual Report on the status of internal financial control in the public sector in the Republic of Serbia of the Central Harmonization Unit of the Ministry competent for finance shows that obliged parties performed their duties | Not required | The Consolidated Annual Report on the status of internal financial control in the public sector in the Republic of Serbia is published on the MF website. The measure refers to the obliged parties defined by the Budget System Law |
| 3.2.1.3 | Building capacities of public funds beneficiaries which set up their own internal audit | Conduct an assessment of the required number of operators in terms of risks, complexity of operations and amount of funds that a public fund beneficiary disposes with | 6 months after adoption of the law | All public funds beneficiaries | The Consolidated Annual Report on the status of internal financial control in the public sector in the Republic of Serbia of the Central Harmonization Unit of the Ministry competent for finance shows that obliged parties performed their duties | Not required | The measure refers to the obliged parties defined by the Budget System Law |
|  |  | Harmonize systematization and the number of operators with results of the assessment | 15 months after adoption of the law |  |  | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Harmonize salaries and the system of awarding internal auditors | 15 months after adoption of the law |  |  | In accordance with the needs analysis |  |
|  |  | Train internal auditors in the fields that may be the subject of audit, as well as in ways of action in case they detect significant irregularities and frauds. | permanent | The Central Harmonization Unit |  | 10.000.000 |  |
| 3.2.1.4 | Building capacities of the Central Harmonization Unit | Harmonize the existing CHU systematization with the workload | 6 months after adoption of the law | The Ministry competent for finance | The Consolidated Annual Report on the status of internal financial control in the public sector in the Republic of Serbia of the Central Harmonization Unit of the Ministry competent for finance shows that the necessary capacities are ensured | Not required |  |
|  |  | Initiate the process of recruitment of adequate staff | 15 months |  |  | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Harmonize salaries and the system for awarding of employees in the CHU with the amount of salaries and system for awarding auditors in the SAI | 15 months |  |  | In accordance with the needs analysis |  |
|  |  | Ensure that CHU employees connect with other participants in the PIFC, as well as with employees in CHUs in other countries | permanent |  |  | Not required |  |
| 3.2.1.5 | Increasing the number of trained managers and employees in the public sector in the meaning and importance of the financial management and control system | Organize and conduct training in financial management and control | permanent | The Central Harmonization Unit of the Ministry competent for finance | The number of trained persons is constantly increasing in comparison to the data in the Consolidated Annual Report for the previous year | RSD 10,000,000.00 |  |
| 3.2.1.6 | Increasing the number of trained internal auditors | Organize training for internal auditors and their certification | permanent activity | The Central Harmonization Unit of the Ministry competent for finance | The number of trained persons and certified internal auditors has increased in comparison to 2012 | RSD 60,000,000.00 |  |
| 3.1.2.7 | Creating electronic records of obliged parties in terms of introduction of the PIFC system at all levels | Develop software, define what data are necessary and collect and enter information about obliged parties | 12 months | The Ministry competent for finance | A transparent electronic database is created and all the information is regularly updated | RSD 2,000,000.00 |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.3.2 | Objective | Change the legal framework to ensure complete financial and operational independence of the SAI in accordance with the standards of the International Organization of Supreme Audit Institutions (INTOSAI) and carry out the audit of appropriacy |  |  |  |  |  |
|  | Indicator | An independent assessment of the level of SAI conformity with INTOSAI standards shows conformity. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.3.1 | Amending the Law on the State Audit Institution which ensures complete financial and operational independence | Prepare amendments to the law harmonized with the standards of the International Organization of Supreme Audit Institutions (INTOSAI). | 10 months | The relevant committee of the National Assembly | A proposal of amendments is in accordance with INTOSAI standards | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Extend the term of office of Council members and other SAI officials to be longer than term of office of the legislative and executive officers, ensure that the SAI official, whose term of office is terminated, continues professional work in SAI. Increase the number of deputies that can initiate dismissal of Council members. Strengthen financial independence and immunity of Council members. |
|  |  | Adopt the law | 12 months | The National Assembly | The law is adopted | Not required |  |
| 3.2.3.2 | Building SAI capacities and improving working conditions by increasing the number of employees and permanent resolving of the problem of premises for work | Increase the number of employees in accordance with the SAI staffing plan | 15 months | SAI, the Ministry of Finance gives approval | The SAI staffing plan is timely fulfilled at the annual level | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Ensure adequate office space that can be staffed with SAI employees | 15 months | The Government of the RS | SAI is moved to new premises | 150,000 dinars per month (the rent) | The whole institution is at one place |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2 PUBLIC FINANCE |  |  |  |  |  |  |  |
| 3.2.3.3 | Objective | Establish and develop the system for prevention, detection, reporting and treatment of irregularities using means from EU funds and funds of other international institutions and organizations |  |  |  |  |  |
|  | Indicator | Positive EU evaluation of the prevention system established in Serbia. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.2.4.1 | Improving the normative framework that governs prevention, detection, reporting and treatment of irregularities in the context of use of means from EU funds | Adopt amendments to the Regulation of the European Union on Decentralized Development Assistance Fund Management as part of IPA | 6 months | The Ministry of Finance, the Government of the RS | Amendments are adopted | Not required | Consult donors in the RS during development |
|  |  | Adopt the law governing IPA in the program period 2014-2020 | 18 months |  | The law is adopted | Not required |  |
| 3.2.4.3. | Conducting campaigns for raising awareness about the need for conscientious management of funds | Develop a campaign program | 2 months after adoption of the law | The Ministry of Finance, the Government of the RS | The program is developed | Not required | The work involves donors and NGOs |
|  |  | Organize and conduct a campaign | 12 months after adoption of the law |  | The campaign is conducted | 5.000.000 |  |
| 3.2.4.5. | Establishing an organizational unit for combating irregularities and frauds in the MoI (AFCOS) as a mechanism of cooperation of competent institutions with the European Anti-Fraud Office (OLAF) | Change the systematization of posts in the MoI | 8 months | MoI | The systematization is changed | Not required |  |
|  |  | Provide adequate space for the operation of the AFCOS office | 10 months |  | AFCOS has adequate conditions | In accordance with the needs analysis |  |
|  |  | Staffing | 10 months |  | The number of employed persons | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Implement the program for training AFCOS employees | 18 months |  | The training is conducted | In accordance with the needs analysis (for each training 300.000) |  |

3.3.   PRIVATIZATION AND PUBLIC-PRIVATE PARTNERSHIP

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3 PRIVATIZATION AND PUBLIC-PRIVATE PARTNERSHIP |  |  |  |  |  |  |  |
| 3.3.1 | Objective | Change the legal framework to eliminate risks of corruption in the regulations governing the procedure and control of privatization, reorganization and bankruptcy of the companies with state and social capital. |  |  |  |  |  |
|  | Indicator | The number of oversights of the privatization, reorganization and bankruptcy procedures of the companies with state and social capital has increased by 30% in comparison to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.1.1.1 | Conducting the analysis of provisions of the regulations governing the procedures of privatization, reorganization and bankruptcy in terms of the risk of corruption | Develop a methodology for the analysis of effects and risk of corruption | 3 months | The Anti-Corruption Agency | The methodology is developed | Not required |  |
|  |  | Conduct an analysis of regulations on the basis of the ACA methodology | 9 months | The Ministry competent for finance and economy, АCA, ACC | A report on the analysis of regulations | Not required | The work involves representatives of the Republic Public Prosecutor's Office (RPPO), the Supreme Court of Cassation (SCC), the Privatization Agency (PA), the Ministry of Interior (MoI), the Ministry of Justice and Public Administration (MJPA) and the Civil Society Organization (CSO) |
| 3.3.1.2 | Amending the Privatization Law to eliminate deficiencies that provide for corruption (as well as other laws in accordance with the analysis) | Formulate and submit draft amendments to the law that comply with the analysis | 15 months | The Ministry competent for finance and economy | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Specify the subject of privatization and allocation of strategic resources (e.g. electricity, water supply, telecommunications network, etc.), the manner of advertizing the privatization process and increase publicity of the privatization process; precisely define ways of deciding on the method of privatization and control of privatization agreements; prescribe the obligation of investigating the economic importance of restructuring, contents of the privatization agreement and financial statement, criteria for the appointment of the director of the Privatization Agency; the land ownership structure must first be considered for the privatization procedure; regulate cases in which the government directly or through public companies undertakes obligations in case the buyer of a privatized company does not fulfill its obligations, etc. |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 17 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments to the Privatization Law | 18 months | The National Assembly | The Law on amendments to the Privatization Law is adopted | Not required |  |
| 3.1.1.3 | Amending the Law on Bankruptcy and the Agency for Licensing of Bankruptcy Trustees to eliminate deficiencies that provide for corruption (as well as other laws in accordance with the analysis) | Formulate and submit draft amendments to the law which is in accordance with the analysis | 15 months | The Ministry competent for finance and economy | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Specify the manner of determining classes of creditors, expert's evaluation of the property value (with or without encumbrance); the bankruptcy trustee must be legally obliged to analyze operations of the debtor prior to the commencement of the bankruptcy procedure, to identify reasons that led to the bankruptcy and to notify creditors by submitting a detailed report; delete an exception that the bankruptcy judge can select a bankruptcy trustee, and specify greater powers of the assembly of creditors to dismiss a bankruptcy trustee; specify powers and procedures involving the Privatization Agency; |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 17 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Put a proposed law on amendments to the NA's agenda for adoption | 18 months | The Speaker of the National Assembly | The bill is placed on the NA's agenda | Not required |  |
| 3.1.1.4 | Harmonizing by-laws with amendments to the law | Harmonize and adopt by-laws | 21 months | The Ministry competent for finance and economy | All by-laws are harmonized with amendments to the law | Not required |  |
| 3.1.1.5 | Conducting professional training of employees in new solutions of the regulations before its implementation | Prepare a training program and manuals | 20 months | The Ministry competent for finance and economy | Professional training program is prepared | Not required |  |
|  |  | Organize and conduct training | permanent |  | Professional training is organized and conducted | In accordance with the needs analysis (for each training 300.000) ? | Involve the SCO |
| 3.1.1.6 | Conducting campaigns for informing the citizens about the procedure | Organize and conduct campaigns | permanent | The Ministry competent for finance and economy | Campaigns are organized and conducted | 10.000.000 | Involve the SCO |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3. PRIVATIZATION AND PUBLIC-PRIVATE PARTNERSHIP |  |  |  |  |  |  |  |
| 3.3.2 | Objective | Establish a system for efficient implementation and control of enforcement of positive regulations in the field of privatization, reorganization and bankruptcy of the companies with state and social capital. |  |  |  |  |  |
|  | Indicator | The number of the procedures of control of restructuring, bankruptcy and ownership transformation of the companies with public and social capital on the basis of alleged corruption has decreased by 30% in comparison to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.3.2.1 | Establishing the system of continuous and compulsory coordination of public authorities and organizations for the purposes of proactive approach to the prevention of the risk of corruption | Conclude memorandums of cooperation with the Ministry of Interior, Republic Public Prosecutor's Office, the Supreme Court of Cassation, ACA and the Anti-Corruption Council | 3 months | The Privatization Agency | The memorandum of cooperation | Not required | The Privatization Agency, line ministry, justice, MoI, Agency, Council |
|  |  | Organize semi-annual meetings | every half a year | The Privatization Agency | Meeting minutes | Not required |  |
|  |  | Define a manual of good practice and ways of actions, as a preventive action mechanism | 12 months | The Privatization Agency | The manual is published and available on the website of the Privatization Agency | 5.000.000 | Required cooperation with the MoI, RPPO, SCC, ACA and Anti-Corruption Council (ACC) |
| 3.3.2.2 | Developing and conducting the program of mutual professional training of the authorities participating in the privatization process and the authorities competent for the prevention and criminal prosecution of cases of corruption | Develop professional training programs | 12 months | The Judicial Academy | Professional training program | Not required |  |
|  |  | Conduct professional training programs at all levels of the government | permanent | The Judicial Academy | The number of professional training sessions conducted | In accordance with the needs analysis (for each training 300.000) |  |
| 3.3.2.3 | Conducting an analysis of powers of the Ministry competent for finance and economy to control the appropriacy of work of the Privatization Agency | Conduct an analysis of powers and problems in appropriacy oversight | 6 months | The Ministry competent for finance and economy | The analysis is conducted | Not required |  |
|  |  | Suggest amendments to regulations or take other measures | 12 months |  | Measures are suggested | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3 PRIVATIZATION AND PUBLIC-PRIVATE PARTNERSHIP |  |  |  |  |  |  |  |
| 3.3.3. | Objective | Eliminate risks of corruption in the field of public-private partnerships and concessions and its consistent application |  |  |  |  |  |
|  | Indicator | An ex-post analysis of the effects of the Law on public-private partnership and concessions does not establish the existence of an extremely high risk of corruption. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.3.3.1 | Conducting an analysis of the risk of corruption and degree of compliance with other laws | Determine risks of corruption | 12 months | The Ministry competent for finance and economy, ACA and ACC | A report on conducted analysis and results | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Formulate precise, clear and objective criteria for determining a "balanced relation" in the sharing of risks between partners; specify competences of the Public-Private Partnership Commission to prevent a potential conflict of interest in practice, having in mind the provision of the Law that the Commission shall give its opinion in the procedure of approval of a public-private partnership in whose preparation it is involved. |
| 3.3.3.2 | Adopting amendments to the Law on the Public-Private Partnership in accordance with the analysis | Formulate and submit draft amendments to the law which is in accordance with the analysis | 18 months | The Ministry competent for finance and economy | Draft amendments to the law is submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 20 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law | 22 months | The National Assembly | The law is adopted | Not required |  |
| 3.3.3.3 | Adopting related by-laws | Define and adopt by-laws | 24 months | The Ministry competent for finance and economy | By-laws are adopted | Not required |  |
| 3.3.3.4 | Conducting professional training of employees in new solutions of the regulation before its implementation | Develop a professional training program and manuals | 20 months | The Ministry competent for finance and economy | Professional training program is developed | Not required |  |
|  |  | Organize and conduct professional training | permanent |  | Professional training is organized and conducted | In accordance with the needs analysis (for each training 300.000) | Involve the SCO |
| 3.3.3.5 | Conducting campaigns for informing the public about the public-private partnership | Organize and conduct campaigns | permanent | The Ministry competent for finance and economy | Campaigns are organized and conducted | 10.000.000 | Involve the SCO |
| 3.3.3.6 | Establishing mechanisms for control and transparency of work of the Public-Private Partnership Commission | Regularly publish and update data on the website about the appropriacy of the public-private partnership and concessions | permanent | The Ministry competent for finance and economy | Data about the appropriacy of the public-private partnership are available on the website and are regularly updated | Not required |  |

3.4. JUDICIARY

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.1 | Objective | Ensure full independence or autonomy and transparency of the judiciary system in terms of budgetary powers |  |  |  |  |  |
|  | Indicator | The HJC and SPC are fully competent and accountable for the judicial budget until the end of 2017 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.1.1 | Forming HJC and SPC capacities for independent budget planning and execution | Conduct the needs analysis | 6 months | HJC, SPC, the Ministry competent for justice, the Government of the RS | An analysis report | Not required | Deadlines can be modified to comply with activities envisaged in the Strategy for Judicial Reform |
|  |  | Change systematization so to increase the number of employees in the HJC and SPC Administrative Office according to the needs | 15 months | HJC, SPC, the Ministry competent for justice, the Government of the RS | The number of employees in the HJC Administrative Office | Not required |  |
|  |  | Employ according to the systematization | 17 months | HJC, SPC, the Ministry competent for justice, the Government of the RS | Decisions on establishing employment relations in budget planning and execution are adopted | According to the systematization (min. gross 50,000 per employee) |  |
|  |  | Provide necessary equipment | 20 months | HJC, SPC, the Ministry competent for justice, the Government of the RS | Equipment is provided in accordance with the needs analysis | Depending on the needs analysis |  |
| 3.4.1.2. | Setting clear criteria for the selection of managers in courts and public prosecutor's offices | Define and adopt criteria | 6 months | The High Judiciary Court | Decision on the adoption of criteria, Rulebook on the Systematization of Job Positions. | Not required |  |
|  |  |  | 6 months | The State Prosecutorial Council | Decision on the adoption of criteria, Rulebook on the Systematization of Job Positions. | Not required |  |
| 3.4.1.3. | Including training and professional development program for employees in the HJC and SPC Administrative Office into the Judicial Academy training program | Set up an analysis of needs in terms of professional training of employees in the HJC and SPC Administration Office | 6 months | The High Judiciary Court, State Prosecutorial Council, Judicial Academy | An analysis document is developed and adopted | 300,000 (Experts for conducting the needs analysis, material for conducting a survey among employees) |  |
|  |  | Adopt the training curriculum | 6 months | The High Judiciary Court, State Prosecutorial Council, Judicial Academy | The curriculum is adopted | Not required |  |
|  |  | Conduct training of employees according to the plan | permanent activity | The High Judiciary Court, State Prosecutorial Council, Judicial Academy | A report on work states that training was conducted according to the curriculum | According to the needs (min. 300,000 per training course) |  |
|  |  | Conduct annual evaluation | once a year | The High Judiciary Court, State Prosecutorial Council, Judicial Academy | A report on the evaluation of the training program | Not required |  |
| 3.4.1.4. | Ensuring transparency of data on HJC and SPC financing | Publish the annual financial statement on the HJC and SPC website | annually | HJC, SPC | The report is published in accordance with the Law on Budget System | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.2 | Objective | Ensure that the process of selection, promotion and accountability of holders of judiciary functions is based on clear, objective, transparent and pre-determined criteria. |  |  |  |  |  |
|  | Indicator | Criteria for the selection, promotion and accountability are consistently applied according to the assessment of the holders of judiciary functions (according to a survey conducted on a representative sample) until the end of 2017 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.2.1 | Amending the Law on Judges and the Law on Public Prosecutor's Office so to introduce an advantage for persons completing initial training in the Judicial Academy before setting the JA mandatory condition for the first selection for the judicial function | Formulate and submit draft amendments to the law so to introduce an advantage for persons completing the initial training in the JA when selecting judges, and/or deputy public prosecutors | 8 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government of the RS | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit proposed amendments to the National Assembly | 10 months | The Government of the RS | Proposed amendments to the law are submitted to the National Assembly | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The laws are adopted | Not required |  |
| 3.4.2.2. | Amending the Rulebook on the contents and manner of taking the entrance exam so as to increase transparency in the process of enrolment to the Judicial Academy | Form a working group for drafting the Rulebook | 12 months | The Judicial Academy | A decision on forming a working group | Not required |  |
|  |  | Draft and adopt the Rulebook | 16 months |  | The Rulebook is adopted | Not required |  |
| 3.4.2.3. | Promoting the initial and ongoing training at the Judicial Academy | Organize and conduct informative seminars, distribute information materials, etc. | permanently | The Judicial Academy | The number of seminars, flyers, advertising material | According to the needs ( min 5,000,000) | Promoting the Judicial Academy among students of the faculties of law and assistant judges and prosecutors |
| 3.4.2.4 | Amending the Law on the Judicial Academy, the Law on High Judicial Council, the Law on the State Prosecutorial Council, so to introduce mandatory ongoing training for holders of judicial functions | Formulate and submit draft amendments to the law | 8 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government of the RS | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit proposed amendments to the National Assembly | 10 months | The Government of the RS | Proposed amendments to the law are submitted to the National Assembly | Not required |  |
|  |  | Adopt the law on amendments | 12 months | The National Assembly | The laws are adopted | Not required |  |
| 3.4.2.5 | Adopting a normative framework that defines clear criteria and procedures for selection and progress of holders of the judicial function (criteria that will be objectively measured) | The HJC adopts the Rulebook on objective selection and promotion criteria | 6 months | The High Judicial Council | The Rulebook on objective selection and promotion criteria is in effect | Not required |  |
|  |  | The SPC adopts the Rulebook on objective selection and promotion criteria | 6 months | The State Prosecutorial Council |  | Not required |  |
|  |  | Publish HJC and SPC Rulebooks on their website | 6 months | The High Judicial Council, State Prosecutorial Council | HJC and SPC Rulebooks are published on their websites | Not required |  |
| 3.4.2.6 | Establishing transparency in the process of selection of a candidate | Publish a ranking of candidates who applied, in accordance with legal protection of personal data | permanently | The High Judicial Council, State Prosecutorial Council | The ranking of candidates is published on the website | Not required |  |
|  |  | Publish a decision on the selection of a candidate with a statement of reasons made in accordance with criteria | permanently | The High Judicial Council, State Prosecutorial Council | The decision on the selection of a candidate is published together with the statement of reasons | Not required |  |
| 3.4.2.7 | Adopting a normative framework that defines clear criteria and procedures for the responsibility of holders of judicial and public prosecutor's function | Implement provisions of the Rulebook on a disciplinary procedure and disciplinary accountability in order to establish a functional system of the disciplinary prosecutor and disciplinary commission | permanently | The High Judicial Council, State Prosecutorial Council | The number of processed holders of judiciary functions | Not required |  |
|  |  | Conduct an analysis of effects of application of the Rulebook | permanently | The High Judicial Council, State Prosecutorial Council | A risk analysis document is prepared | Not required |  |
|  |  | Amend the Rulebook so to precisely define more serious breaches of the Code of Ethics as well as other improvements identified with the analysis of effects of application | 6 months | The High Judicial Council, State Prosecutorial Council | Amendments to the Rulebook are adopted | Not required |  |
| 3.4.2.8. | Conducting an analysis of what data could be treated as confidential in a personal record and harmonizing the Law on the Public Prosecutor's Office and the Law on Judges with the Law on Data Secrecy | Conduct an analysis on what data should be considered confidential in a personal record and harmonize it with the stated laws | 6 months | The High Judicial Council, the State Prosecutorial Council, the Ministry competent for justice | A report on conducted analysis | 500,000 (Experts; information on best practices) | The activity should be conducted with the Commissioner for Information of Public |
|  |  | Formulate and submit draft amendments to the law | 8 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government of the RS | 1,600,000 (costs of public hearings) |  |
|  |  | Submit proposed amendments to the National Assembly | 10 months | The Government of the RS | Proposed amendments to the law are submitted to the National Assembly | Not required |  |
|  |  | Adopted the law on amendments | 12 months | The National Assembly | The law is adopted | Not required |  |
| 3.4.2.9. | Establishing a procedure for regular publishing of statistical data and practices of HJC and SPC disciplinary authorities | Semi-annually publish statistics on the HJC website | permanently | The High Judicial Council | Reports are semi-annually published on the website | Not required | The number of charges, types of infringements, types and number of decisions, period required for their adoption |
|  |  | Semi-annually publish statistics on the SPC website | permanently | The State Prosecutorial Council | Reports are semi-annually published on the website | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.3 | Objective | Establish efficient and proactive actions in detecting and prosecuting criminal offenses related to corruption |  |  |  |  |  |
|  | Indicator | The number of criminal proceedings related to corruption resulting in judgments will increase by 30% until the end of 2017, in comparison to 2012 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.3.1 | Creating a multidisciplinary training program for conducting proactive investigations for the police, prosecution and court | Conduct an analysis of past experiences in the filed of legality and admissibility of evidence gathered during investigation and special investigative actions | 12 months | The Supreme Court of Cassation, the Republic Public Prosecutor's Office | The analysis document is prepared and adopted | 1,600,000 (Еexperts; information on best practices) |  |
|  |  | Integrate analysis results in the training program | 18 months | The Judicial Academy | The curriculum is adopted | Not required |  |
|  |  | Prepare a manual for the use of special investigative techniques | 15 months | The Judicial Academy | The manual is published | 5,000,000 |  |
|  |  | Conduct training according to the annual training curriculum | continuous activity | The Judicial Academy | The number of conducted training sessions and attendees | According to the needs ( min. 300,000 per training course) |  |
| 3.4.3.2. | Implementing and developing a proactive investigation process | Create statistics about initiated proactive investigations (use special techniques and act on the initiative of the police and prosecutor's office) | 12 months | The Republic Public Prosecutor's Office, the Ministry of Interior | The number of initiated proactive investigations has increased in comparison to the previous year | Not required |  |
|  |  | Keep records of proactive actions related to corruption offenses | permanent |  | Records are created | Not required |  |
| 3.4.3.3 | Amending the Law on Seizure and Confiscation of the Proceeds from the Crimes so to introduce an obligation for MoI to submit to the prosecutor's office a completed financial investigation in addition to a criminal charge | Formulate and submit draft amendments to the law | 3 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government | 1,600,000 (Experts in the field of legislation; costs of public hearings) |  |
|  |  | Put proposed amendments to the law on the NA's agenda for adoption | 5 months | The Government of the RS | Draft law is submitted to the NA | Not required |  |
|  |  | Adopt the law | 6 months | The National Assembly of the RS | The law is adopted | Not required |  |
| 3.4.3.4 | Building capacities of judicial authorities for conducting proactive investigations | Conduct the needs analysis |  | The Republic Public Prosecutor's Office, the State Prosecutorial Council | The analysis report | Not required |  |
|  |  | Increase the number of deputy public prosecutors in accordance with the analysis that act in corruption offense cases in the special prosecutor's office for organized crime, special division of higher prosecutor's offices | 6 months | The Republic Public Prosecutor's Office, the State Prosecutorial Council | The Act on Systematization | According to the systematization (min. gross 50,000 per employee) |  |
|  |  | Ensure specialized training for deputy prosecutors and judges | 6 months | The Republic Public Prosecutor's Office, the State Prosecutorial Council, the Judicial Academy | Proposed amendments to the law is submitted | According to the needs ( min. 300,000 per training course) |  |
| 3.4.3.5 | Continuous training of judges and prosecutors in financial investigation | Adopt a training curriculum and develop a training manual | 6 months | The Republic Public Prosecutor's Office, the State Prosecutorial Council, the Judicial Academy | The curriculum; manual | 5,000,000 |  |
|  |  | Every year, the HJC and SPC prescribe the number of days of training of judges and prosecutors | permanent | The High Judicial Council, the State Prosecutorial Council, | The act providing for mandatory training days is adopted | Not required |  |
|  |  | Conduct training according to the plan | permanent | The Judicial Academy | The curriculum is implemented at the annual level | According to the needs ( min. 300,000 per training course) |  |
| 3.4.3.6 | Changing the legal framework so to enable sending MoI members to the special prosecutor's office for organized crime | Formulate and submit draft amendments to the law | 3 months | The Ministry competent for justice, the Ministry of Interior | Draft amendments to the law are submitted to the Government | 1,600,000 (Experts in the field of legislation; costs of public hearings) |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 3 months | The Government of the RS | Proposed amendments to the law are submitted | Not required |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 3 months | The National Assembly of the RS | The law is adopted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.4 | Objective | Improve the substantive criminal law and harmonize it with international standards |  |  |  |  |  |
|  | Indicator | All GRECO recommendations are implemented. All necessary UNCAC standard are fulfilled. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.4.1 | Amending the Criminal Code so to introduce the criminal offense of Illicit enrichment | Formulate and submit draft amendments to the law | 9 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government | 500,000 (Experts, information on best practices) |  |
|  |  | Submit proposed amendments to the National Assembly | 12 months | The Government of the RS | Proposed amendments to the law are submitted | 1,600,000 (costs of public hearings) |  |
|  |  | Adopt the law on amendments | 15 months | The National Assembly | The law on amendments is adopted | Not required |  |
| 3.4.4.2 | Codifying corruption offense through amendments to the Criminal Code | Formulate and submit draft amendments to the law | 9 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government | 500,000 (Еexperts; information on best practices) |  |
|  |  | Submit proposed amendments to the National Assembly | 12 months | The Government of the RS | Proposed amendments to the law are submitted | 1,600,000 (costs of public hearings) |  |
|  |  | Adopt the law on amendments | 15 months | The National Assembly | The law on amendments is adopted | Not required |  |
| 3.4.4.3 | Conducting the campaign for rising public awareness about implementation of new provisions | Organize and conduct campaign | 6 months since the adoption of amendments to the Criminal Code | The Judicial Academy of the RS | Campaigns are organized and conducted | 5,000,000 |  |
| 3.4.4.4. | Training holders of judicial functions and police members in new legislation | Prepare the training program | 3 months since the adoption of amendments to the Criminal Code | The Judicial Academy of the RS | The training program contains methods, fields and training manner | Not required |  |
|  |  | Create the manual | 6 months since the adoption of amendments to the Criminal Code |  | The training manual is created | 5,000,000 |  |
|  |  | Conduct training | permanently |  | The number of conducted training sessions | According to the needs ( min. 300,000 per training course) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.5 | Objective | Establish efficient horizontal and vertical cooperation and exchange of information between the police, prosecutor’s offices, judiciary, other state authorities and institutions, regulatory and supervisory bodies, and European and international institutions and organizations. |  |  |  |  |  |
|  | Indicator | Average duration of criminal investigations of criminal offenses related to corruption, measured at the annual level will reduce by 30% until 2017, in comparison to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.5.1 | Improving cooperation and coordination in anti-corruption activities between relevant institutions | Conclude a memorandum of cooperation between the police, public prosecutor's offices, judiciary, other public authorities and institutions, which will determine the method of cooperation and focal points | 6 months | HJC SPC, the Ministry competent for justice, police, High Judicial Council, Republic Public Prosecutor's Office, ACA, Public Procurement Directorate, Tax Administration, SAI | The memorandum is concluded | Not required | Particularly promote proactive actions, acting upon reports by the ACA, SAI, Tax Administration, Public Procurement Directorate, etc. |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.6 | Objective | Establish a unique record system (electronic register) for criminal offenses related to corruption. |  |  |  |  |  |
|  | Indicator | The Ministry responsible for justice has a possibility to develop a reliable annual report on cases related to corruption, containing information about investigation, appeals and judgments by the end of 2017 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.6.1 | Amending by-laws in order to establish a unique methodology for data collection, recording and statistical reporting | Establish a multi-sect oral working group that will determine a unique methodology for data collection and statistical reporting | 6 months | The Ministry competent for justice | A decision on establishing a multi-sectoral working group, methodology is developed | 500,000 (Еxperts; information on best practices) |  |
|  |  | On the basis of the conducted analysis, define and adopt amendments to by-laws | 12 months | The Ministry competent for justice | By-laws are adopted and in effect | Not required |  |
| 3.4.6.2. | Establishing a system for the monitoring of criminal offense cases related to corruption | Establish a unique recording system (electronic register) for criminal offenses related to corruption | 18 months | The Ministry competent for justice, the Republic Public Prosecutor's Office, the State Prosecutorial Council, the Supreme Court of Cassation, the High Judicial Council, the Ministry of Interior, the special prosecutor's office for organized crime | The electronic register | According to the needs (min. 50,000,000) |  |
|  |  | Introduce mutually compatible electronic forms in the police, courts and public prosecutor's offices designed for archiving and tracking criminal cases | 20 months |  | Compatible electronic forms | 5.000.000 (Costs of creating forms, printing, distribution) | Forms should contain an option for the monitoring of proactive cases, actions upon requests of the ACA, SAI, Tax Administration, Public Procurement Directorate, etc. |
|  |  | Establish a system of regular control and exchange of information | 22 months |  | Reports on work | Not required |  |
|  |  | Determine focal points responsible for cooperation | 22 months |  | Reports on work | Not required |  |
| 3.4.6.3. | Enabling interconnection between databases on criminal investigations, and/or electronic exchange of information and access to database by prosecutors and the police, customs administration, tax administration and other relevant authorities | Pass an act governing interconnection of databases | 16 months | The Ministry competent for justice, the Republic Public Prosecutor's Office, the State Prosecutorial Council, the Supreme Court of Cassation, the High Judicial Council, the Ministry of Interior, the special prosecutor's office for organized crime | The act governing interconnection of database is passed | Not required |  |
|  |  | Conduct a feasibility study |  |  | A report on the feasibility study | 1,000,000 |  |
|  |  | Create technical conditions for connecting databases | 18 months |  | Technical conditions are provided | According to the feasibility study (min. 50,000,000) |  |
|  |  | Train employees in administration and use of a database | permanent | The Judicial Academy, the Police Academy | The number of employees trained | According to the needs (min. 300,000 per training course) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.6. | Objective | Improve mechanisms for prevention of conflict of interest In judiciary professions |  |  |  |  |  |
|  | Indicator | The number of procedures initiated by competent authorities due to conflict of interest in judiciary professions will increase by 40% until 2017 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.6.1 | Establishing an efficient mechanism for the control of court experts | Adopt a rulebook that would introduce objective criteria for the selection of court experts and ensure even distribution of court experts to subject matters | 6 months | The Ministry competent for justice | The rulebook is adopted | Not required | Introduce sanctions for the judges that do not apply the rulebook on even distribution of court experts |
|  |  | Introduce mandatory reporting of the court to the Ministry competent for justice on any case when judgment was reversed due to erroneous expert's report | 6 months | The High Judicial Council | The form for the stated report, number of reports | Not required |  |
| 3.4.6.2 | Training holders of judiciary functions in rights and obligations of court experts | Develop and implement the training plan | permanent | The Judicial Academy | Training plan, number of trained judges and prosecutors | According to the needs (min. 300,000 per training course) |  |
| 3.4.6.3 | Adopting a rulebook that would regulate the method of use of funds raised through the institution of criminal prosecution delay | Develop the most appropriate method for the procedure of allocation of funds raised through the institution of criminal prosecution delay | 6 months | The Republic Public Prosecutor's Office | The analysis of the methodology is set up | 500,000 (Еexperts, information on best practices) |  |
|  |  | Formulate and adopt the rulebook | 8 months |  | The rulebook is adopted | Not required |  |
| 3.4.6.4 | Enacting a law on assessing bodies | Formulate and submit the draft law | 16 months | The Ministry competent for urban planning | Draft amendments to the law are submitted to the Government of the RS | 1,600,000 (costs of public hearings) |  |
|  |  | Put the proposed law to the NA's agenda for adoption | 18 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted to the NA | Not required |  |
|  |  | Adopt the law | 20 months | The National Assembly | The law is adopted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.8. | Objective | Provide adequate resources in the public prosecutor’s office and courts for dealing with cases of corruption (capacity building) |  |  |  |  |  |
|  | Indicator | The number of unresolved court cases related to corruption will decrease by 30% until 2017, in comparison to 2012 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.8.1. | Building capacities of judicial authorities for conducting criminal proceedings | Conduct the needs analysis | 6 months | The Ministry competent for justice, the High Judicial Council, the State Prosecutorial Council | A report on the needs analysis | Not required | The number of deputy prosecutors and judges, and/or assistant prosecutors and judges acting in the criminal offense case procedures in the Special Prosecutor's Office for Organized Crime, special division of higher prosecutor's offices, has increased |
|  |  | Change systematization and employ an appropriate number of qualified staff according to the analysis | 15 months |  | The Act on the Systematization, number of personnel employed | According to the systematization (min. gross 50,000 per employee) |  |
|  |  | Introduce the professional training system in public prosecutor's offices | permanent | The Republic Public Prosecutor's Office, the State Prosecutorial Council, the Judicial Academy | The number of professionally trained deputy prosecutors and assistant prosecutors | According to the needs (min. 300,000 per training course) |  |
|  |  | Train holders of judicial functions | permanent | The Judicial Academy | Reports on training, program and evaluation of seminar, participants | According to the needs (min. 300,000 per training course) |  |
|  |  | Provide equipment | 25 months | The Ministry competent for justice, HJC, SPC | Receipts on purchased equipment | According to the needs analysis (min. 5,000,000) |  |
| 3.4.6.2 | Introducing a team of economic forensics in public prosecutor's offices | Conduct the needs analysis according to the structure of cases and number of deputy public prosecutors | 6 months | The Republic Public Prosecutor's Office, the State Prosecutorial Council, the Ministry competent for justice | A report on the needs analysis | Not required |  |
|  |  | Change systematization and employ an appropriate number of economic forensics | 24 months |  | The Act on the Systematization, number of employed economic forensics | According to the systematization (min. gross 50,000 per employee) |  |
|  |  | Amend the Rulebook on the Systematization of Job Positions in Public Prosecutor's Offices and the Rulebook on Governance in Public Prosecutor's Offices | 12 months | The State Prosecutorial Council, the Ministry of Justice | Amendments to the rulebook are adopted | Not required |  |
|  |  | Conduct training of economic forensics | permanent | The Judicial Academy | The number of conducted training sessions | According to the needs (min. 300,000 per training course) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.4 JUDICIARY |  |  |  |  |  |  |  |
| 3.4.9. | Objective | Adopt a long-term strategy which in a comprehensive manner improves financial investigations. |  |  |  |  |  |
|  | Indicator | Determined strategic objectives comprehensively improve efficiency of financial investigations. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.4.9.1. | Adopting a strategy which comprehensively improves financial investigations | Conduct a comparative legal analysis, take into consideration experiences from practice and define strategic objectives for achieving more efficient financial investigations | 24 months | The Ministry competent for justice and the Ministry of Interior | The strategy is adopted | 4,000,000 (Costs of analysis, experts, public hearings) | The working group should include the Republic Public Prosecutor's Office, Special Prosecutor's Office for Organized Crime, High Judicial Council, Directorate for Prevention of Money Laundering, Tax Administration, SAI, and civil society organizations. |
| 3.4.9.2. | Training holders of judicial functions and police members in new strategic solutions | Develop a training program | 3 months after adoption | The Judicial Academy of the RS | The training program contains methods, fields and training manners | Not required |  |
|  |  | Develop a manual | 6 months after adoption |  | The training manual is developed | 5,000,000 |  |
|  |  | Conduct training | permanent |  | The number of training sessions | According to the needs (min 300,000 per training course) |  |

3.5. POLICE

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5 POLICE |  |  |  |  |  |  |  |
| 3.5.1 | Objective | Build police capacities required for investigations of criminal offenses related to corruption |  |  |  |  |  |
|  | Indicator | The number of criminal reports on basic and qualified forms of criminal offenses that resulted in raising charges increased in comparison to 2012 |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.5.1.1 | Establishing mechanisms for basic, specialized and continuing training of police officers in anti-corruption activities | Conduct the analysis of needs for the training of police officers | 6 months | МoI, Directorate for Police Education and Academy of Criminalistic and Police Studies | The analysis document is prepared and adopted | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Adopt a police officers training curriculum as part of the basic, specialized and continuing police training | 10 months | МoI, Directorate for Police Education and Academy of Criminalistic and Police Studies | The curriculum is adopted | Not required | The training program should be based on a multidisciplinary approach that includes specific modern investigative techniques (financial forensics, etc.) |
|  |  | Conduct training of police officers according to the curriculum | permanent | МoI, Directorate for Police Education and Academy of Criminalistic and Police Studies | The curriulum is implemented at the annual level | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Carry out annual evaluation of effects of the training conducted | once in a calendar year | МoI, Directorate for Police Education and Academy of Criminalistic and Police Studies | Results of annual testing | 500.000 annualy (Evaluation experts, costs of surveys and interviews) |  |
| 3.5.1.2 | Amending the Law on Police and the Act on Systematization and Internal Organization - MoI, for the purposes of establishing efficient mechanisms for coordination of anti-corruption actors in terms of strategy, tactic and operation | Formulate and submit draft amendments to the law | 8 months | The Ministry competent for internal affairs | Draft amendments to the law are submitted to the Government | 1.600.000 (costs of public hearings) |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 10 months | The Government of the RS | Proposed amendments to the law are submitted | Not required |  |
|  |  | Adopt amendments to the law | 14 months | The National Assembly of the RS | The law is adopted | Not required |  |
|  |  | Develop amendments to the Act on Systematization of Job Positions | 3 months | The Ministry competent for internal affairs | Proposed admendments to the Act are submitted to the Office of the line Minister | Not required |  |
|  |  | Adopt amendments to the Act on Systematization of Job Positions | 5 months | The Ministry competent for internal affairs | The Act came into force | Not required |  |
| 3.5.1.3 | Improving material and technical conditions of work, and organizational and personnel structure of anti-corruption actors within the police | Establish an anti-corruption organizational unit in the Criminal Police Directorate | 14 months | The Ministry competent for internal affairs | The act on establishing the organizational unit is adopted | Funds for personal incomes, equipment and professional training In accordance with the needs analysis |  |
|  |  | Establish separate organizational units within the Criminal Police Directorate in Belgrade and Criminal Police Department in Novi Sad , Kragujevac and Niš, and detrermine contanct persons in other RPDs | 14 months | The Ministry competent for internal affairs | The act on establishing the organizational unit is adopted | Funds for personal incomes, equipment and professional training in accordance with the needs analysis |  |
|  |  | Increase the number of members of the Sector of Internal Control of the Police in accordance with EU strandards, to the level of 1% of employees in the MoI | 2 years | The Ministry competent for internal affairs | The Sector of Internal Control is staffed to the level of 1% of employees in the MoI | Funds for personal incomes, equipment and professional training in accordance with the needs analysis |  |
| 3.5.1.4. | Establishing efficient mechanisms for internal and external coordination between anti-corruption actors in terms of strategy, tactic and operation | Develop a normative framework for creating, access, administration, use and changes of the single data base on perpetrators of criminal offenses in the field of corruption | 8 months | The Ministry competent for internal affairs | The act defining creation, access, administration, use and changes to the single database on perpetrators of criminal offenses in the field of corruption is adopted | Experts in the field of legislation; information on best practices in accordance with the needs analysis |  |
|  |  | Create a single database of perpetrators of criminal offenses in the field of corruption | 18 months | The Ministry competent for internal affairs | The single database is used in everyday work of the MoI | Experts for programming, software solutions and hardware |  |
|  |  | Establish procedures for direct coordination and early warning between the police and prosecution | 12 months | The Ministry competent for internal affairs | The acts regulating coordination and early warning procedures are adopted | Preparation of information on best practices |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.5 POLICE |  |  |  |  |  |  |  |
| 3.5.2 | Objective | Strengthen integrity and internal control mechanisms for the purposes of combating corruption in the police sector |  |  |  |  |  |
|  | Indicator | The Corruption Perception Index in the police sector is reduced according to public opinion polls conducted in the Republic of Serbia |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
|  | Organizational integration of control of legality of actions and work of the police in the MoI Sector of Internal Control and improvement of coordination with the Internal Control Service | Normative and operational integration of control of legality of actions of the police, other organizational units and the Office for complaints and appeals in the MoI Sector of Internal Control | 6 months | The Office of the Minister competent for internal affairs | The acts integrating the process of control of police actions are adopted | Not required |  |
|  |  | Increase the number of employees in the Sector of Internal Control | 6 months | The Office of the Minister competent for internal affairs | The number of employees in the Sector of Internal Control has increased in 10 % by the end of the calendar year | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Provide technical equipment in the MoI Sector of Internal Control | 6 months | The Office of the Minister competent for internal affairs | Accounts of the acquired equipment, reports on donations | Funds for technical equipment In accordance with the needs analysis |  |
| 3.5.2.1 | Building capacities for the execution of internal control by developing control and instruction activities | Adopt guidelines on the manner and forms of conducting internal control | 6 months | The Office of the Minister competent for internal affairs | The guidelines are published and in effect | Not required |  |
|  |  | Adopt a Rulebook on collecting, processing and analysis of data on corruption for the purposes of a risk analysis and assessment of the situation | 6 months | The Office of the Minister competent for internal affairs | The Rulebook is published and in effect | Not required |  |
|  |  | Develop preventive plans of headquarter directorates | once a year | Police directorates in the headquarters | The number of adopted preventive plans | An analysis of best practices and models for preventive plan development |  |
|  |  | Develop preventive plans of regional police directorates | once a year | Regional police directorates | The number of adopted preventive plans | An analysis of best practices and models for preventive plan development |  |
|  |  | Develop annual reports on preventive plans implementation | once a year | Police directorates in the headquarters | The report is published on the MoI website | Not required |  |
| 3.5.2.3 | Developing mechanisms for the strengthening of police officers integrity | Conduct all activities envisaged by the Integrity Plan in set periods of time | 3 years | The Ministry competent for internal affairs | Assessment of fulfillment of the integrity plan given by the ACA | Resources envisaged by the integrity plan |  |
|  |  | Conduct an analysis of a risk of corruption in the organizational structure of the police | once a year | The Ministry competent for internal affairs, Sector for Internal Control (SIC) | The risk analysis document is developed | An analysis and experts' advice on best practice |  |
|  |  | Implement measures for the strengthening of integrity of employees in the positions holding a risk of corruption | permanent | The Ministry competent for internal affair, SIC | The number of measures implemented | An analysis and experts' advice on best practice |  |
|  |  | Establish a test integrity mechanism | 1 year | The Ministry competent for internal affair, SIC | The integrity test is used in work of the SIC | Test equipment and running costs |  |
|  |  | Ensure monitoring of the implementation of the Code of Police Ethics and sanction its violation | once a year | The Ministry competent for internal affair, SIC | The number of sanctions imposed at the annual level | Not required |  |
|  |  | Publicly disclose quarterly reports on anti-corruption results achieved by the MoI | quarterly | The Ministry competent for internal affair | Reports are published quarterly on the MoI website | Not required |  |
| 3.5.2.4 | Establishing a personnel monitoring and development system together with the Sector of Internal Control through control of integrity of a person in his/her professional career | Adopt an act on the organization of material and criteria for career advancement | 6 months | The Ministry competent for internal affair | The act is adopted and entered into force | An analysis of best practice |  |
|  |  | Develop bi-annual reports on consistent application of standards for career advancement prepared by the Human Resource Management Service | every two years | The Human Resource Management Service | The report is published on the MoI website | Not required |  |

3.6. SPATIAL PLANNING AND CONSTRUCTION

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.6 SPATIAL PLANNING AND CONSTRUCTION |  |  |  |  |  |  |  |
| 3.6.1 | Objective | Register all the real estate and utility lines in the Republic of Serbia and related data in the public electronic Real Estate and Utility Lines Cadastre. |  |  |  |  |  |
|  | Indicator | Number of the real estate and utility lines which are registred is increasing by 15% annually relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.6.1.1 | Providing an information desk and free legal assistance in real estate cadastre services | Make amendments to the Systematization Act by introducing appropriate posts | 6 months | The Republic Geodetic Authority, Real Estate Cadastre Services and the Ministry responsible for construction and urban planning | The Systematization Act envisages posts for work at the information counter | Not required |  |
|  |  | Employ qualified personnel in accordance with the systematization | 15 months |  | The number of employed qualified personnel matches the number in the systematization act | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Prepare the customers' manual and information flyers with the data about procedures and documents required | 12 months |  | The customers' manual and information flyers with the data about procedures and documents required are available to the citizens | 5.000.000 |  |
|  |  | Educate employees at the information desk about relations with customers | 18 months |  | The number of conducted training sessions | In accordance with the needs analysis (for each training 300.000) |  |
| 3.6.1.2 | Adopting amendments to the Regulation on Compensation for the Use of Surveying and Cadastre Data | Introduce incentive mechanisms for timely reporting on data amendments and set objective criteria for urgent registration in the cadastre | 6 months | The Ministry of Construction and Urban Planning | The Regulation on Compensation on Compensation for the Use of Surveying and Cadastre Data contains the stated incentives and criteria | Not required |  |
| 3.6.1.3 | Organizing a campaign for the promotion of the electronic real estate cadastre, registered real estate values, and required procedures and documents | Prepare a program and manner of conducting the campaign, ensure supporting materials and media coverage | 6 months | The Republic Geodetic Authority, Real Estate Cadastre Services and the Ministry responsible for construction and urban planning | Materials, campaign program, media reports | 2.000.000 |  |
|  |  | Conduct the campaign | 18 months |  | Campaign is organized and conducted | 3.000.000 |  |
| 3.6.1.4 | Building capacities of organizational units in real estate cadastre services as well as of the internal control within the Sector for Professional and Administrative Supervision in the Republic Geodetic Authority | Conduct the needs analysis | 9 months | The Republic Geodetic Authority, Real Estate Cadastre Services and the Ministry responsible for construction and urban planning | The needs analysis is conducted | Not required |  |
|  |  | Employ qualified personnel in accordance with the needs analysis | 15 months |  | The number of employed qualified personnel matches the number in the needs analysis | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Professional training of employees | permanent |  | The number of organized and conducted professional training sessions | In accordance with the needs analysis (for each training 300.000) |  |
| 3.6.1.5 | Amending the Rulebook on Geodetic-Cadastral Information System and the Rulebook on the Manner of Keeping, Inspection and Issuance of Cadastral Information | Adopt amendments to the Rulebook by also enabling appropriate registered access for natural persons | 6 months | The Republic Geodetic Authority | Amendments to the Rulebook are adopted | Not required |  |
|  |  | Change the electronic cadastre database | 18 months |  | Natural persons have registered access to the electronic cadastre | In accordance with the needs analysis and software |  |
| 3.6.1.6 | Adopting the Rulebook which harmonizes the manner of issuance of a cadastral certificate so that it has a form of an electronic document and contains an electronic signature | Formulate and adopt the Rulebook to comply with the Law on Electronic Signature and the Law on Electronic Document | 6 months | The Republic Geodetic Authority | The cadastral certificate has a form of an electronic document and contains an electronic signature | Not required |  |
|  |  | Change the electronic cadastre database | 18 months | The Republic Geodetic Authority |  | In accordance with the needs analysis and software |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.6 SPATIAL PLANNING AND CONSTRUCTION |  |  |  |  |  |  |  |
| 3.6.2 | Objective | Reduce the number of procedures and introduce a single window system for issuing building and other permits and approvals. |  |  |  |  |  |
|  | Indicator | The number of permits and approvals issued through the single window system reaches TBD in 2017. The amount of time required to issue a building permit decreases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.6.2.1 | Amending the Law on Planning and Construction so as to simplify procedures and make them match the type of a building | Formulate and propose amendments to the law | 12 months | The Ministry competent for construction and urban planning | Draft amendments to the law is submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposed law on amendments to the National Assembly | 15 months | The Government of the Republic of Serbia | Proposal of amendments to the law is submitted to the NA | Not required |  |
|  |  | Adopt the law on amendments | 17 months | The National Assembly | The law on amendments is adopted | Not required |  |
| 3.6.2.2 | Ensure professional training of employees in new solutions of the law before its implementation | Prepare professional training program and manuals | 17 months | The Ministry of Construction and Urban Planning | Professional training program | Not required |  |
|  |  | Organize and conduct professional training | until commencement of the application of the Law |  | Professional training is organized and conducted | In accordance with the needs analysis (at least 50.000 gross per employee) | If necessary, professional training can be continued after implementation of the law |
| 3.6.2.3 | Carrying out a campaign aimed at informing the public about the procedure | Organize and conduct campaigns | permanent | The Ministry of Construction and Urban Planning | Campaigns are organized and conducted | 5.000.000 |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.6 SPATIAL PLANNING AND CONSTRUCTION |  |  |  |  |  |  |  |
| 3.6.3 | Objective | Ensure transparency of criteria and involvement of the public in the process of consideration, amendments and adoption of spatial and urban plans at all levels of the government. |  |  |  |  |  |
|  | Indicator | The percentage of plans on which public consultation is held annually increases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.6.3.1 | Amending the Law on Planning and Construction so as to introduce an obligation of early notification about the commencement of development of plans as well as draft plan publication on websites | Formulate and propose amendments to the law | 12 months | The Ministry competent for construction and urban planning | Draft amendments to the law submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposed law on amendments to the NA | 15 months | The Government of the Republic of Serbia | Proposal of amendments to the Law is submitted to the NA | Not required |  |
|  |  | Adopt the law on amendments | 17 months | The National Assembly | The law on amendments is adopted | Not required |  |
| 3.6.3.2 | Amending the Rulebook on the Manner of Development and Contents of Planning Documents so as to harmonize and standardize the contents of plans and to clearly define purposes and general principles of compatibility of purposes | Harmonize and standardize the contents of plans, define purposes and general principles of compatibility of purposes; | 20 months | The Ministry competent for construction and urban planning | The Rulebook on the Manner of Development and Contents of Planning Documents is amended | 500.000 (Experts, information on best practices; costs of publishing) |  |
|  |  | Publish standardized contents of plans | 20 months |  |  |  |  |
| 3.6.3.3 | Organizing campaigns for informing the public about the importance of early inspection of plans and public hearings | Create a manual for modalities of citizens' participation in the development of plans at an early stage | 12 months | The Ministry competent for construction and urban planning, the Ministry of Natural Resources, Mining and Spatial Planning | The manual for modalities of citizens' participation at an early stage | 5.000.000 | The Ministry competent for construction and urban planning, the Ministry of Natural Resources, Mining and Spatial Planning; All in cooperation with local self-government units. It is more favorable also to involve the Civil Society Organization. |
|  |  | Organize and conduct campaigns in local self-government units | 24 months |  | Campaigns are organized and conducted | 5.000.000 |  |
| 3.6.3.4 | Adopting the guidelines for uniform actions of local self-government units in the field of issuance of building and other permits and approvals, legalization process and land conversion. | Adopt the guidelines and forward them to all local self-government units | 6 months | The Ministry competent for construction and urban planning | The guidelines are adopted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.6 SPATIAL PLANNING AND CONSTRUCTION |  |  |  |  |  |  |  |
| 3.6.4 | Objective | Ensure efficient internal and external control in the process of issuing building and other permits and approvals in the field of urban planning. |  |  |  |  |  |
|  | Indicator | The number of inspections conducted according to an annual plan increases by 75% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.6.4.1 | Provide citizens with access to the web portal for case progress monitoring | Feasibility studies for the introduction of a web portal for case progress monitoring | 15 months | The Ministry competent for construction and urban planning | Report on the study | Experts, IT technology, information on best practices; (at least 500.000) | Similar to the court portal for case progress monitoring |
|  |  | Amendments to regulations for the purposes of introducing legal grounds | 25 months |  | Regulations are amended | Not required |  |
|  |  | Procurement of equipment and software development | 35 months |  | Report on work | In accordance with the needs analysis (50.000.000) |  |
| 3.6.4.2 | Professional training of employees | Prepare professional training program and manuals | 35 months | The Ministry competent for construction and urban planning | Professional training program | Not required |  |
|  |  | Organize and conduct professional training | until beginning of the use of the web portal |  | Professional training is organized and conducted | In accordance with the needs analysis (for each training 300.000) |  |
| 3.6.4.3 | Organizing a campaign for informing the public | Organize and conduct campaigns | permanent | The Ministry competent for construction and urban planning | Campaigns are organized and conducted | 5.000.000 |  |
| 3.6.4.4 | Amending the Law on Planning and Construction so as to expand the network of inspection services | Conduct the analysis of needs for the extension of the seat of inspection services | 6 months | The Ministry competent for construction and urban planning | Report on the conducted analysis | Not required |  |
|  |  | Prepare amendments to the Law so that expansion of the network of inspection services is carried out in compliance with the analysis | 15 months |  | The draft amendments to the Law are submitted to the Government | Not required |  |
|  |  | Submit a proposed law on amendments to the NA | 17 months | The Government of the RS | A proposal of amendments to the Law is submitted to the NA | Not required |  |
|  |  | Adopt the law on amendments | 18 months | The National Assembly | The law on amendments is adopted | Not required |  |
| 3.6.4.5 | Strengthening capacities of inspection services | Conduct the needs analysis | 9 months | The Republic Geodetic Authority, Real Estate Cadastre Services and the Ministry responsible for construction and urban planning | The needs analysis is conducted | Not required |  |
|  |  | Employ qualified personnel in accordance with the analysis | 15 months |  | The number of employed qualified personnel matches the number in the needs analysis | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Professional training of employees | permanent |  | The number of organized and conducted professional training sessions | In accordance with the needs analysis (for each training 300.000) |  |
| 3.6.4.2 | Improving proactive approach of inspection services by envisaging a larger number of inspections in the annual plan | The annual plan of inspection services should envisage a larger number of inspections | permanent | The Ministry competent for construction and urban planning | The number of conducted inspections | Cost of inspection, petrol, equipment, at least 30,000 for each |  |

3.7. HEALTH CARE SYSTEM

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.7 HEALTH CARE SYSTEM |  |  |  |  |  |  |  |
| 3.7.1 | Objective | Identify and eliminate all deficiencies in the legal framework that pose a risk of corruption. |  |  |  |  |  |
|  | Indicator | The number of well-founded complaints per year that are related to the health sector decreases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.7.1.1 | Amending the Law on Health Care, the Law on Health Insurance, the Law on the Chambers of Health Care Professionals and the Law on Medicines and Medical Devices to eliminate deficiencies that pose a risk of corruption | Develop a methodology for the analysis of effects and risks of corruption in the field of health care | 6 months | The Anti-Corruption Agency | The methodology is developed | Not required | It is necessary to change the legal framework so that the appointment of directors of health care institutions and health care workers is performed through a competition and on the basis of determined objective criteria; to introduce the electronic information system for tracking the flow of money, especially non-standard services and ones own revenues (separately from the information system for the provision of health care services); to introduce mechanisms of financial motivation of employees in the field of health care based on performance; to precisely regulate legal conditions under which health care workers in pubic institutions can render health care services in private institutions; to regulate the status of health care workers in accordance with the status of public service employees |
|  |  | Conduct an analysis of corruption provisions of stated systemic laws in the field of health care | 12 months since the development of the methodology (18 months in total) | The Ministry competent for health care, the Health Forum, the National Health Insurance Fund | The Ministry competent for health care adopted a decision on establishing a working group which includes the Health Forum; the analysis is conducted | 20.000.000 (Experts, information on best practices) |  |
|  |  | Formulate and submit draft amendments to the law | 24 months | The Ministry competent for health care | Draft amendments to the Law are submitted to the Government | 1.600.000 (costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 25 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments for the purposes of adoption | 26 months | The National Assembly | Laws on amendments are adopted | Not required |  |
| 3.7.1.2 | Harmonizing by-laws with amendments to the Law on Health Care, the Law on Health Insurance, the Law on the Chambers of Health Care Professionals and the Law on Medicines and Medical Devices | Harmonize and adopt by-laws | 30 months | The Ministry competent for health care | All by-laws are harmonized with amendments to the law | Not required |  |
| 3.7.1.3 | Continuing with the analysis of the entire legal framework for health in terms of corruption | Conduct an analysis of corruption provisions of all the laws in the field of health care | from the 30th month onwards, for one year (42 months) | The Ministry competent for health care, the Health Forum, the Republic Secretariat for Health | The Ministry competent for health care adopted a decision on establishing a working group which includes the Health Forum; the analysis is conducted | 50.000.000 (Experts, information on best practices) |  |
|  |  | Formulate and submit draft amendments to the law in accordance with the analysis | 48 months | The Ministry competent for health care | Draft amendments to the law are submitted to the Government | Not required |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 50 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Put a proposed law on amendments on the NA's agenda for adoption | 51 months | The Speaker of the National Assembly | A proposed law is on the NA's agenda | Not required |  |
| 3.7.1.4 | Ratifying the European Charter of Patients' Rights from 2002 | Prepare and submit the Law on the Ratification of the European Charter of Patients' Rights from 2002 | 6 months | The Ministry competent for health care | Draft amendments to the law are submitted to the Government | 100.000 Costs of authorized translation |  |
|  |  | Submit a proposed law to the National Assembly | 8 months | The Government of the Republic of Serbia | A proposed law is submitted | Not required |  |
|  |  | Adopt the law on amendments for the purposes of adoption | 10 months | The National Assembly | Laws on amendments are adopted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.7 HEALTH CARE SYSTEM |  |  |  |  |  |  |  |
| 3.7.2 | Objective | Provide efficient mechanisms for integrity, accountability and transparency in the adoption and implementation of decisions |  |  |  |  |  |
|  | Indicator | Conflict of interest standards have been published for all aspects of clinical trials and donations by 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.7.2.1 | Improving cooperation and coordination of anti-corruption activities between relevant institutions | Conclude a memorandum on cooperation between the ministries competent for health care, justice, internal affairs, the Health Committee of the National Assembly, the Republic Prosecutor's Office, SAI and ACA | 3 months | The Ministries competent for health, justice, internal affairs, the Health Committee of the National Assembly, the Republic Prosecutor's Office , SAI and ACA | A concluded memorandum on cooperation determining contact points and the method of work. | Not required | The work involves professional associations, the Chambers of Health Care Professionals |
| 3.7.2.2 | Amending the Law on Health Care and the Law on Medicines and Medical Devices so as to regulate with clear and transparent rules the field of donation of medical devices, the relation with the pharmaceutical industry, amount and treatment of gifts, as well as the conflict of interest of health care workers and associates, and persons performing functions (and do not have the status of an official in terms of the Law on the Anti-Corruption Agency) | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for health | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments for the purposes of adoption | 17 months | The National Assembly | Laws on amendments are adopted | Not required |  |
| 3.7.2.3 | Amending the Law on Donations and Humanitarian Aid so as to introduce obligations in terms of donations in the health care system for the purposes of establishing a committee that will assess viability, costs and cost-effectiveness of donations | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for financial affairs | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | The Commission is established at the level of a health care institution; In cooperation with the Ministry competent for health |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt the law on amendments for the purposes of adoption | 17 months | The National Assembly | Laws on amendments are adopted | Not required |  |
| 3.7.2.4 | Building inspection capacities within the Ministry competent for health care | Conduct an analysis of needs of the health inspection | 12 months | The Ministry competent for health | The needs analysis is conducted | Not required |  |
|  |  | Employ the matching number of qualified personnel in accordance with the needs analysis | 36 months | The Ministry competent for health | The number of qualified personnel matches the needs | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Professional training of employees | permanent |  | The number of conducted professional training sessions | In accordance with the needs analysis (for each training 300.000) |  |
|  |  | Provide equipment in accordance with the needs analysis | 36 months |  | The equipment matches the needs analysis | In accordance with the needs analysis |  |
| 3.7.2.5 | Improving the quality control and implementation of the program for continuous professional training by the Health Council | Conduct an analysis of reasons why control is not carried out or ensured transparency of reporting on results | 3 months | The Health Committee, the Government of the RS | A report with recommendations | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | The Health Council should check whether the accredited program is really implemented in the manner it was approved. |
|  |  | Create a report with specific recommendations to address deficiencies | 6 months | The Health Committee, the Government of the RS |  | Not required |  |
|  |  | Submit a report to the Government of the RS on the execution of recommendations from the report | permanent | The Health Committee | A report on the execution of recommendations | Not required |  |
| 3.7.2.8 | Introducing the obligation of preparing and publishing a report on completed public procurements in the field of health care. | Create and publish a report after every procurement | permanent | The Ministry competent for health | Reports are published after every procurement | The cost of publishing and maintaining web-presentation (average 50,000 per month) | For every health care institution |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.7 HEALTH CARE SYSTEM |  |  |  |  |  |  |  |
| 3.7.3 | Objective | Ensure a transparent information system in the health care system and participation of the public in the control of work of health care institutions |  |  |  |  |  |
|  | Indicator | The percentage of public medical institutions fully converted to a unified electronic system of health records that has been approved by the Commissioner for Information of Public Importance and Personal Data Protection is 75% or above in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.7.3.1 | Adopting a new Law on Health Records to enable the use of electronic medical documents and introduction of a uniform information system | Formulate and submit a law | 18 months | The Ministry competent for health | A draft law submitted to the Government | Not required | Harmonize with international standards |
|  |  | Submit a proposed law to the National Assembly | 21 months | The Government of the Republic of Serbia | A proposed law is submitted | Not required |  |
|  |  | Adopt the law | 23 months | The National Assembly | The law is adopted | Not required |  |
| 3.7.3.2 | Creating a uniform information system at all levels of health care | Create a uniform database of waiting lists for specialist medical examinations and surgical procedures | 5 years | The Ministries competent for financial affairs, health, education, for labor and social policy | A uniform database of waiting lists for specialist medical examinations and surgical procedures is accessible to the public and is regularly updated | In accordance with the needs analysis (at least 20.000.000 gross per employee) | The time for establishing the stated databases shall commence with the implementation of the Law on Electronic Signature, the Law on Electronic Document, and with other laws which are a prerequisite for the use of the databases |
|  |  | Create a database of suppliers of medicines and medical materials with average prices. |  |  | A database of suppliers of medicines and medical materials with average prices is accessible to the public and is regularly updated | In accordance with the needs analysis (at least 20.000.000 gross per employee) |  |
|  |  | Create a central register of issued invoices for medical services. |  |  | A central register of issued invoices for medical services is accessible to the public and is regularly updated | In accordance with the needs analysis (at least 20.000.000 gross per employee) |  |

3.8. EDUCATION AND SPORT

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.8 EDUCATION AND SPORT |  |  |  |  |  |  |  |
| 3.8.1 | Objective | Change the legal framework for the appointment , position and powers of the directors of primary and secondary schools, as well as deans of the faculties |  |  |  |  |  |
|  | Indicator | The percentage of directors, deans, and faculty per year who receive scores of [satisfactory] or better on evaluation by the independent commission reaches 75% in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.8.1.1 | Amending the Law on Primary and Secondary Education and the Law on Higher Education so as to introduce the legal obligation of appointment, periodical evaluation of work and performance of directors, deans and teachers, on the basis of objective, clear, precise and pre-determined criteria. | Conduct an analysis of regulations in terms of a risk of corruption | 10 months | The Ministry competent for education and science | A report on the analysis | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | Director cannot be appointed to this function more thatn two times and the employment period at the post from which he/she was appointed will be frozen during both terms of office; discretionary powers of directors, deans and teachers/professors should be limited as much as possible with objective, precise, clear and pre-determined criteria; their discretionary decisions must be reasoned and transparent; revize and equalize the salary range; the comissions for the selection of employment candidates should consist of the school director, representatives of school boards, employees and parents, and an external expert. Minutes from the discussion should be saved in case of a complaint. |
|  |  | Formulate and submit draft amendments to the law | 12 months |  | Draft amendments to the law are submitted to the Government |  |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt a proposal of amendments to the law | 17 months | The National Assembly | The law on amendments to the Law on Primary and Secondary Education and the Law on Higher Education is adopted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.8 EDUCATION AND SPORT |  |  |  |  |  |  |  |
| 3.8.2 | Objective | Strengthen capacities of the education inspection |  |  |  |  |  |
|  | Indicator | The number of inspections per year that result in negative findings decreases by 50% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.8.2.1 | Conducting an analysis of the laws governing the field of education inspection | Analyze regulations governing the education inspection | 7 months | The Ministry competent for education; ACA | A report on the analysis | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | The normative framework in the Republic of Serbia is not fully capable of ensuring transparent operation of schools and the use of privately raised funds. It does not determine permitted sources of school revenues. Determine a list of permissible sources of school revenues to ensure that economic activities in schools do not have a negative influence on the process of education. Review the rules for giving classes to teachers' own pupils / professors' own students and for the preparation for entrance exams for higher education in terms of conflict of interest and a risk of corruption. |
|  |  | Define what regulations need to be amended/adopted | 7 months |  | A report on the analysis |  |  |
|  |  | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for education | Draft amendments to the law are submitted to the Government | Not required |  |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt a proposal of amendments to the law | 17 months | The National Assembly | The law on amendments to the Law on Primary and Secondary Education and the Law on Higher Education is adopted | Not required |  |
| 3.8.2.2 | Building inspection capacities in the field of education at all levels of the government | Conduct an analysis of the number and structure of required personnel, and of other needs | 7 months | The Ministry competent for education | A report on the analysis | Not required | Particularly pay attention to the financial control of school revenues as it is not strong enough to be adequate and to control the inflow of private funds into the system. Additional oversight is recommended to be ensured through proper operation of school boards cooperating with the education inspection to ensure that employees do not undermine the process of procurement of textbooks. Develop and strengthen the supervisory capacity of local authorities. |
|  |  | Increase the number of employees in the education inspection in accordance with the analysis | 15 months |  | A report on work; the number and structure of employees | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Provide equipment in accordance with the analysis | 25 months |  | A report on work | In accordance with the needs analysis (at least 3.000.000) |  |
|  | Adopting and implementing the Code of Conduct for teachers | Adopt the Code of Conduct, submit it to all school facilities | 6 months | The Ministry competent for education | A Code of Conduct for teachers/professors | Not required |  |
|  |  | Conduct a campaign for the purposes of introducing teachers/professor and pupils/students to the rules of the Code | 18 months |  | The number of organized and conducted activities in the campaign | 5.000.000 |  |
|  | Re-examining requests for the conclusion of lease agreements for school facilities | Process and record all requests for the conclusion of lease agreements for school facilities to gain a more accurate insight into the scope and value of school obligations under the agreement, as well as of any irregularities. | 15 months | The Ministry competent for education; Republic Directorate for Property | A report on records about the lease agreements | Not required |  |
|  | Improving the mechanism for complaints and appeals in the Ministry competent for education | The citizens should be informed about the procedures for complaints and submissions as well as about measures taken on the basis of their complaints. | permanent | The Ministry competent for education | A report on work | Not required |  |
|  |  | Conduct qualitative inspection of the most common appeals and analyze their causes. | annually |  | A report on work | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.8 EDUCATION AND SPORT |  |  |  |  |  |  |  |
| 3.8.3 | Objective | Ensure transparency of the procedures for registration and evaluation of knowledge in all academic institutions |  |  |  |  |  |
|  | Indicator | The percentage of oversight reviews that result in disciplinary action decreases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.8.3.1 | Amending the Law on Primary and Secondary Education and the Law on Higher Education so that the enrollment procedure and criteria are objective as much as possible | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for education and science | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | The enrollment procedure should be as transparent as possible and it should not interfere with the privacy of pupils and students; control of the regularity of the procedure should last no longer than three months after completion of the enrollment procedure for the purposes of initiating appropriate actions against the persons responsible; private lessons and preparatory admission courses cannot be given by persons participating in the entrance examination process. |
|  |  | Submit a proposal to the National Assembly of amendments to the law | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt a proposal of amendments to the law | 17 months | The National Assembly | The law on amendments to the Law on Primary and Secondary Education and the Law on Higher Education is adopted | Not required |  |
| 3.8.3.2 | Intensifying efforts to make the central management information system in education fully operational. | Consolidate existing data collection and information systems and eliminate overlapping | 24 months | The Ministry competent for education and science, Statistical Office | A report on work | 50.000.000 | For example, a measure may be carried out by agreeing on the feasible allocation of responsibilities for data collection between the ministry competent for education and science, the Statistical Office and educational institutions. |
|  |  | Invest in the expansion of analytical capacities of the institutions in charge of data processing | 24 months |  | A report on work | 30.000.000 |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.8 EDUCATION AND SPORT |  |  |  |  |  |  |  |
| 3.8.4 | Objective | Ensure that the process of accreditation and subsequent control of fulfillment of conditions for work of public and private educational institutions is based on clear, objective, transparent and pre-determined criteria. |  |  |  |  |  |
|  | Indicator | The number of inspections per year made by the Accreditation Commission as an independent agency reaches TBD in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.8.4.1 | Improving work of the Accreditation and Quality Assurance Commission (AQAC) | Make necessary amendments to the quality assurance standards with full participation of the academic community, students and employers | 24 months | AQAC and the Ministry competent for education and science | An act on amended quality assurance standards | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) | The external quality assurance and the accreditation process in the future should be conducted by the national body that operates independently from the academic community and the ministry and that is a full member of the international associations ENQA and EQAR. On the basis of positive experience of other countries, the Accreditation and Quality Assurance Commission may be transformed to the National Accrediting Agency which will operate as a highly professional independent institution. |
|  |  | Include independent (domestic ad foreign) experts, students and employers in the accreditation process | permanent | AQAC and the Ministry competent for education and science | A report on work | Not required |  |
|  |  | Publicly disclose reports on the findings of reviewers and the AQAC relevant for the adoption of the accreditation decision. | permanent | AQAC and the Ministry competent for education and science | A report on work (published reports relevant for the adoption of the accreditation decision) | Not required |  |
|  |  | Publish reports on work at least once a year | at least once a year | AQAC | A report on work | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.8 EDUCATION AND SPORT |  |  |  |  |  |  |  |
| 3.8.5 | Objective | Establish transparency in the sports financing and ownership structure of sports clubs and federations |  |  |  |  |  |
|  | Indicator | The normative framework for transparent funding of sport, planned in measures under this objective, are adopted at the national, provincial and local level by the end of the 2015. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 3.8.5.1 | Adopting amendments to the Law on Sports for the purposes of determining the status of sports federations and associations, property ownership, and financing from public funds at the national and local level | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for sports | Draft amendments to the law is submitted to the Government | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |
|  |  | Submit a proposal of amendments to the law to the National Assembly | 15 months | The Government of the Republic of Serbia | A proposal of amendments to the law is submitted | Not required |  |
|  |  | Adopt amendments to the law | 20 months | The National Assembly | The law is adopted | Not required |  |
| 3.8.5.2. | Amending by-laws that will regulate transparent financing of sports activities at all levels of the government | Adopt amendments to the Rulebook on the approval and financing of programs for achieving general interest in the field of sports in (1) the Republic of Serbia; (2) at the level of the autonomous province and (3) local self-government units | 12 months | (1) The Ministry of Youth and Sports; (2) The Provincial Secretariat for Sports; (3) The City Secretariat for Sports | The Rulebook on the financing of programs for achieving general interest in the field of sports is adopted in the Republic of Serbia; at the level of the autonomous province and local self-government units | Not required |  |
| 3.8.5.3. | Categorizing and ranking sports organizations at the national level, the level of autonomous provinces and local self-governments, on the basis of clear criteria | Formulate and submit amendments to the Rulebook on the categorization of sports organizations at the level of autonomous provinces, adhering to the national categorization | 12 months | Autonomous provinces | The Rulebook on the categorization of sports organizations is adopted in the autonomous provinces | Not required |  |
|  |  | Formulate and submit amendments to the Rulebook on the categorization of sports organizations at the level of local self-governments, adhering to the national categorization | 12 months | Local self-government units | The Rulebook on the categorization of sports organizations is adopted at the level of autonomous provinces | Not required |  |
|  |  | Make rankings of sports organizations in the Republic of Serbia according to categories | 24 months | The Ministry of Youth and Sports | Ranking of sports organizations made in the Republic of Serbia | Not required |  |
|  |  | Make rankings of sports organizations at the level of autonomous provinces | 24 months | Autonomous provinces | Ranking of sports organizations made in autonomous provinces | Not required |  |
|  |  | Make rankings of sports organizations in local self-government units | 24 months | Local self-government units | Ranking of sports organizations made in local self-government units | Not required |  |
| 3.8.5.4 | Developing a Rulebook on the allocation of funds for sports in public companies on the basis of clear criteria, and abolishing discretionary rights of directors of public companies to the allocation of companies' funds to sports organizations on the basis of no criteria | Adopt the Rulebook on the allocation of funds in public companies for financing programs in the field of sports | 12 months | The Ministry of Youth and Sports | The Rulebook on the allocation of funds in public companies for financing programs in the field of sports is adopted and effective | Not required | The development should include: the Olympic Committee of Serbia, the Sports Federation of Serbia, the Institute of Sports Medicine and Sports and representatives of public companies |
| 3.8.5.5 | Changing the normative framework regulating the profession of sports managers in terms of conflict of interest in carrying out activities, and financial flows in this field | Formulate and adopt amendments to the Rulebook on the Nomenclature of Sports Professions so as to introduce provisions on the prohibition of conflict of interest in the profession of sports manager | 12 months | The Ministry of Youth and Sports | The Rulebook is adopted and effective | Not required |  |
|  |  | Carry out an analysis and provide recommendations for the improvement of the existing wider normative framework regulating the work of sports managers and the financial segment of their work, in order to harmonize them with international sports rules and standards for transparent business operations | 24 months | The Ministry of Youth and Sports | The analysis document is prepared and published | 1.600.000 (Experts in the field of legislation; IT technology, information on best practices; costs of public hearings) |  |

3.9. MEDIA

| Action Plan to the Anti-Corruption Strategy 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority Area 3.9 - Media |  |  |  |  |  |  |  |
| 3.9.1 | Objective | Transparent ownership, media funding and editorial policy |  |  |  |  |  |
|  | Indicator | Representatives of the Commissioner for Information of Public Importance, independent journalist associations, the Agency and the civil society have agreed to allow the citizens access to information about media ownership and funding. |  |  |  |  |  |
| No. | Measure |  | Deadline (as of the date the Action Plan comes into force) | Responsible actors | Indicators | Resources needed | N.B. |
| 3.9.1.1 | Adopting the Amendments to the Public Information Act, Broadcasting Act, Advertising Act so to enable transparency of information about the ultimate/majority owners, at all levels | Drafting a law regulating public information | 6 months | Ministry competent for public informing | Draft Amendments to the Act delivered to the Government | 1.600.000 (Experts in the field of legislation; information about the best practices; costs of public hearing) | Working group to include representatives of the ministry competent for judicial affairs, trade and commerce, finances and economics, as well as the Anti-Corruption Agency; For public services, it is necessary to regulate the transparency of major financiers and advertisers. |
|  |  | Drafting a law on electronic media (harmonization with the Directive AVMS) | 6 months | Ministry competent for public informing | Draft Amendments to the Act delivered to the Government |  |  |
|  |  | Submitting the Act Amendments Bill to the National Assembly | 9 months | Government of RS | Amendments Bill submitted | Not needed |  |
|  |  | Adopting the Amendments to the Act | 12 months | National Assembly of RS | Act adopted | Not needed |  |
| 3.9.1.2 | Creating, maintaining and regularly updating the public data base/media Registry (ownership structure) | Creating and developing the Registry | 12 months from the day it is created | Public authority determined by the new Act | The created data base has been tested and approved by the public authority newly appointed under the new Act | Experts for creating the data base; website programmers; funds for hardware and maintenance (at least 50.000.000) | Start date is calculated from passing laws regulating the field of public information and electronic media |
|  |  | Drafting the plan and procedures for regular monthly updating | 13 months from the day it is created |  | Plan and procedures adopted | Not needed |  |
|  |  | Regular (monthly) updating and maintenance of the Registry | permanent activity |  | All monthly statements about any changes made in the Registry have been made and delivered to the Anti-Corruption Agency. | IT staff |  |
| 3.9.1.3 | Adopting the Amendments to the Public Companies Act, which prohibits commercial advertising and sponsoring to public companies and business in which the State has shares in ownership, and which are market monopolists | Formulating and submitting the Draft Amendments to the Act | 9 months | Ministry competent for financial activities | Draft Amendments to the Act delivered to the Government | 1.600.000 (Experts in the field of legislation; information about the best practices; costs of public hearing) |  |
|  |  | Submitting the Act Amendments Bill to the National Assembly | 12 months | Government of RS | Amendments Bill submitted | Not needed |  |
|  |  | Adopting the Amendments to the Act | 15 months | National Assembly of RS | Act adopted | Not needed |  |
| 3.9.1.4. | Harmonization of the provisions of national legislation which provides funding of media from the state budgets, at all levels of government, with the EU acquis. | Commencing with the implementation of Action plan for the implementation of media strategy, covering the state aid to the media and its alignment with the acquis. | 15 months | Ministry responsible for public information. | Adopted amendments to regulations | In line with the costs specified in the Media Strategy | Provisions that allow financing of certain media from State budget remain to be harmonized with the EU acquis, as it is a state aid. With Interim Trade Agreement, Serbia has assumed the obligation to harmonize the method of allocation of EU state aid rules. |

IV CORRUPTION PREVENTION

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.1. | Objective | Set up an analysis of the risk of corruption in the process of preparation of regulations |  |  |  |  |  |
|  | Indicator | The number of draft laws submitted to the National Assembly per year that include an analysis of the risks of corruption in the draft law reaches 95% in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.1.1. | Enact the Law on Amendments to the Law on Anti-Corruption Agency so to authorize the Agency to prescribe a methodology for the analysis of effects on corruption in regulations, and bind the proposing bodies to implement it | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for justice | Draft amendments to the law are submitted to the Government | 1.600.000 Experts in the field of legislation; information on best practices; costs of public hearings; | This provision should also include authorities of the territorial autonomy and local self-government units and public authorities when they enact their regulations in accordance with the Law on Public Administration as well as organizations entrusted by the law to exercise public/regulatory powers |
|  |  | Submit to the National Assembly proposed amendments to the law | 15 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted to the National Assembly | Not required |  |
|  |  | Adopt amendments to the law | 20 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.1.2. | Adopting the methodology for the analysis of the risk of corruption in regulations and guidelines for its implementation | Formulate a methodology and guidelines for the implementation of the methodology | 24 months | The Anti-Corruption Agency | The methodology and guidelines for the implementation of the methodology are formulated | Not required |  |
|  |  | Adopt the methodology and guidelines for the implementation of the methodology | 26 months | The Anti-Corruption Agency | The methodology and guidelines for the implementation of the methodology are adopted | Not required |  |
| 4.1.3. | Amending the Rules of Procedure of the National Assembly so to bind the bodies proposing the law to include the analysis of the risk of corruption in the statement of reasons for the proposed law | Formulate amendments to the Rules of Procedure of the National Assembly | 6 months after adoption of the methodology | The National Assembly | Proposed amendments to the Rules of Procedure are submitted | Not required |  |
|  |  | Adopt amendments to the Rules of Procedure of the National Assembly | 3 months after submission of draft amendments to the Rules of Procedure | The National Assembly | Proposed amendments to the Rules of Procedure are adopted | Not required |  |
| 4.1.4. | Amending the Rules of Procedure of the Government of the RS so to determine an obligation of the Government of the RS to submit draft laws and proposed regulations to the ACA for opinion, and to attach ACA's opinion (if submitted within 10 days) to the proposal when submitting it to the National Assembly | Formulate amendments to the Rules of Procedure | 6 months after adoption of the methodology | The Government of the Republic of Serbia | Proposed amendments to the Rules of Procedure are submitted | Not required |  |
|  |  | Adopt amendments to the Rules of Procedure | 3 months after submission of draft amendments to the Rules of Procedure | The Government of the Republic of Serbia | Proposed amendments to the Rules of Procedure are adopted | Not required |  |
| 4.1.5. | Training representatives of the bodies proposing the draft law in implementing the methodology for the analysis of the risk of corruption in regulations according to the plan developed and implemented by the Agency | Adopt the plan for the training of representatives of the bodies proposing the law and other regulations | 26 months | The Anti-Corruption Agency | The plan for the training of representatives of the bodies proposing the law and other regulations is adopted | Not required |  |
|  |  | Organize training according to the adopted plan | permanent task | The Anti-Corruption Agency | The training plan is implemented per year of implementation of the Strategy | 800.000 (Training organization costs) |  |
| 4.1.6. | Training representatives of proposing and enacting bodies, at the level of the territory of the autonomy and local self-government, in implementing the methodology for the analysis of the risk of corruption in regulations according to the plan developed and implemented by the Agency | Adopt the plan for the training of representatives of the bodies proposing and passing regulations | 26 months | The Anti-Corruption Agency | The plan for the training of representatives of the bodies proposing the law and other regulations is adopted | Not required |  |
|  |  | Organize training according to the adopted plan | permanent task | The Anti-Corruption Agency | The training plan is implemented per year of implementation of the Strategy | 800.000 (Training organization costs) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.2. | Objective | Establish the system of employment and promotion in public authorities on the basis of criteria and merits |  |  |  |  |  |
|  | Indicator | The percentage of complaints per year alleging unfair recruitment that are upheld decreases by 30% in 2017, relative to 2012. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.2.1. | Establishing conditions and criteria for employment and promotion in the public sector in accordance with the principles of competition and transparency | Analyze regulations governing employment and legal status in public authorities | 30 months | The Ministry competent for justice and public administration | A report on the conducted analysis | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Formulate and submit draft amendments to the law | 36 months | The Ministry competent for justice and public administration | Draft amendments to the law are submitted to the Government |  |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 39 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted to the National Assembly | Not required |  |
|  |  | Adopt amendments to the law | 40 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.2.2. | Harmonizing the salary system and social rights in public authorities | Analyze regulations governing the salary system and social rights in public authorities | 30 months | The Ministry competent for justice and public administration | A report on conducted analysis and modalities of harmonization | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Develop modalities of harmonization of wages and salaries according to the nature, scope and complexity of work | 36 months |  | A report on conducted analysis and modalities of harmonization |  |  |
|  |  | Amend regulations in accordance with the analysis and modalities of harmonization of wages and salaries and social rights | 39 months |  | Regulations are amended in accordance with the analysis | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.3. | Objective | Ensure transparency of work of public authorities |  |  |  |  |  |
|  | Indicator | The percentage of requests per year to the Commissioner for Information of Public Importance and Personal Data Protection for action on FOIA requests that are upheld decreases by 50% in 2017, relative to 2012. The percentage of public authorities that have posted on their website an up-to-date manual of internal procedures is 95% or above in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.3.1. | Amending the Law on Free Access to Information of Public Importance so to authorize the Commissioner for Information of Public Importance to initiate misdemeanor proceedings against a responsible person that does not act according to a Commissioner's decision or measures, or does not inform the public and the nominating/selecting/appointing authority about the failure to act according to Commissioner's decisions and measures | Formulate and submit draft amendments to the law | 9 months | The Ministry competent for justice and public administration | Draft amendments to the law are submitted to the Government | Not required |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 12 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted | Not required |  |
|  |  | Adopt amendments to the law | 15 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.3.2. | Building capacities of the Commissioner for Information of Public Importance | Conduct the needs analysis | 6 months | The Commissioner for Information of Public Importance | A report on the needs analysis | Not required |  |
|  |  | Change systematization and employ an appropriate number of qualified personnel in accordance with the analysis | 15 months | The Commissioner for Information of Public Importance; Ministry competent for justice and public administration and finance | The number and structure of qualified personnel matches the needs analysis | Not required |  |
|  |  | Educate employees | permanent | The Commissioner for Information of Public Importance | Reports on education, program and evaluation of seminars, participants | In accordance with the needs analysis (each training 300.000) |  |
|  |  | Provide equipment and adequate space | 15 months | The Commissioner for Information of Public Importance; the Government of the RS | Equipment matches the needs | In accordance with the needs analysis |  |
| 4.3.3. | Developing an internal manual on procedures for work of public authorities and publishing it on the website | Develop manuals, distribute them to all employees and publish on the website | 15 months | The Ministry competent for public administration | The Regulation is enacted | 5.000.000 |  |
| 4.3.4. | Changing the legal framework in the field of data confidentiality so to oblige public authorities to adopt guidelines which, in accordance with international standards, define criteria for determining the type and degree of confidentiality, method of handling confidential information, and special safeguards for data confidentiality. | Enact a Regulation determining classification of data confidentiality, the method of handling and safeguards | 3 years | The Government of the Republic of Serbia | The Regulation is enacted | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.4. | Objective | Ensure continuing education about corruption and anti-corruption methods |  |  |  |  |  |
|  | Indicator | There are clear standards and procedures for public participation in government decision making at all levels of government. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.4.1. | Introducing anti-corruption contents in the state qualifying examination | Amend the Regulation on State Qualifying Examination so to introduce anti-corruption contents of regulations and practice in the examination program | 6 months | The Ministry competent for public administration | The Regulation is amended | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
| 4.4.2. | Amending the Law on Civil Servants so to ensure for the High Civil Service Council to monitor implementation of the Code of Ethics, collect information, and conduct analysis | Formulate and submit draft amendments to the law | 9 months | The Ministry competent for justice and public administration | Draft amendments to the law are submitted to the Government | Not required |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 12 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Adopt amendments to the law | 15 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.4.3. | Ensuring that public officials and employees in public authorities receive professional training in the field of anti-corruption, ethics and integrity | Develop professional training curriculum | 6 months | The Anti-Corruption Agency | The curriculum | Not required |  |
|  |  | Organize and conduct professional training | permanent | The Human Resources Management Service of the Government of the RS | The number of conducted professional training sessions, performance evaluation | 3.000.000 | Professional training can be conducted in cooperation with the Judicial Academy |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.5. | Objective | Create conditions for more active participation of civil society organizations in anti-corruption (endowments, foundations and associations) |  |  |  |  |  |
|  | Indicator | The number of companies per year that receive tax deductions for anti-corruption donations or work is TBD or above in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.5.1. | Amending the Regulation on funds for developing programs or missing parts of funds for the financing of programs of public interest implemented by associations so to introduce an obligation for all beneficiaries to also enclose a statement, when applying for the allocation of public funds, on the absence of conflict of interest and an internal act on the anti-corruption policy | Prepare amendments to the Regulation | 6 months | The Ministry competent for public administration | A draft Regulation is submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Adopt the Regulation | 12 months | The Government of the RS | The Regulation is adopted | Not required | An internal act implies all types of acts dealing with the anti-corruption policy, including the Code of Ethics |
| 4.5.2. | Amending the Law on Public Administration so to establish clear standards of cooperation of public authorities with the civil society in accordance with standards of the Council of Europe and the UN Convention Against Corruption (UNCAC) | Formulate and submit draft amendments to the law | 12 months | The Ministry competent for public administration | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) | This refers to consultations and participation of the public in adopting decisions and passing acts |
|  |  | Submit to the National Assembly proposed amendments to the law | 15 months | The Government of the RS | Proposed amendments to the law are submitted | Not required |  |
|  |  | Adopt amendments to the law | 18 months | The National Assembly of the RS | The law is adopted | Not required |  |
| 4.5.3. | Developing a methodology for the monitoring of implementation of the programs/projects financed from budgetary funds, particularly monitoring their implementation in the field and unifying monitoring of the use of funds to prevent inappropriate expenditure of funds | Adopt the methodology and monitor its implementation | permanent | The Ministry competent for finance | A report on the use of funds, a report on the implementation of the project/program | 3.000.000 | In cooperation with the Office for Cooperation with the Civil Society |
| 4.5.4. | Developing a legal framework related to the criteria, conditions, scope, method and procedure for the allocation of funds already defined in the Regulation on funds for developing programs or missing parts of funds for the financing of programs of public interest implemented by associations ("Official Gazette of the RS" No. 8/12) | Limit discretionary rights of committee members deciding on the funds to be allocated to associations, selecting members, and regulate the issue of accountability and control of allocations performed | 6 months | The Ministry competent for finance | Amendments to the Regulation are adopted | Not required | In cooperation with the Office for Cooperation with the Civil Society |
| 4.5.5. | The Anti-Corruption Agency carries out public competitions for the allocation of funds to CSOs for projects in the field of anti-corruption for initiatives at the national and local level as well as for media initiatives in the field of anti-corruption | Develop the ACA Rulebook on the allocation of funds to CSOs | 6 months | The Government of the RS | The Rulebook on the manner of allocation of funds to CSOs is adopted | Not required |  |
|  |  | Ensure additional funds in the annual ACA budget | permanent activity | The Government of the RS | The annual ACA budget envisages funds to be allocated to CSOs | Minimum RSD 6 million at the annual level |  |
|  |  | Organize annual competitions for the allocation of funds to CSOs at the national and local level as well as to media projects | permanent activity | ACA | At least one competition is carried out in a calendar year | Funds for announcing a competition |  |
| 4.5.6. | The Anti-Corruption Agency establishes a system for continuous coordination and training for CSOs | Organize regular coordination meetings with CSOs | 6 months | ACA | The number of coordination meetings held in a calendar year | Funds for organizing meetings |  |
|  |  | Develop a training plan and modules for CSOs | 9 months | ACA | The training plan is developed | Not required |  |
|  |  | Conduct the training of CSOs | 12 months | ACA | The number of training sessions conducted in a calendar year | 2.500.000 Funds for printing materials and organization of training |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.6. | Objective | Create conditions for more active participation of the private sector in anti-corruption |  |  |  |  |  |
|  | Indicator | The number of companies per year that receive tax deductions for anti-corruption donations or work is TBD or above in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.6.1. | Amending the Law on Income Tax of Legal Persons so that anti-corruption is stated as one of purposes/activities for which companies providing financial support to the civil society are granted with special a tax relief | Formulate and submit draft amendments to the law | 15 months | The Ministry competent for finance | Draft amendments to the law are submitted to the Government | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 18 months | The Government of the RS | Proposed amendments to the law are submitted | Not required |  |
|  |  | Adopt the law on amendments to the law | 24 months | The National Assembly of the RS | The law on amendments is adopted | Not required |  |
| 4.6.2. | The Serbian Chamber of Commerce enacts and publishes anti-corruption standards and practices such as: the Code of Business Ethics, Code of Corporate Governance, promotion of ICC anti-corruption standards, rules of the Anti-Corruption Declaration of the Global Compact Serbia, as well as the companies which adopted anti-corruption plans or integrity plans | Enact and publish the stated Codes in the "Official Gazette of the RS" and rules on the website of the Serbian Chamber of Commerce | permanent activity | The Serbian Chamber of Commerce | Codes and standards are published on the SCC website | Presentation maintaining and updating |  |
|  |  | Organize meetings and seminars in the field of anti-corruption in cooperation with RS institutions and promote companies' good practices in the field of anti-corruption | permanent activity | The Serbian Chamber of Commerce | The number of organized meetings in a calendar year | 5.000.000 (Preparing aterials for conferences and seminars, organizational costs) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.7. | Objective | Ensure that the National Assembly monitors implementation of its conclusions related to recommendations of the independent state authorities monitoring work of public authorities |  |  |  |  |  |
|  | Indicator | The percentage of National Assembly recommendations based on independent agency reports that are implemented by executive branch bodies is 50% or above in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.7.1. | Amending the Law on National Assembly so to introduce an obligation of the Government to submit to the National Assembly, at least once a year, a report on the implementation of NA's conclusions adopted for consideration of reports of independent state authorities, organizations and bodies, within six months from the adoption of NA's conclusions, with an obligation to review the Government's report at the meeting of the National Assembly | Submit proposed amendments to the law | 15 months | The National Assembly | Proposed amendments to the law are submitted | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Adopt proposed amendments to the law | 20 months | The National Assembly | Proposed amendments to the law are submitted | Not required |  |
| 4.7.2. | Amending the Law on National Assembly so to establish an obligation to organize semi-annual meetings of representatives of independent state authorities and competent boards of the National Assembly on which it will be discussed about the execution of recommendations of independent state authorities not included in NA's conclusions, which will be attended by representatives of institutions which recommendations refer to. | Submit proposed amendments to the law | 15 months | The National Assembly | Proposed amendments to the law are submitted | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) |  |
|  |  | Adopt proposed amendments to the law | 20 months | The National Assembly | Proposed amendments to the law are adopted | Not required |  |
| 4.7.3. | Building capacities of the National Assembly for executing new competences within the objective 4.7. | Formulate and adopt amendments to the Rulebook on Systematization in the National Assembly | 26 months | The National Assembly | Amendments to the Rulebook on the Systematization in the National Assembly are adopted | Not required |  |
|  |  | Employ new officials at work places envisaged for the execution of new competences within the objective 4.7. | 36 months | The National Assembly | New employees at work places envisaged for the execution of new competences | In accordance with the needs analysis (at least 50.000 gross per employee) |  |
|  |  | Organize training for new employees in the field of new competences | 40 months | The National Assembly | Training of new employees in the field of new competences is organized | In accordance with the needs analysis (for each training 300.000) |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.8. | Objective | Extend and/or specify competences and build personnel capacities and working conditions of the Anti-Corruption Agency, Protector of Citizens, Commissioner for Information of Public Importance and Personal Data Protection and State Audit Institution |  |  |  |  |  |
|  | Indicator | The Anti-Corruption Agency, Ombudsman, Commissioner for Information o fPublic Importance and Personal Data Protection,and State Audit Institution have permanent, modern premises adequate to hold all approved staff. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.8.1. | Analyzing needs of the Anti-Corruption Agency, Protector of Citizens, Commissioner for Information of Public Importance and Personal Data Protection and State Audit Institution in terms of extending and/or specifying competences, building personnel capacities and working conditions | Formulate the needs analysis | 2 months | The Anti-Corruption Agency, Protector of Citizens, Commissioner for Information of Public Importance and Personal Data Protection, State Audit Institution | Analyses are formulated | 1.600.000 (Experts in the field of legislation; information on best practices; costs of public hearings) | Oblige public authorities to ensure for the Agency to investigate, through direct insight, the risks of corruption in the existing practice of application of regulations of public authorities and public officials, and to give recommendations on best practice. Public authorities would be obliged to submit a report on measures taken according to recommendations. |
|  |  | Submit the needs analysis to the Government of the Republic of Serbia, the Ministry competent for justice, the Ministry competent for public administration and the Ministry competent for finance | 3 months | The Anti-Corruption Agency, Protector of Citizens, Commissioner for Information of Public Importance and Personal Data Protection, State Audit Institution | The needs analyses are submitted to the Government of the Republic of Serbia, the Ministry competent for justice, the Ministry competent for public administration and the Ministry competent for finance | Not required |  |
|  |  | Provide written statement of reasons for the refusal of the recommendations unacceptable for the Government of the Republic of Serbia | 6 months | The Government of the RS | Written statements of reasons for refusals of unacceptable recommendations are submitted to the Anti-Corruption Agency, the Protector of Citizens, the Commissioner for Information of Public Importance and Personal Data Protection and to the State Audit Institution | Not required |  |
| 4.8.2. | Executing recommendations from the analysis of needs adopted by the Government of the Republic of Serbia | Develop a plan for the execution of recommendations from the analysis in the field of expanding and/or specifying competences; | 8 months | The Ministry competent for justice, the Legislation Committee of the National Assembly, the Ministry competent for public administration, the Ombudsman | The plan for the execution of recommendations in the field of extending and/or specifying competences is developed | Not required | The plan will designate an authority that will be responsible for plan implementation |
|  |  | Develop a plan for the execution of recommendations in the field of building capacities and providing working conditions | 8 months | The Ministry competent for finance | The plan for the execution of recommendations in the field of building capacities and providing working conditions is developed | Not required | The plan will designate an authority that will be responsible for plan implementation |
|  |  | Implement a plan in the field of expanding and/or specifying competences | Within the period set by the plan | Authorities defined by the plan | The plan is implemented in periods per year of application of the Strategy | In accordance with the needs analysis |  |
|  |  | Implement a plan in the field of building capacities and providing working conditions | Within the period set by the plan | Authorities defined by the plan | The plan is implemented in periods per year of application of the Strategy | In accordance with the needs analysis |  |
|  |  | Create a report on the implementation of the plan in the field of expanding and/or specifying competences and submit it to the Government and independent state authorities included in the plan | After the period envisaged for the implementation of the plan, at least once in six months | The Ministry competent for justice The Ministry competent of public administration | The report is created and submitted to the Government of the Republic of Serbia and to independent state authorities included in the plan | Not required |  |
|  |  | Create a report on the implementation of the plan in the field of building capacities and providing working conditions and submit it to the Government and independent state authorities included in the plan | After the period envisaged for the implementation of the plan, at least once in six months | The Ministry competent for finance | The report is created and submitted to the Government of the Republic of Serbia and to independent state authorities included in the plan | Not required |  |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority field 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.9. | Objective | Establish efficient and effective protection of whistleblowers (persons that report suspected corruption) |  |  |  |  |  |
|  | Indicator | The number of whistleblowers per year provided with protection under the law reaches TBD in 2017. |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.9.1. | Adopting a comprehensive Law on Protection of Whistleblowers (persons that report suspected corruption or make disclosures in public interest) | Formulate and submit draft amendments to the law | 6 months | The Ministry competent for justice and public administration | Draft amendments to the law is submitted to the Government | Not required |  |
|  |  | Submit to the National Assembly proposed amendments to the law | 9 months | The Government of the Republic of Serbia | Proposed amendments to the law is submitted | Not required |  |
|  |  | Adopt amendments to the law | 12 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.9.2. | Adopting by-laws which precisely govern procedures and actions | Define and enact by-laws | 15 months | The Ministry competent for justice and public administration | By-laws are adopted | Not required |  |
| 4.9.3. | Conducting professional training of persons employed in the public and private sector in protection of whistleblowers. | Adopt the training plan | 33 months | The Anti-Corruption Agency, the Ministry competent for justice and public administration | The training plan is adopted | Not required |  |
|  |  | Organize training according to the adopted plan | permanent task | The Anti-Corruption Agency, Commissioner for Information of Public Importance and Personal Data Protection, | The training plan is implemented per year of implementation of the Strategy | In accordance with the needs analysis (for each training 300.000) |  |
| 4.9.4. | Conduct campaigns for raising awareness of citizens about rights and protection of whistleblowers | Develop a plan for conducting the campaign | 30 months | The Anti-Corruption Agency, Commissioner for Information of Public Importance and Personal Data Protection, | The plan for conducting the campaign | Not required |  |
|  |  | Organize and conduct the campaign | 40 months |  | The plan for conducting the campaign is implemented | 2.500.000 (Costs of conducting the campaign) | Also involve CSOs |

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority field 4 CORRUPTION PREVENTION |  |  |  |  |  |  |  |
| 4.10. | Objective | Establish a system for prevention of conflict of interest of employees in public administration |  |  |  |  |  |
|  | Indicator | The number of conflict of interest notifications that are filed by public sector employee is TBD or above in 2017s |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 4.10.1. | Adopting a law which in a unique manner regulates prevention of conflict of interest of employees in the public sector, as well as the issue of submission and control of property cards of the officials working in public administration | Formulate and submit draft amendments to the law | 24 months | The Ministry competent for justice and public administration | Draft amendments to the law are submitted to the Government | Not required | This measure should be coordinated with the objective 3.2.1.2 |
|  |  | Submit to the National Assembly proposed amendments to the law | 29 months | The Government of the Republic of Serbia | Proposed amendments to the law are submitted | Not required |  |
|  |  | Adopt amendments to the law | 30 months | The National Assembly | Amendments to the law are adopted | Not required |  |
| 4.10.2. | Adopting by-laws that specifically govern the procedure and actions in case of conflict of interest, submission and control of property cards of the officials working in public administration, as well as consequences of violations of these provisions | Define and enact by-laws | 33 months | The Ministry competent for justice and public administration | By-laws are adopted | Not required |  |
| 4.10.3. | Conducing professional training of persons assigned with the obligations stated in the law, as well as of persons employed in control bodies. | Adopt the training plan | 33 months | The Anti-Corruption Agency, the Ministry competent for justice and public administration | The training plan is adopted | Not required |  |
|  |  | Organize training according to the adopted plan | permanent task | The Anti-Corruption Agency | The training plan is implemented per year of implementation of the Strategy | In accordance with the needs analysis (for each training 300.000) |  |

V IMPLEMENTATION AND MONITORING IMPLEMENTATION OF THE STRATEGY

| The Action Plan of the Anti-Corruption Strategy for 2013-2018 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| IMPLEMENTATION AND OVERSIGHT OF THE IMPLEMENTATION OF THE STRATEGY |  |  |  |  |  |  |  |
| 5. | Objective | Establish a system for implementation, coordination and oversight of the implementation of the Strategy and Action Plan |  |  |  |  |  |
|  | Indicator | Established system for implementation, coordination and oversight of the implementation of the Strategy and Action Plan |  |  |  |  |  |
| No. | Measure | Activity | Period (with respect to the effective date of the Action Plan) | Responsible entities | Indicators | Required resources | Notes |
| 5.1. | The Ministry competent for public administration should establish an appropriate organizational unit that will be in charge of coordination of the Strategy implementation and that will be a focal point in cooperation with other holders of public powers and international organizations | Amend the Systematization Act so as to form a group for coordination of implementation of the Strategy and Action Plan in the Minister's Office | 1 month | The Ministry competent for justice, the Government of the RS | The Systematization Act is amended | Not required |  |
|  |  | Create a list of focal points in public authorities that will be the obliged in terms of the Action Plan and publish the list on the website |  | The Ministry competent for justice | The list of focal points from public authorities that are obligors in terms of the Action Plan is published on the website | Not required |  |
| 5.2. | Amending the Rulebook on work of the Anti-Corruption Council | Govern the issue of collecting information on the performance of public authorities, submit a report to the Government and publish the report on the website if the Government does not inform the Council on the measures taken and proposed in the report | 1 month | The Anti-Corruption Council | The Rules of Procedure are amended | Not required |  |
| 5.3. | Amending the Law on the Anti-Corruption Agency by amending provisions of the report on the implementation of the Strategy | Separate the report on the implementation of the Strategy from the annual report, determine a deadline for the submission to the NA, introduce an obligation for the obligors to submit to the AP semi-annual reports (instead of quarterly reports), extend the scope to offenses to the issue of non-submission of evidence with the report and failure to respond to the invitation of the ACA, and introduce by the law an obligation of submitting evidence to the report and obligation to respond to the invitation | 6 months | The Ministry competent for justice | The law is amended | Not required |  |
| 5.4. | Amending the Law on the National Assembly in order to establish mechanisms by which the Government of the RS reports to the National Assembly on the implementation of conclusions of the National Assembly | Introduce an obligation for the Government to submit to the National Assembly, minimum once a year, a report on the implementation of conclusions of the National Assembly adopted for consideration of ACA reports, within six months from the adoption of conclusions of the National Assembly, together with an obligation to consider the report of the Government on the National Assembly's session | 6 months | The Republic Committee for Legislation | The law is amended | Not required |  |