Pursuant to Article 38, paragraph 1 of the Law on the Planning System of the Republic of Serbia (Official Gazette of the RS", No. 30/18),

The Government hereby enacts the following

ACTION PLAN FOR THE PERIOD 2024-2025 FOR THE IMPLEMENTATION OF THE 2024-2028 NATIONAL STRATEGY FOR THE FIGHT AGAINST CORRUPTION

| Action Plan: | Action plan for the period 2024-2025 for the Implementation of the 2024-2028 National Strategy for the Fight Against Corruption |
| --- | --- |
| Proposer: | Ministry of Justice of the Republic of Serbia |
| Coordination and Reporting: | Ministry of Justice of the Republic of Serbia |

| OVERALL OBJECTIVE: A permanent commitment by public authorities and political entities to suppress corruption, efficiently and consistently apply and continuously improve anti-corruption rules, timely detect and adequately punish corrupt behavior, and strengthen awareness of the causes, state, and harmfulness of corruption. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Supervising the Implementation: Agency for Prevention of Corruption |  |  |  |  |  |  |
| Indicator at the Level of the Overall Objective | Unit of Measure | Source of Verification | Baseline | Base Year |  | Target Value in 2025 |
| Corruption Perception Index Transparency International | International index | Annual Report on the Corruption Perceptions Index, Transparency International, https://www.transparency.org/en/cpi/2022 | 36 | 2023 |  | 38 |
| Specific Objective 1: Improvement of the regulatory framework for more effective prevention and suppression of corruption |  |  |  |  |  |  |
| Institution responsible for coordinating implementation: Ministry of Justice |  |  |  |  |  |  |
| Indicator(s) at the Level of the Specific Objective (Outcome Indicator) | Unit of Measure | Source of Verification | Baseline |  | Base Year | Target Value in 2025 |
| Progress in the fight against corruption recognized in the European Commission annual Serbia Report | YES/NO | Annual progress report on Serbia | NO |  | 2023 | YES |
| Compliance with GRECO recommendations from the fourth evaluation round related to normative changes, expressed as a percentage, | % | GRECO Evaluation Report | 76.92 |  | 2023 | 90 |
| Compliance with GRECO recommendations from the fifth evaluation round related to normative changes, expressed as a percentage | % | GRECO Evaluation Report | 4.17 |  | 2023 | 35 |
| Reports of the UN Office on Drugs and Crime (UNODC) on compliance with the UN Convention against Corruption | YES/NO | Reports of the UN Office on Drugs and Crime on compliance with UNCAC | NO |  | 2023 | YES |

| Measure 1.1: Improvement of the regulatory framework for suppression of corruption for the purpose of more efficient detection and prosecution of corruption crimes |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Regulatory |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of conducted analyzes of the normative framework in the area of corruption suppression, aimed at establishing a more efficient system | Number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 6 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  | 4,290 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 1.1.1. Development of the analysis of the Criminal Procedure Code enforcement to define the need for broadening the procedural powers of the public prosecutor in pre-investigation and criminal proceedings | Ministry of Justice | Supreme Court Supreme Public Prosecutor's Office Ministry of Internal Affairs | 2nd quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 in Fight Against Corruption and Fundamental Rights) |  |  | 2,040 |
| 1.1.2. Development of the analysis of the Law on the Organization and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption in the area of organization and competence of state authorities competent for suppression of corruption | Ministry of Justice | Supreme Court Supreme Public Prosecutor's Office Ministry of Internal Affairs Public Prosecutor's Office for Organized Crime | 3rd quarter of 2025 | IPA 2019 - Flexible Mechanism for Chapter 24 - EU for Fight against Serious and Organized Crime, OSCE |  |  | 2,250 |
| 1.1.3. Analysis of compliance of the RS normative framework with FATF recommendations for conducting financial investigations in parallel with criminal investigations, which will serve as a basis for developing a strategic framework in the area of the fight against financial crime and the accompanying Action Plan (related activity 6.2.5.4. AP PG 24) | Ministry of Justice | Ministry of Internal Affairs | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |
| 1.1.4. Establishment of the working group for amendments to the Law on the Organization and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption in accordance with the analysis findings | Ministry of Justice |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |
| 1.1.5. Analysis of the need for the introduction of a specific criminal offense of unjust enrichment | Ministry of Justice |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |
| 1.1.6. Analysis of the needs assessment for adopting a public policy document in the area of organized crime and high corruption (related activity 6.2.6.7. AP PG 24) | Ministry of Justice | Ministry of Internal Affairs | . 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |

| Measure 1.2: Improvement of the normative framework to reduce the possibility of corrupt behavior in the public sector and in the interaction between the public and private sectors |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Regulatory |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted analyses of the regulatory framework to reduce corrupt behavior | Number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 3 |
| Amended and supplemented regulations to reduce the possibility of corrupt behavior | Number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 9 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity |  | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity |  | Source of Funding |  |  | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | 2024 | 2025 |  |
| 1.2.1. Analysis of the need for amendments to the Public Procurement Law to identify corruption risks and recommendations for their elimination, in order to exclude exceptions in the enforcement of the Law that do not comply with the EU acquis | Public Procurement Office |  | Supreme Public Prosecutor's Office State Audit Institution Commission for the Protection of Competition Republic Commission for Protection of Rights in Public Procurement Procedures | 4th quarter of 2024 |  | Donor funds |  |  |  |  |  |  |
| 1.2.2. Analysis of the Law on Financing Political Activities to identify and eliminate the risk of corruption | Agency for Prevention of Corruption |  | Ministry of Finance | 4th quarter of 2024 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 56/1601/0007/411, 412 |  |  |  |
| 1.2.3. Analysis of the Law on Health Care to identify and eliminate the risk of corruption | Ministry of Health |  |  | 3rd quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 27.0 1801/0001/ 411, 412 |  |  |  |
| 1.2.4. Amended Rules on the Content of the Report of the Temporary Capital Representative following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.5. Amended Rules on the amount of fees and the amount of compensation for actual expenses of the temporary capital representative following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.6. Amendment to the Regulation on Strategic Partnership | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.7. Amendment to the Regulation on the Conditions, Procedure, and Manner of Sale of Capital and Assets by the Method of Public Invitation to Bid with Subsequent Public Bidding following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.8. Amendment to the Regulation on the Conditions, Manner, and Procedure for Sale of Capital of Large Privatization Subjects by the Method of Public Invitation to Bid following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.9. Amendment to the Regulation on the Conduct of Persons Performing the Duties of Temporary Capital Representative in the Privatization Subjects following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.10. Amendment to the Regulation on Monitoring the Execution of Buyer's Obligations from the Contract for the Sale of Capital or Assets following the Analysis of the Risk of Corruption in the by-laws of the Privatization Law (from the Operational Plan) | Ministry of Economy |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular activities |  |  | 21/1508/0003/411, 412 |  |  |  |
| 1.2.11. Amendment to the Law on Lobbying to introduce the obligation to publish contact with registered and unregistered lobbyists in order to comply with the GRECO recommendations from the 5th evaluation round | Ministry of Justice | Agency for Prevention of Corruption |  |  | 2nd quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular funds | 23/1602/0010/411, 412 |  |  |  |  |
| 1.2.12. Analysis of ODHIR recommendations aimed at amending the Law on Financing of Political Activities | Ministry of Finance | Agency for Prevention of Corruption |  |  | 4th quarter of 2025 |  | 01 Budget of the RS - current expenses of employees within regular funds | 16/2301/0013 |  |  |  |  |

| Measure 1.3: Improvement of the regulatory framework for the selection/appointment procedure in public enterprises and other publicly owned companies |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Economy |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Regulatory |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted analysis of the legislative framework related to public enterprises to eliminate the risk of corruption, including the management of conflicts of interest with a special emphasis on the selection/appointment, employment and promotion process | Number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 1 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 1.3.1. Analysis of the legislative framework related to the selection/appointment procedure for management bodies in public enterprises | Ministry of Economy | Standing Conference of Towns and Municipalities (SKGO) | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 21/1508/0001/ 411, 412 |  |  |
| 1.3.2. Establishment of a working group for drafting amendments to regulations in accordance with the findings and recommendations outlined in the analyses from the activity 1.3.1. | Ministry of Economy |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 21/1508/0001/411, 412 |  |  |

| Measure 1.4: Improvement of the normative framework to eliminate the risk of corruption in selection/appointment, employment and promotion procedures in the public sector, including local self-government. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Public Administration and Local Self-Government |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Regulatory |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of developed instructions, guidelines and materials in the public sector and local self-government. | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 3 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds - Program: Partnership for Good Local Self-Government |  | 600 |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 1.4.1. Adoption of professional instructions and definition of criteria for actions of school administrations and regional subgroups in the procedure of granting consent for announcing recruitment for permanent positions in primary and secondary education institutions | Ministry of Education |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 26.0/2001/0001/411, 412 26.0/2001/0002/411, 412 |  |  |
| 1.4.2. Drafting of guidelines for regulating conflicts of interest in recruitment procedures for positions in LSG bodies | Ministry of Public Administration and Local Self-Government | SKGO | 4th quarter of 2024 | Donor funds: Program: Partnership for Good Local Self-Government (financed by: SDC, implemented by: SKGO) |  | 240 |  |
| 1.4.3. Compilation of materials for an info-corner of an LSG unit website for candidates in competitive recruitment procedures, with special reference to the transparency of the recruitment procedure, potential conflicts of interest and exercise of rights in the recruitment procedure. | Ministry of Public Administration and Local Self-Government | SKGO | 4th quarter of 2024 | Donor funds: Program: Partnership for Good Local Self-Government (financed by: SDC, implemented by: SKGO) |  | 360 |  |

| Measure 1.5: Harmonization of the regulatory framework with the EU acquis, as well as relevant international standards, principles, and best practices in the area of the fight against corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Regulatory |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2024 |
| Conducted analyses on the compliance of RS regulations with the EU acquis in the area of the fight against corruption | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 3 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  | 5,040 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 1.5.1. Analysis of the enforcement and compliance of the Whistleblowing Protection Law with the EU Directive 2019/1937 on the protection of whistleblowers who report breaches of Union law, and analysis of laws adopted on the basis of the Directive in the EU member states. | Ministry of Justice |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 1.5.2. Amendments to the Criminal Code in order to prescribe criminal offenses related to financial resources from European Union funds | Ministry of Justice | Ministry of Finance / AFKOS | 4th quarter of 2024 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |
| 1.5.3. Analysis of compliance of the RS regulations with the EU acquis in the area of mutual legal assistance in criminal matters | Ministry of Justice | Supreme Court Supreme Public Prosecutor's Office | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 5,040 |

| Specific Objective 2: Strengthening the institutional framework for preventing and combating corruption in order to more efficiently prevent and suppress corruption |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institution Competent for Coordination and Reporting: Ministry of Justice |  |  |  |  |  |
| Indicator(s) at the Level of the Specific Objective (Outcome Indicator) | Unit of Measure | Source of Verification | Baseline | Base Year | Target Value in 2025 |
| The resolution rate of criminal cases in relation to the number of filed and disposed cases based on the CEPEJ Dashboard Report | % | CEPEJ Dashboard Report | Over 100% | 2022 | Over 100% |

| Measure 2.1: Strengthening the administrative capacity and financial resources of state authorities responsible for the fight against corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings in the area of the fight against corruption, following the activities and target groups defined through the activities within measure 2.1. | number | Activity Report of the Judicial Academy. |  | 10 | 2023 | 13 |
| Staffing rate, expressed as a percentage, in the organizational units of the Ministry of Internal Affairs responsible for combating corruption | % | Report on the Implementation of the National Strategy |  | 91%, | 2023 | 95% |
| The number of employees in the Public Prosecutor's Office for Organized Crime and the Special Departments for Corruption Suppression within Higher Public Prosecutor's Offices. | number | Report on the Implementation of the National Strategy |  | 116 | 2023 | 151 |
| The number of employees in Special Departments for Corruption Suppression within Higher Courts and the Special Department for Organized Crime within the Higher Court in Belgrade | number | Report on the Implementation of the National Strategy |  | 175 | 2023 | 184 |
| The number of employees in the Directorate for the Administration of Seized Assets. | number | Report on the Implementation of the National Strategy |  | 16 | 2023 | 28 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget | 8.3/1604/0008/411,412 8.5/1604/0012/411,412 6.6/1603/0014/411,412 6.6/1603/0014/411,412 23.2/1602/0008/411,412 |  | 47,661 33,360 18,853 12,625 14,730 |
| EU financial assistance IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 39,600 |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.1.1. Continuous filling of vacant positions in accordance with the Rulebook on Systematization of Positions in Public Prosecutor's Office for Organized Crime (JTOK) | Ministry of Justice | Public Prosecutor's Office for Organized Crime | 4th quarter of 2025 | 01 Budget of the RS | 8.3/1604/0008/411,412 |  | 47,661 |
| 2.1.2. Continuous filling of vacant positions in accordance with the Rulebook on Systematization of Positions in Special Departments for Corruption Suppression within Higher Public Prosecutor's Offices | Ministry of Justice | Higher Public Prosecutor's Offices in Belgrade, Novi Sad, Niš and Kraljevo | 4th quarter of 2025 | 01 Budget of the RS | 8.5/1604/0012/411,412 |  | 33,360 |
| 2.1.3. Continuous filling of vacant positions in accordance with the Rulebook on Systematization of Positions in Special Departments for Corruption Suppression within Higher Courts | Ministry of Justice | Higher Courts in Belgrade, Novi Sad, Niš and Kraljevo | 4th quarter of 2025 | 01 Budget of the RS | 6.6/1603/0014/411,412 |  | 18,853 |
| 2.1.4. Continuous filling of vacant positions in accordance with the Rulebook on Systematization of Positions in the Special Department for Organized Crime within the Higher Court in Belgrade | Ministry of Justice | Higher Court in Belgrade | 4th quarter of 2025 | 01 Budget of the RS | 6.6/1603/0014/411,412 |  | 12,625 |
| 2.1.5. Strengthening the capacities of the Directorate for the Administration of Seized Assets in accordance with the Rulebook on Systematization (related activity 2.3.5.3 AP PG23) | Ministry of Justice |  | 4th quarter of 2025 | 01 Budget of the RS | 23.2/1602/0008/411,412 |  | 14,730 |
| 2.1.6. Continuous increase the staffing rate in organizational units of the Ministry of Internal Affairs responsible for combating corruption (Internal Control Sector, Department for the Fight against Corruption, Department for the Fight against High Corruption) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/411, 412 |  |  |
| 2.1.7. Continuous organization of trainings for judges, public prosecutors, police officers, and judicial and prosecutors' assistants about the competencies of the Special Departments for Corruption Suppression and the Public Prosecutor's Office for Organized Crime (JTOK), to ensure more efficient enforcement of the Law on the Organization and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption, in accordance with Annual Training Program (related activity 6.2.2.3. AP PG 24) | Judicial Academy | High Judicial Council High Prosecutorial Council Ministry of Justice Ministry of Internal Affairs | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 10,800 |
| 2.1.8. Conducting trainings on special evidence gathering procedures for proving corrupt criminal offenses, for judges, public prosecutors, and judicial and prosecutors' assistants, in accordance with the Judicial Academy's Annual Training Program | Judicial Academy |  | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 10,800 |
| 2.1.9. Conducting trainings on financial investigations that run in parallel with criminal investigations and procedures for the temporary and permanent seizure of proceeds of crime, for police officers, judges, public prosecutors, and judicial and prosecutors' assistants, in accordance with the JA Annual Training Program (related activity 6.2.5.1 and 6.2.5.2. AP PG 24) | Judicial Academy |  | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 6,000 |
| 1.2.12. Conducting trainings in the area of public procurement for judges, public prosecutors, and judicial and prosecutors' assistants, in accordance with the JA Annual Training Program | Judicial Academy |  | . 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 2.1.11. Conducting trainings for judges and public prosecutors prosecuting legal entities for corrupt criminal offenses, in accordance with the JA Annual Training Program | Judicial Academy |  | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 12,000 |
| 2.1.12. Conducting trainings for police officers, prosecutors and judges, on complex financial investigations that are conducted in parallel with criminal investigations and procedures for temporary and permanent seizure of proceeds of crime | Judicial Academy |  | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  |  |

| Measure 2.2: Strengthening the capacities of authorities and bodies responsible for preventing corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Agency for Prevention of Corruption |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of employees in the Agency for Prevention of Corruption | number | Report on the Implementation of the National Strategy Activity Report of the Agency for Prevention of Corruption (APC) |  | 91 | 2022 | 104 |
| The number of trainings on financial forensics and the number of trained employees in the APC | number | Activity Report of the Agency for Prevention of Corruption (APC) |  | 0 trainings 0 trained individuals |  | 2 trainings, 6 trained individuals |
| The number of the members of the Anti-Corruption Council | number | Activity Report of the Anti-Corruption Council Government decision |  | 6 | 2023 | 13 |
| An efficient IT system has been established to manage data from the registers maintained by the Agency for Prevention of Corruption | YES/NO | Activity Report of the Anti-Corruption Council |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget | 3.8/1601/0001/423 56/1601/0007/411 56/1601/0007/412 | 1,344* | 8,200* 10,689.97110 1,656.94552 |
| EU financial assistance IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 585.75 |
| Donor funds |  |  | 1,350* |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.2.1. Filling of vacant positions in the Anti-Corruption Council and ensuring a greater degree of cooperation between the Government and the Council | General Secretariat of the Government |  | 4th quarter of 2025 | 01 Budget of the RS | 3.8/1601/0001/423 | 1,344* | 8,200* |
| 2.2.2. Filling of vacant positions in accordance with the Rulebook on Systematization of Positions in the Agency for Prevention of Corruption | Agency for Prevention of Corruption | HR service | 2nd quarter of 2025 | 01 Budget of the RS | 56/1601/0007/411 56/1601/0007/412 |  | 10,689.97110 1,656.94552 |
| 2.2.3. Trainings for employees of the Agency for Prevention of Corruption on financial forensics for assessing and monitoring the financial status of public officials, similar to the training received by financial forensic officers in the special units of public prosecutor's offices. | Agency for Prevention of Corruption |  | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 in Fight Against Corruption and Fundamental Rights) |  |  | 585.75 |
| 2.2.4. Setting up an efficient IT system to manage data from the registers maintained by the Agency for Prevention of Corruption | Agency for Prevention of Corruption |  | 4th quarter of 2025 | Donor funds* |  |  | 1,350* |
| 2.2.5. Analysis of the effectiveness and efficiency of sanctions for the criminal offense of failing to declare assets and income or providing false information regarding assets and income (in accordance with transitional measure 27) | Ministry of Justice |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23/1602/0010/411, 412 |  |  |
| 2.2.6. The new Rules of Procedure of the Anti-Corruption Council were adopted | Anti-Corruption Council |  | 4th quarter of 2025 | 01 Budget of the RS - within regular activities | 3.8/1601/0001 |  |  |

| Measure 2.3: Strengthening capacities for conducting inspection oversight and performing internal control of inspections |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Public Administration and Local Self-Government |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of analyzes conducted on the system and organization of work in inspection activities and control | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 1 |
| A training program was developed to eliminate the risk of corruption for republic, provincial, city, and municipal educational inspectors, aimed at standardizing procedures for recognizing and addressing corrupt practices in inspection oversight | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| The number of inspections conducted to verify the selection procedure for the position of lecturer and associate in higher education institutions, by way of a checklist | number | Report on the Implementation of the National Strategy |  |  | 2023 | 40 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  | 900* | 450* |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.3.1. Analysis of the inspection system and work organization, accompanied by recommendations for improving their position and operations | Ministry of Public Administration and Local Self-Government |  | 4th quarter of 2024 | Donor funds |  | 900* |  |
| 2.3.2. Development of a Training Program to eliminate the risk of corruption for republic, provincial, city, and municipal educational inspectors, aimed at standardizing procedures for recognizing and addressing corrupt practices in inspection oversight. | Ministry of Education | Agency for Prevention of Corruption, Governmental Coordinating Commission for Inspection Oversight | 4th quarter of 2025 | Donor funds |  |  | 450* |
| 2.3.3. Organizing regular inspection oversights in higher education institutions until the end of the 2024/2025 school year to verify the selection process for the position of lecturer and associate using a checklist | Ministry of Education |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 26.0/2001/0003/ 411, 412 |  |  |

| Measure 2.4: Strengthening the efficiency of the customs system |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Finance - Customs Administration |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Internal control departments equipped with the necessary supporting equipment | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| Installed video surveillance of commodity outposts | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.4.1. Analysis of the capacities of the internal control department and the necessary supporting equipment | Ministry of Finance - Customs Administration |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 16.1/2303/0001/ 411, 412 |  |  |
| 2.4.2. Strengthen the capacities of the internal control department through the acquisition of appropriate supporting equipment | Ministry of Finance - Customs Administration |  | 4th quarter of 2025 | The costs will be determined after the analysis referred to in the activity 2.4.1 |  |  |  |
| 2.4.3. Analysis of the most risky border crossings and commodity outposts from the aspect of corruption in order to define the needs for installing video surveillance and the dynamics of introduction | Ministry of Finance - Customs Administration |  | 3rd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 16.1/2303/0001/ 411, 412 |  |  |
| 2.4.4. Installation of video surveillance at commodity outposts in line with the analysis referred to in the activity 2.4.3 | Ministry of Finance - Customs Administration |  | 4th quarter of 2025 | The costs will be determined after the analysis referred to in the activity 2.4.3 |  |  |  |
| 2.4.5. Development of internal instructions and procedures in sectors that are not regulated in detail by the bylaws | Ministry of Finance - Customs Administration |  | 3rd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 16.1/2303/0001/ 411, 412 |  |  |
| 2.4.6. Informing employees about the developed internal instructions | Ministry of Finance - Customs Administration |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 16.1/2303/0001/ 411, 412 |  |  |

| Measure 2.5: Strengthening the capacities of the Tax Administration |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Finance - Tax Administration |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of employees in the internal control of the Tax Administration | number | Report on the Implementation of the National Strategy |  | 20 | 2023 | 32 |
| The number of trainings for the Tax Administration employees | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 2 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.5.1. Strengthening the capacities of internal control personnel by filling vacant positions in accordance to the Rulebook on systematization | Ministry of Finance - Tax Administration |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 16.2/2302/0001/ 411, 412 |  |  |
| 2.5.2. Analysis of the training needs of the Tax Administration employees | Ministry of Finance - Tax Administration |  | 4th quarter of 2024 | 01 Budget of the RS - current expenses of employees within regular activities | 16.2/2302/0001/ 411, 412 |  |  |
| 2.5.3. Development of continuous training programs for the Tax Administration employees | Ministry of Finance - Tax Administration |  | 3rd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 16.2/2302/0001/ 411, 412 |  |  |
| 2.5.4. Conducting trainings for the Tax Administration employees | Ministry of Finance - Tax Administration | National Academy of Public Administration (NAJU) University of Criminal Investigation and Police Studies | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 16.2/2302/0001/ 411, 412 |  |  |

| Measure 2.6: Improving and formalizing the cooperation of state authorities in the fight against corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| A planning document focusing on the fight against financial crime has been prepared | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| A link between databases of significance for the fight against corruption has been established | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| An internal enactment on the implementation of financial investigations has been drafted | YES/NO | Report on the Implementation of the National Strategy Activity Report of the Supreme Public Prosecutor's Office |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2015 "IT Equipment and Software for Improvement of Case Management System in the Prosecutor's Office" |  |  | 128,712 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.6.1. Development of software with centralized databases on events, processes, and enactments in criminal proceedings that are important to judicial authorities, aimed at facilitating the electronic exchange of data, information, and documents (related activity 2.3.2.5. AP PG 23) | Ministry of Justice |  | 4th quarter of 2024 | EU financial assistance: IPA 2015 "IT Equipment and Software for Improvement of Case Management System in the Prosecutor's Office" |  |  | 128,712 |
| 2.6.2. Adopted bylaw referred to in Article 16, paragraph 4 of the Law on the Organization and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption, which will regulate the deadlines, procedure and manner of official communication between the police and the public prosecutor's office in cases of organized crime and corruption (related activity 2.3.2.6. AP PG 23 and activities 6.2.2.1. and 6.2.2.2. AP PG 24) | Ministry of Justice | Ministry of Internal Affairs Supreme Public Prosecutor's Office Public Prosecutor's Office for Organized Crime | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23.0/1602/0010/411, 412 |  |  |
| 2.6.3. Development of general binding instructions on conducting financial investigations | Supreme Public Prosecutor's Office |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 8.1/1604/0004/ 411, 412 |  |  |

| Measure 2.7: Strengthening international cooperation in the detection and prosecution of cross-border fraud and embezzlement of the EU funds |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Performed analysis on the establishment of cooperation with the European Public Prosecutor’s Office | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| The number of judges, public prosecutors and police officers trained in connection with the protection of EU financial interests | number | Judicial Academy Activity Report |  | 70 | 2023 | 90 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 4,290 |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.7.1. Analysis of the modalities for establishing cooperation with the European Public Prosecutor’s Office | Ministry of Justice |  | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 1,890 |
| 2.7.2. Conducting trainings and workshops on the protection of EU financial interests for judges, public prosecutors, and police officers, in accordance with the JA's Annual Training Program | Judicial Academy | Supreme Public Prosecutor's Office Ministry of Finance AFKOS | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 2,400 |

| Measure 2.8: Strengthening the system of monitoring the financing of political activities |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Agency for Prevention of Corruption |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Number of analyses conducted to strengthen the system of monitoring the financing of political activities. | number | Report on the Implementation of the National Strategy Report of the Agency for Prevention of Corruption (APC) |  | 0 | 2023 | 2 |
| Implementation of recommendations from the analysis of irregularities in the financing of political activities within the competence of the APC, expressed as a percentage | % | Report on the Implementation of the National Strategy Report of the Agency for Prevention of Corruption |  | 0% | 2023 | 60% |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 2.8.1. Develop an analysis of irregularities in the financing of political activities within the competence of the APC | Agency for Prevention of Corruption |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses within regular activities | 56/1601/0007/ 411, 412 |  |  |
| 2.8.2. Publish the reports of observers of the Agency for Prevention of Corruption on the Agency's website | Agency for Prevention of Corruption |  | Along with the campaign for the upcoming elections | 01 Budget of the RS - current expenses within regular activities | 56/1601/0007/ 411, 412 |  |  |
| 2.8.3. Analysis of the modality for introducing a public registry of reports on violations of election rules, which would allow visibility of the subject of each report, its current status, and the decisions made regarding each report | Agency for Prevention of Corruption |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses within regular activities | 56/1601/0007/ 411, 412 |  |  |

| Specific Objective 3: Improving transparency |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institution Competent for Coordination and Reporting: Ministry of Justice |  |  |  |  |  |
| Indicator(s) at the Level of the Specific Objective (Outcome Indicator) | Unit of Measure | Source of Verification | Baseline | Base Year | Target Value in 2025 |
| SIGMA indicator: Access to information of public importance | Point, scale ranging from 0 to 30 | SIGMA Monitoring Report http://www.sigmaweb.org/publications/monitoring-reports.htm | 22/30 | (2021) | 24/30 |

| Measure 3.1: Strengthening capacities of bodies responsible for the fight against corruption, particularly in their communication with the public |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Judicial Academy |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The percentage of trained media spokespersons in the Special Departments for Corruption Suppression within the Higher Courts and the Special Department for Organized Crime within the Higher Court in Belgrade. | % | Report on the Implementation of the National Strategy Judicial Academy Activity Report |  | 70% | 2023 | 90% |
| Estimate of trained media spokespersons in the Special Departments for Corruption Suppression within the Higher Public Prosecutor's Offices and the Public Prosecutor's Office for Organized Crime | % | Report on the Implementation of the Strategy |  | 70% | 2023 | 90% |
| Press conferences held | number |  |  | 0 | 2023 | 2 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 1,600 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.1.1. Trainings for media spokespersons in the Special Departments for Corruption Suppression within the courts | Judicial Academy |  | 4th quarter of 2025 | 01 Budget of the RS - within regular activities IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) | 23.3/1602/0009/ 411, 412 |  | 800 |
| 3.1.2. Training for media spokespersons in the Special Departments for Corruption Suppression within the Public Prosecutor Offices | Judicial Academy |  | 4th quarter of 2025 | 01 Budget of the RS - within regular activities IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) | 23.3/1602/0009/ 411, 412 |  | 800 |
| 3.1.3. Regular publication of the docket of the Special Departments for Corruption Suppression on the websites of the higher courts in Belgrade, Novi Sad, Niš and Kraljevo | High Judicial Council | Ministry of Justice | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 5/1602/0002 |  |  |
| 3.1.4. Regular updating of the case law database with anonymized decisions under the competence of Special Departments for Corruption Suppression | Supreme Court | Judicial Academy Ministry of Justice | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 6.1/1603/0003/ 411, 412 |  |  |
| 3.1.5. Regular semi-annual press conferences (Special Departments for Corruption Suppression within the Higher Public Prosecutor Offices) | Supreme Public Prosecutor's Office |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 8.1/1604/0003/ 411, 412 |  |  |
| 3.1.6. Regular semi-annual press conferences (Special Departments for Corruption Suppression within the Higher Courts) | Supreme Court | Courts of Appeal in Belgrade, Novi Sad, Niš and Kragujevac Special departments for corruption suppression within higher courts in Belgrade, Niš, Novi Sad, Kraljevo. | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 6.1/1603/0003/ 411, 412 |  |  |

| Measure 3.2: Strengthening capacities of the media outlets to report on the work of authorities responsible for the fight against corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Judicial Academy |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings for journalists on reporting related to criminal proceedings, the fight against corruption, and prevention mechanisms | number | Report on the Implementation of the National Strategy Judicial Academy Activity Report |  | 0 | 2023 | 1 |
| Conducted trainings for journalists on reporting related to corruption prevention mechanisms (integrity regime) | number | Report on the Implementation of the National Strategy Activity Report of the Agency for Prevention of Corruption (APC) |  | 0 | 2023 | 2 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 800 |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.2.1. Continuous organization of trainings for journalists on reporting related to criminal proceedings and the fight against corruption in accordance with the JA Annual Training Program | Judicial Academy | Independent Journalists’ Association of Serbia Journalists’ Association of Serbia | 4th quarter of 2025 | 01 Budget of the RS - within regular activities IPA 2019 Complementary assistance for the implementation of sectoral budget support | 23.3/1602/0009 |  | 800 |
| 3.2.2. Organizing trainings for journalists on reporting related to corruption prevention mechanisms (integrity regime) | Agency for Prevention of Corruption |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 56/1601/0007/ 411, 412 |  |  |

| Measure 3.3: Improvement of statistical reporting on the fight against corruption |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Ensured consistent entry of statistical data in the register of corruption cases | YES/NO | Report on the Implementation of the National Strategy Activity Report of the Supreme Public Prosecutor's Office |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds EU/Council of Europe "Support for the Judicial Reform" |  |  | 600 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.3.1. Analysis of statistical reporting on corruption and improvement recommendations (including data required for reporting to the EC) | Ministry of Justice | Supreme Public Prosecutor's Office | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 23/1602/0010 |  |  |
| 3.3.2. Amendment to the Rules of Administration of Public Prosecutor's Offices to establish a special register for the confiscation of material gain referred to in Art. 91 and 92 of the Criminal Code | Ministry of Justice | Supreme Public Prosecutor's Office High Judicial Council | 2nd quarter of 2025 | Donor funds EU/Council of Europe Joint Project "Support for the Judicial Reform" |  |  | 300 |
| 3.3.3. Amendment to the Court Rules of Procedure to establish a special register for the confiscation of material gain referred to in Art. 91 and 92 of the Criminal Code | Ministry of Justice | Supreme Court | 2nd quarter of 2025 | Donor funds EU/Council of Europe Joint Project "Support for the Judicial Reform" |  |  | 300 |
| 3.3.4. Standardize the use of the electronic register of corruption cases in the Special Departments for suppression of corruption in the courts and public prosecutor's offices for drafting prescribed reports, by providing instructions for use of this software | Ministry of Justice | Supreme Public Prosecutor's Office | 3rd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 23/1602/0010 |  |  |
| 3.3.5. Organize trainings on the use of the electronic register of corruption cases for employees of special departments for corruption suppression in the courts and public prosecutor's offices | Ministry of Justice | Supreme Public Prosecutor's Office | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 23/1602/0010 |  |  |

| Measure 3.4: Strengthening the proactive publication of data of public interest, and the open format data |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution competent for implementation: Supreme Public Prosecutor's Office |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Catalogs, guidelines, newsletters created and published | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| The number of analysis conducted with the aim to proactively publish data of public interest, and the open format data | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 3 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  | 500 | 1,700 |
| Donor funds OSCE The "Local Self-Government for the 21st Century" project, implemented with the financial support of the Swiss Government (SDC) |  | 1,060 750 | 2,100* 1,060 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.4.1. Regular publication of annual bulletins of special departments for corruption suppression within the higher prosecutor's offices. They are published as part of the Bulletin of the Supreme Public Prosecutor's Office | Supreme Public Prosecutor's Office |  | 1st quarter 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  | 500 | 500 |
| 3.4.2. Development of guidelines for publication of data of special departments for corruption suppression within the higher prosecutor's offices | Supreme Public Prosecutor's Office | Commissioner for Information of Public Importance and Personal Data Protection | 3rd quarter of 2025 | OSCE |  | 1,060 | 1,060 |
| 3.4.3. Analysis of the amendment to the Law on Local Self-Government to assess a potential need for recommending that local self-government units publish information on regulations and public policy documents on the E-Consultations Portal. | Ministry of Public Administration and Local Self-Government |  | 4th quarter of 2024 | The "Local Self-Government for the 21st Century" project, implemented with the financial support of the Swiss Government (SDC) | 20/0608/4005 | 720 |  |
| 3.4.4. Creating a catalog of public offices | Agency for Prevention of Corruption |  | 4th quarter of 2025 | Donor funds |  |  | 300* |
| 3.4.5. Analysis of the establishment of a uniform electronic record of all illegally constructed buildings | Republic Geodetic Authority |  | 4th quarter of 2025 | Donor funds |  |  | 1,800* |
| 3.4.6. Finding legal solutions for optimization, acceleration and more efficient implementation of the legalization procedure in order to legalize and register all illegally constructed buildings | Republic Geodetic Authority |  | 4th quarter of 2025 | Donor funds |  |  |  |
| 3.4.7. Analysis of the status of criminal investigations for criminal offenses of corruption in privatization | Ministry of Justice |  | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 1,200 |

| Measure 3.5: Capacity building for the enforcement of the Law on Free Access to Information of Public Importance |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Commissioner for Information of Public Importance and Personal Data Protection |  |  |  |  |  |  |
| Implementation Period: 2024- 2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The number of organized discussions with the local media outlets and stakeholders about the enforcement of the Law | number | Report on the Implementation of the National Strategy Activity Report of the Commissioner for Information of Public Importance and Personal Data Protection |  | 0 | 2023 | 5 |
| The number of trainings for persons authorized to act on requests for access to information of public importance in the local self-government bodies | number | Report on the Implementation of the National Strategy Activity Report of the Commissioner for Information of Public Importance and Personal Data Protection |  | 0 | 2023 | 5 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds Program: Partnership for Good Local Self-Government (financed by: SDC, implemented by: SKGO) |  | 867* 453 | 578* 302 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.5.1. Organization of discussion at the local self-government level with media outlets and stakeholders regarding the enforcement of the Law on Access to Information of Public Importance | Commissioner for Information of Public Importance and Personal Data Protection |  | 4th quarter of 2025 | Donor funds* |  | 867* | 578* |
| 3.5.2. Organization of trainings for persons authorized to act on requests for access to information of public importance in the local self-government bodies | Commissioner for Information of Public Importance and Personal Data Protection | SKGO | 4th quarter of 2025 | Program: Partnership for Good Local Self-Government (financed by: SDC, implemented by: SKGO) |  | 453 | 302 |

| Measure 3.6: Enhancing the transparency of fund allocation to programs and projects implemented by civil society organizations and media outlets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry for Human and Minority Rights and Social Dialogue |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification | Baseline | Base Year | Target Value in 2025 |
| A calendar of public tenders with an overview of approved programs/projects has been created and is publicly available | YES/NO | Report on the Implementation of the National Strategy | NO | 2023 | YES |
| The percentage of funds allocated through public tendering compared to other allocation procedures | % | Annual summary report on the expenditure of funds allocated and disbursed to associations and other civil society organizations from the RS budget, intended to support program and project activities | 70% | 2023 | 80% |
| The number of trainings conducted for employees in public administration bodies on the planned and transparent allocation, monitoring and evaluation of the allocation of budget funds intended for CSO programs and projects | Number (per year) | Report of the National Academy for Public Administration (NAJU) Reports of the Local Self Government Units (LSGU) | 50 | 2023 | 70 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 3.6.1. Improve the Calendar of Public Tenders Application | Ministry for Human and Minority Rights and Social Dialogue |  | 4th quarter of 2025 | This activity is budgeted within the AP proposal for the period 2024 -2026 for the implementation of the 2022-2030 Strategy for creating an enabling environment for the development of civil society in the Republic of Serbia |  |  |  |
| 3.6.2. Conduct trainings for the employees of LSGUs on Funding of public interest programs implemented by the associations | Ministry for Human and Minority Rights and Social Dialogue | SKGO National Academy for Public Administration (NAJU) | 4th quarter of 2025 | Program: Partnership for Good Local Self-Government (financed by: SDC, implemented by: SKGO) |  |  |  |
| 3.6.3. Direct support to the five local self-government units for the improvement of internal procedures and capacities for allocation of funds and publication of data related to public interest programs implemented by the associations | Ministry for Human and Minority Rights and Social Dialogue | SKGO | 4th quarter of 2025 | Project "Enhancing the application of good governance principles in local self-governments" (UNOPS - SCGO) |  |  |  |

| Specific Objective 4: Strengthening integrity in the public sector and authorities responsible for corruption suppression |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institution Competent for Coordination and Reporting: Ministry of Justice |  |  |  |  |  |
| Indicator(s) at the Level of the Specific Objective (Outcome Indicator) | Unit of Measure | Source of Verification | Baseline | Base Year | Target Value in 2025 |
| Compliance with GRECO recommendations from the fourth evaluation round related to integrity strengthening, expressed as a percentage | % | GRECO Evaluation Report | 76.92 | 2023 | 90 |
| Compliance with GRECO recommendations from the fifth evaluation round related to integrity strengthening, expressed as a percentage | % | GRECO Evaluation Report | 4.17 | 2023 | 35 |

| Measure 4.1: Improvement of anti-corruption mechanisms in the work of the public prosecutor’s offices |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: High Prosecutorial Council |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings on professional ethics in the prevention and fight against corruption | number | Report on the Implementation of the National Strategy Judicial Academy Activity Report |  | 1 | 2023 | 2 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget | 1602/0009/423 |  | 400 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.1.1. Organization of trainings on professional ethics in the prevention and fight against corruption, for public prosecutors and employees in public prosecutor's offices | Judicial Academy | High Prosecutorial Council | 4th quarter of 2025 | 01/1604/0011/423 |  |  | 400 |

| Measure 4.2: Improvement of anti-corruption mechanisms in the work of the courts |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: High Judicial Council |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings on professional ethics in the prevention and fight against corruption and the number of trained individuals | number | Report on the Implementation of the National Strategy Judicial Academy Activity Report |  | 1 | 2023 | 2 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD by Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget | 1602/0009/423 |  | 400 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.2.1. Organization of trainings on professional ethics in the prevention and fight against corruption, for judges and court employees | Judicial Academy | High Judicial Council | 4th quarter of 2025 | 01 Budget of the RS | 1602/0009/423 |  | 400 |

| Measure 4.3: Improvement of anti-corruption mechanisms in the work of the Ministry of Internal Affairs |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Internal Affairs |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  | Law on Internal Affairs |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Operational Plan for Preventing Corruption in the Police adopted | YES/NO | Report on the Implementation of the National Strategy Annual Activity Report of the Internal Control Sector |  | NO | 2024 | YES |
| Number of conducted integrity tests in the MoI | number | Report on the Implementation of the National Strategy Annual Activity Report of the Internal Control Sector |  | 21 | 2023 | 28 |
| Compliance with GRECO recommendations from the fifth evaluation round related to the Ministry of Internal Affairs competence, expressed as a percentage | (%) | Greco Evaluation Report |  | 10% | 2024 | 100% |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.3.1. Development of the Operational Plan for Prevention of Corruption in the Police | Ministry of Internal Affairs |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.2. Establishment of a Commission for Police Ethics, in accordance with the new Police Code of Ethics (in line with GRECO recommendation xvi. from the Fifth Evaluation Round) | Ministry of Internal Affairs | University of Criminal Investigation and Police Studies | 4th quarter of 2024 | 01 Budget of the RS - current expenses of employees within regular activities | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.3. Annual increase of at least 10% in the number of integrity tests conducted in the MoI (in line with GRECO recommendation xvi. from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.4. Organization of trainings for new members of working groups for corruption risk analysis in the Ministry of Internal Affairs | Ministry of Internal Affairs | Agency for Prevention of Corruption | 4th quarter of 2024 | Donor funds* |  |  |  |
| 4.3.5. Organization of trainings on the method and procedures for reporting the financial status of managers and employees at high-risk positions in the Ministry of Internal Affairs | Ministry of Internal Affairs |  | 4th quarter of 2025 | Donor funds* |  |  |  |
| 4.3.6. Introduction of an obligation to perform regular security checks for all police officers (in line with GRECO recommendation xix. from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 15.0/1409/0003/ 411, 412 |  |  |
| 4.3.7. Amendment to the legislative framework for the selection, appointment and re-appointment of senior managers in the Ministry of Internal Affairs (in line with GRECO recommendation xviii from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 2nd quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.8. Training for police officers on implementing the complaint procedure, attended by persons authorized to resolve complaints, including members and presidents of the Complaints Resolution Commission (in line with GRECO recommendation xxiii. from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.9. Create a Register of Risks at workplaces in lines of work with a high corruption risk (in line with GRECO recommendation xx. from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS | 15.0/1408/0001/423 | 14,400 |  |
| 4.3.10. Preparation of decisions on the deployment/relocation of police officers based on proposals of the managers of the competent organizational unit, in accordance with current regulations | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.11. Implementation of internal / public recruitment announcements, in accordance with current regulations | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.12. Drafting the Instruction on the procedure for granting consent to employees of the Ministry of Internal Affairs to engage in secondary employment (in line with GRECO recommendation xxi from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.13. Establishing records of secondary employment of police officers, in accordance with current regulations (in line with GRECO recommendation xxi from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.14. Strengthening awareness among employees of the Ministry of Internal Affairs regarding whistleblower protection through regular notifications about their rights under the Law on Protection of Whistleblowers (in line with GRECO recommendation xxiv from the Fifth Evaluation Round), | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.15. Training on the topic: Enforcement of the Law on Protection of Whistleblowers (in line with GRECO recommendation xxiv from the Fifth Evaluation Round) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |
| 4.3.16. Analysis of the need to introduce as an elective course at the University of Criminal Investigation and Police Studies a course related to the role of whistleblowers in criminal proceedings, and the cooperation of police officers with whistleblowers in the detection and investigation of corruption-related and other criminal offenses. | Ministry of Internal Affairs | University of Criminal Investigation and Police Studies | 4th quarter of 2025 | Donor funds |  |  |  |
| 4.3.17. Implement measures aimed at strengthening the integrity of organizational units and employees in the Police Directorate (related activity 6.1.1.25 AP PG 24) | Ministry of Internal Affairs |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 15.0/1408/0001/ 411, 412 |  |  |

| Measure 4.4: Improvement of anti-corruption mechanisms in the work of the public sector |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Agency for Prevention of Corruption |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Number of adopted professional instruction, analyses, guidelines, manuals, for the improvement of anti-corruption mechanisms | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 4 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  | 300* |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.4.1. Adoption of professional instruction for implementing the verification procedure for institutions (prescribe the procedures and deadlines for the competent sectors within the legal timeframe) | Ministry of Education |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 26.0/2001/0001/ 411, 412 26.0/2001/0003/ 411, 412 |  |  |
| 4.4.2. Analysis of the modalities for introducing a preliminary integrity check for candidates applying for public office | General Secretariat of the Government | Agency for Prevention of Corruption | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 3.7/2102/0008/ 411, 412 |  |  |
| 4.4.3. Update to the Guidance for Officials on Conflicts of Interest, addressing the GRECO recommendations from the Fifth Evaluation Round regarding the expanded remit over top executive public officials (recommendation IV) | Agency for Prevention of Corruption |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 56/1601/0007/ 411, 412 |  |  |
| 4.4.4. Development of a Manual on prevention of Corruption in the Education System | Agency for Prevention of Corruption | Ministry of Education Institute for the Improvement of Education, Institute for Evaluation of the Quality of Education | 4th quarter of 2025 | Donor funds* |  | 300* |  |
| 4.4.5 Adoption of rules for conducting integrity checks on chiefs of staff and advisors before their appointment | General Secretariat of the Government |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 3.7/2102/0008/ 411, 412 |  |  |
| 4.4.6. Publication of the names and responsibilities of chiefs of staff and advisors on the official websites of Government bodies | General Secretariat of the Government |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 3.7/2102/0008/ 411, 412 |  |  |
| 4.4.7. Adoption of the Rulebook on whistleblowing for persons in the highest executive positions | General Secretariat of the Government |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 3.7/2102/0008/ 411, 412 |  |  |
| 4.4.8. Formation of a Government Working Body for the purpose of implementing GRECO recommendations. | General Secretariat of the Government |  | 4th quarter of 2024 | 01 Budget of the RS - current expenses of employees within regular activities | 3.7/2102/0008/ 411, 412 |  |  |

| Measure 4.5: Strengthening the ethical infrastructure in the health care sector |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Health |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Analysis of the capacity and authority of ethics committees in health care institutions in relation to the level of trained health care workers in health care institutions and the level of corruption in the health care sector | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 2 |
| Trainings on ethics for employees in health care institutions | number | Report on the Implementation of the National Strategy |  | 0 | 2023 | 50 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.5.1. Analysis of the capacity and authority of ethics committees in health care institutions | Ministry of Health |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 27.0 1801/0001/411, 412 |  |  |
| 4.5.2. Regular trainings for employees in healthcare institutions on corrupt practices in healthcare, with special emphasis on corruption reporting channels and whistleblower protection measures. | Ministry of Health |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 27.0 1801/0001/411, 412 |  |  |
| 4.5.3. Conducted trainings in accordance with established needs | Ministry of Health |  | 4th quarter of 2025 | The costs will be determined after the development of a training program referred to under point 4.5.2 |  |  |  |

| Measure 4.6: Improving the enforcement of whistleblower rules |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Analysis of whistleblower protection practices, and recommendations for improving the practical enforcement of the protection, has been prepared | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds USAID Improving Public Procurement Project |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.6.1. Analysis of the case law regarding whistleblower protection practices, and recommendations for improving the practical enforcement of whistleblower protection | Ministry of Justice | Supreme Court | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.6.2. Analysis of the internal and external whistleblowing system, in order to improve efficiency. Forward the established recommendations, derived from the analysis, to the relevant institutions. | Ministry of Justice |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.6.3. Analysis of the actions of public prosecutors' offices based on the reports from whistleblowers from the private and public sectors. | Ministry of Justice |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.6.4. Organization of a workshop for competent bodies to discuss the distinction between external and internal whistleblowing | Ministry of Justice |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |

| Measure 4.7: Establishment of efficient control over public sector activities in the implementation of all stages of public procurement |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Judicial Academy |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| The percentage of developed Guidelines for strengthening control over public sector activities in the implementation of public procurement | % | Report on the Implementation of the National Strategy |  | 0 | 2023 | 100 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds UNDP Public Procurement Improvement |  |  | 1,200 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.7.1. Adoption of guidelines for market research aimed at collecting data and information to assist in defining the subject of public procurement, estimating its value, developing technical specifications, selecting the appropriate type of public procurement procedure, and evaluating the bids | Public Procurement Office | Serbian Chamber of Commerce | 3rd quarter of 2025 | UNDP |  |  | 1,200 |
| 4.7.2. Drafting of guidelines on public procurement in the health care and construction sectors, for criminal department judges | Judicial Academy |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.7.3. Drafting of guidelines for the effective resolution of complex misdemeanor proceedings under the Public Procurement Law and the Budget System Law | Judicial Academy |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.7.4. Drafting of guidelines for harmonizing practice in public procurement cases | Judicial Academy |  | 4th quarter of 2024 | USAID Improving Public Procurement Project |  |  |  |
| 4.7.5. Conducting a workshop for both the Public Procurement Office and the public prosecutors' offices on challenges in detection and prosecution of criminal offenses in the area of public procurement | Judicial Academy | Public Procurement Office Supreme Public Prosecutor's Office | 4th quarter of 2025 | 01 Budget of the RS - within regular funds USAID Improving Public Procurement Project | 23.3/1602/0009 |  |  |
| 4.7.6. Conducting a workshop for both the misdemeanor courts and the budget inspections, on challenges in determining responsibility for misdemeanors under the Budget System Law | Judicial Academy | Misdemeanor Court of Appeal Budget inspection | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 4.7.7. Conducting a workshop for both the Commission for Protection of Competition and the prosecutor’s offices, on restrictive agreements | Judicial Academy | Commission for Protection of Competition, Supreme Public Prosecutor's Office | 2nd quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |

| Measure 4.8: Improving monitoring of the enforcement of the normative framework for conflict of interest management and record keeping |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Agency for Prevention of Corruption |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Complete and timely information on cases of conflict of interest and imposed sanctions submitted to the Agency for Prevention of Corruption (APC) and the High Civil Service Council | YES/NO | Report on the Implementation of the National Strategy Report of the Agency for Prevention of Corruption Report of the High Civil Service Council |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 4.8.1. Regular monitoring of conflict of interest cases, including the number and degree of enforced sanctions (related to AP 23 (2.2.3.4) | Agency for Prevention of Corruption | Supreme Public Prosecutor's Office misdemeanor courts | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 56/1601/0007/ 411, 412 |  |  |
| 4.8.2. Each resolved conflict of interest case involving a civil servant must be reported to the High Civil Service Council, as well as information on disciplinary measures taken, if any | High Civil Service Council |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses within regular activities of the High Civil Service Council | 3.9/0606/0002 |  |  |

| Specific Objective 5: Raising awareness about the harmful effects of corruption |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Institution Competent for Coordination and Reporting: Ministry of Justice |  |  |  |  |  |
| Indicator(s) at the Level of the Specific Objective (Outcome Indicator) | Unit of Measure | Source of Verification | Baseline | Base Year | Target Value in 2024 |
| Share of citizens who reported corruption compared to the total number of those who have encountered corruption | % | Report on the Implementation of the National Strategy | 29 | 2022 | 33 |

| Measure 5.1: Raising awareness among public sector employees about various forms of corruption, its harmful effects, and the appropriate ways to report it |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: National Academy of Public Administration (NAJU) |  |  |  |  |  |  |
| Implementation Period: 2023-2024 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings on corruption prevention, following the updated annual training program of the National Academy of Public Administration (NAJU) | number | Report on the Implementation of the National Strategy Report of the National Academy of Public Administration |  | 19 | 2023 | 38 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance |  |  |  |
| Donor funds |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 5.1.1. Updating the NAJU annual training program with new mechanisms for preventing and combating corruption | National Academy of Public Administration (NAJU) | Agency for Prevention of Corruption | 4th quarter of 2024 | 01 Budget of the RS - current expenses of employees within regular activities | 65/0615/0001 |  |  |
| 5.1.2. Continuous organization of trainings for public sector employees in line with the NAJU program | National Academy of Public Administration (NAJU) | Agency for Prevention of Corruption | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 65/0615/0001 |  |  |
| 5.1.3. Improvement of the 2026 Training Program for Managers in State Bodies in the section Training Program for Newly Appointed Senior Civil Servants, concerning corruption prevention (prevention of conflicts of interest, rules on gifts, lobbying, obligations to declare assets) | National Academy of Public Administration (NAJU) | Agency for Prevention of Corruption | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 65/0615/0001 |  |  |
| 5.1.4. Conducting online training courses "Ethics and Integrity" and "Corruption, Favoritism, Fraud - How to Prevent Them in Local Self-Government" | National Academy of Public Administration (NAJU) |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 65/0615/0001 |  |  |

| Measure 5.2: Raising awareness among the employees in courts and public prosecutor's offices about various forms of corruption, its harmful effects, and the appropriate ways to report it |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Judicial Academy |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted trainings on corruption prevention, following the annual program of the Judicial Academy | number | Report on the Implementation of the National Strategy Judicial Academy Activity Report |  | 0 | 2023 | 1 |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| EU financial assistance IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 36,000 |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 5.2.1. Updating the Judicial Academy annual training program with new mechanisms for preventing and combating corruption | Judicial Academy (JA) | Agency for Prevention of Corruption | 1st quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular activities | 23.3/1602/0009/ 411, 412 |  |  |
| 5.2.2. Continuous organization of trainings for the employees in courts and public prosecutor's offices, in accordance with the Judicial Academy Annual Training Program | Judicial Academy (JA) | Agency for Prevention of Corruption | 4th quarter of 2025 | IPA 2019 Complementary assistance for the implementation of sectoral budget support |  |  | 36,000 |

| Measure 5.3: Raising awareness among citizens about forms of corruption in the public sector, its harmful effects, and the ways to report it |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Institution Competent for Implementation: Ministry of Justice |  |  |  |  |  |  |
| Implementation Period: 2024-2025 |  |  | Type of Measure: Institutional, managerial and organizational |  |  |  |
| Regulations that need to be amended/adopted for the measure implementation: |  |  |  |  |  |  |
| Indicator(s) at the Measure Level (Output Indicator) | Unit of Measure | Source of Verification |  | Baseline | Base Year | Target Value in 2025 |
| Conducted campaign for citizens on forms of corruption, its harmful effects, and the ways to report it | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |
| Percentage of citizens willing to report corruption | % | Report on the Implementation of the National Strategy |  | 29% | 2023 | 33% |
| Awareness raising among citizens conducted by distributing the leaflets about the competences of the MoI Internal Control Department and the appropriate ways to report corruption | YES/NO | Report on the Implementation of the National Strategy |  | NO | 2023 | YES |

| Source of Measure Funding | Link to the Program Budget | Total Estimated Funds in 000 RSD per Year of Implementation |  |
| --- | --- | --- | --- |
|  |  | 2024 | 2025 |
| Revenues from the budget |  |  |  |
| IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 3,900 |
| Donor funds OSCE Mission |  |  |  |

| Activity Title: | The Authority Implementing the Activity | Partner Authorities in the Implementation of the Activity | Deadline for Completion of the Activity | Source of Funding | Link to the Program Budget | Total Estimated Funds by Sources in 000 RSD |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | 2024 | 2025 |
| 5.3.1. Conducting a campaign aimed at raising the level of citizens’ awareness of the Law on Protection of Whistleblowers and increasing their willingness to act as whistleblowers | Ministry of Justice |  | 4th quarter of 2025 | USAID Improving Public Procurement Project |  |  |  |
| 5.3.2. Development of materials on corruption intended for teaching staff and their classes for primary and secondary school pupils. | Agency for Prevention of Corruption | Ministry of Education Institute for the Improvement of Education Institute for Evaluation of the Quality of Education | 4th quarter of 2025 | IPA 2019 - Flexible Facility Supporting the Strengthening of the Rule of Law in the Republic of Serbia (Support to AP 23 Fight Against Corruption and Fundamental Rights) |  |  | 3,900 |
| 5.3.3. Creation, printing and distribution of leaflets to members of the Ministry of Interior and citizens, outlining the competences of the Ministry of Interior Internal Control Department, methods of declaring assets, and ways to report corruption | Ministry of Internal Affairs |  | 2nd quarter of 2025 | Donor funds* |  |  |  |
| 5.3.5. Preparation of an awareness raising campaign for public officials about preventing corruption and strengthening integrity; for citizens about the consequences of corruption and its negative impact on their lives and about strengthening citizens' trust in the work of the Agency, in three local self-governments (Novi Sad, Kragujevac and Niš) | Agency for Prevention of Corruption |  | 4th quarter of 2025 | 01 Budget of the RS - current expenses of employees within regular funds | 56/1601/0007/ 411, 412 |  |  |

ASSESSMENT OF FUNDS NECESSARY FOR THE EXECUTION OF THE ACTION PLAN

The total funds required for the implementation of this Action Plan are estimated at 406,787,666.62.00 RSD. The planned amount for 2024 is 21,174,000.00 RSD, while for 2025 the planned amount is 385,613,666.62 RSD.

The assessment of the necessary funds for the execution of measures and activities established in the Action Plan was performed by the Ministry of Justice as the proposer and promoter of certain actions outlined in the Plan, in accordance with planning and budgetary procedures. In this regard, all action promoters from this Action Plan conducted an indicative preliminary assessment of the costs for engaging human and other resources required for the implementation of the planned activities, based on the 2024 Budget Law of the Republic of Serbia (Official Gazette of the RS, no. 92/23, 79/24). The fund assessment was performed in accordance with the limits set by the Ministry of Finance for all budget beneficiaries, within the specified sections and corresponding programs under which funds are planned for the implementation of the activities presented in this Action Plan. It also adhered to the Rulebook on the Manner of Expressing and Reporting on the Estimated Financial Impact of Laws, Other Regulations or Enactments on the Budget, i.e.

Financial Plans of Mandatory Social Insurance Organizations.

The assessment of the funds necessary for the implementation of the measures and activities planned for 2024 and 2025 was conducted following the established planning and budgetary procedures, and their financing will comply with the limits set by the Ministry of Finance for all budget beneficiaries.

For certain activities, the provision of funds from the Budget of the Republic of Serbia is uncertain. According to Article 58, paragraph 1, item 4), indent 3 of the Regulation on the Methodology of Public Policy Management, Impact Analysis of Public Policies and Regulations, and the Content of Individual Public Policy Documents, those activities shall be executed conditionally.

Donor funding is planned for specific activities. In this context, and in accordance with Article 58, paragraph 1, point 4), indent 3 of the Regulation on the Methodology of Public Policy Management, Impact Analysis of Public Policies and Regulations, and the Content of Individual Public Policy Documents, those activities shall be executed conditionally due to donor funding.

All activities stated as part of the programs implemented with budget funds imply the regular work of civil servants and state employees within their prescribed tasks. This includes their participation in working groups or individual work on monitoring the implementation of regulations, preparing analyses, reports, data collection, and similar tasks, which do not require special budgeting.

The implementation of the measures outlined in this Action Plan will not impact the international financial obligations of the state, as no borrowing is planned.

PUBLICATION OF THE ACTION PLAN

This Action Plan shall be published on the Government's website, the Ministry of Justice's website, and the e-Government portal within seven working days of its adoption.

05 Number: 021-13162/2024-1

In Belgrade, 26 December 2024

GOVERNMENT

|  | PRESIDENT Miloš Vučević |
| --- | --- |

The IT system should facilitate not only electronic submission of reports and other forms but also more efficient database searches, data export in various formats, and preparation of data for further processing and analysis. Additionally, it should enable targeted checks based on risk factors and/or random selection, formal credibility checks, early warning red flags, etc.

When preparing all the analyses envisaged in the Action Plan, all corruption risks identified in the Ex-ante analysis will be taken into account.

Official Gazette of the RS, number 119/23

The estimated funds marked with an asterisk have not been secured. In accordance with the provisions of Article 58, paragraph 1, item 4), indent 3 of the Regulation on the Methodology of Public Policy Management, Impact Analysis of Public Policies and Regulations, and the Content of Individual Public Policy Documents, those activities shall be executed conditionally.

Official Gazette of the RS, number 8/19