| REPUBLIC OF SERBIA NEGOTIATION GROUP FOR CHAPTER 23 ACTION PLAN FOR CHAPTER 23 -DRAFT- December 2014 |  |
| --- | --- |
| CONTENT |  |

- INTRODUCTION…………………………………………………………………...3

- JUDICIARY ………………………………………………………………………...9

- FIGHT AGAINST CORRUPTION...............………………………………………97

- FUNDAMENTAL RIGHTS………………………………………………………163

Introduction

- Commitment to European values

The Republic of Serbia is fully committed to the process of European integration and aware that this process requires substantial and fundamental changes in the judiciary, the anti-corruption system and the protection of fundamental rights, both at the normative and the implementation level. In this sense, in the process of developing the reform steps in Chapter 23, Serbia was primarily guided by the EU acquis. In areas where there is no acquis or it does not cover the whole area, the established standards and best comparative practices were used as a guide for creating reforms, particularly considering the legal heritage of the Republic of Serbia, as well as socio-economic factors conditioning the applicability of the solutions that provide good results in other legal systems.

We  have attempted to be completely objective in assessing the current situation in all three areas, and ambitious but also realistic in setting the goals, estimating the optimal balance between the needs reflected in the achievements of European standards, often tight deadlines, institutional and administrative capacity and limited financial resources.

In the process of drafting the Action Plan, it was helpful that priorities and courses of action were previously defined through a series of strategic documents in the areas such as the judiciary, anti-corruption, anti-discrimination, Roma rights, media freedom and the like. Tangible progress was made in the implementation of sad strategic document. The Action Plan for Chapter 23 follows the course mapped out in these strategic documents, but also advances the process by defining objectives and activities for which the subsequent need arose or it was necessary to identify more detailed evaluation. In this sense, the Action Plan for Chapter 23 represents the overarching strategic document with which all the other strategic documents shall be aligned upon its approval.  In this way, the public policy in this area will be precisely defined, and implementation, coordination, timing and funding of the reforms shall be significantly improved.

- Methodology of drafting the Action Plan

In the process of drafting the Action Plan, the negotiating Group for Chapter 23 followed the principles of full transparency and inclusiveness. In accordance with these principles, the work proceeded in two tracks. The first track involved the activities common to all three subchapters, while the second track included work on the individual parts of the Plan on the judiciary, the fight against corruption and fundamental rights.

When it comes to activities common to the entire chapter, they included preparatory workshops in the field of methodology of drafting strategic documents, consultative meetings and workshops with the representatives of the negotiating groups of the countries in the region, as well as training in the methodology of budgeting action plans. In addition, the mechanism of the consultative process with civil society organizations has been created at the level of the entire chapter. Therefore, already in the period preceding the bilateral screening, civil society organizations were involved in making presentations on harmonization of the legal system of the Republic of Serbia with the acquis.  All civil society organizations were invited to take part in the negotiation process, through a public call addressed through the website of the Office for Cooperation with Civil Society and the Ministry of Justice. Immediately upon receipt of the official version of the screening report, the Ministry of Justice published it at the website, along with the translation into Serbian language.

In accordance with the recommendations of TAIEX experts and the Guidelines for the inclusion of civil society organizations in the process of adopting regulations, adopted by the Government of the Republic of Serbia, civil society organizations were invited once again, using the aforementioned methodology, to give their suggestions on the content of the Action Plan, and subsequently a significant portion of their suggestions was adopted and implemented in the form of activities. The first draft of the Action Plan was published on the website of the Ministry of Justice in Serbian and English language. With the support of GIZ, a round table for 150 representatives of civil society organizations was organized, focusing on the discussion on the role of civil society in the design of reform steps in the negotiation process. Simultaneously, the third call to civil society organizations to provide comments on the first draft of the Action Plan was published. The comments have been included in the content of the activities, whereas the negotiating group prepared and published the Report on the involvement of civil society organizations in the process of negotiations for Chapter 23 on the website of the Ministry of Justice and the Office for Cooperation with Civil Society with regard to the extent and manner of adopting the suggestions of civil society, as well as the whole course and the modalities of the consultation process.

Since the Parliament has a key role in a procedure for adoption of the strategic documents in Serbia, the Action Plan is under scrutiny of the Parliament, too. Considering all abovementioned, as a final result, the Action Plan is product of consensus of the all of three branches of government, the independent regulatory bodies, and civil society organizations.

With regard to the methodology of drafting the text of the Action Plan in certain areas, the approach of plenary and bilateral consultative meetings, as well as daily online consultations led by coordinators of the subchapters has been used.

For the field of the judiciary, in the process of developing the first draft of the Action Plan, there were three plenary and eighteen bilateral meetings that included representatives of the High Judicial Council, the State Prosecutors Council, Ministry of Justice, Supreme Court of Cassation, the Republic Public Prosecutor's Office, the Prosecutors’ Office for the War Crimes, Judicial Academy and Anti-corruption Agency. Online consultations performed on a daily basis had an important role in the development of the plan, allowing for significant refinement of the activities.

For the field of the fight against corruption more than ten consultative meetings was held with representatives of numerous institutions in the field of health, education, customs, including Anti corruption Agency and Council for fight against corruption.

In the field of fundamental rights, due to the nature of the subchapter encompassing a number of areas, a method of bilateral consultative meetings and online consultations was applied. In the process of developing the first draft of the Action Plan, 19 bilateral meetings were held as well as daily online consultations. The representatives of the following institutions were actively involved in the process: the Ministry of Justice, Ministry of Labour, Employment, Veterans and Social Affairs, the Ministry of Culture and Information - Department of Information, Ministry of Interior, the Ministry of State Administration and Local Self-Government, Ministry of Education, Science and Technological Development, the Office of Human and Minority rights, the Republic Public Prosecutor's Office, the Supreme Court of Cassation, the Commissariat for Refugees and Migration, the Administration for Enforcement of Criminal Sanctions, the Administration for Cooperation with Churches and Religious Communities, the Team for Social Inclusion and Poverty Reduction, the Ombudsman, the Commissioner for Information of Public Importance and Personal Data Protection, the Provincial Ombudsman and UNICEF.

When it comes to the methodological and technical approach to the development of the Action Plan, efforts were made to define the activities in a manner that provides a clear, chronological overview of the necessary legislative changes, the institutional framework, as well as the need to strengthen administrative capacities, with the highest possible level of accuracy available at this time, since the implementation of some of the activities is planned in four or five years. Concurrently, a precise definition of the activities whose content is determined by the previous implementation of specific analyses or assessments, had to be postponed for a period after such assessments are performed and their results are available as a starting point for the creation of further reform steps. Consequently, it may requires periodical review and amendments of the Action plan.

In determining the authorities in charge for realization of the planned activities, the maximum level of specification was required to allow the establishment of an effective system of accountability in the implementation of the Action Plan.

A major challenge was the assessment of sufficiently ambitious yet realistic timetables, taking into account both the logical flow of the reforms that needs to be respected, as well as the institutional, administrative and budgetary burden per each year. It was particularly taken into account that the Action Plan envisages amendments to the Constitution, which brings the need for harmonization of the entire normative framework with the adopted changes, and, in this sense, the period immediately following the possible constitutional changes is therefore maximally unloaded from other activities.

Special attention was given to the determination of the indicators to provide mechanisms to measure the impact of the undertaken activities i.e. enabling insight into the degree of the desired results achievement. It was insisted on the fact that the indicators, especially those of the quantitative character are set for all the activities (or parts thereof) in which it was possible to do so.

One of the imperatives of the plan development was its financial sustainability. In this regard, particular attention was given to reducing additional budgetary burden on the minimum and maximum utilization, reorganization and coordination in the use of available resources. The costs of implementing the planned activities are expressed with great precision, using a uniform methodology developed for the purposes of Chapter 23 and 24, in cooperation with international financial experts. The methodology is designed in a way that allows that any subsequent updates and changes to the Action Plan result in a very precise expression of the financial effects.

One of the important factors in establishing relationships between activities, timelines and funding sources, was the dynamics of the planning and implementation of projects financed from IPA funds.

For a more complete picture of the reform roadmap the Action Plane includes several Annexes:

- Uniform Methodology for budgeting;

- Summary of the costs of the Action Plan’s implementation;

- Report on CSO involvement in negotiation process for Chapter 23;

- List of Recommendations from the World Bank Judicial Functional Review with detailed references to the Action Plan’s activities.

- Mechanisms for implementation of the Action Plan

1.1. Subjects responsible for monitoring the implementation of the Action Plan

The responsibility for monitoring the implementation of the activities envisaged in the Action Plan will be shared and entrusted to the Secretariat for implementation of the Action Plan for Chapter 23 (hereinafter: Secretariat), the President of the Negotiating Group for Chapter 23, the Coordination body for the process of accession of the Republic of Serbia to the European Union (hereinafter: Coordination body) and the Council of the Coordination body.

The Government of the Republic of Serbia shall make a decision on the establishment of the Secretariat, as a special working body of the Government for the support to the Negotiating Group for Chapter 23, within two months from the adoption of the Action Plan. The Government of the Republic of Serbia shall nominate the members of the Secretariat upon the proposal of the President of the Negotiating Group for Chapter 23. The method of the work of the Secretariat shall be precisely regulated by the Rules of Procedure.

The Secretariat for the implementation of the Action Plan for the negotiations for Chapter 23 shall monitor the implementation of the activities envisaged in the Action Plan on a daily basis, instigate early warning mechanism in case of delays and other problems in the implementation of the Action Plan, coordinate the reporting process and provide administrative and technical support to the Negotiating Group for the Chapter 23.

The Secretariat shall submit monthly reports on the implementation of the Action Plan to the President of the Negotiating Group on Chapter 23 and the Council of the Coordination Body.

In cooperation with the Office for European Integration, the Secretariat shall submit quarterly reports on the implementation of the Action Plan to the Coordination Body and the Committee for European Integration of the National Assembly, as well as an annual report examined and approved by the National Assembly.

In cooperation with the European Integration Office, the Secretariat shall ensure the coordination of the reporting process, attempting to avoid overlaps or gaps due to the parallel monitoring of the same or related activities foreseen in the Action Plan and national strategies and action plans in specific areas, for the purpose of the rational use of resources. Within this activity, the Secretariat shall establish ongoing communication with the bodies responsible for monitoring the implementation of national strategic documents and the Secretary of the Negotiating Group, and shall also develop a joint reporting calendar.

Administrative, professional and technical support provided by the Secretariat to the Negotiating Group for Chapter 23, includes:

- Preparation of reports on the implementation of the Action Plan;

- Preparation of proposals for the update of the Action Plan;

- Coordination with representatives of other bodies responsible for the implementation of relevant strategies and action plans;

- Review of projects financed from international sources;

- Cost estimation of the activities envisaged by the Action Plan;

- Collection and compilation of statistical data necessary for making strategic decisions, as well as other data determined as indicators for the implementation of the Action Plan;

- Collection, compilation, processing and analysis of data from all bodies determined as responsible authorities for specific activities set in the Action Plan;

- Preparation of draft decisions and documents of the Negotiating Group on the basis of the collected and analyzed data.

1.2 Early warning mechanism in case of delays in implementation of the Action Plan

In the case of perceived delays, setbacks or other problems in the implementation of the Action Plan, in addition to the regular reports, the Secretariat may issue a warning which is also delivered to the President of the Negotiating Group on Chapter 23 and the Council of the Coordination Body. Depending on the nature of the problems and the responsibilities for their elimination, these bodies shall undertake further measures towards the responsible authorities with a view to remedy the problems in the implementation. In the event that delays or problems in the implementation of activities persist, the President of the Negotiating Group and the Council of the Coordination body shall so inform the Coordination Body and the Committee for European Integration of the National Assembly, which shall, within its jurisdiction, take further measures towards the subjects foreseen in the Action Plan as responsible authorities for undertaking activities whose implementation is delayed or there are other problems in their implementation.

| 1. JUDICIARY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CURRENT STATE OF PLAY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The legislative framework regulating judiciary in Serbia encompasses: National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 57/13); Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 71/13 and 55/14); The Constitution of the Republic of Serbia ("Official Gazette of the RS", No. 98/06); Law on the Constitutional Court ("Official Gazette of the RS", No. 109/07 and 99/11); Law on the High Judicial Council ("Official Gazette of the RS", No. 116/08, 101/10 and 88/11); Law on Judges ("Official Gazette of the RS", No. 116/08, 58/09 – decision of the Constitutional court, 104/09, 101/10, 8/12 – decision of Constitutional court, 121/12 and 101/13); Law on Organization of Courts ("Official Gazette of the RS", No. 116/08, 104/09, 101/10, 31/11 – state law, 78/11 – state law, 101/11 and 101/13); Law on the State Prosecutorial Council ("Official Gazette of the RS", No. 116/08, 101/10 and 88/11); The Law on Public Prosecutor’s Office ("Official Gazette of RS", No. 116/08, 104/09, 101/10, 78/11 – state law, 101/11, 38/12 – decision of the Constitutional court, 121/12 and 101/13 ); Law on the Seats and Territorial Jurisdictions of Courts and Public Prosecutors’ Offices ("Official Gazette of the RS", No. 101/13); Law on the Judicial Academy ("Official Gazette of RS", No. 104/09 and decision of Constitutional court No. 32/14); Criminal Procedure Code ("Official Gazette of the RS", No. 72/11, 101/11, 121/12, 32/13, 45/13 and 55/14); Civil Procedure Law ("Official Gazette of the RS", No. 72/11 49/13 – decision of Constitutional court, 74/13 – decision of Constitutional court, 55/14); Law on Non-Contentious Proceedings ("Official Gazette of the RS", No. 25/82 and 48/88 and "Official Gazette of the RS", No. 46/95 – state law, 18/05 – state law, 85/12, 45/13 – state law and 55/14); Law on Enforcement and Security ("Official Gazette of the RS", No. 31/11, 99/11 – state law, 109/13 – decision of Constitutional court and 55/14); Law on Public Notaries ("Official Gazette of the RS", No. 31/11, 85/12, 19/13 and 55/14 – state law); Law on Mediation ("Official Gazette of the RS", No. 55/14); Law on the Bar Exam ("Official Gazette of the RS", No. 16/97); Law on Misdemeanors ("Official Gazette of the RS", No. 65/13); Law on the Public Attorney's Office ("Official Gazette of the RS", No. 55/14); Court Rules of Procedure ("Official Gazette of RS", No. 110/09, 70/11, 19/12 and 89/13); Rules of Procedure of the High Judicial Council ("Official Gazette of the RS", No. 29/13); Rules of Procedure of the State Prosecutorial Council ("Official Gazette of the RS", No. 55/09); Rules on the Administration in Public Prosecution ("Official Gazette of the RS", No. 77/04, 52/07, 2/08, 11/09 and 44/09); Code of Ethics for Judges ("Official Gazette of the RS", No. 96/10), Code of Ethics of Public Prosecutors and Deputy Public Prosecutors of the Republic of Serbia ("Official Gazette of the RS", No. 87/13); Code of Ethics for members of the State Prosecutorial Council ("Official Gazette of the RS ", No. 60/14); Rules of procedure on disciplinary procedure and disciplinary accountability of judges ("Official Gazette of the RS ", No. 71/10); Rules on disciplinary procedure and disciplinary accountability of public prosecutors and deputy public prosecutors ("Official Gazette of the RS ", No. 64/12, 58/14); Rulebook on the criteria for transfer of a judge to another court in the case of the abolition of the substantial part of the jurisdiction of the court to which he was elected ("Official Gazette of the RS", No. 105/13); Rules of Procedure on the criteria and standards for performance appraisal of public prosecutors and deputy public prosecutors ("Official Gazette of the RS", No. 58/14) – Rules of Procedure are experimentally implemented in 18 public prosecutors’ offices in the period from June 18th until December 15th 2014. Upon completion of the experimental implementation, the State Prosecutorial Council will analyze and compile report on the implementation of the Rules of Procedure, stating whether it is necessary to amend it; Rulebook on the criteria, standards, process and bodies for performance evaluation of judges and court presidents ("Official Gazette of the RS", No. /14); Uniform backlog reduction program in the Republic of Serbia, which has been in implementation since January 1st 2014 (Supreme Court of Cassation Court adopted Uniform program on December 25th 2013); Rules of Procedure on public notary exam ("Official Gazette of the RS", No. 71/11, 81/11, 3/12, 78/12 and 31/13); Initial training program for candidates for exercise of the profession of public notaries for 2014 (adopted on April 7th 2014); Rules of Procedure on temporary number of public notaries’ positions and the official seats of public notaries and public notaries’ positions for which a competition will be announced for the first 100 public notaries ("Official Gazette of the RS", No. 31/12 and 57/14); Rulebook on determining the number of bailiff/enforcement officers ("Official Gazette of the RS", No. 61/14). The institutional framework encompass: Constitutional Court, the High Judicial Council, the State Prosecutorial Council, Ministry of Justice, Judicial Academy, Supreme Court of Cassation, four appellate courts, 25 higher courts, 66 basic courts with 25 court units, Misdemeanor court of appeal with three departments, 44 misdemeanor courts, Commercial Court of Appeal, 16 commercial courts, Administrative Court with three departments, the Republic Public Prosecutor’s Office, four appellate public prosecutors’ offices, 25 higher public prosecutors’ offices, 58 basic public prosecutors’ offices. The judicial system in the Republic of Serbia, as of September 1st 2014, encompasses 2800 judges, 90 public prosecutors and 741 deputy public prosecutors. National Assembly of the Republic of Serbia enacted the National Judicial Reform Strategy for the period 2013-2018 on July 1st 2013, which has determined priorities, strategic goals and strategic guidelines of reform measures. The Government of the Republic of Serbia adopted an Action plan for implementation of the National Judicial Reform Strategy for the period 2013-2018 on July 31st which envisages concrete measures and activities for implementation of strategic objectives, defines the deadlines and competent authorities for its implementation and financial sources. National Judicial Reform Strategy for the period 2013-2018 envisages mechanism to monitor the implementation of reform measures, in the form of Commission for Implementation of the National Judicial Reform Strategy for the period 2013-2018, with the composition of 15 members who are representatives of all relevant stakeholders in the reform process. Strategy envisages independence, impartiality, competence, accountability and efficiency of the judiciary, as five basic principles and defined priorities, strategic objectives and strategic guidelines of reform measures. Concerning independence of judiciary, National Judicial Reform Strategy for the period 2013-2018 has identified the need of amending the Constitution in the part which deals with the interference of legislative and executive powers in the process of appointment and dismissal of judges, court presidents, public prosecutors and deputy public prosecutors, elected members of the High Judicial Council and State Prosecutorial Council, and the need for précising the role and status of Judicial Academy, as mechanism for entry to judiciary. In addition, due to length and complexity of amending the Constitution, a series of interim measures are provided aimed at strengthening the independence of the judiciary through amendments to the judicial laws within the provisions of the Constitution of the Republic of Serbia. The High Judicial Council and State Prosecutorial Council, in accordance with the strategic objectives, should become the key institutions of the judiciary with full capacities of their competencies and with precisely defined system of transparency and accountability. In the first year of implementation of the National Judicial Reform Strategy for the period 2013-2018 set of judicial laws has been amended and judicial independence has been strengthened with these interim measures, within the framework of the current Constitution. At the same time, work has commenced, on an analysis of the provisions of the Constitution of the Republic of Serbia and on the identification of necessary amendments in the part relating to the judiciary. Presidents of the courts of all levels have been appointed. The High Judicial Council and State Prosecutorial Council adopted criteria and standards for the performance appraisal of judges, presidents of courts, public prosecutors and deputy public prosecutors and the Councils have commenced preparing the criteria and standards for appointment to judicial offices. Planed amendments to the Law on the High Judicial Council and State Prosecutorial Council will significantly improve transparency in the work of the Councils. Introduction of program budgets has commenced and capacities of the administrative offices of the High Judicial Council and State Prosecutorial Council have been strengthened. Taking into account the constantly extending the scope of competences of the Councils, it is still evident the need for strengthening the capacities in the fields of finance, analytics and strategic planning. National Judicial Reform Strategy for the period 2013-2018 stipulates implementation of the measures aimed at improvement of impartiality, ethics and integrity of the judicial office holders as well as at the alignment and complete accessibility to the case law and the full realization of the right to the natural judge. In this regard, State Prosecutorial Council has established Board of Ethics, and the same activity is underway in High Judicial Council. The same strategic document also stipulates establishment of a system of appointment and promotion of judges and public prosecutors according to clear, objective and criteria determined in advance. Following measures in the reform of Judicial Academy are set forth as the strategic approach: Improving initial and continuously training of judges’ and public prosecutors’ associates and assistants, and judicial office holders as well as of representatives of legal professions, along with the system of development of a comprehensive annual training programs and assessment of attendees. Improvement of operation of disciplinary bodies of the High Judicial Council and State Prosecutorial Council is set forth in the National Judicial Reform Strategy for the period 2013-2018. Despite commencement of operation of those disciplinary bodies, their work has to be much more efficient. Proposed amendments to Law on High Judicial Council and Law on State Prosecutorial Council establishes clear mechanisms of accountability of members of these bodies. Taking into account that inefficiency has been the biggest judiciary’s problem in the Republic of Serbia for a long time, the National Judicial Reform Strategy for the period 2013-2018 envisages a series of measures aimed at improving efficiency, commencing from improving the procedural laws, establishing e-justice system, as well as the monitoring and correction of the functioning of the judicial network. Alleviation of court of its workload is planned by introducing a system of bailiff/enforcement officers, public notaries and mediation in disputes resolution, which would, along with swift resolution of case backlog and infrastructure investments achieve shorter duration of court proceedings and improve access to justice. From January 1st 2014 new judicial network has entered into force with increased number of courts and public prosecutors’ offices, which should reduce expenses and contribute to easier access to justice. There have been considerable investments in infrastructure that already, by the end of 2014, suppose to lead to a significant increase in the number of courtrooms, especially in Belgrade, where this problem has existed for decades. Improvement of Information and Communication Technology in courts and public prosecutors’ offices has continued, however there is still a problem with the parallel operation of multiple incompatible systems, making it difficult to monitor the statistical parameters of judicial efficiency, the exchange of information between courts and public prosecutors’ offices, parties’ insight into the status of the case, as well as the duration of proceedings. This status of Information and Communication Technology has a negative impact also on the reach of the automatic case management, which improvement is also caused by the need for the introduction of a case weighting system. The Supreme Court of Cassation has adopted a Uniform backlog-reduction program in the Republic of Serbia that stipulates reduction of backlog of cases by 2018. Furthermore, significant steps have been made towards the relief of courts by using the system of bailiff/enforcement officers. From September 1st 2014 public notaries have commenced working, and from January 1st 2015, upon the enactment of the Law on mediation, legislative framework for the operation of the system of mediation has been created. From October 1st 2013 the implementation of the Criminal Procedure Code from 2011 has commenced in all courts and public prosecutors’ offices of general jurisdiction, which has introduced prosecutorial investigation as the most important novelty. Despite initial obstacles in implementation, there has been a significant increase in the percentage of proceedings completed by applying the principle of opportunity in criminal prosecution and plea bargain. Considering that National Judicial Reform Strategy for the period 2013-2018 (priorities and defined goals in the Strategy correspond to recommendations from screening report) has been developed as a result of general consent of all relevant subjects in the field of judiciary, during the process of drawing up the Strategy particular attention was given to take into account crucial activities envisaged in the Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018. In this way, higher degree of coherence between these two documents is achieved and supervision over reform implementation is facilitated. In addition, activities envisages in the Action plan for negotiations represent “map” of the reforms, whereas Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018 includes broader scope of detail activities. In order to achieve complete cohesion of two documents (particularly concerning deadlines), revision of Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018 will be conducted after adoption of Action plan for negotiations. A functional analysis of judiciary in the Republic of Serbia was conducted with the support of the World Bank, with the aim of objective consideration of overall current state of play, as of July 1st 2014, in the judiciary in the Republic of Serbia, as well as concerning the degree of implementation of the measures provided in the Action Plan for implementation of the National Judicial Reform Strategy for the period 2013-2018. Conclusions and guidelines from the Draft of this document were used as a starting point for defining further reform activities, all in the context of recommendations encompassed in Report from screening. WAR CRIMES The legal framework in Serbia encompass: Criminal Code (“Official Gazette of RS”, No 121/12); Criminal Procedure Code (“Official Gazette of RS” No. 72/11, 101/11, 121/12, 32/13,45/13 and 55/14); Law on Mutual Legal Assistance in Criminal Matters (“Official Gazette of RS” No.20/2009); Law on Organization and Competence of Government Authorities in War Crimes Proceedings („Official Gazette of the RS“ No. 67/03, 104/2009); Law on Protection program for participants in Criminal Proceedings („Official Gazette of the RS“ No. 85/2005); Law on Cooperation with the ICTY („Official Gazette of the SRJ“ No. 18/2002, and “Official Gazette of SCG” No. 16/2003); Memorandums and protocols on cooperation concluded directly between Serbian war crime prosecutors office and countries in the region and foreign judicial institutions with the purpose of direct cooperation, and more efficient exchange of information regarding war crimes and perpetrators (Croatia, Bosnia and Herzegovina, Montenegro, EULEX). Jurisdiction for War Crimes in Serbia: 1) Criminal offences from art. 370 through 386 of the Criminal Code; 2) Serious violations of International Humanitarian Law committed in the territory of the former Yugoslavia since January 1st 1991 stipulated in the Statute of the International Criminal Tribunal for the Former Yugoslavia; 3) Criminal offence from Art. 333 of the Criminal Code - assistance to the perpetrator after the commission of crime, if committed in relation to criminal offences from point 1) and 2) of this Article. Institutional framework: War Crimes Prosecutor’s Office: Prosecutor, 6 Deputy Prosecutors, 2 Advisers, 3 Assistants; Higher Court, War Crime Department: 6 Judges, 1 Judge for the pre-trial; Ministry of the Interior, War Crimes Investigation Service: Head of the Service, Deputy Head, 2 Chiefs of the Departments, 4 Sections Chiefs, 43 member of the Service; Ministry of the Interior, Witness protection unit; Victims and Witnesses assistance and support Section: 3 employees; It was recognized on the international level that the judicial and prosecutorial resources need to be adequate. This especially, in the light of the number of evidence/cases that are being transferred from the ICTY and regional cooperation. War Crimes Prosecutor’s Office has received, in the recent months, tens of thousands documents, as well as a large number of photo albums and documents from the Prosecutor’s Office of ICTY. In order to address the aforementioned increased inflow of evidence and the workload, War Crimes Prosecutor’s Office should at least build their capacities which are provided in the current systematization. Upon the completion of mandate of Tribunal in the Hague, the responsibility for the prosecution of war crimes is fully transferred to the Republic of Serbia, which must demonstrate that its institutions are dedicated and administratively able to responsibly process all remaining war crimes suspects and to contribute to the process of transitional justice. New Criminal Procedure Code (CPC) was introduced in War Crime proceedings since January 15th 2012 and has enabled prosecution control/administration over the investigative phase of the proceedings and has introduced new relations with State authorities and their duties in criminal proceedings. According to new CPC the prosecutor office is leading the pre-investigation proceedings (not investigative judge) and conducting investigation (possibility to conduct investigation against unknown person). Prosecutor’s office has jurisdiction to instruct the police to conduct certain measures while police has obligation to act and to inform prosecutor’s office upon their requests. New CPC has given wider jurisdiction for prosecution in collecting evidence during the investigation and elevated responsibility for the legality in obtaining of evidence. It has been widely agreed by the international observes and organizations that the courts processes cases more efficiently and the judges perform better under new procedural rules. In addition to general protection and support for witnesses and victims envisaged by the Criminal Procedure Code in the War Crime proceedings additional special legislation apply in the field of witness and victims support that allows for full implementation for EU Directives regulating this area (2012/29/EU declaration regarding rights, support and protection of victims). In war crime proceedings witnesses and victims have access to: video link testimony; right to interpretation and translation; right to access victim support services; right to avoid contact between victim and offender; protection against secondary victimization; individual assessment of victims to identify specific protection needs; training of staff. Criminal Procedure Code envisages the category of especially vulnerable witness who may be examined outside the Court or with the assistance or a psychologist, social worker or other relevant expert by introducing support during pre-investigation and investigation, improving staff resources and introducing new qualified staff in War Crimes Prosecutor’s Office. Protection of witnesses outside the court proceedings was criticized regardless of the fact that the law and opportunities for protection exist (available measures include a change of residence; concealment of the witness identity or complete change of identity). Most criticisms were directed towards the Witness protection unit and the activities envisaged in this action plan should address those criticisms by introducing new criteria for hiring new members of the unit based on professional standards, improving the status of its members and training of unit members. During the cooperation with the ICTY, Serbia handed over 46 suspects to International Criminal Tribunal for the former Yugoslavia (ICTY). Serbia has daily cooperation with the ICTY prosecutor’s office. It should be noted that the Residual Mechanism of the ICTY (pursuant to the Completion Strategy of the ICTY) started functioning on July 1st 2013 and that certain problems arose with transferring evidence from the ICTY to the War Crime Prosecutor’s Office. Namely, redacted witness statements given to investigators of the ICTY are transferred but disclosure of witness identity to the Serbian War Crime Prosecutor’s Office is lacking. War Crime Prosecutor’s Office is for now receiving scarce number of statements on case by case basis but still without the ones that could identify the perpetrators. Statements by those witnesses would open several war crime cases against several members of paramilitary formations and high officials and solution of this problem will be the main incentive for cases against high level perpetrators. Statistics of war crime proceedings have changed since the Screening report for PG23. Through domestic trials, at the moment 435 persons were processed, currently there is 14 ongoing cases in 1st instance (against 40 defendants) in comparison to 10 cases against 34 defendants in the screening report. As regards regional cooperation, Serbia at this moment has 264 exchanges of information and evidence related to 131 cases with Croatia, 42 with Bosnia and Herzegovina, 9 with Montenegro and 83 with EULEX and the United Nations Interim Administration Mission in Kosovo (UNMIK). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - INDEPENDENCE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.1. With the support of external experts, Serbia should make a thorough analysis of the existing solutions/possible amendments to the Constitution bearing in mind the Venice Commission recommendations and European standards, ensuring independence and accountability of the judiciary. Changes should include, inter alia, the following points: - The system for the recruitment, selection, appointment, transfer and termination of judge’s office, presidents of Courts, and prosecutors should be independent of political influence and remain of the responsibility of the High Judicial and State Prosecutorial Councils. Entry in the judiciary shall be based on merit-based objective criteria, fair in selection procedures, open to all suitably qualified candidates and transparent in terms of public scrutiny. The High Judicial Council and the Prosecutorial Council should be empowered with leadership and the power to manage the judicial system, including when it comes to immunities. They should have a pluralistic composition, without involvement of the National Assembly (unless solely declaratory), with at least 50% of members stemming from the judiciary, representing different levels of jurisdiction. Their elected members should be selected by their peers; - Legal or executive authorities should not have the power to supervise or monitor operations of the judiciary; - Reconsider the probation period of three years for candidate judges and deputy prosecutors; - Clarify the grounds for the dismissal of judges; - Clarify the rules for terminating the mandate of Judges of the Constitutional Court; |  |  |  |  |  |  | Adopted new Constitution and judicial laws aligned with new Constitution which, taking into account the recommendations of the Venice Commission and European standards, ensures the independence of the judiciary from political influence, maximally restricting influence of legislative and executive powers in the process of recruitment, selection, appointment, transfer and termination of the judge’s office, presidents of the courts, and (deputy) public prosecutors, which must be based on precise criteria. Constitution guarantees entrance in the judiciary based on merit-based objective criteria, fair in selection procedures, open to all suitably qualified candidates and transparent in terms of public scrutiny. The role of High Judicial Council and State Prosecutorial Council in terms of the management of the judiciary, as well as in the supervision and control of the judiciary has been strengthened; their composition encompasses at least 50% of members, selected by their peers, from the ranks of judges and public prosecutors, stemming from different levels of jurisdiction (the role of the National Assembly is solely declaratory). The Constitution clarifies the rules for terminating the mandate of the judges of the Constitutional Court. |  |  |  |  | - Positive opinion of Venice Commission on new Constitution in part which deals with judiciary; - Positive evaluation by European Commission stated in Annual Progress Report on Serbia, concerning improvement of Constitutional provisions. |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.1.1. |  |  | Conduct analysis of provisions of the Constitution and proposing amendments to the Constitution taking into account opinion of Venice Commission and European standards. |  | - Commission for the reform of judiciary (Working group for conducting analysis of amending constitutional framework) |  | IV quarter of 2015. |  | Budget of the Republic of Serbia, Budgeted in activity 1.1.1.3. TAIEX-1750 € In 2015 |  |  | Analysis conducted and report on the results of the analysis submitted to the Government of the Republic of Serbia and to the National Assembly. |  |  |
| 1.1.1.2. |  |  | Initiating the process of amending the Constitution and the adoption of a proposal in the National Assembly to amend the Constitution. |  | -Authorized proposing authorities according to Article 203 of the Constitution of the Republic of Serbia -National Assembly |  | … |  | Budget of the Republic of Serbia Budgeted in activity 1.1.1.3. In 2015 |  |  | A proposal to amend the Constitution adopted in the National Assembly. |  |  |
| 1.1.1.3. |  |  | Preparing the draft of the Constitution and conducting the public debate. |  | -Working group for preparing the draft of the Constitution -National Assembly -Government of the Republic of Serbia |  | … |  | Budget of the Republic of Serbia- 521.168€ |  |  | Conducted public debate concerning the draft of the Constitution. |  |  |
| 1.1.1.4. |  |  | Submitting the Draft of the Constitution to the Venice Commission on opinion. |  | -Government of the Republic of Serbia |  | … |  | Budget of the Republic of Serbia Budgeted in activity 1.1.1.3. |  |  | Venice Commission issued Opinion on proposal to amend the Constitution. |  |  |
| 1.1.1.5. |  |  | Adoption of the new Constitution. |  | -National Assembly |  | … |  | Budget of the Republic of Serbia- 39.375 € |  |  | New Constitution adopted. |  |  |
| 1.1.1.6. |  |  | Adoption of the Constitutional law. |  | -National Assembly |  | … |  | Budget of the Republic of Serbia Budgeted in activity 1.1.1.5. |  |  | Constitutional law adopted. |  |  |
| 1.1.1.7. |  |  | Alignment of judicial laws with new constitutional provisions (Law on Organization of Courts, Law on Seats and territorial Jurisdiction of Courts and Public Prosecutors’ Offices, Law on Judges, Law on Public Prosecutor’s Office, Law on High Judicial Council, Law on State Prosecutorial Council, Law on Judicial Academy) |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly |  | …during two quarters after adopted amendments to the Constitution |  | Budget of the Republic of Serbia and TAIEX Calculation per law from normative framework |  |  | Adopted judicial laws aligned with new constitutional provisions |  |  |
| 1.1.1.8. |  |  | Alignment of by-laws with amended judicial laws |  | - Ministry of Justice -High Judicial Council -State Prosecutorial Council -Supreme Court of Cassation -Republic Public Prosecutor’s Office -Judicial Academy |  | ...during two quarters after alignment of judicial laws with new Constitution |  | Budget of the Republic of Serbia Calculation per law from normative framework |  |  | By-laws in the field of judiciary aligned with amended judicial laws. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.2. Ensure permanent appointment of remaining Court presidents (in particular of Basic and High Courts); |  |  |  |  |  |  | Court presidents of remaining basic and higher courts appointed. |  |  |  |  | Courts are managed by appointed court presidents. |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.2.1. |  |  | The National Assembly appoints the remaining court presidents at the proposal of the High Judicial Council. |  |  | -High Judicial Council -National Assembly | I quarter of 2015 | Budget of Republic of Serbia Activity requiring insignificant costs |  |  |  | Remaining court presidents of basic and higher courts are appointed |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OWERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.3. A fair and transparent system of promotion of judges and prosecutors needs to be established, together with a periodical professional assessment of judges and prosecutors' performance. A system to monitor and evaluate the application of those standards in practice should be established. The Councils should bear the responsibility for taking decisions on promotion, demotion or dismissal; |  |  |  |  |  |  | Established fair and transparent system, in which Councils are accountable for decision making for promotion, demotion and dismissal of judges and public prosecutors, based on periodical professional assessment of judges’ and public prosecutors’ performance |  |  |  |  | - Positive evaluation issued by European Commission in Annual Progress Report on Serbia - Positive evaluation stated in the Report of High Judicial Council’s Working group for monitoring results of judicial laws’ implementation - Positive evaluation stated in the Report of State Prosecutorial Council’s Working group for monitoring results of judicial laws’ implementation |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.3.1. |  |  | Adoption of the Rules on criteria and standards for evaluation of qualification, competence and worthiness for election of judges and court presidents. (Criteria for election to office). (the same activity 1.3.1.3.) |  |  | -High Judicial Council | I quarter of 2015. |  | In total 10.392€ Budget of the Republic of Serbia-8.642€ TAIEX-1.750€ In 2015 |  |  | Adopted Rules on criteria and standards for evaluation of qualification, competence and worthiness for election process of judges and court presidents. |  |  |
| 1.1.3.2. |  |  | Adoption of the Rules on criteria, standards and procedures for evaluation of judicial assistants. |  |  | -High Judicial Council | I quarter of 2015. |  | In total 8.642€ Budget of the Republic of Serbia-8.642€ TAIEX- Budgeted in activity 1.1.1.3. In 2015 |  |  | Rules on criteria, standards and procedures for evaluation of judicial assistants adopted. |  |  |
| 1.1.3.3. |  |  | Council, according to the new criteria from a) Rules on criteria and standards for evaluation of qualification, competence and worthiness for election of judges and court presidents and from b) Rules on criteria, standards and procedures for evaluation of judicial assistants, decides on promotion, election and dismissal of holders of judicial offices as interim approach until amending the Constitution and alignment of laws and by-laws to new Constitutional provisions. |  |  | -High Judicial Council | Commencing from II quarter of 2015. |  | Budget of the Republic of Serbia. Activity requiring insignificant costs |  |  | Council decides on promotion, election and dismissal of holders of judicial offices according to the new criteria. |  |  |
| 1.1.3.4. |  |  | The establishment and efficient operation of the working group of High Judicial Council for the monitoring of the results of implementation of judicial laws. |  |  | -High Judicial Council -Working group of the High Judicial Council for the monitoring of the results of implementation of judicial laws | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-30.878 € In 2015- 7.719 € In 2016- 7.719 € In 2017- 7.719 € In 2018- 7.719 € |  |  | Working group of High Judicial Council for the monitoring of the results of implementation of judicial laws established and works efficiently. |  |  |
| 1.1.3.5. |  |  | Adoption of Rules on the criteria and standards for the evaluation of qualification, competence and worthiness of candidates for election process of holders of prosecutorial office. (Criteria for election to office). (the same activity 1.3.1.4.) |  |  | -State Prosecutorial Council | I quarter of 2015. |  | Budget of the Republic of Serbia-8.642€, TAIEX- Budgeted in activity 1.1.3.1. In 2015 |  |  | Adopted Rules on the criteria and standards for the evaluation of qualification, competence and worthiness of candidates for election of prosecutorial office holders. |  |  |
| 1.1.3.6. |  |  | State Prosecutorial Council, according to the new criteria from Rules on criteria and standards for evaluation of qualification, competence and worthiness for proposing and selection of candidates to public prosecutor’s office, decides on promotion, selection and dismissal of holders of public prosecutors’ offices as interim approach until amending the Constitution and alignment of by-laws to new Constitutional provisions. |  |  | -State Prosecutorial Council | Commencing from II quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | State Prosecutorial Council decides, according to new criteria, on promotion, selection and dismissal of holders of the public prosecutor’s office. |  |  |
| 1.1.3.7. |  |  | The establishment and efficient operation of working group of State Prosecutorial Council for monitoring the implementation of the judicial laws. |  |  | -State Prosecutorial Council | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-30.878 € In 2015- 7.719 € In 2016- 7.719 € In 2017- 7.719 € In 2018- 7.719 € |  |  | Working group of State Prosecutorial Council for the monitoring of implementation of judicial laws established and works efficiently. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.4. Sufficient administrative capacities and financial authority over their own budget needs to be ensured to allow the High Judicial and the State Prosecutorial Councils to effectively perform their tasks. Their work should be governed by transparency and institutional accountability; |  |  |  |  |  |  | The High Judicial Council and State Prosecutorial Council have completely been ensured with budgetary competencies; their administrative capacities have been strengthened, their work is transparent and is subject to institutional accountability. |  |  |  |  | - Increased structure and number of employees in Administrative office of High Judicial Council according to new systematization based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with extending High Judicial Council’s competencies; - Increased structure and number of employees in Administrative office of State Prosecutorial Council according to new systematization based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with extending of State Prosecutorial Council’s competencies; - High Judicial Council independently proposes and executes judicial budget; - State Prosecutorial Council independently proposes and executes budget of public prosecutor’s office; - Sessions of High Judicial Council are, as a rule, open to the public; - Decisions of High Judicial Council are reasoned; - Reports on work of High Judicial Council are published on the web page of the Council; - Clear procedures for institutional responsibility of High Judicial Council and State Prosecutorial Council are established. |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.4.1. |  |  | Adoption of Law on amendments and supplements to Law on the High Judicial Council which, within current Constitutional provisions and opinion of Venice Commission, envisages following: -introducing principle of the most transparent work of this body -within the provisions of current Constitution, improving procedure of election of High Judicial Council’s members, all in the context of strengthening judicial independence -introducing mechanisms of institutional liability of High Judicial Council; |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | I quarter of 2015. |  | Budget of the Republic of Serbia-30.878 € In 2015 |  |  | Adopted Law on amendments and supplements to Law on the High Judicial Council which, within current Constitutional provisions, envisages following: -introducing principle of the most transparent work of this body -within the provisions of current Constitution, improving procedure of election of High Judicial Council’s members, all in the context of strengthening judicial independence -introducing mechanisms of institutional liability of High Judicial Council; |  |  |
| 1.1.4.2. |  |  | Adoption of Law on amendments and supplements to the Law on the State Prosecutorial Council which, within current Constitutional provisions, envisages following: -introducing principle of the most transparent work of this body -improving procedure of election of State Prosecutorial Council’s members, all in the context of strengthening judicial independence -introducing mechanisms of institutional liability of State Prosecutorial Council; |  |  | -Ministry of Justice -Government of the republic of Serbia -National Assembly | I quarter of 2015. |  | Budget of the Republic of Serbia-30.878 € In 2015 |  |  | Adopted Law on amendments and supplements to the Law on the State Prosecutorial Council which, within current Constitutional provisions, envisages following: -introducing principle of the most transparent work of this body -improving procedure of election of State Prosecutorial Council’s members, all in the context of strengthening judicial independence -introducing mechanisms of institutional liability of State Prosecutorial Council; |  |  |
| 1.1.4.3. |  |  | Amending the Rules of procedure of High Judicial Council in accordance with amended Law on the High Judicial Council. (Activity 1.1.4.2.) |  |  | -High Judicial Council | I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.4.2. |  |  | Rules of procedure of High Judicial Council amended in accordance with amended Law on the High Judicial Council. |  |  |
| 1.1.4.4. |  |  | Complete transfer of budgetary competencies from Ministry of Justice to High Judicial Council. |  |  | -Ministry of Justice -High Judicial Council | II quarter of 2016. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Budgetary competencies transferred from Ministry of Justice to High Judicial Council. |  |  |
| 1.1.4.5. |  |  | Introduction of program budget in High Judicial Council |  |  | -High Judicial Council | Commencing from I quarter of 2015. |  | Budget of the Republic of Serbia- 8.642€ In 2015 |  |  | High Judicial Council introduced program budget. |  |  |
| 1.1.4.6. |  |  | Adoption of new Act of systematization of work places in the Administrative Office of High Judicial Council and strengthening the capacities of Administrative office of High Judicial Council according to new systematization based on the needs of strengthening the analytical, statistical and managerial capacities, with the aim of changing professional structure of employees, in accordance with extending the scope of High Judicial Council’s competencies. |  |  | -High Judicial Council | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-17.285€ In 2015 |  |  | Capacities of Administrative Office of High Judicial Council strengthened according to the new systematization based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with extending the scope of High Judicial Council’s competencies. |  |  |
| 1.1.4.7. |  |  | Amending Rules of Procedure of State Prosecutorial Council according to amended Law on State Prosecutorial Council. (Activity 1.1.4.2) |  |  | -State Prosecutorial Council | I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.4.2. |  |  | Amended Rules of Procedure of State Prosecutorial Council according to amended Law on State Prosecutorial Council. |  |  |
| 1.1.4.8. |  |  | Complete transfer of budgetary competencies from Ministry of Justice to State Prosecutorial Council. |  |  | -Ministry of Justice -State Prosecutorial Council | II quarter of 2016. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Budgetary competencies transferred from Ministry of Justice to State Prosecutorial Council. |  |  |
| 1.1.4.9. |  |  | Introduction of program budget in State Prosecutorial Council. |  |  | -State Prosecutorial Council | Commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-8.642€ In 2015 |  |  | State Prosecutorial Council introduced program budget. |  |  |
| 1.1.4.10. |  |  | Adoption of new Act of systematization of work positions in the Administrative Office of State Prosecutorial Council and strengthening the capacities of Administrative office of State Prosecutorial Council according to the new systematization based on the needs of strengthening the analytical, statistical and managerial capacities, with the aim of changing professional structure of employees, in accordance with extending the scope of State Prosecutorial Council’s competencies. |  |  | -State Prosecutorial Council | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-17.285 € In 2015 |  |  | Capacities of Administrative office of State Prosecutorial Council strengthened according to the new systematization based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with extending the scope of State Prosecutorial Council’s competencies. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.5. Establish a clear procedure for both Councils to react publicly in cases of political interference in the judiciary and prosecution; |  |  |  |  |  |  | High Judicial Council and State Prosecutorial Council react according to clear and in-advance established procedures in case of political interference in the judiciary. |  |  |  |  | High Judicial Council and State Prosecutorial Council regularly (periodically), and, if necessary, extraordinarily address to the public presenting assessment on political interference in the judiciary. |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.5.1. |  |  | Amending Rules of Procedure of High Judicial Council to define clear procedure for public reacting in cases of political interference in the judiciary which includes regular/periodic, as well as extraordinary public addressing of High Judicial Council, concerning the political interference in the judiciary |  |  | -High Judicial Council | I quarter of 2015. | Budget of the Republic of Serbia Budgeted in activity 1.1.4.2. |  |  |  | Clear procedure for public reacting in cases of political interference in the judiciary defined in amended Rules of Procedure of High Judicial Council |  |  |
| 1.1.5.2. |  |  | Amending Rules of Procedure of State Prosecutorial Council to define clear procedure for public reacting in cases of political interference in the operation of public prosecutor’s office which includes regular/periodic, as well as extraordinary public address of State Prosecutorial Council, concerning the political interference in operation of public prosecutor’s office. |  |  | -State Prosecutorial Council | I quarter of 2015. | Budget of Republic of Serbia Budgeted in activity 1.1.4.2. |  |  |  | Clear procedure for public reacting in cases of political interference in operation of public prosecutor’s office defined in amended Rules of Procedure of State Prosecutorial Council. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.6. Ensure the full respect of court decisions including by raising the awareness that criticizing decisions, in particular by politicians puts the independence at risk; |  |  |  |  |  |  | Judicial decisions are fully respected whereas awareness, that criticizing decisions puts the independence at risk, has been improved. |  |  |  |  | - Percentage increase of judges and public prosecutors who claim that are knowledgeable of European standards concerning restrictions of criticizing judicial decisions; - Percentage increase of journalists who claim that are knowledgeable of European standards and national norms concerning reporting on court proceedings; - Percentage decrease of judges and public prosecutors who consider that their independence has been put at risk by public criticizing judicial decisions; - Number of petitions for initiating misdemeanor proceedings concerning violation of the presumption of innocence and the unauthorized disclosure of information in relation to criminal proceedings. - Number and structure of decisions which finalized misdemeanor proceedings concerning violation of the presumption of innocence and the unauthorized disclosure of information in relation to criminal proceedings. |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.6.1. |  |  | Adoption of Code of conduct for Members of Parliament (MPs) which regulates commenting judicial decisions and procedures. |  |  | -National Assembly | II quarter of 2015 |  | Budget of the Republic of Serbia-17.285 € In 2015 |  |  | Adopted Code of conduct for Members of Parliament (MPs) which regulates commenting judicial decisions and procedures. |  |  |
| 1.1.6.2. |  |  | Adoption of Code of conduct for Members of the Government of the Republic of Serbia, which regulates commenting judicial decisions and procedures. |  |  | -Government of the Republic of Serbia | IV quarter of 2015. |  | Budget of the Republic of Serbia-17.285 € In 2015 |  |  | Adopted Code of conduct for Members of the Government of the Republic of Serbia, which regulates commenting judicial decisions and procedures. |  |  |
| 1.1.6.3. |  |  | Amendments and supplements to the Code of ethics in Police in part which deals with liability of police officers for unauthorized publication to the media of information concerning current or planned criminal investigations (Activity 3.5.2.10.) |  |  | -Government of the Republic of Serbia at the proposal of Ministry of Interior | II quarter of 2015 |  | Budget of the Republic of Serbia Budgeting in Negotiating Chapter 24 (Activity 3.5.2.10.) |  |  | Amended and supplemented Code of ethics in Police in part which deals with liability of police officers for unauthorized publication to the media of information concerning current or planned criminal investigations. |  |  |
| 1.1.6.4. |  |  | Amendments and supplements to Code of Ethics and Rules of disciplinary procedure and disciplinary liability of public prosecutors and deputy public prosecutors in part which deals with liability for unauthorized publication in media of information concerning current or planned criminal investigations. |  |  | -State Prosecutorial Council | During II and III quarters of 2015 |  | Budget of the Republic of Serbia- 8.642 € In 2015 |  |  | Amended and supplemented to Code of Ethics and Rules of disciplinary procedure and disciplinary liability of public prosecutors and deputy public prosecutors, improved in part which deals with liability for unauthorized publication in media of information concerning current or planned criminal investigations. |  |  |
| 1.1.6.5. |  |  | Drawing up electronic brochure on the limits of permissible commenting judicial decisions and procedures for political office holders and its publication on the web pages of the National Assembly and the Government of the Republic of Serbia. |  |  | -Republic Secretariat for Legislature with the support of Ministry of Justice, High Judicial Council and State Prosecutorial Council | IV quarter of 2015 |  | Budget of the Republic of Serbia, 8.642 € In 2015 |  |  | Drawn up electronic brochure on the limits of permissible commenting judicial decisions and procedures for political office holders and publicized on the web pages of the National Assembly and the Government of the Republic of Serbia. |  |  |
| 1.1.6.6. |  |  | Conducting initial anonymous surveys among judges and public prosecutors concerning their perceptions in relation to putting independence at risk through commenting judicial decisions. |  |  | -High Judicial Council -State Prosecutorial Council -Partners | IV quarter of 2015. |  | IPA 2012 judicial efficiency, first component In total 2.500.000 € In 2016-40 % (1.000.000 €) In 2017-40 % (1.000.000 €) In 2018- 20% (500.000 €) |  |  | Surveys conducted among judges and public prosecutors on their perceptions in relation to putting independence at risk through commenting judicial decisions. |  |  |
| 1.1.6.7. |  |  | Organizing seminars, printing and distribution of educational material to judges and public prosecutors in order to adopt European standards concerning respect for judicial decisions and concerning limits of permissible critique of judicial decisions in the context of respect of judiciary’s independence. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Judicial Academy -Partners | During I and II quarters of 2016. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2016 |  |  | Seminars for judges and public prosecutors are organized periodically and educational material is distributed to judges and public prosecutors. |  |  |
| 1.1.6.8. |  |  | Conducting repeated anonymous surveys among judges and public prosecutors on perception of putting independence at risk through commenting judicial decisions. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Partners | IV quarter of 2016. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2016 |  |  | Repeated surveys conducted among judges and public prosecutors on perception of putting independence at risk through commenting judicial decisions. |  |  |
| 1.1.6.9. |  |  | Conducting initial research among journalists on the subject of knowledge of European standards and national regulation in the field of reporting on court proceedings. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Partners | IV quarter of 2015. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2015. |  |  | Initial research conducted among journalists on the subject of knowledge of European standards and national regulation in the field of reporting on court proceedings. |  |  |
| 1.1.6.10. |  |  | Organizing seminars, printing and distribution of educational material to journalists in order to adopt European standards and national regulations concerning respect for judicial decisions and concerning respect of reporting on court proceedings. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Ministry of information, Council for press -Partners | Continuously, commencing from I quarter of 2016. |  | IPA 2012 Budgeted in activity 1.1.6.6. In 2016. |  |  | Organized seminars, printed and distributed educational material to journalists in order to adopt European standards and national regulation concerning respect for judicial decisions and limits of permissible critique of judicial decisions in the context of respecting judiciary’s independence. |  |  |
| 1.1.6.11. |  |  | Conducting repeated research among journalists on the subject of knowledge of European standards and national regulation in the field of reporting on court proceedings. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Ministry of information, Council for press | I quarter of 2017. |  | IPA 2012 Budgeted in activity 1.1.6.6. In 2017. |  |  | Conducted repeated research among journalists on the subject of knowledge of European standards and national regulation in the field of reporting on court proceedings. |  |  |
| 1.1.6.12. |  |  | Conducting initial research on citizens’ perceptions concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Partners | IV quarter of 2015. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2015 |  |  | Initial research conducted on citizens’ perception concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  |
| 1.1.6.13. |  |  | Conducting media campaign to increase awareness of citizens concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Partners | I and II quarter of 2016. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2016 |  |  | Media campaign conducted in order to increase awareness of citizens concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  |
| 1.1.6.14. |  |  | After completion of media campaign, conducting repeated research on awareness of citizens concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  | -High Judicial Council, Public Relations Service -State Prosecutorial Council, Public Relations Service -Partners | I quarter of 2017. |  | IPA 2012- Budgeted in activity 1.1.6.6. In 2017 |  |  | Repeated research conducted on awareness of citizens concerning limits of permissible critique of judicial decisions in the context of respect for judiciary’s independence. |  |  |
| 1.1.6.15. |  |  | Efficient processing of cases of public violations of presumption of innocence and tracking records concerning this type of proceedings. |  |  | -Ministry of Information, Sector for information and media -Public prosecutors’ offices -Misdemeanor courts -Republic Public Prosecutor’s Office -Supreme Court of Cassation | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia-42.550 € In 2015-10.638€ In 2016-10.638€ In 2017-10.638€ In 2018-10.638€ |  |  | Cases of public violations of presumption of innocence efficiently processed at the motion of Ministry of Information whereas Supreme Court of Cassation tracks precise records concerning this type of proceedings. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.7. Ensure the involvement of civil society and professional organizations in defining further steps in the reform process and in monitoring the implementation of the action plans; |  |  |  |  |  |  | Civil society and professional organizations are involved in defining the further steps in the reform process and in monitoring the implementation of action plans. |  |  |  |  | Suggestions and comments of civil society and professional organizations related to defining the further steps in the reform process are regularly discussed at meetings of the bodies for monitoring the implementation of action plans (Strategy Implementation Strategy i.e. Commission for the Implementation of the National Judicial Reform Strategy for the period 2013-2018). |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.7.1. |  |  |  | Quarterly publication of public call to civil society and professional organizations to submit suggestions and comments for defining further steps in the reform process. |  | -The Office for Cooperation with civil society | Quarterly, commencing from IV quarter of 2014. | Budget of the Republic of Serbia-21.275 € In 2015- 4.255 € In 2016- 4.255 € In 2017- 4.255 € In 2018- 4.255 € |  |  |  | The Office for Cooperation with Civil Society quarterly publishes public call to civil society and professional organizations to submit suggestions and comments relating to the defining further steps in the reform process. |  |  |
| 1.1.7.2. |  |  |  | Submitting and consideration of quarter reports on comments and suggestions of civil society organizations referring to defining further steps in reform process. |  | -The Office for Cooperation with Civil Society -Strategy Implementation Commission | Quarterly, commencing from I quarter of 2015. | Budget of the Republic of Serbia-17.020 € In 2015- 4.225 € In 2016- 4.225 € In 2017- 4.225 € In 2018- 4.225 € |  |  |  | The Office for Cooperation with civil society quarterly submits reports whereas body in charge of monitoring of action plans’ implementation (Strategy Implementation Commission) takes into consideration submitted quarterly reports on comments and suggestions of civil society organizations referring to defining further steps in reform process. |  |  |
| 1.1.7.3. |  |  |  | Periodically organizing roundtables which would discuss achieved goals and possibilities of improving cooperation in creating and implementing reform steps. |  | -Office for Cooperation with Civil Society | Continuously, commencing from II quarter of 2015. | Budget of the Republic of Serbia-2.000 € In 2015- 500 € In 2016- 500 € In 2017- 500 € In 2018- 500 € |  |  |  | Office for Cooperation with Civil Society periodically organizing roundtables which would discuss achieved goals and possibilities of improving cooperation in creating and implementing reform steps. |  |  |
| 1.1.7.4. |  |  |  | Improving other types of cooperation with civil society in the process of defining reform steps, in accordance with: a) Guidelines (prepared with the support of experts from TAIEX) for cooperation between institutions (which participate in Chapter 23) and civil society and b) Guidelines for inclusion of civil society in legislative process. |  | -Negotiating Group for Chapter 23 (the Chair) -Ministry of Justice | Continuously, commencing from III quarter of 2014. | In total 15.015 € Budget of the Republic of Serbia- 13.265 € TAIEX- 1750 € In 2014- 2.553€ In 2015- 4.803 € In 2016- 2.553 € In 2017- 2.553 € In 2018- 2.553 € |  |  |  | Improved cooperation with civil society in the process of defining reform steps, in accordance with: a) Guidelines (prepared with the support of experts from TAIEX) for cooperation between institutions (which participate in Chapter 23) and civil society and b) Guidelines for inclusion of civil society in legislative process. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 1.1.8. Ensure the enactment of a special legislation with regards to Serbian judicial institutions with jurisdiction in Kosovo, consistent with Serbian obligations under the First Agreement of 19th April 2013. |  |  |  |  |  |  | Adopted special regulation with regards to judicial institutions in the Republic of Serbia in accordance with obligations of the Republic of Serbia arising from First agreement of April 19th 2013. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  |  | RESULT | IMPLEMENTATION STATUS |  |
| 1.1.8.1. |  |  | Defining the activities necessary for implementation of this recommendation, as well as deadlines for its implementation, will be feasible upon formation of Kosovo’s government and after continuation of negotiations between Belgrade and Priština. |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | Deadline will be defined during negotiations between Belgrade and Priština | Budget of the Republic of Serbia-unknown at this moment |  |  |  |  |  |  |
| - IMPARTIALITY AND ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.2.1. Clarify and implement the rules for random allocation of cases, including through finding technical solutions to avoid circumventing the system. Ensure that the system is not open to manipulation and make it subject to regular inspection by the inspectorate; |  |  |  |  |  |  | Rules for random allocation of cases are clarified and are implemented consistently, regular inspection on their implementation is carried out by Inspectorate of High Judicial Council and State Prosecutorial Council |  |  |  | - All cases are randomly allocated in courts and prosecution offices. - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases, from report of supervisory body in High Judicial Council. - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases, from report of supervisory body in State Prosecutorial Council. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.2.1.1. |  |  |  | Conduct analysis of current Information and Communication Technology systems in terms of hardware, software and human resources in courts, public prosecutors offices and prisons, with focus on urgent changes, with recommendations for their improvement. (the same activity 1.3.6.6. and 1..3.8.2.) |  | -Ministry of justice -Expert team USAID -Expert team MDTF/WB | II quarter of 2015. |  | In total 178.342€ Budget of the Republic of Serbia- 8.642 €, MDTF/WB-32.700€, USAID -137.000€ In 2015 |  | Conducted analysis of current Information and Communication Technology systems, in terms of hardware, software and human resources in courts, public prosecutors offices and prisons, with focus on urgent changes, with recommendations for their improvements. |  |  |  |
| 1.2.1.2. |  |  |  | Drawing up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources (the same activity 1.3.6.7 and 1.3.8.3.). Guidelines will be based on the results of Functional analysis of judiciary and Analysis of current state of play (activity 1.2.1.1, 1.3.6.6. and 1.3.8.2.). |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | During I and II quarter of 2016. |  | In total 19.035 € Budget of the Republic of Serbia- 17.285 €, TAIEX- 1.750 € IPA 2012- Budgeted in activity 1.1.6.6. In 2016 |  | Drawn up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources. Guidelines are based on the results of Functional analysis of judiciary and Analysis of current state of play (activity 1.2.1.1, 1.3.6.6. and 1.3.8.2.). |  |  |  |
| 1.2.1.3. |  |  |  | Conduct Feasibility study for the interoperability of current Information and Communication Technology systems within the court system, as well as with the Information and Communication Technology system of the Republic Public Prosecutor's Office and with the Administration for the Enforcement of Penal Sanctions as well as with the information systems of bailiff/enforcement officers, public notaries, etc. (the same activity 1.3.6.8. and 1.3.8.4.) |  | -Ministry of Justice -Expert team | II quarter of 2016. |  | In total 2.517.285 € Budget of the republic of Serbia- 17.285 €, IPA 2012- judicial efficiency, third component In total 2.500.000€ In 2016.-1.017.285€ In 2017.-1.000.000€ In 2018.- 500.000€ |  | Prepared Feasibility study for the interoperability of current Information and Communication Technology systems within the court system, as well as with the Information and Communication Technology system of the Republic Public Prosecutor's Office and with the Administration for the Enforcement of Penal Sanctions, as well as with the information systems of bailiff/enforcement officers, public notaries, etc. |  |  |  |
| 1.2.1.4. |  |  |  | On the basis of the Feasibility Study (Activity 1.2.1.3.) prepare technical specifications for: a) development of web services for exchanging data between information systems in judiciary, and b) improvement of software for automatic management of cases in courts of general jurisdiction, commercial courts, Republic Public Prosecutor's Office and in the Administration for the Enforcement of Criminal Sanctions. (the same activity 1.3.6.9. and 1.3.8.5.) |  | -Ministry of Justice -Expert team | III quarter of 2016. |  | IPA 2012 Budgeted in activity 1.2.1.3. |  | On the basis of the Feasibility Study (Activity 1.2.1.3.) prepared technical specifications for: a) development of web services for exchanging data between information systems in judiciary, and b) improvement of software for automatic management of cases in courts of general jurisdiction, commercial courts, Republic Public Prosecutor's Office and in the Administration for the Enforcement of Criminal Sanctions. |  |  |  |
| 1.2.1.5. |  |  |  | Institutionalization of coordination and management of ICT system through public-private or public-public partnership. (the same activity 1.3.6.0. and 1.3.8.6.) |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | Continuously, Commencing from II quarter of 2015. |  | IPA 2012- Budgeted in activity 1.2.1.3. USAID-unknown at this moment, USAID will notify after drawing up the guidelines |  | Coordination and management of ICT system institutionalized through public-private and public-public partnership. |  |  |  |
| 1.2.1.6. |  |  |  | Drawing up protocol on input and exchange of data in ICT system with the purpose of unification of conduct in entire judicial system. (the same activity 1.3.6.11 and 1.3.8.7.) |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | II quarter of 2016 |  | Budget of Republic of Serbia-17.285 € In 2016, IPA 2012 Budgeted in activity 1.1.6.6. |  | Drafted protocol on input and exchange of data in ICT system with the aim of unification of conduct in entire judicial system. |  |  |  |
| 1.2.1.7. |  |  |  | Conducting trainings and commencement of implementation of Protocol on input and exchange of data in ICT system. (the same activity 1.3.6.12. and 1.3.8.8.) |  | -Judicial Academy, Ministry of Justice, High Judicial Council, State Prosecutorial Council, all courts and public prosecutors offices | Commencing from IV quarter of 2016 and I quarter of 2017. |  | USAID- Unknown at this moment, USAID will notify after drawing up the guidelines IPA 2012- Budgeted in activity 1.1.6.6. In 2016 |  | After conducted trainings, input and exchange of data in ICT system is carried out in accordance to Protocol. |  |  |  |
| 1.2.1.8. |  |  |  | Preparing and adoption of the Program for weighing of cases, as a prerequisite for introducing the complexity of the case as one of the criteria for its allocation. |  | -Working group, established by Minister of Justice, which encompass representatives of all instances of courts and public prosecutors’ offices and Ministry of Justice | During I and II quarter of 2016. |  | Budget of Republic of Serbia-30.878 €, IPA 2012 Budgeted in activity 1.1.6.6. In 2016 |  | Prepared and adopted the Program for weighing of cases, which introduced the complexity of the case as one of the criteria for its allocation. |  |  |  |
| 1.2.1.9. |  |  |  | Amendments to the Law on judges in part which deals with allocation of cases by chance, aiming at implementation of Program for weighing of cases. |  | -Ministry of Justice -Government of the republic of Serbia -National Assembly | III quarter of 2016. |  | Budget of the Republic of Serbia- 55.697 € In 2016 |  | Amended Law on judges in part which deals with allocation of cases by chance, aiming at implementation of Program for weighing of cases. |  |  |  |
| 1.2.1.10. |  |  |  | Adoption of amendments to the Law on Public Prosecutor’s Office in order to ensure transfer of competencies for adoption of Rules on administration in the public prosecution and transfer of supervision over its implementation from Ministry of Justice to State Prosecutorial Council. |  | -Ministry of Justice -Government of the Republic of Serbia -National assembly | III quarter of 2015. |  | Budget of the Republic of Serbia-55.697 € In 2015 |  | Adopted amendments to the Law on Public Prosecutor’s Office which ensured transfer of competencies for adoption of Rules on administration in the public prosecution and transfer of supervision over its implementation from Ministry of Justice to State Prosecutorial Council. |  |  |  |
| 1.2.1.11. |  |  |  | Adopt amendments to the Court Rules of Procedure in order to clarify rules concerning random allocation of cases (by chance), which will take into account complexity of cases as one of criteria for case allocation. |  | -High Judicial Council | During IV quarter of 2016 and I quarter of 2017. |  | Budget of the Republic of Serbia-30.878 €, In 2016 IPA 2012 Budgeted in activity 1.1.6.6. |  | Rules concerning random allocation of cases (allocation of cases by chance) have been clarified upon adoption of amendments to the Court Rules of Procedure. |  |  |  |
| 1.2.1.12. |  |  |  | Adopt amendments to the Rules on administration in public prosecutors offices in order to clarify rules of random allocation of cases (by chance), which will take into account complexity of cases as one of criteria for case assignment. |  | -State Prosecutorial Council | During IV quarter of 2016 and I quarter of 2017. |  | Budget of the Republic of Serbia-30.878 €, In 2016 IPA 2012 Budgeted in activity 1.1.6.6. |  | Rules concerning random allocation of cases (allocation of cases by chance) have been clarified upon adoption of amendments to the Rules on administration in public prosecution. |  |  |  |
| 1.2.1.13. |  |  |  | Establishing preparatory departments in courts, which are in charge of, inter alia, weighing of cases. |  | -High Judicial Council | During IV quarter of 2016 and I quarter of 2017. |  | IPA 2012- Budgeted in activity 1.1.6.6. |  | Preparatory departments in courts have been established. |  |  |  |
| 1.2.1.14. |  |  |  | Establishing preparatory departments in public prosecutors’ offices, which are in charge of, inter alia, weighing of cases. |  | -State Prosecutorial Council | During IV quarter of 2016 and I quarter of 2017. |  | IPA 2012- Budgeted in activity 1.1.6.6. |  | Preparatory departments in public prosecutors’ offices have been established. |  |  |  |
| 1.2.1.15. |  |  |  | Preparing of program of training for work in preparatory departments for weighing of cases and carrying out training of judicial associates and prosecutorial assistants for work in preparatory departments for weighing of cases. |  | -Judicial Academy -High Judicial Council -State Prosecutorial Council | During IV quarter of 2016 and I quarter of 2017. |  | Budget of the Republic of Serbia-17.285 €, In 2016 IPA 2012- Budgeted in activity 1.1.6.6. |  | Conducted training of judicial associates and prosecutorial assistants for work in preparatory departments of courts and public prosecutors’ offices. |  |  |  |
| 1.2.1.16. |  |  |  | Commencement of the implementation of provisions of Law on organization of the courts that regulates jurisdiction for the conducting of duties of judiciary administration in order to transfer jurisdiction of Ministry of justice in the field of following duties: supervision over the work of courts, supervision over the results of the work of courts, collecting of statistical data and analysis of statistical data from Ministry of Justice to High Judicial Council. |  | -Ministry of Justice -High Judicial Council | Commencing from II quarter of 2016. |  | Budget of Republic of Serbia- 30.878 € IPA 2012- Budgeted in activity 1.1.6.6 In 2016 |  | Commenced implementation of provisions of Law on organization of the courts that regulates jurisdiction for the conducting of duties of judiciary administration in order to transfer jurisdiction of Ministry of justice in the field of following duties: supervision over the work of courts, supervision over the results of the work of courts, collecting of statistical data and analysis of statistical data from Ministry of Justice to High Judicial Council. |  |  |  |
| 1.2.1.17. |  |  |  | Coherent implementation of amended rules on random allocation of cases in courts with regular supervision of their implementation. |  | -Supreme Court of Cassation -High Judicial Council | Continuously, commencing from II quarter of 2017. |  | Budget of the Republic of Serbia Part of regular activities, without special costs (ICT system) |  | Rules on random allocation of cases in courts are coherently implemented and regular supervision of their implementation is carried out. |  |  |  |
| 1.2.1.18. |  |  |  | Coherent implementation of amended rules on random allocation of cases in public prosecutors’ offices with regular supervision of their implementation |  | -Republic Public Prosecutor’s Office -State Prosecutorial Council | Continuously, commencing from II quarter of 2017. |  | Budget of the Republic of Serbia Part of regular activities, without special costs (ICT system) |  | Rules on random allocation of cases in public prosecutors offices are consistently implemented and regular supervision of their implementation is carried out |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.2.2. Strengthen the accountability of judges and prosecutors through a strict application of all legal and disciplinary means, including through : - Ensuring the effective implementation of "conflict of interest" rules and amending them if need be; - Ensuring the effective verification of asset declarations and cross-checking with other relevant information; - Effective monitoring of compliance with the code of ethics and carrying out further evaluation activities and training of judges and prosecutors in ethical behavior; - Review where necessary and effectively implement rules on disciplinary and dismissal procedures; - Re-assessing the system of functional immunity ensuring full accountability of judges and prosecutors under criminal law. |  |  |  |  |  |  | The accountability of judges and public prosecutors strengthened through a strict application of all legal and disciplinary means, including through the effective implementation of "conflict of interest" rules; effective verification and cross-checking of asset declarations; effective monitoring of compliance with the code of ethics and carrying out trainings for judges and public prosecutors in the field of ethics; effective implementation of rules on disciplinary accountability, functional immunity, dismissal procedures and accountability of judges and public prosecutors. The respective Councils have both an inspection capacity based on clear rules and bestowed with powers allowing them to act ex officio or on signals from citizens, state bodies or other legal entities related to inter alia questions of integrity or professional failure |  |  |  | - Positive evaluation by European Commission concerning the system of accountability of judges and public prosecutors stated in the Annual Progress Report on Serbia; - Number of asset declarations of judges and public prosecutors which were subject to effective verification and cross-checking in the course of one year; - Increased number of judges and public prosecutors included in ethics training; - Results of the evaluation of judges and public prosecutors included in ethics training; - Positive evaluation on the degree of compliance with the code of ethics from the reports of ethics committees of the High Judicial Council and State Prosecutorial Council; - Data on the number of disciplinary charges and disciplinary proceedings against judges and public prosecutors from the reports of the disciplinary bodies of the High Judicial Council and State Prosecutorial Council; - Data on criminal charges and criminal proceedings against judges and public prosecutors; |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.2.2.1. |  |  | Amending the Law on the Anti-Corruption Agency in order to strengthen competencies, entrusted to Agency, in relation to monitoring of implementation of the provisions concerning: conflicts of interests, verification and cross-checking of information from assets declaration which have been delivered by the judicial office holders. (Connected activity 2.2.1.1.) |  |  | -Ministry of Justice -Anti-Corruption Agency -Government of the Republic of Serbia -National Assembly | I quarter of 2015. |  | In total 72.886 € Budget of the republic of Serbia- 71.136 €, ТАIEX- 1.750 € In 2015 |  | Amendments to the Law on the Anti-Corruption Agency adopted which have strengthened the control mechanism of the Agency in the implementation of the provisions on conflicts of interests, as well as verification and cross-checking information from assets declaration of the judicial office holders. |  |  |  |
| 1.2.2.2. |  |  | Regular notification by institutions to the Anti-Corruption Agency concerning taking the judicial office and concerning termination of the judicial offices in order to, in more efficient manner, check the existence of conflict of interests. |  |  | -Presidents of the courts and public prosecutors -Anti-Corruption Agency | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Court presidents and public prosecutors regularly submit notifications concerning taking the judicial offices and their termination. |  |  |  |
| 1.2.2.3. |  |  | Regular notifying of High Judicial Council on submitted notifications to Anti-Corruption Agency concerning taking the judicial offices and their termination. |  |  | -Presidents of the courts -High Judicial Council | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Presidents of the courts regularly notify High Judicial Council on submitted notifications to the Anti-Corruption Agency concerning taking the judicial office and their termination. |  |  |  |
| 1.2.2.4. |  |  | Regular notifying of State Prosecutorial Council on submitted notifications to the Anti-Corruption Agency concerning taking the prosecutorial office and its termination. |  |  | -Public Prosecutors -State Prosecutorial Council | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Public prosecutors regularly notify State Prosecutorial Council on submitted notifications to the Anti-Corruption Agency concerning taking the prosecutorial office and its termination. |  |  |  |
| 1.2.2.5. |  |  | Improvement of cooperation between High Judicial Council and State Prosecutorial Council on the one side and Anti-Corruption Agency on the other side in order to coherently implement duties of submitting reports on assets and incomes (assets declaration) of judicial office holders. |  |  | -Judicial office holders | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Judicial office holders regularly submit assets declaration to the Anti-Corruption Agency. Improved cooperation between High Judicial Council and State Prosecutorial Council on the one side and Anti-Corruption Agency on the other side. |  |  |  |
| 1.2.2.6. |  |  | Strengthening administrative capacities of Anti-Corruption Agency in accordance with the previously conducted analysis of existing capacities in particularly: -organization structure -number of employees -level of competence In line with the new systematization prepared in accordance with amendments and supplements to Law on Anti corruption Agency (Connected activity 2.2.1.4.) |  |  | -Anti-Corruption Agency | For analysis: II quarter of 2016. For acting according to analysis: IV quarter of 2017. . |  | Budget of the Republic of Serbia, IPA 2013 Budgeting in activity 2.2.1.4. |  | Strengthened Agency’s capacities in accordance to the new systematization which is drawn up according to amendments and supplements to the Law on Anti-Corruption Agency. |  |  |  |
| 1.2.2.7. |  |  | Analysis and amending normative framework which regulates: -requirements for dismissal of judges with the aim of précising the requirements; -jurisdiction for conducting disciplinary procedure and decision making, with the aim of examination of double jurisdiction of disciplinary commission; -statute of limitations for disciplinary misdemeanor |  |  | -Working group established by Minister of Justice -Ministry of Justice -Government of the Republic of Serbia -National Assembly | During II and III quarter of 2015. |  | In total 32.628 € Budget of the Republic of Serbia- 30.878 € , ТАIEX- 1.750 € In 2015 |  | Requirements for dismissal of judges are précised; provisions that regulate jurisdiction of Disciplinary commission and statute of limitations for disciplinary misdemeanor are précised and redefined. |  |  |  |
| 1.2.2.8. |  |  | Analysis and amending normative framework which regulates: -requirements for dismissal of public prosecutor’s office holders with the aim of précising the requirements; -jurisdiction for conducting disciplinary procedure and decision making, with the aim of examination of double jurisdiction of disciplinary commission; -statute of limitations for disciplinary misdemeanor |  |  | -Working group established by Minister of Justice -Ministry of Justice -Government of the Republic of Serbia -National Assembly | During II and III quarter of 2015. |  | Budget of the Republic of Serbia, Budgeted in activity 1.2.2.7. |  | Requirements for dismissal of public prosecutors are précised; provisions that regulate jurisdiction of Disciplinary commission and statute of limitations for disciplinary misdemeanor are précised and redefined. |  |  |  |
| 1.2.2.9. |  |  | Amending Rules of Procedure of High Judicial Council which envisages establishment of Board of Ethics of High Judicial Council as a permanent working body. |  |  | -High Judicial Council | I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.4.2. |  | Adopted amended Rules of Procedure of High Judicial Council which provides establishment of Board of Ethics of High Judicial Council. |  |  |  |
| 1.2.2.10. |  |  | Amending Code of Ethics for Judges in order to clarify provisions which define disciplinary liability of judges for non-compliance with Code of Ethics for Judges. |  |  | -High Judicial Council | During II and III quarter of 2015. |  | Budget of the Republic of Serbia-8.642 € In 2015 |  | Adopted amended Code of Ethics for Judges with clarified provisions which stipulate disciplinary liability of judges for non-compliance with Code of Ethics for Judges. |  |  |  |
| 1.2.2.11. |  |  | Amending Code of Ethics for public prosecutors and deputy public prosecutors in order to clarify provisions which stipulate disciplinary liability of public prosecutors’ office holders for non-compliance with Code of Ethics. |  |  | -State Prosecutorial Council | During II and III quarters of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.6.4. |  | Adopted amended Code of Ethics for public prosecutors and deputy public prosecutors with clarified provisions which stipulate disciplinary liability of public prosecutors’ office holders for non-compliance with Code of Ethics for public prosecutors and deputy public prosecutors. |  |  |  |
| 1.2.2.12. |  |  | Adoption of Rules of Procedure of Board of Ethics of High Judicial Council which will regulate monitoring of compliance with Code of Ethics for Judges and conducting activities of evaluation and training of judges on ethics. |  |  | -High Judicial Council | II quarter of 2015. |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Rules of Procedure of Board of Ethics of High Judicial Council adopted which regulates monitoring of compliance with Code of Ethics for Judges and conducting activities of evaluation and training of judges on ethics. |  |  |  |
| 1.2.2.13. |  |  | Adoption of Rules of Procedure of Board of Ethics of State Prosecutorial Council which will envisage monitoring of compliance with Code of Ethics for public prosecutor’s office holders and conducting activities of evaluation and training of public prosecutor’s office holders on ethics. |  |  | -State Prosecutorial Council | IV quarter of 2014. |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Rules of Procedure of Board of Ethics of State Prosecutorial Council adopted which envisages monitoring of compliance with Code of Ethics for public prosecutors and deputy public prosecutors and conducting activities of evaluation and training of public prosecutors’ office holders on ethics |  |  |  |
| 1.2.2.14. |  |  | Organizing seminars for judicial office holders on integrity rules and ethics. |  |  | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from III quarter of 2015. |  | IPA 2013 (Strengthening of consistent legal system of the Republic of Serbia through improvement of uniform implementation of laws and improvement of educational activities of Judicial Academy) In total 2.100.000€ In 2015- 840.000€ In 2016- 840.000€ In 2017- 420.000€ |  | Seminars for judicial office holders on integrity rules and ethics are regularly organized. |  |  |  |
| 1.2.2.15. |  |  | Drawing up brochure for judges for increasing awareness on ethics’ rules. Publishing brochure on the web page of High Judicial Council. |  |  | -High Judicial Council | IV quarter of 2015. |  | Budget of the Republic of Serbia-8.642 € In 2015 |  | Brochure encompassing ethics’ rules is drawn up and available on the web page of High Judicial Council. |  |  |  |
| 1.2.2.16. |  |  | Drawing up brochure for public prosecutors for increasing awareness on rules of ethics. Publishing brochure on the web page of State Prosecutorial Council. |  |  | -State Prosecutorial Council | IV quarter of 2015. |  | Budget of the Republic of Serbia-8.642 € In 2015 |  | Brochure encompassing ethics’ rules is drawn up and available on the web page of State Prosecutorial Council. |  |  |  |
| 1.2.2.17. |  |  | Amending Rules of Procedure on disciplinary proceedings and disciplinary liability of judges with the purpose of introducing proactive approach of disciplinary bodies in monitoring of compliance with Code of Ethics for Judges. |  |  | -High Judicial Council | III quarter of 2015. |  | Budget of the Republic of Serbia-8.642 € In 2015 |  | Adopted amended Rules of Procedure on disciplinary proceedings and disciplinary liability of judges which stipulates proactive approach of disciplinary bodies in monitoring of compliance with Code of Ethics for Judges adopted. |  |  |  |
| 1.2.2.18. |  |  | Amending Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors with the purpose of introducing proactive approach of disciplinary bodies in monitoring of compliance with Code of Ethics for public prosecutors and deputy public prosecutors. |  |  | -State Prosecutorial Council | III quarter of 2015. |  | Budget of the Republic of Serbia-8.642 € In 2015 |  | Adopted amended Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors which stipulates proactive approach of disciplinary bodies in monitoring of compliance with Code of Ethics for public prosecutors and deputy public prosecutors adopted. |  |  |  |
| 1.2.2.19. |  |  | Effective implementation of Rules of Procedure on disciplinary proceedings and disciplinary liability of judges. |  |  | -High Judicial Council, disciplinary bodies | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Disciplinary bodies of High Judicial Council effectively implement Rules of Procedure on disciplinary proceedings and disciplinary liability of judges. |  |  |  |
| 1.2.2.20. |  |  | Effective implementation of Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors. |  |  | -State Prosecutorial Council, disciplinary bodies | Continuously |  | Budget of the Republic of Serbia Part of regular activities, without special costs |  | Disciplinary bodies of State Prosecutorial Council effectively implement Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors. |  |  |  |
| 1.2.2.21. |  |  | Conduct analysis of provisions that regulate functional immunity of judicial office holders. |  |  | -Working group, established by Minister of Justice, whose members are representatives of Ministry of Justice, High Judicial Council and State Prosecutorial Council | IV quarter of 2015. |  | In total-17.189€ Budget of the Republic of Serbia-15.439 €, TAIEX- 1.750 €, |  | Conducted analysis of provisions that regulate functional immunity of judicial office holders. |  |  |  |
| 1.2.2.22. |  |  | Implementation of measures in accordance with conducted analysis. |  |  | -Ministry of Justice -High Judicial Council -State Prosecutorial Council | I quarter of 2016. |  | Budget of the Republic of Serbia Unknown at this moment |  | Implemented measures in accordance with conducted analysis. |  |  |  |
| - PROFESSIONALISM/COMPETENCE/EFFICIENCY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.1. Develop the Judicial Academy as a center for continuously and initial training of judges and prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the public prosecution and the Judicial Academy, including through: - introducing a yearly curriculum covering all areas of law, including EU law; - allocating sufficient resources and introduce a quality control system for initial and specialized training; |  |  |  |  |  |  | The Judicial Academy has been improved as a center for continuous and initial training of judges and public prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the Public prosecutor’s Office and the Judicial Academy. Trainings are held according to annual curriculum covering all areas of law, including EU law and are subject to regular control. |  |  |  | - Continuous and initial trainings are held according to annual curriculum; - Infrastructure and staff capacities of Judicial Academy have been strengthened; - Programs of continuous, specialized and initial trainings are subject to regular control of quality and are improved according to the results of control; - Needs for training and education for judicial office holders are determined as part of their annual evaluation, and in accordance with the real needs of the system. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.1.1. |  |  | Conducting Functional analysis of Judicial Academy’s needs which encompasses data on program duties, organizational, financial and spacious needs and determining funds in accordance with the results of the analysis. |  |  | -Judicial Academy -Ministry of Justice -High Judicial Council -State Prosecutorial Council | IV quarter of 2014. |  | Total - 64.358 € Budget of the Republic of Serbia-30.878 €, SIDA(PROFID FOND)- 33.480 € In 2014 |  | Conducted Functional analysis of Judicial Academy’s needs and determined funds in accordance with the results of the analysis. |  |  |  |
| 1.3.1.2. |  |  | Implementation of measures for improvement of program, organization of work, financial and spacious needs of Judicial Academy in accordance with the results of functional analysis (activity 1.3.1.1.), with the focus on transition from donor/project financing (which dominates in the period of capacity building of Judicial Academy) to budget financing after Judicial Academy starts working in full capacities. |  |  | -Judicial Academy -Ministry of Justice -High Judicial Council -State Prosecutorial Council | Continuously, commencing from I of 2015. |  | Budget of the Republic of Serbia, donations Budgeted in activity 1.3.1.7. |  | Coherent implementation of measures for improvement of program, organization of work, financial and spacious needs of Judicial Academy in line with the results of functional analysis (activity 1.3.1.1.). Since capacities of the Judicial Academy have been built with the significant assistance of donor/project funds, budget of the Republic of Serbia becomes dominant source of financing. |  |  |  |
| 1.3.1.3. |  |  | Adoption of Rules on the Criteria and Standards for the Evaluation of the Qualification, Competence and Worthiness of Candidates for election of judges and presidents of courts, which envisages initial training completed at Judicial Academy as significant advantage during evaluation of qualifications and competences for election to judicial office. (connected activity 1.1.3.1.) |  |  | -High Judicial Council | I quarter of 2015. |  | Budget of Republic of Serbia, Budgeted in activity 1.1.3.1. |  | Adopted Rules on the Criteria and Standards for the Evaluation of the Qualification, Competence and Worthiness of Candidates for election of judges and presidents of courts, which envisages initial training completed at Judicial Academy as significant advantage during evaluation of qualifications and competences for election to judicial office. |  |  |  |
| 1.3.1.4. |  |  | Adoption of Rules on the Criteria and Standards for the Evaluation of the Qualification, Competence and Worthiness of Candidates for the process of nominating and selection to Prosecutorial Office, which envisages initial training completed at Judicial Academy as significant advantage during evaluation of qualifications and competence for selection to public prosecutorial office. (connected activity 1.1.3.5.) |  |  | -State Prosecutorial Council | I quarter of 2015. |  | Budget of Republic of Serbia, Budgeted in activity 1.1.3.5. |  | Adopted Rules on the Criteria and Standards for the Evaluation of the Qualification, Competence and Worthiness of Candidate for the process of nominating and selection to Prosecutorial Office Holders, which envisages initial training completed at Judicial Academy as significant advantage during evaluation of qualifications and competence for selection to public prosecutorial office. |  |  |  |
| 1.3.1.5. |  |  | Number of attendees of initial training is determined taking into account conclusions and recommendations from Strategy of Human Resources for Judiciary (activity 1.3.4.2.) |  |  | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from IV quarter of 2016. |  | Budget of Republic of Serbia Budgeted in activity 1.3.1.7. |  | Number of attendees of initial training reflects real necessities of judicial network and is in accordance with conclusions and recommendations from Strategy of Human Resources for Judiciary. |  |  |  |
| 1.3.1.6. |  |  | Drawing up and adoption of annual curriculum of training that covers all areas of law (including EU law and human rights) and skills necessary for work in judiciary, and in particular usage of ICT system, legal analysis, methodology and method of decision drafting. Annual training curriculum has to encompass education in the field of management intended for court managers, court presidents and public prosecutors. |  |  | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from IV quarter of 2016 |  | Budget of Republic of Serbia, IPA 2013, TAIEX Budgeted in activity 1.3.1.7. |  | Judicial Academy regularly proposes whereas High Judicial Council and State Prosecutorial Council adopt annual curriculum of trainings. |  |  |  |
| 1.3.1.7. |  |  | Preparing assessment of budgetary load which includes several years transition plan, due to complete transfer of Judicial Academy to financing at the expense of the budget of the Republic of Serbia. |  |  | -Judicial Academy in cooperation with Ministry of Finance, Ministry of justice, High judicial Council and State Prosecutorial Council | IV quarter of 2015 |  | Budget of Republic of Serbia-4.076.500€ In 2015.-1.019.125€ In 2016.-1.019.125€ In 2017.-1.019.125€ |  | Assessed future budgetary load due to complete transfer of Judicial Academy to financing at the expense of the budget, in accordance with several years transition plan. |  |  |  |
| 1.3.1.8. |  |  | Development of monitoring system concerning quality of initial, continuous and specialized training. |  |  | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia, Budgeted in activity 1.3.1.7. |  | Developed system concerning monitoring of quality of initial, continuous and specialized training. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.2. Develop a system that allows assessing training needs as part of the overall evaluation of performance of judges and prosecutors; |  |  |  |  |  |  | The assessment of training needs is part of the performance appraisal of judges and public prosecutors. |  |  |  | - Developed system of evaluation and of appraisal of training attendance; - High Judicial Council and State Prosecutorial Council send judges and public prosecutors to continuous training based on the results of their performance appraisal, and based on the results of the evaluations from previous trainings; - Annual curriculums of trainings for judges and public prosecutors are proposed and adopted taking also into account performance appraisal results of judges and public prosecutors. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.2.1. |  |  | Defining criteria for sending judges to additional training based on the performance appraisal results, and based on the results of the evaluations from previous trainings; sending judges to additional training according to the results of performance appraisal; implementation of training. |  |  | -High Judicial Council -Judicial Academy | Continuously, commencing from III and IV quarter of 2015. |  | Budget of the Republic of Serbia, Budgeted in activity 1.3.1.7. |  | High Judicial Council sends judges to additional trainings (which are implemented by Judicial Academy), according to criteria set in advance in accordance to the performance appraisal results and in accordance to the results from the evaluations from previous trainings. |  |  |  |
| 1.3.2.2. |  |  | Defining criteria for sending public prosecutor’s office holders to additional trainings based on performance appraisal results, and based on the results of evaluations from previous trainings. Sending public prosecutor’s office holders to additional trainings. |  |  | -State Prosecutorial Council -Judicial Academy | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia, Budgeted in activity 1.3.1.7. |  | State Prosecutorial Council sends public prosecutor’s office holders to additional trainings which are implemented by Judicial Academy based on the criteria for sending public prosecutor’s office holders to additional training based on performance appraisal results, and based on the results of evaluations from previous trainings defined. |  |  |  |
| 1.3.2.3. |  |  | Annual curriculums for training for judges are proposed and adopted taking also into account performance appraisal results of judges. |  |  | -High Judicial Council -Judicial Academy | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. |  | Annual curriculums for training for judges are proposed and adopted taking into account also performance appraisal results of judges. |  |  |  |
| 1.3.2.4. |  |  | Annual curriculums for trainings for public prosecutor’s office holders are proposed and adopted taking also into account performance appraisal results of public prosecutors or deputy public prosecutors. |  |  | -State Prosecutorial Council -Judicial Academy | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. |  | Annual curriculums for trainings for public prosecutor’s office holders are proposed and adopted taking also into account performance appraisal results of public prosecutor’s office holders. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.3. Conduct a comprehensive analysis prior to taking further steps in the reform of the court network, including in terms of cost, efficiency and access to justice; |  |  |  |  |  |  | Conducted comprehensive analysis of the costs, efficiency and access to justice as the foundation for taking further steps in the reform of the court network. |  |  |  | - Using clear, in advance defined, methodology following data are regularly monitored: - number of courts and public prosecutors offices per 100 000 inhabitants; - number of judges and public prosecutors per 100 000 inhabitants; - average and maximum distances of courts and public prosecutors offices from settlements on the territory of that court or public prosecutor’s office; - the terms and scope of the exercise the right to free legal aid; - the terms and scope of the exercise of the right to a legal remedy; -the amount of court fees; - the number of cases per court and public prosecutor’s office; - the number of cases per judge and per public prosecutor; - the costs of operation of the judicial network; - duration of court proceedings (according to the matter) on average; - number of backlogged cases; - number of old cases; - number of admitted applications before the European Court of Human Rights relating to the violation of the right to trial within a reasonable time; |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.3.1. |  |  | Taking into account conclusions and recommendations from Functional analysis, conducting comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, recruitment and education of staff. (the same activity 1.3.4.1. and 1.3.5.1.) |  |  | Working group formed by Strategy Implementation Commission | During IV quarter of 2015 and I quarter of 2016. |  | Budget of the Republic of Serbia, 61.755. € In 2015 30.878 € In 2016 30.878€ IPA 2012 Budgeted in activity 1.1.6.6. |  | Taking into account conclusions and recommendations from Functional analysis, conducting comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. |  |  |  |
| 1.3.3.2. |  |  | Undertaking further reform steps on correction of infrastructure judicial network, improvement of infrastructure and internal procedures, according to results of comprehensive analysis from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1. |  |  | -Ministry of Justice -High Judicial Council -State Prosecutorial Council -Supreme Court of Cassation -Republic Public Prosecutor’s Office | Continuously, commencing from II quarter of 2016. |  | Budget of the Republic of Serbia, Donations Costs currently unknown |  | Underwent reform steps on correction of infrastructure judicial network, improvement of infrastructure and internal procedures, according to results of comprehensive analysis of judicial network. |  |  |  |
| 1.3.3.3. |  |  | Conducting comprehensive functional analysis of judiciary. |  |  | -Expert team with the participation and support of representatives from following institutions: High Judicial Council, State Prosecutorial Council, Ministry of Justice, Judicial Academy, Supreme Court of Cassation and Republic Public Prosecutor’s Office. | During IV quarter 2017 and I quarter of 2018 |  | Budget of the Republic of Serbia, IPA 2015 Total 565.000€ In 2017 282.500€ In 2018 282.500€ |  | Conducted comprehensive functional analysis of judiciary. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.4. Establish and implement a medium-term human resource strategy for the judiciary, based on an analysis of needs and workload, and bearing in mind possible further changes in the structure of courts, recruitment and training; |  |  |  |  |  |  | A mid-term human resource strategy for the judiciary, based on an analysis of needs and workload, and bearing in mind possible further changes in the structure of courts, recruitment and training adopted and implemented. |  |  |  | - Positive evaluation from European Commission, stated in Annual progress report on Serbia, on the existence of a strategic approach to human resources in judiciary; |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.4.1. |  |  | Taking into account conclusions and recommendations from Functional analysis, conducting comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. (the same activity 1.3.3.1. and 1.3.5.1.) |  |  | -Working group formed by Strategy Implementation Commission | During IV quarter of 2015. and I quarter of 2016 | Budget of the Republic of Serbia, IPA 2012 Budgeted in activity 1.3.3.1. |  |  | Taking into account conclusions and recommendations from Functional analysis, conducted comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. |  |  |  |
| 1.3.4.2. |  |  | In accordance with the results of the analysis from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1., draw up and adopt midterm Strategy on human resources in judiciary. |  |  | -Working group formed by Strategy Implementation Commission | During II and III quarters of 2016. | Budget of the Republic of Serbia, 30.878€ IPA 2012 Budgeted in activity 1.1.6.6. In 2016. |  |  | Midterm Strategy on human resources in judiciary prepared and adopted. |  |  |  |
| 1.3.4.3. |  |  | Implementation of midterm Strategy on human resources in judiciary. |  |  | -High Judicial Council -State Prosecutorial Council -Ministry of Justice | Continuously, commencing from IV quarter of 2016- II quarter of 2019. | Budget of the Republic of Serbia, Costs currently unknown. |  |  | Efficient implementation of midterm Strategy on human resources in judiciary. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.5. Ensure herewith a sustainable solution for workload imbalances; |  |  |  |  |  |  | Established efficient system for balancing the workload for judges and public prosecutors. |  |  |  | - Number of cases per court; - Number of cases per public prosecutor’s office; - Number of cases per judge; - Number of cases per public prosecutor or deputy public prosecutor. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.5.1. | Taking into account conclusions and recommendations from Functional analysis, conducting comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, selection and education of staff. (the same activity 1.3.3.1. and 1.3.4.1.) |  |  |  |  | -Working group formed by Strategy Implementation Commission | During IV quarter of 2015 and I quarter of 2016. |  | Budget of the Republic of Serbia, IPA 2012 Budgeted in activity 1.3.3.1. |  | Taking into account conclusions and recommendations from Functional analysis, conducting comprehensive analysis of following: -judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; -needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. |  |  |  |
| 1.3.5.2. | Implementation of measures for balancing the number of cases per judge and public prosecutor/deputy public prosecutor according to the results of the analysis e.g. encouraging voluntary mobility of judicial office holders with adequate compensation. |  |  |  |  | -High Judicial Council -State Prosecutorial Council -Ministry of Justice | Continuously, commencing from II quarter of 2016. |  | Budget of the Republic of Serbia, IPA 2012 Costs currently unknown. |  | Measures for balancing the number of cases per judge and public prosecutor/deputy public prosecutor are implemented according to the results of analysis. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.6. Implement the backlog reduction program, including introducing alternative dispute resolution tools; |  |  |  |  |  |  | Coherent implementation of the backlog reduction program and efficiently introduced alternative dispute resolution tools. |  |  |  | - Duration of court proceedings (per matter) on average; - Total number of backlogged cases; - Annual percentage of reduction of backlogged cases; - Total percentage reduction of backlog; - Reduced number of cases, on annual basis, which are categorized as backlogged cases; - Number of disputes resolved before mediator in one year; - Number of transactions concluded via public notaries. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.6.1. |  |  | Adoption of new Civil Procedure Law in order to improve efficiency particularly in part which deals with: delivery of documents, hearing recording and discipline during the proceedings. |  |  | -Ministry of Justice | II quarter of 2016. |  | Budget of the Republic of Serbia, 71.136€ IPA 2012, Budgeted in activity 1.1.6.6. In 2016. |  | Adopted new Civil Procedure Law which provisions improve efficiency in particular in part dealing with delivery of documents, hearing recording and discipline during the procedure. |  |  |  |
| 1.3.6.2. |  |  | Amending Criminal Procedure Code in order to improve efficiency of the proceedings in particular in part dealing with delivery of documents, trial recording and discipline during the proceedings. |  |  | -Ministry of Justice | IV quarter of 2015. |  | Budget of the Republic of Serbia, 71.136€ IPA 2012 1.1366. in activity 00000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000000 Budgeted in activity 1.1.6.6. In 2015. |  | Adopted new Criminal Procedure Code, which provisions improve efficiency, particularly in part dealing with delivery of documents, trial recording and discipline during the proceedings. |  |  |  |
| 1.3.6.3. |  |  | Amending Law on Enforcement and Security in order to improve efficiency of enforcement procedure. |  |  | -Ministry of Justice | II quarter of 2015. |  | Budget of the Republic of Serbia, 71.136€ IPA 2012 GiZ RoLE Project Budgeted in activity 1.3.6.17. In 2015. |  | Amendments to the Law on Enforcement and Security adopted in order to improve efficiency of enforcement procedure. |  |  |  |
| 1.3.6.4. |  |  | Amending Court Rules of Procedure in order to facilitate implementation of Uniform backlog reduction program. |  |  | -Ministry of Justice | III quarter of 2015. |  | Budget of the Republic of Serbia, 8.642€ In 2015. |  | Amended Court Rules of Procedure in order to facilitate implementation of Uniform backlog reduction program. |  |  |  |
| 1.3.6.5. |  |  | Amending Uniform backlog reduction program in accordance with initial results of implementation. |  |  | -Supreme Court of Cassation | I quarter of 2016. |  | Budget of the Republic of Serbia, 8.642€ IPA 2012 Budgeted in activity 1.1.6.6. In 2016. |  | Amended Uniform backlog reduction program in accordance with initial results of implementation. |  |  |  |
| 1.3.6.6. |  |  | Conduct analysis of current Information and Communication Technology systems in regards to hardware, software and human resources in courts, public prosecutors’ offices and prisons, focusing on urgent necessity of changes, along with identifying recommendations for its improvement. (the same activity as 1.2.1.1. and 1.3.8.2.) |  |  | -Ministry of Justice -Expert team of USAID -Expert team MDTF/WB | II quarter of 2015. |  | Budget of the Republic of Serbia, , MDTF/WB, USAID Budgeted in activity 1.2.1.1. |  | Analysis of current Information Communication Technology systems conducted in regard to hardware, software and human resources in courts, public prosecutors’ offices and prisons, focusing on urgent necessity of changes, with recommendations for its improvement. |  |  |  |
| 1.3.6.7. |  |  | Drawing up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources (the same activity 1.2.1.2. and 1.3.8.3.). Guidelines will be based on the results of Functional analysis of judiciary and Analysis of current state of play (activity 1.2.1.1, 1.3.6.6. and 1.3.8.2.). |  |  | -Working group that includes participation of representatives from following institutions: Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | During I and II quarters of 2016. |  | Budget of the Republic of Serbia, TAIEX, IPA 2012 Budgeted in activity 1.2.1.2. |  | Drawn up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources (the same activity 1.2.1.1.). Guidelines are based on the results of Functional analysis of judiciary and Analysis of current state of play. |  |  |  |
| 1.3.6.8. |  |  | Conduct Feasibility study of compatibility of current Information and Communication Technology systems in: courts, Republic Public Prosecutor’s Office, Directorate for Enforcement of Criminal Sanctions, and private bailiffs/enforcement officers, public notaries etc. (activity 1.2.1.3. and 1.3.8.4.). |  |  | -Ministry of Justice -Expert team | II quarter of 2016. |  | Budget of the Republic of Serbia, IPA 2012 Budgeted in activity 1.2.1.3. |  | Conducted Feasibility study of compatibility of current Information and Communication Technology systems in: courts, Republic Public Prosecutor’s Office, Directorate for Enforcement of Criminal Sanctions, and private bailiffs/enforcement officers, public notaries etc. |  |  |  |
| 1.3.6.9. |  |  | On the basis of the Feasibility Study (Activity 1.2.1.3. and 1.3.6.8.) preparing technical specifications for: a) development of web services for exchanging data between information systems in the judiciary, and for b) improvement of software for automatic case management in courts of general jurisdiction, commercial courts, the Republic Public Prosecutor's Office and in the Directorate for Enforcement of Criminal Sanctions. (the same activity 1.2.1.4. and 1.3.8.5.) |  |  | -Ministry of Justice -Expert team | III quarter of 2016. |  | Budget of the Republic of Serbia, IPA 2012 Budgeted in activity 1.2.1.4. |  | On the basis of the Feasibility Study (Activity 1.2.1.3. and 1.3.6.8.) prepared technical specifications for: a) development of web services for exchanging data between information systems in the judiciary, and for b) improvement of software for automatic case management in courts of general jurisdiction, commercial courts, the Republic Public Prosecutor's Office and in the Directorate for Enforcement of Criminal Sanctions. |  |  |  |
| 1.3.6.10. |  |  | Institutionalization of coordination and management of ICT system through public-private or public-public partnership. (the same activity 1.2.1.5. and 1.3.8.6.) |  |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | Commencing from II quarter of 2015. |  | Budget of the Republic of Serbia, IPA 2012, USAID Budgeted in activity 1.2.1.5. |  | Coordination and management of ICT system institutionalized through public-private and public-public partnership. |  |  |  |
| 1.3.6.11. |  |  | Drawing up protocol on input and exchange of data in ICT system with the aim of unification of conduct in entire judicial system. (the same activity 1.2.1.6. and 1.3.8.7.) |  |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | II quarter of 2016 |  | Budget of the Republic of Serbia, TAIEX, IPA 2012 Budgeted in activity 1.2.1.6. |  | Drawn up protocol on input and exchange of data in ICT system with the aim of unification of conduct in entire judicial system. |  |  |  |
| 1.3.6.12. |  |  | Conducting trainings and commencement of implementation of Protocol on entering and exchange of data in ICT system. (the same activity 1.2.1.7. and 1.3.8.8.) |  |  | -Judicial Academy, Ministry of Justice, High Judicial Council, State Prosecutorial Council, all courts and public prosecutors offices | Commencing from IV quarter of 2016 and I quarter of 2017. |  | Budget of the Republic of Serbia, USAID, IPA 2012 Budgeted in activity 1.2.1.7. |  | After conducted trainings, input and exchange of data in ICT system is carried out in accordance to Protocol. |  |  |  |
| 1.3.6.13. |  |  | Amending Rules of Procedure on internal organization and systematization of jobs in Ministry of Justice and employment of IT experts in accordance with new systematization. |  |  | -Ministry of Justice | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia 75.503€ In 2016 – 30.926€ In 2017 – 22.287€ In 2018 – 22.287€ |  | Rules of Procedure on internal organization and systematization of jobs in Ministry of Justice amended and IT experts employed in accordance with new systematization. |  |  |  |
| 1.3.6.14. |  |  | Amending Rules of Procedure on internal organization and systematization of jobs in Supreme Court of Cassation and employment of IT experts in accordance with new systematization. |  |  | -Supreme Court of Cassation | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia 75.503€ In 2016 – 30.926€ In 2017 – 22.287€ In 2018 – 22.287€ |  | Rules of Procedure on internal organization and systematization of jobs in Supreme Court of Cassation adopted and IT experts employed in accordance with new systematization. |  |  |  |
| 1.3.6.15. |  |  | Forming teams in courts in charge of reduction of backlogged cases. |  |  | -Supreme Court of Cassation -Presidents of Courts | During IV quarter of 2014 and I quarter of 2015. |  | Budget of the Republic of Serbia 368.736€ In 2015 – 92.184€ In 2016 – 92.184€ In 2017 – 92.184€ In 2017 – 92.184€ |  | Formed teams in courts in charge of reduction of backlogged cases. |  |  |  |
| 1.3.6.16. |  |  | Signing of the Memorandums on Cooperation between courts and other relevant institutions, with the aim of efficient resolution of backlogged cases. |  |  | -President of the Supreme Court of Cassation -Court Presidents -Authorized persons representing institutions with whom courts cooperate during implementation of Uniform backlog reduction program | Continuously, commencing from IV quarter of 2014. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Memorandums on Cooperation between courts and other relevant institutions, with the aim of efficient resolution of backlogged cases signed. |  |  |  |
| 1.3.6.17. |  |  | Adoption of amendments to Law on Public Notaries in order to gradually extend subject-matter jurisdiction of public notaries and in regards to issue of enforceability of public notaries’ documents. |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | Periodically, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia, 71.136€ GIZ Program for legal and judicial reforms, 10.500.000. € In 2014 – 5.250.000€ (this amount contains funds for 2011, 2012, 2013 and 2014) In 2015 – 1.383.636€ (GIZ 1.312.500€ + Budget RS 71.136€) In 2016 – 1.312.500€ In 2017 – 1.312.500€ In 2017 – 1.312.500€ |  | Amendments to Law on Public Notaries adopted which extended subject-matter jurisdiction of public notaries and which redefined provisions concerning enforceability of public notaries’ documents. |  |  |  |
| 1.3.6.18. |  |  | Drawing up and adopting by-laws which adoption is envisaged in Law on Public Notaries. |  |  | -Minister of Justice -Chamber of Public Notaries | I quarter of 2015. |  | Budget of the Republic of Serbia, GIZ Program for legal and judicial reforms Budgeted in activity 1.3.6.17. |  | By-laws envisaged in Law on Public Notaries adopted. |  |  |  |
| 1.3.6.19. |  |  | Establishment of Chamber of Public Notaries and appointment of additional number of public notaries. |  |  | -Chamber of Public Notaries | Commencing from III quarter of 2014. |  | Budget of the Republic of Serbia, 17.285€ GIZ Program for legal and judicial reforms Budgeted in activity 1.3.6.17. In 2014. |  | Chamber of Public Notaries established. |  |  |  |
| 1.3.6.20. |  |  | Establishment of special unit in Ministry of Justice in charge of supervision of work of public notaries. |  |  | -Ministry of Justice | III quarter of 2014. |  | Budget of the Republic of Serbia, GIZ Program for legal and judicial reforms Budgeted in activity 1.3.6.17. |  | Special unit in Ministry of Justice in charge of supervision of work of public notaries established. |  |  |  |
| 1.3.6.21. |  |  | Improvement of promotion of public notaries’ work. |  |  | -Ministry of Justice, Public Relations Service -Chamber of Public Notaries | Continuously, commenced in I quarter of 2013 |  | GIZ Program for legal and judicial reforms Budgeted in activity 1.3.6.17. |  | System of promotion of public notaries’ work improved. |  |  |  |
| 1.3.6.22. |  |  | Implementation of trainings for public notaries. |  |  | -Judicial Academy -Chamber of Public Notaries | Continuously, commencing from III quarter of 2014. |  | GIZ Program for legal and judicial reforms Budgeted in activity 1.3.6.17. |  | Trainings for public notaries are organized regularly. |  |  |  |
| 1.3.6.23. |  |  | Drawing up and adopting by-laws in accordance with Law on Mediation |  |  | -Minister of Justice | IV quarter of 2014. |  | Budget of the Republic of Serbia 17.285€ In 2014. |  | By-laws adopted in accordance with Law on Mediation. |  |  |  |
| 1.3.6.24. |  |  | Adoption of program for education of mediators and its implementation. |  |  | -Ministry of Justice -Judicial Academy -Other accredited organizations and institutions | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia, 8.642€ In 2015. |  | Program for education of mediators adopted. |  |  |  |
| 1.3.6.25. |  |  | Establishment of registry of licensed mediators. |  |  | -Ministry of Justice | II quarter of 2015. |  | Budget of the Republic of Serbia, 8.642€ In 2015. |  | Registry of licensed mediators established. |  |  |  |
| 1.3.6.26. |  |  | Establishment of special unit in Ministry of Justice in charge of supervision of work of mediators |  |  | -Ministry of Justice | IV quarter of 2015. |  | Budget of the Republic of Serbia 236.148€ In 2014 – 32.944€ In 2015 – 50.801€ In 2016 –50.801€ In 2017 -50.801€ In 2018 - 50.801€ |  | Special unit in Ministry of Justice in charge of supervision of work of mediators established. |  |  |  |
| 1.3.6.27. |  |  | Improvement of promotion of alternative dispute resolution. |  |  | -Ministry of Justice, Public Relations Service | Continuously, commencing from III quarter of 2014. |  | Budget of the Republic of Serbia 2.555€ In 2014 – 509€ In 2015 – 511€ In 2016 –511€ In 2017 -511€ In 2018 - 511€ |  | System of promotion of alternative dispute resolution improved. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.7. Strengthen the enforcement of judgments, in particular in civil cases; |  |  |  |  |  |  | Improved efficiency of enforcement of judgments in particular in civil law cases. |  |  |  | - Reduced number of case backlog in enforcement; - Reduced average duration of enforcement proceedings; |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.7.1. |  |  | Conduct comprehensive analysis of enforcement and security system in the Republic of Serbia. |  |  | -Expert team of GiZ RoLE project | IV quarter of 2014. |  | Budget of the Republic of Serbia, IPA 2012- GiZ RoLE project Budgeted in activity 1.3.6.17. |  | Comprehensive analysis of enforcement and security system in the Republic of Serbia conducted. |  |  |  |
| 1.3.7.2. |  |  | Adoption of amendments to the Law on Enforcement and Security according to the results of analysis. |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | II quarter of 2015. |  | Budget of the Republic of Serbia, 40.258€ GiZ RoLE project Budgeted in activity 1.3.6.17. In 2015. |  | Amendments to the Law on Enforcement and Security, according to the results of analysis, adopted. |  |  |  |
| 1.3.7.3. |  |  | Monitoring efficiency of private bailiffs’ system by Chamber of bailiffs; regular reporting to Strategy Implementation Commission and undertaking, in cooperation with Ministry of Justice, necessary measures in order to solve problems and improve their work. |  |  | -Chamber of bailiffs -Strategy Implementation Commission -Ministry of Justice | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia 10.212€ In 2015 – 2553€ In 2016 –2553€ In 2017 -2553€ In 2018 - 2553€ |  | Chamber of bailiffs monitors efficiency of the system and regularly notifies Strategy Implementation Commission on that issue and undertakes, in cooperation with Ministry of Justice, necessary measures in order to solve problems and improve their work. |  |  |  |
| 1.3.7.4. |  |  | Improvement of efficiency of system of private bailiffs/enforcement officers in accordance with the results of analysis, amendments to the Law on Enforcement and Security and problems spotted in the course of monitoring of functioning of the system. |  |  | -Ministry of Justice -Chamber of Bailiffs/Enforcement officers | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia, GiZ RoLE project Budgeted in activity 1.3.6.17. |  | Efficiency of system of private bailiffs/enforcement officers improved. |  |  |  |
| 1.3.7.5. |  |  | Efficiency improvement of judicial enforcement in line with the results of the analysis and amendments to Law on enforcement and security. |  |  | -Supreme Court of Cassation | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.6.17. |  | Efficiency improvement of judicial enforcement in line with the results of the analysis and amendments to Law on enforcement and security. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.8. Gradually develop an e-Justice system as a means to improve the efficiency, transparency and consistency of the judicial process, building on the existing automated case management system. Ensure the visibility of reliable and consistent judicial statistics and introduce a system to monitor the length of trials; |  |  |  |  |  |  | Developed an e-Justice system as a means to improve the efficiency, transparency and consistency of the judicial process, building on the existing automated case management system. Ensured the visibility of reliable and consistent judicial statistics and introduced a system to monitor the length of trials. |  |  |  | - Increased number of statistical parameters of efficiency of judiciary that can be monitored by means of Information and Communication Technology; - Possibility of actual monitoring of length of court proceedings by introducing the uniform case number; - Perception of transparency of the court proceedings through availability of data via Information and Communication Technology (judicial office holders, attorneys-at-law, citizens); - Perception of data transparency, in relation to the efficiency of the judiciary, through availability of data via Information and Communication Technology (judicial office holders, advocacy, citizens); |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.8.1. |  |  | Amending Court Rules of Procedure in part dealing with: - Criteria for defining input of data based on a previously defined list of data which input is necessary to monitor the statistical parameters of efficiency of judiciary by using Information and Communication Technology, and in particular of length of proceedings. Activity linked with items 2.3.4.1., 2.3.4.2. 2. Introduction of a system that envisages assignment of uniform number to court case file, which retains until conclusion of legal remedies proceedings. |  |  | -Working group of Ministry of Justice in charge of defining data input -Ministry of Justice | Continuously, commencing from IV quarter of 2014 | Budget of the Republic of Serbia, 30.878€ IPA 2012 Budgeted in activity 1.2.1.11. In 2015. |  |  | Amended Court Rules of Procedure in part related to criteria for defining input of data based on a previously defined list of data which input is necessary to monitor the statistical parameters of judiciary’s efficiency by using Information and Communication Technology. |  |  |  |
| 1.3.8.2. |  |  | Conduct analysis of current Information and Communication Technology system in particular hardware, software and human resources in courts, public prosecutors offices and prisons, focusing on necessity of urgent adoption of amendments, and defining recommendations for its improvement. (the same activity as 1.2.1.1. and 1.3.6.6.) |  |  | -Ministry of Justice -Expert team of USAID -Expert team of MDTF/WB | II quarter of 2015. | Budget of the Republic of Serbia, MDTF/WB, USAID Budgeted in activity 1.2.1.1. |  |  | Conducted analysis of Information and Communication Technology system in particular hardware, software and human resources in courts, public prosecutors’ offices and prisons, focusing on necessity of urgent adoption of amendments, and defining recommendations for its improvement. |  |  |  |
| 1.3.8.3. |  |  | Drawing up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources. Guidelines will be based on the results of Functional analysis of judiciary and Analysis of current state of play (activity 1.2.1.1, 1.3.6.6. and 1.3.8.2.). (the same activity 1.2.1.1. and 1.3.6.7.). |  |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | During I and II quarter of 2016. | Budget of the Republic of Serbia, TAIEX, IPA 2012 Budgeted in activity 1.2.1.2. |  |  | Drawn up Guidelines which determines directions of ICT system development in Serbia and which include data on infrastructure of Information and Communication Technology and costs of its maintenance, software and human resources. Guidelines are based on the results of Functional analysis of judiciary and Analysis of current state of play (activity 1.2.1.1, 1.3.6.6. and 1.3.8.2.). |  |  |  |
| 1.3.8.4. |  |  | Conduct Feasibility study for identifying compatibility of current Information and Communication Technology system between following institutions: courts, Republic Public Prosecutor’s Office, Administration for Enforcement of Criminal Sanctions, and private bailiffs/enforcement officers, public notaries etc. (the same activity as 1.2.1.3. and 1.3.6.8.) |  |  | -Ministry of Justice -Expert team | II quarter of 2016. | Budget of Republic of Serbia, IPA 2012 Budgeted in activity 1.2.1.3. |  |  | Feasibility study for identifying compatibility of current Information and Communication Technology system between following institutions: courts, Republic Public Prosecutor’s Office, Administration for Enforcement of Criminal Sanctions, and private bailiffs/enforcement officers, public notaries etc. conducted. |  |  |  |
| 1.3.8.5. |  |  | On the basis of the Feasibility Study (Activity 1.2.1.3. and 1.3.6.8.) preparing technical specifications for: a) development of web services for exchanging data between information systems in the judiciary and for b) improvement of software concerning automatic case management in courts of general jurisdiction, commercial courts, the Republic Public Prosecutor's Office and in the Administration for Enforcement of Criminal Sanctions. (the same activity as 1.2.1.4. and 1.3.6.9.) |  |  | -Ministry of Justice -Expert team | III quarter of 2016. | Budget of the Republic of Serbia, IPA 2012 Budgeted in activity 1.2.1.4. |  |  | On the basis of the Feasibility Study (Activity 1.2.1.3. and 1.3.6.8.) prepared technical specifications for: a) development of web services for exchanging data between information systems in the judiciary and for b) improvement of software concerning automatic case management in courts of general jurisdiction, commercial courts, the Republic Public Prosecutor's Office and in the Administration for Enforcement of Criminal Sanctions. |  |  |  |
| 1.3.8.6. |  |  | Institutionalization of coordination and management of ICT system through public-private or public-public partnership. (the same activity 1.2.1.5. and 1.3.6.10.) |  |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | Commencing from II quarter of 2015. | Budget of the Republic of Serbia, IPA 2012, USAID Budgeted in activity 1.2.1.5. |  |  | Coordination and management of ICT system institutionalized through public-private and public-public partnership. |  |  |  |
| 1.3.8.7. |  |  | Drawing up protocol on input and exchange of data in ICT system with the aim of unification of conduct in entire judicial system. (the same activity 1.2.1.6. and 1.3.6.11.) |  |  | -Working group which includes participation of representatives of Ministry of Justice, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation and Republic Public Prosecutor’s Office | II quarter of 2016. | Budget of the Republic of Serbia, TAIEX, IPA 2012 Budgeted in activity 1.2.1.6. |  |  | Drawn up protocol on input and exchange of data in ICT system with the aim of unification of conduct in entire judicial system. |  |  |  |
| 1.3.8.8. |  |  | Conducting trainings and commencement of implementation of Protocol on input and exchange of data in ICT system. (the same activity 1.2.1.7. and 1.3.6.12.) |  |  | -Judicial Academy, Ministry of Justice, High Judicial Council, State Prosecutorial Council, all courts and public prosecutors offices | Commencing from IV quarter of 2016. and I quarter of 2017. | Budget of the Republic of Serbia, USAID, IPA 2012 Budgeted in activity 1.2.1.7. |  |  | Upon conducted trainings, input and exchange of data in ICT system is carried out in accordance with Protocol. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.9. Improve consistency of jurisprudence through judicial means (consider simplification of the court system by abolishing courts of mixed jurisdiction and possibility to file an appeal before the Supreme Court of Cassation based on legal grounds against any final decision) and by ensuring complete electronic access to court decisions and motivations and their publication within a reasonable amount of time; |  |  |  |  |  |  | Jurisprudence in all areas of law is consistent; judicial decisions and judicial motivations are timely published in all available electronic data bases. |  |  |  | - Established uniform and comprehensive electronic database of jurisprudence available to everyone which is in compliance with regulations governing data confidentiality and protection of personal data; - Positive opinion from European Commission, stated in Annual Progress Report on Serbia, concerning progress achieved in the field of uniformity and availability of jurisprudence. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.9.1. |  |  | Conduct analysis of the normative framework which regulates: the issue of binding of jurisprudence, right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning. |  |  | -Working group for legal analysis of constitutional framework on judiciary in the Republic of Serbia -Working group, established by Minister of Justice, for analysis of laws and by-laws which regulate issues of binding of jurisprudence and principled positions and publishing of judicial decisions and motivations -Working group for analysis of availability of right to legal remedy and jurisdiction for deciding on legal remedies | II quarter of 2014- II quarter of 2015. |  | Budget of the Republic of Serbia 30.878€ In 2015. |  | Conducted analysis of normative framework which regulates: the issue of binding of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning. |  |  |  |
| 1.3.9.2. |  |  | Defining rules which regulate anonymization of judicial decisions prior to their announcement in accordance to rules of European court for human rights. |  |  | -Ministry of Justice -Supreme Court of Cassation | II quarter of 2015. |  | Budget of the Republic of Serbia, 8.642€ IPA 2012 Budgeted in activity 1.1.6.6. In 2015. |  | Defined rules which regulate anonymization of judicial decisions prior to their announcement, in accordance to rules of European court for human rights. |  |  |  |
| 1.3.9.3. |  |  | Amending normative framework which regulates: the issue of binding of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning. |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | Commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia, 71.136€ IPA 2012 Budgeted in activity 1.1.6.6. |  | Amended normative framework which regulates: the issue of binding of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning. |  |  |  |
| 1.3.9.4. |  |  | Access to jurisprudence: Establishing and improving of uniform and comprehensive electronic databases of jurisprudence available to everyone which is in compliance with regulations regulating data confidentiality and protection of personal data. |  |  | -Ministry of Justice -Supreme Court of Cassation -Republic Public Prosecutor’s Office -Government of the Republic of Serbia -Public Enterprise “Official Gazette” | Continuously, commencing from III quarter of 2014. |  | Budget of the Republic of Serbia, IPA 2012, Budgeted in activity 1.1.6.6. |  | Uniform, comprehensive electronic databases of jurisprudence available to everyone which is in compliance with regulations governing data confidentiality and protection of personal data is established and is updated and improved regularly. |  |  |  |
| 1.3.9.5. |  |  | Capacity strengthening and improvement of efficiency of operation of departments for jurisprudence in Supreme Court of Cassation, in accordance with the amendments to the normative framework which regulates the issues of binding of jurisprudence and its publishing. |  |  | -Supreme Court of Cassation | Continuously, commencing from II quarter of 2016. |  | Budget of the Republic of Serbia, Cost currently unknown. IPA 2012 Budgeted in activity 1.1.6.6. |  | Capacities and efficiency of operation of department for jurisprudence in the Supreme Court of Cassation are continuously improved in accordance with the amendments to the normative framework which regulates the issues of binding of jurisprudence and its publishing. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.10. Monitor the implementation of the new Criminal Procedure Code and take corrective measures where needed. |  |  |  |  |  |  | Established efficient system for monitoring the implementation of the new Criminal Procedure Code and measures implemented for improvement of the Code and its implementation. |  |  |  | - Opinion concerning efficiency of the implementation of Criminal Procedure Code stated by the Commission for monitoring the implementation of Criminal Procedure Code in its quarterly and annual reports to the Strategy Implementation Commission; - Positive opinion by European Commission on efficiency of implementation of Criminal Procedure Code stated in Annual Progress Report on Serbia |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.10.1. |  |  | Commission for monitoring the implementation of the Criminal Procedure Code reports quarterly and annually to the Strategy Implementation Commission in which it provides an overview of deficiencies in the implementation of the Criminal Procedure Code and suggests potential measures to remedy identified problems. |  |  | -Commission for monitoring the implementation of Criminal Procedure Code -Strategy Implementation Commission | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia, 61.755€ In 2015 – 15.439€ In 2016 –15.439€ In 2017 -15.439€ In 2018 - 15.439€ |  | Commission for monitoring the implementation of the Criminal Procedure Code reports quarterly and annually to the Strategy Implementation Commission in which provides an overview of deficiencies in the implementation of the Criminal Procedure Code and suggests potential measures to remedy identified problems. |  |  |  |
| 1.3.10.2. |  |  | Strategy Implementation Commission, on the basis of the report of the Commission for monitoring the implementation of the Criminal Procedure Code, recommends undertaking measures to competent institutions aimed at eliminating identified problems. |  |  | -Strategy Implementation Commission | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.10.1. |  | Strategy Implementation Commission, on the basis of the report of the Commission for monitoring the implementation of the Criminal Procedure Code, recommends undertaking measures to competent institutions aimed at eliminating identified problems. |  |  |  |
| 1.3.10.3. |  |  | Competent institutions to which Strategy Implementation Commission recommended implementation of corrective measures, quarterly report to the Strategy Implementation Commission on the implementation of recommended measures. |  |  | -Republic Public Prosecutor’s Office -Supreme Court of Cassation -High Judicial Council -State Prosecutorial Council -Ministry of Justice -Strategy Implementation Commission | Continuously, commencing from II quarter of 2015. |  | Budget of the Republic of Serbia 10.893€ In 2015 – 2.723€ In 2016 –2.723€ In 2017 -2.723€ In 2018 - 2.723€ |  | Competent institutions to which Strategy Implementation Commission recommended implementation of corrective measures, quarterly report to the Strategy Implementation Commission on the implementation of these measures. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.3.11. Conduct a mid-term review at the end of 2015 as well as an impact assessment in 2018 of the results generated by the 2013 Strategy and its revised action plan. Define on that basis and where needed measures to cover the remaining period up until accession. |  |  |  |  |  |  | A mid-term review assessed the impact of the reform of judiciary for period up until 2018 and an impact assessment on that basis served to define measures for period after 2018 up until accession. |  |  |  | - Data from analysis of mid-term results of implementation of reform in 2015; - Data from impact projections for the period up until 2018; - Measures planned for period from 2018 up until accession, based on an analysis of the mid-term results and projection for period until 2018. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.3.11.1. |  |  | Conduct a mid-term review or analysis, as of 2015, of implementation of National Judicial Reform Strategy for the period 2013-2018 and updating the Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. |  |  | -Ministry of Justice -Strategy Implementation Commission | IV quarter of 2015. | Budget of the Republic of Serbia 61.755€ In 2015 – 15.439€ In 2016 –15.439€ In 2017 -15.439€ In 2018 - 15.439€ |  |  | Conducted a mid-term review or analysis, as of 2015, of implementation of National Judicial Reform Strategy for the period 2013-2018 and updated the Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. |  |  |  |
| 1.3.11.2. |  |  | Within Functional analysis of judiciary, conduct an impact assessment of implementation, in the period until 2018, of: a) National Judicial Reform Strategy for the period 2013-2018 and b) Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. (Connected activity 1.3.3.3.) |  |  | -Expert team with the participation and support of representatives from following institutions: High Judicial Council, State Prosecutorial Council, Ministry of Justice, Judicial Academy, Supreme Court of Cassation and Republic Public Prosecutor’s Office. | During IV quarter of 2017 and I quarter of 2018. | IPA 2015 Budgeted in activity 1.3.3.3. |  |  | Within Functional analysis of judiciary, conducted an impact assessment of implementation, in the period until 2018, of: a) National Judicial Reform Strategy for the period 2013-2018 and b) Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. |  |  |  |
| 1.3.11.3. |  |  | Proposing measures which will cover period remaining up until accession. Proposal will be based on an impact assessment of implementation in the period until 2018 of: a) National Judicial Reform Strategy for the period 2013-2018 and b) Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. |  |  | -Ministry of Justice -Strategy Implementation Commission | During II and III quarters of 2018. | Budget of the Republic of Serbia Currently unknown |  |  | Proposed measures which cover period remaining up until accession. Proposal is based on an impact assessment of implementation in the period until 2018 of: a) National Judicial Reform Strategy for the period 2013-2018 and b) Action Plan for implementation of National Judicial Reform Strategy for the period 2013-2018. |  |  |  |
| - WAR CRIMES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.4.1 Ensure that all allegations are properly investigated and subsequently prosecuted and tried; |  |  |  |  |  |  | All allegations have been properly investigated and all trials for war crimes have been completed, with full and accurate implementation of international standards concerning the support of victims and witnesses and their protection, |  |  |  | - The number of new cases (Indictments/indicates) initiated towards suspects, regardless on their rank which they used to have in the moment of perpetration of the crime and which they have today; - Total number of cases - Number of proceedings completed with final judgment - Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; - Reports of other relevant governmental and nongovernmental organizations - Public Opinion Survey (opinion of the public on the issue whether the suspects for war crimes are properly investigated and punished) - Duration of war crime proceedings (efficient pre-investigative and investigative proceedings) - Quality of proceedings and judgments for war crimes in comparison to international standards. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.4.1.1. |  | Preparation of reports by the War Crimes Prosecutor’s Office, which will be available to the public, on the subject which will present what has been done concerning all criminal charges since 2010, in order to determine, and in addition to represent, whether all allegations of war crimes have been investigated appropriately. |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice | I and II quarters of 2015. |  |  | Budget of Republic of Serbia 8.642€ In 2015. | Report of War Crimes Prosecutor’s Office has been published. |  |  |  |
| 1.4.1.2. |  | Organizing the Round table “Creating the Prosecutorial Strategy for investigation and prosecution of war crimes in Serbia in the light of the Completion Strategy of the ICTY” with the involvement and support of the ICTY, MICT, ICC, Regional prosecutors and NGOs and publishing conclusions from the Round table Creating the WCP strategy for investigation and prosecution of War crimes based on the conclusions from the Round table and implementation of the Strategy. Prerequisite establishing: - what allegation of war crimes have been investigated in accordance with international standards; - what viable investigations are pending before the WCP; - what viable investigations are pending before the Police; - which viable investigations need to be prioritized over other based on identified criteria (category 1 - 3 cases); - what timeline is envisaged for the investigation and prosecution of all category 1 – 3 cases. (support obtained from ICTY and MICT) (Shared activity with recommendation 1.4.3) |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice | I and II quarter of 2015 Continuously, commencing from I quarter of 2015 |  |  | Budget of Republic of Serbia 18.285€ In 2015. | The Conference organized with published conclusions and recommendations. Creating the Strategy and its implementation in Serbia. |  |  |  |
| 1.4.1.3. |  | Establishing the criteria’s for the selection of war crime cases and creating the list of priority and important war crime cases that must be resolved in order to fulfill obligation that all allegations are properly investigated and that all priority and important cases are subsequently prosecuted and tried. (support obtained from ICTY and MICT) (Shared activity with recommendation 1.4.3) |  |  |  | -War Crimes Prosecutor’s Office -Ministry of justice | I and II quarter of 2015 |  |  | Budget of Republic of Serbia 17.285€ In 2015. | Established criteria for selection of cases and creating the list of priority cases of the WCP (working on cases based on the above mentioned internationally recognizes Strategy) |  |  |  |
| 1.4.1.4. |  | Complete insight and research of International Criminal Tribunal for former Yugoslavia (ICTY) and Residual Mechanism (MICT) archives, analysis of the discovered documents through the EU established liaison officers project ensuring that all priority and serious allegations or war crimes are properly investigated and subsequently prosecuted and tried (considering that the archive of the ICTY and MICT are today the most comprehensive ones in relation to war crimes in the territory of Former Yugoslavia, namely including documents not only from Serbia but from BiH and RH, and considering that independent prosecutors of ICTY worked already on general and specific allegations). This will ensure transparency and quality of the eventual charges. Identifying ICTY/MICT materials and evidence which are relevant to the cases identified as a priority under activity 1.4.1.3 above and transferring of the found documents and evidence from the ICTY and MICT to the War Crime Prosecutor Office (support obtained and memorandum of understanding signed) - Cooperation of the WCP with the ICTY/MICT on concrete cases in which the evidence was transferred in order to also obtain general and case specific knowledge, expertise and strategies from the ICTY and MICT investigators/prosecutors (ensuring transparency considering that information and expertise were obtained from independent experts) - Cooperation of the WCP with the ICTY and MICT on concrete cases in which the evidence was transferred in order to also shared the strategy and transfer knowledge and practice on jurisprudence relating to crimes and types of responsibility that will be used as allegation in concrete cases (ensuring transparency considering that the strategy of concrete prosecution is shared and supported by the ICTY and MICT prosecutors and experts). • Presence of the WCP advisor in the ICTY and MICT prosecutor’s office on ad hoc basis related to concrete cases, analyzing ICTY prosecutor’s case files and developing a strategy for concrete cases that will be prosecuted by the WCP before the High Court in Belgrade. |  |  |  | -War crimes Prosecutor’s Office -Ministry of justice | Continuously, commencing from II quarter of 2015 IV quarter of 2015 - continuously III quarter of 2015 - continuously III quarter of 2015-continuoulsy |  |  | Budget of the Republic of Serbia, 69.138€ In 2015 – 17.285€ In 2016 –17.285€ In 2017 -17.285€ In 2018 - 17.285€ | Complete research of the ICTY and MICT archives Completion of evidence transferred. Strategy related to concrete cases formed and implemented |  |  |  |
| 1.4.1.5. |  | Establishing a system of training and education in the field of international humanitarian law and on criminal investigation under the new CPC for the participants in the war crimes trials (enabling transferring from the old material truth system to the new CPC system of conducting Trials). Ensuring that the latest IHL developments are included. |  |  |  | -War Crime Prosecutor’s Office -Higher Court in Belgrade, War Crime Chamber -High Judicial Council -State Prosecutorial Council -Judicial Academy | Continuously, commencing from II quarter of 2015 |  |  | Budget of the Republic of Serbia, 34.569€ In 2015 – 8.642€ In 2016 –8.642€ In 2017 -8.642€ In 2018 - 8.642€ Donations Currently unknown | Trainings in the field of international humanitarian law are held continuously according to program which has been ascertained in advance. |  |  |  |
| 1.4.1.6. |  | Preparation of analysis(report) of legislative and factual status and needs of the Office for War Crimes of Ministry of Interior in order to determine needs for Office's reform (special focus on whether the office has sufficient investigators and analysts and proper methodology) (for example in BiH prosecutor office number of war crime cases stands: more than 600 investigation files; more than 1000 pre-investigation files and more than 1700 cases against unknown perpetrators. Example of BiH is given because in some cases there is parallel jurisdiction with Serbia and perpetrators are in Serbia and because the process of transferring the case files and documents from the ICTY and MICT is finished unlike the case with Serbia where this process just started). |  |  |  | -Ministry of Interior -Ministry of justice | I quarter of 2015 |  |  | Budget of the Republic of Serbia, 8.642€ In 2015. Donations Currently unknown | Prepared analysis of legislative and factual status of Office for War Crimes in Ministry of Interior in order to determine needs for Office's reform and implementation of the reform |  |  |  |
| 1.4.1.7. |  | Implementation of measures to improve the status and capacity of Office for War Crimes of the Ministry of the Interior in accordance with the results of the analysis (report) under 1.4.1.6 |  |  |  | -Ministry of Interior -Ministry of Justice | Continuously, commencing from I quarter of 2016 |  |  | Budget of the Republic of Serbia, donations Costs will be specified after conducting the analysis. | Measures to improve the status of Office for War Crimes of the Ministry of the Interior are being implemented in accordance with the results of the analysis (report). |  |  |  |
| 1.4.1.8. |  | Enhancement of the WCP web-site in order for public to be able to monitor what activities and when have been performed by the WCP in relation to specific criminal charges |  |  |  | -War Crime Prosecutor Office -Ministry of Justice | II quarter of 2015 |  |  | Budget of Republic of Serbia 2.553€ In 2015 – 851€ In 2016 –851€ In 2017 -851€ In 2018 - 851€ | Enhanced WCP website which provides an opportunity for public to monitor with which activities have been performed by the WCP in relation to specific criminal charges. |  |  |  |
| 1.4.1.9. |  | Strengthening the capacities of War Crimes Prosecutor’s Office through electing: two deputies of special prosecutor IV quarter 2014 – III quarter 2015; two assistants/advisors IV quarter 2014 – III quarter 2015; one deputy of special prosecutor IV quarter 2015 – III quarter 2016; one assistant/advisor IV quarter 2015 – III quarter 2016; one deputy of special prosecutor IV quarter 2016 – III quarter 2017; two assistants/advisors IV quarter 2016 – III quarter 2017; one deputy of special prosecutor IV quarter 2017 – III quarter 2018; one assistant/advisor IV quarter 2017 – III quarter 2018; one deputy of special prosecutor IV quarter 2018 – III quarter 2019; (Deputy Prosecutors would be elected and it could be expected that some of the advisors from the WCP office will be promoted and elected because of the previous experience during work in WPC, which would enchase the capacity of the WCP. Assistants/advisors would be either employed or transferred depending of the qualification of the candidates interested. Qualifications requested by the candidates are knowledge and practice in the field of IHL and experience in criminal law. If best candidates are from the regular prosecutor’s office they will be transfer but considering the number of assistants this would not affect the capacity of the regular prosecutor’s office. |  |  |  | - War Crimes Prosecutor’s Office -Ministry of Justice | IV quarter of 2014 – III quarter 2015 first measures and onwards continuously |  |  | Budget of Republic of Serbia 1.091.520€ In 2015 – 181.920€ In 2016 –181.920€ In 2017 -363.840€ In 2018 - 363.840€ | Strengthened the capacities of War Crimes Prosecutor’s Office through electing special prosecutor’s deputies and employment/transfer of prosecutor’s assistants |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.4.2. Ensure proportionality of sentences; |  |  |  |  |  |  | Imposed sentences are proportional to criminal offence in accordance with the international standards. |  |  |  | - Level of sentences imposed in comparison to the jurisprudence of international tribunals - Positive evaluation from analysis and reports of international and non-governmental organizations concerning proportionality of sentences - Implementation of international criteria (including aggravating and mitigating circumstances) in imposition of sentences in war crimes cases. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.4.2.1. |  | Organizing the round table on the subject “Type and level of sentences and establishing the criteria applied in the war crime cases before the ICTY, national jurisdictions in Croatia, Serbia and BiH (in the light of Maktuf and Damjanovic Judgment before the ECHR)”, with special emphasis on the criteria for determining the aggravating and mitigating circumstances in determining sentence in the international jurisprudence and the preparation of a manual for judges and prosecutors on the basis of established international standards. |  |  |  | - Higher Court in Belgrade, War Crime Chamber - War Crime Prosecutor Office -Ministry of Justice | II and III quarter of 2015. | Budget of Republic of Serbia 1000€ In 2015. |  |  | The Conference organized and held. |  |  |  |
| 1.4.2.2. |  | Publishing the report and conclusions on criteria from the Conference |  |  |  | -Higher Court in Belgrade -War Crimes Prosecutor’s Office -Ministry of Justice | III and IV quarter of 2015. | Budget of Republic of Serbia Activity requiring insignificant costs. |  |  | Published report with criteria. |  |  |  |
| 1.4.2.3. |  | Preparation of a manual for judges and prosecutors on the criteria for determining the aggravating and mitigating circumstances in determining sentences in the international jurisprudence and preparation of a manual for judges and prosecutors on the basis of established international standards. |  |  |  | -Higher Court in Belgrade, -War Crimes Prosecutor’s office -Ministry of Justice | IV quarter of 2015. and I quarter of 2016 | Budget of the Republic of Serbia Budgeted in activity 1.4.1.9. |  |  | Printed and distributed manual for judges and prosecutors on the criteria for determining the aggravating and mitigating circumstances in determining sentences in the international jurisprudence and preparation of manual for judges and prosecutors on the basis of established international standards. |  |  |  |
| 1.4.2.4. |  | Preparing and publishing of report on jurisprudence in Serbia concerning imposing sentences in war crime cases and identification of cases in which sentences were determined near or below minimum stipulated by the law. Prepare recommendations (if needed) based on the results of the report to assure that no sentences are issued that go bellow the statutory minimum defined by law. |  |  |  | -Higher Court in Belgrade, Department for War Crimes | Reporting period commences from IV quarter of 2015 and continuously adding new jurisprudence on sentencing | Budget of the Republic of Serbia Budgeted in activity 1.4.1.9. |  |  | Report on jurisprudence in Serbia concerning imposing sentences in war crime cases has been prepared and published and cases in which sentences were determined near or below minimum stipulated by the law have been identified |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.4.3. Ensure equal treatment of suspects, including in cases of high level officers allegedly involved in war crimes; |  |  |  |  |  |  | Suspects – independently of their (former) rank or grade - are treated equally before the court both in terms of sentencing as well as in terms of the speed of bringing their cases forward. |  |  |  | - The number of new cases against high level officers. - The number of completed cases against high level officers - Positive evaluation in the report of the ICTY Chief Prosecutor and President to the Security Council - Positive evaluation in the reports from relevant international and nongovernmental organizations |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.4.3.1. |  | Organizing the Round table “Creating the Prosecutorial Strategy for investigation and prosecution of war crimes in Serbia in the light of the Completion Strategy of the ICTY” with the involvement and support of the ICTY, MICT, ICC, Regional prosecutors and NGOs and publishing conclusions from the Round table. Creating the WCP strategy for investigation and prosecution of War crimes based on the conclusions from the round table and implementation of the Strategy. Prerequisite establishing: - what allegation of war crimes have been investigated in accordance with international standards; - what viable investigations are pending before the WCP; - what viable investigations are pending before the Police; - which viable investigations need to be prioritized over other based on identified criteria (category 1 - 3 cases); - what timeline is envisaged for the investigation and prosecution of all category 1 – 3 cases. (support obtained from ICTY and MICT) (Shared activity with recommendation 1.4.1) |  |  |  | -War Crime’s Prosecutor’s Office -Ministry of Justice | I and II quarter of 2015 Continuously commencing from I quarter 2015 | Budget of Republic of Serbia 1000€ In 2015. (development of a strategy is budgeted in activity 1.4.1.2) |  |  | The Conference organized and conclusions and recommendations published. Creating the Strategy and its implementation in Serbia. |  |  |  |
| 1.4.3.2. |  | Establishing the criteria’s for the selection of war crime cases and creating the list of priority and important war crime cases that must be resolved in order to fulfill obligation that all allegations are properly investigated and that all priority and important cases are subsequently prosecuted and tried. (support obtained from ICTY and MICT) (Shared activity with recommendation 1.4.1) |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice | I and II quarter of 2015. | Budget of Republic of Serbia Budgeted in activity 1.4.1.3 |  |  | Established criteria for selection of cases and creating the list of priority cases of the WCP (working on cases based on the above mentioned internationally recognized Strategy) |  |  |  |
| 1.4.3.3. |  | Cooperation on individual cases between the WCP and the ICTY and MICT on sharing the strategy in cases of high level officers and transferring the knowledge on judicial practice relevant for types of responsibility and crimes (command responsibility; crimes against humanity; specific direction of aiding and abetting) |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice | Continuously, commencing from II quarter of 2015. | Budget of Republic of Serbia 34.569€ In 2015 – 8.642€ In 2016 –8.642€ In 2017 -8.642€ In 2018 - 8.642€ |  |  | Sharing the knowledge on judicial practice on crimes and types of responsibility in the cases of high level officers transferred and transparency of the creation of prosecutorial strategy in concrete cases |  |  |  |
| 1.4.3.4. |  | Preparing and publishing the Report by the WCP on the activities in relation to all criminal charges since 2010 specifically emphasizing the cases related to high level officers |  |  |  | -War Crime Prosecutor Office -Ministry of Justice | II and III quarter of 2015. (reporting period from II to III quarter of 2015) | Budget of Republic of Serbia Budgeted in activity 1.4.3.3. |  |  | WCP’s report on the activities in relation to all criminal charges since 2010, specifically emphasizing the cases related to high level officers, has been published. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.4.4. Step up security of witnesses and informants and improve witness and informant support services; |  |  |  |  |  |  | Security of witnesses and informants has been stepped up and support services for witnesses and informants have been improved. |  |  |  | - The number of witnesses in witness protection program and increased number of witnesses who would like to testify without protection in war crimes cases; - European Commission has issued, in its Annual progress report on Serbia, positive evaluation concerning the level of security of witnesses and informants and concerning functioning of support services for witnesses and informants - Decrease in number of cases in which the status of witnesses and connected information is endangered or in which there is the risk of making witnesses and information publically available - Positive evaluation in the reports from relevant international and nongovernmental organizations |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.4.4.1. |  | Analysis of current practice in the implementation of Article 102, paragraph 5 of the Criminal Procedure Code in order to identify existing needs for amending Article and better protection of witnesses. |  |  |  | -Working group, established by the Minister of Justice, which encompasses representatives of following institutions: Ministry of Justice, War Crimes Prosecutor’s Office, Higher Court in Belgrade-Department for War Crimes, Ministry of Interior- Witness protection unit | Second half of 2015. | Budget of the Republic of Serbia 17.285€ In 2015. |  |  | Prepared analysis of current practice in the implementation of Article 102, paragraph 5 of the Criminal Procedure Code in order to identify existing needs for amending Article and better protection of witnesses. |  |  |  |
| 1.4.4.2. |  | Preparation of analysis (report) of conduct and work in past years of the Ministry of Interior’s „Unit for witness protection“ in order to determine needs for Office's reform, specifically its working methods (involving independent members from WCP, Higher Court, relevant scholars and eventually member of the ICTY witness and victims unit in analyzing the report of the Unit and making recommendations ). |  |  |  | -Ministry of Interior | I and II quarter of 2015 (reporting period since the establishment of the Unit) | Budget of the Republic of Serbia Budgeting in Chapter 24, activity 6.2.11.2. |  |  | Creation the analysis (report) |  |  |  |
| 1.4.4.3. |  | Amendments of the Rules of the witness and victims support unit (addressing expanding the jurisdiction of the unit on investigation and pre- investigation). |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice -Higher Court in Belgrade, War Crime Chamber | During III quarter of 2015. | Budget of the Republic of Serbia Budgeted in activity 1.4.1.9. |  |  | Rules of the witness and victims support unit has been amended. |  |  |  |
| 1.4.4.4. |  | Changing the systematization of WCP, introducing the section for employment of the psychologist that will deal with victims and witnesses when needed |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice -Higher Court in Belgrade, War Crime Chamber | II quarter of 2015. | Budget of the Republic of Serbia Budgeted in activity 1.4.1.9. |  |  | The systematization changed and employed psychologists who will deal with witnesses and victims |  |  |  |
| 1.4.4.5. |  | Organizing the Round table „Best practices witness and victims support through the criminal proceeding ICTY and ICC“ |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice -Higher Court in Belgrade, War Crime Chamber | II quarter of 2015. | Budget of Republic of Serbia 1000€ In 2015. |  |  | The Round table organized and published conclusions and recommendations. |  |  |  |
| 1.4.4.6. |  | Improving the Status of the Ministry of Interior’s „Unit for witness protection“ - Changing the rules and criteria for employing and selecting new members of the unit - Training of the new members of the Unit through EU WINPRO program |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Justice -Higher Court in Belgrade, War Crime Chamber | IV quarter of 2015 and I quarter of 2016. | Budget of Republic of Serbia Budgeting in Chapter 24, activity 6.2.11.3. |  |  | Improved the Status of the Ministry of Interior’s „Unit for witness protection“ through changed rules and criteria for employing and selecting new members of the unit. New members of the Unit trained through EU WINPRO program. |  |  |  |
| 1.4.4.7. |  | Amend Rulebook on internal systematization and job classification in the Ministry of Interior in Article 13, which refers to the activities and organization of the Protection Unit. (measure from the Action Plan for Chapter 24, Subchapter- Organized crime) |  |  |  | -War Crimes Prosecutor’s Office -Ministry of Interior | I quarter of 2015 and I quarter of 2016. | Budget of the Republic of Serbia Budgeting in Chapter 24, activity 6.2.11.2. |  |  | Amended Rulebook on internal systematization and job classification in the Ministry of Interior in Article 13, which refers to the activities and organization of the Protection Unit. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |
| 1.4.5. Ensure confidentiality of the investigation including witness and informant testimony. |  |  |  |  |  |  | Investigations are confidential including witness and informant testimony. |  |  |  | - Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; - Positive evaluation issued in Annual progress report on Serbia by European Commission concerning improvement of Constitution’s provisions |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |
| 1.4.5.1. |  | Organizing round tables and lectures for the members of Ministry of Interior (War Crime investigative section and Witness protection unit) on the subject of „Basic communication with media“. |  |  |  | -War Crimes Prosecutor’s Office | III quarter of 2015. | Budget of the Republic of Serbia 1000€ In 2015. |  |  | Round tables organized and lectures delivered. |  |  |  |
| 1.4.5.2. |  | Creating particular segment on WCP website relating to power point presentation on the subject “Basic communication with media” and data that clarify which information from war crime proceedings can be available to the public. |  |  |  | -War Crimes Prosecutor’s Office | III and IV quarter of 2015. | Budget of the Republic of Serbia Budgeted in activity 1.4.1.9. |  |  | Particular segment on WCP website relating to power point presentation on the subject “Basic communication with media” has been created and data, that clarify which information from war crime proceedings can be available to the public, have been specified. |  |  |  |

| - FIGHT AGAINST CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1. IMPLEMENTATION OF ANTI-CORRUPTION MEASURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CURRENT STATE OF PLAY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Republic of Serbia has adopted National Anti-Corruption Strategy for the period 2013-2018 (Strategy) and accompanying Action plan, which determines activities for implementation of strategic objectives. In order to establish a system for coordinating the implementation of the Strategy and Action Plan, the Ministry of Justice implemented the measure 5.1. from Action plan and has formed the Group for the coordination of the implementation of the National Anti-Corruption Strategy. Scope of operation of Group for Coordination includes, among others, the activities related to the coordination and networking of bodies that implement Strategy, gathering data and organizing consultative meetings of representatives of authorities in relation to the implementation of the Strategy and Action Plan. Shortly after the commencement of the implementation of measures and activities from the Action Plan, the practice has shown that sustainable development in the implementation of the Strategy and Action Plan can be achieved only through coordination at the highest political level. This need has also been identified by the Anti-Corruption Council. Taking into account that fight against the corruption is one of the most important objectives in the Republic of Serbia, the Government, decided, on August 7th 2014, on the establishment of the Coordination body for the implementation of the Action Plan for the Implementation of the National Strategy for Combating Corruption, which has established the coordination at the highest political level. The head of the Coordination Body is the Prime Minister and members are ministers in charge of judiciary and finance, as members of the Anti-Corruption Council. The state authorities competent for the implementation of the Action Plan appoint a person from among the ranks of public officials who are in charge of implementing measures from their own competencies. Secretary of State in charge of anti-corruption in the Ministry of Justice, with the participation of the Office for Cooperation with Civil Society and the Group for the coordination of the implementation of the National Anti-Corruption Strategy, is accountable for political and technical coordination between the State Secretaries. Civil society organizations take participation in the process of coordinating the implementation of anti-corruption measures by submitting their reports and suggestions to the Office for Cooperation with Civil Society, which, then, forwards them to the Coordination body for the implementation of the Action Plan for the Implementation of the National Strategy for Combating Corruption. In this way, a legal and institutional mechanism for coordination of the implementation of the Strategy and Action Plan for fight against the Corruption has been established, and measures are aimed at the achieving concrete results in practice. The task of the Anti-corruption Council is to: review the activities in the field of fight against corruption, to propose to the Government measures to be taken in order to effectively fight against corruption, and to monitor their implementation, and to take initiatives for the adoption of regulations, programs, and other acts and measures in this field. As an advisory body of executive power, Anti-Corruption Council used to regularly prepare and submit reports and initiatives to the Government on the phenomena of corruption, systemic corruption, but there was lack of interactive relation between the two bodies. Below are the envisaged measures, which implementation, will ensure that the Government and competent state authorities systematically review reports and initiatives of Anti-Corruption Council during implementing measures in the field of fight against corruption. The Republic of Serbia has ratified all major international instruments in the fight against corruption. Generally, laws and regulations are partly compatible with accepted international standards. To identify deficiencies in the legislative solutions, the representatives of the Republic of Serbia are actively involved in the compatibility assessment conducted by European and international organizations, such as the evaluation by the Group of States against Corruption (GRECO) and the UN Office on Drugs and Crime. Plan to harmonize the internal legal system with the EU acquis for the period 2013-2018, has been determined in the National Programme for the Adoption of the Acquis. This medium-term document, whose structure besides legislative, includes institutional and administrative framework, also governs the field of fight against corruption. Basic guidelines for planning the necessary legislative changes used to represent the measures previously identified in the Action Plan to the National Anti-Corruption Strategy for the period 2013-2018, which, inter alia, stipulates the improvement of corruptive and economic offences. With the adoption of the National Anti-Corruption Strategy for the period 2013-2018, a new system of monitoring of the implementation, coordination and supervision of the implementation of strategic objectives has been established. The Anti-Corruption Agency, as an independent state authority, has continued to supervise the implementation of the Strategy and Action Plan and to report on the degree of realization of these documents to the National Assembly. Anti-Corruption Council has been vested with the competence of the monitoring of the results of the implementation of the Strategy and Action Plan. The Council collects information about the experience and the obstacles for the effective implementation of the Strategy and Action Plan and reports thereon to the Government. The role of the Coordinator is entrusted to the Ministry of Justice, within which the Group for coordination of the implementation of the National Anti-Corruption Strategy has been established. For the timely collection of information about the performance of the given activities, each responsible entity for the implementation of the Action Plan, has appointed a contact person for communication and exchange of experiences. Almost a year after the implementation of the Strategy and Action Plan, there was a change in the system of coordination by formation of the Coordination Body headed by the Prime Minister which raised coordination to the highest political level. As described above, an institutional framework for the implementation, coordination, monitoring of results of implementation and monitoring of the implementation of the Strategy and Action Plan has been established. For the purpose of efficiency of the established system, the need to clarify new competencies and duties of each individual factor in implementing the strategic objectives for the fight against corruption has been identified. The Anti-Corruption Agency(the Agency) is an independent state authority, which reports to the National Assembly for its operation. Law on the Fight Against Corruption ("Official Gazette of RS", no. 97/08, 53/10 66/11-Constitutional Court’s decision and 67/13- Constitutional Court’s decision) provides a wide range of responsibilities of the Agency relating to resolving the incompatibility of public offices and conflict of interest, controlling the assets of public officials and keeping a register of public officials, property and gifts; controlling the financing of political subjects, addressing the complaints of citizens, education, supervision over the implementation of the strategic framework, the analysis of regulations, and so on. Though the Agency has shown some results in the discharge of their competencies, the need for a redefinition of responsibilities and strengthening the capacities of the Agency has been identified, in order to ensure greater efficiency. In order to overcome the shortcomings, the National Anti-Corruption Strategy for the period from 2013 to 2018 and the Action Plan, envisaged measures for changes of normative, administrative and operational framework of the Agency. Aim of these measures is to establish a correlation between the scope of the Agency's jurisdiction and its administrative and budgetary capacities. From the annual report of the Agency also comes the need to provide greater interconnection and interoperability of the Agency, as well as the effective implementation of the conclusions of the National Assembly in relation to the report of the Agency. The adoption of the Law on Financing Political Activities ("Official Gazette of RS", No. 43/11) the Republic of Serbia has significantly improved the legal framework in this area and fully implemented the recommendations of GRECO. The Anti-Corruption Agency, on May 31st 2013, presented the First report on the costs control of political entities - the election campaign after the elections in 2012. Implementation of the Law showed that the changes of certain legal provisions would lead to a better implementation in practice, and in particular the provisions concerning the obligation of the authorities responsible for the control of political actors. To this day there was not made ​​even one external audit of political entities, because they were not provided by law as compulsory subjects of the audit of the State Audit Institution (SAI). An additional problem in this area is the lack of the necessary capacity of authorities responsible for the control of funding. Mechanisms for the prevention and elimination of conflicts of interest in Serbia have been improved by adopting the Law on the Fight against Corruption ("Official Gazette of RS", no. 97/08, 53/10, 66/11 and 67/13), which governs the issue of conflicts of interest that applies only to officials performing public functions. For other employees in state bodies and organizations do not exist or exist only partial legal provisions to prevent conflicts of interest. Inconsistency of legislation in this area is described as the main obstacle in the annual report of the Anti-Corruption Agency in 2013. The lack of a coherent legal framework that would create the same mechanisms for the prevention and elimination of conflicts of interest for all employees in the public sector is hampering combating this phenomenon. Consequently, it is not sufficiently developed awareness of the concept of conflict of interest and methods to prevent at all levels. As the Republic of Serbia ratified international instruments which, among other things, regulate the issue of conflict of interest, it is necessary to take measures in order to harmonize legislation and the practical application of international standards. The UN Convention against Corruption obliges Member States to consider introducing a crime "Illicit enrichment" if it was in accordance with the Constitution and the fundamental principles of the national legal system. The criminal legislation of the Republic of Serbia still does not provide the alleged offense, given that it may be contrary to the fundamental principles of criminal law and the principles of individual responsibility of the offender. On the other hand, the Anti-corruption agency has the authority to monitor and control the reporting of assets and revenue of officials, and in the case of possible irregularities identified, there are no clear mechanisms for sanctioning. Control of assets and income is particularly important from the aspect of implementation of financial investigations and tracing criminal proceeds. National Anti-Corruption strategy for period 2013- 2018, identified the need for a comprehensive analysis of the institutional and legal framework for finding effective solutions for cases of illicit enrichment. The right of citizens to access to information of public importance has been established by the Law on Free Access to Information of Public Importance ("Off. Gazette of RS", no. 120/2004, 54/2007, 104/2009 and 36/2010). Despite the fact that the current law is based on high international standards of exercising the rights from the perspective of the ways to protect the rights, includes body, the number and nature of exceptions to the principle of free access to information and similar criteria, nine-year old practice of application of this law shows that it is necessary to improve. While there are many positive examples of the implementation of the law, in practice it is observed a certain degree of inconsistency in the so-called sensitive cases, which are mostly related to public procurement, privatization, public spending, and so on. The National Anti-Corruption Strategy in Serbia in the period 2013 - 2018 and the Action Plan recognize the need to improve the law and to expand the powers and resources available to the Commissioner for Information of Public Importance and Personal Data Protection (the Commissioner). From the standpoint of the legal framework for the exercise of the right of access to information, it is important that the Government, on the initiative of the Commissioner, through the amendment of the Government’s Rules of Procedure, determined the liability of public authorities to obtain the opinion of competent institutions in the process of adopting regulations and through the amendment of the Rules of the obligation of public debate in drafting laws, enabled the availability of materials and information to the public. One of the main goals of the previous Public Administration Reform Strategy for the period 2004 - 2013 was the professionalization and de-politicization of public administration. In this field a little progress was made, which is the reason why Public Administration Reform Strategy in Serbia, adopted in February 2014, provides a continuation of the ongoing reform activities and extends them with the system of state administration in the public administration system. The two key objectives of the new strategy relating to the de-politicization of public administration were the establishment of a harmonized public service system based on merit and promotion of human resource management, and the strengthening of transparency, ethics and accountability in the performance of public administration. It is planned that the results achieved in this area by introducing civil service system based on the principles of politicization, professionalization, as well as a model of progress and reward according to merit (merit system). Special attention is given to clearly and precisely define the requirements and criteria for candidate selection and promotion, especially in the case of managerial jobs, ie. position. In the area of control mechanisms, regulations on internal audit and financial management and control are aligned with international standards, Central Harmonization Unit continued to direct the technical activities, in particular training and certification of internal audit. Positive legal framework of the Republic of Serbia does not provide adequate protection for persons who, due to report on suspicions of corruption or any other illegal actions, suffer some consequences and often the ones that affect their employment status. In accordance with previous reports on the progress of the Republic of Serbia in the process of European integration, while keeping in mind the United Nations Convention against Corruption, in response to perceived shortcomings of the existing system of protection, the National Anti-Corruption Strategy for the period 2013 - 2018, and the related Action Plan stipulated the obligation enactment of a comprehensive law to regulate the issue of the protection of whistleblowers. The main aim of the law should be to establish an efficient and effective protection of whistleblowers. In addition to establishing an adequate legal framework envisages a series of measures for the effective implementation of regulations in practice and raise awareness about the importance of and how to protect whistleblowers. The Law on Public Procurement ("Official Gazette" No. 124/12, as follows: PPL) predicted a series of measures to strengthen control and supervision over its implementation. There are special provisions on the prevention of corruption and conflict of interest, as well as greater transparency in public procurement procedures. The Public Procurement Office (PPO) and the Republic Commission for the Protection of Rights in Public Procurement Procedures (RK), were given new powers and greater authority. PPO supervise the implementation of the Law on Public Procurement. In order to prevent un-reasoned application of the negotiation procedure without a prior public call introduced an obligation to obtain the prior opinion of the PPO. It is introduced that the PPO and the State Audit institution (DRI) monitor procurement plans and the merits of changes to public procurement contracts. It is prescribed a longer statute of limitations violations of Public Procurement (3 years). PPO has received authorization for initiating misdemeanor proceedings, while the RK responsible for prosecution in the first degree. Both institutions are responsible for initiating the procedure for the determination of the void of the public procurement contract. RK in cases prescribed by law terminates public procurement contract, impose fines and decides on prohibition of misusage of right to petition for protection of the right. A key problem during the past year of implementing the new system of supervision and control of the implementation of the Law on Public Procurement is the limited administrative capacity of PPO, above all in terms of personnel. It is also necessary to analyze the effects of all mechanisms of supervision and control, and in accordance with the findings of the analysis make changes through amendments to the Public Procurement Law, as well as make recommendations in respect of other legislation. Cooperation between the institutions in the system of supervision and control is significantly improved from the beginning of implementation of the Law on Public Procurement on April 1st 2013, but it is necessary to work on its further improvement. The National Anti-Corruption Strategy for the period from 2013 to 2018 recognized the high risk of corruption in privatization and generally in the private sector. Action plan for the implementation of the Strategy provides for amendment of the legal framework so as to eliminate the risks of corruption in the regulations governing the process and control over privatization, reorganization and bankruptcy of state and social capital. Apart from changes of the legal framework, it is necessary to establish a system of effective implementation and control of the implementation of the legislation in the field of privatization. Serbian Chamber of Commerce, as part of the activities of implementation of the strategy, supports and promotes good practices of companies that have adopted Integrity plans, Code of Business Ethics, Rules of the International Chamber of Commerce for the fight against corruption, etc. The National Anti-Corruption Strategy for the period from 2013 to 2018, and the accompanying Action Plan provide a range of concrete measures against corruption in the fields of health, tax, education, police, customs and local self-government. However, the practical implementation of planned measures shall represent an indicator of progress in the fight against corruption in these particularly high-risk areas. Therefore, it is necessary to collect relevant data on the extent and manner of implementation of the measures envisaged in order to determine their effect and anticipate next steps for continuing the fight against corruption in high-risk areas. A large part of the necessary reforms is related to the establishment of an appropriate legal, institutional and administrative framework. Upon the establishment of the above key foundations for the fight against corruption in high-risk areas, relevant indicator of progress will be consistent implementation of the established mechanisms in practice. Article 55 of the Constitution guarantees freedom of political, union or any other association and the right to stay out of any associations, and associations are established without prior approval, by registration in the register kept by the state authority in accordance with the law. In this regard, in January 2011, the Government established the Office for Cooperation with Civil Society Organizations (Office) to support the development of civil dialogue between government institutions and civil society organizations in the process of the reform of the institutions and society in general. The importance and the role of the Office are reflected, inter alia, in the establishment of clear standards and procedures for the involvement of civil society at all levels of decision-making. In recent years, civil society has been very active in monitoring and evaluating the work of public authorities in this field, through public hearings, conferences, round tables and debates organized by various civil society organizations and government institutions. In terms of the development of the National Anti-Corruption Strategy from 2013 to 2018, and the accompanying Action Plan, representatives of civil society organizations were involved in all phases of the aforementioned acts, which have been contributed by their comments, suggestions and proposals. This has resulted in the adoption of the strategic objectives relating to the creation of conditions for active participation of civil society in the fight against corruption. The chapter on criminal offenses against the economy of the Criminal Code of Serbia ("Official Gazette of RS", no. 85/2005, 88/2005, 107/2005, 72/2009, 111 / 2009.121 / 2012 and 104/2013) is harmonized to a great extent with the Criminal Law Convention on Corruption, the UN Convention against corruption, the Convention on the fight against corruption of foreign officials in international transactions and other international instruments. The GRECO report on Serbia’s compliance with the recommendations analyzed the criminal offenses of corruption in the third round of evaluation and offered five recommendations for improvement. Additional report on implementation has been sent to GRECO Secretariat and the report on the implementation of recommendations is expected by the end of 2014. However, there is a need to fully align the chapter on criminal offenses against the economy of the Criminal Code with international instruments. In addition, new methods of performing economic crimes require modernization and improvement of criminalization in national legislation. This need has been recognized in the National Anti-Corruption Strategy for the period from 2013 to 2018, and the accompanying Action Plan, providing for the improvement of economic and corruption offenses in the Criminal Code. A developed efficient and proactive action in detecting and prosecuting corruption and organized crime represent the basis of the repressive action against these phenomena. The key prerequisites for effective acting involve independent competent institutions, adequate staffing, effective horizontal and vertical cooperation established and exchange of information between the police, public prosecutors, courts and other state bodies and institutions. The need for cooperation with national and European institutions and organizations, as well as other international organizations (Eurojust, OLAF, GRECO, OECD, etc.) is particularly emphasized. With the entry into force of the new Criminal Procedure Code ("Official Gazette of RS", no. 72/11, 101/11, 121/12, 32/13, 45/13 and 55/2014), in all public prosecutors’ offices, of general and special competence, the prosecution has obtained a leading role in obtaining evidence and their presentation in court. Certain results have been achieved in practice; however, further progress is necessary particularly in cases of high level corruption. Improving financial investigations is one of the prerequisites for achieving significant results in practice, in addition to strengthening the independence and mutual information exchange between relevant authorities. (See further chapter 24, subchapter fight against organized crime.) Privatization process in Serbia has proved to be one of the most critical areas of corruption. The report of the Anti-Corruption Council and many other indicators point to a number of irregularities that have occurred due to a series of inaccuracies and non-transparency of the privatization legislation. Such vagueness of regulations has created numerous opportunities for abuse. In addition, many of the privatization contracts contain violations of the equivalence of benefits, which was enabled by inadequate control, both in terms of performance of the contract, and in the exercise of powers of the Director of the Privatization Agency. The National Anti-Corruption Strategy in the period from 2013 to 2018 provides a number of measures to prevent corruption in the privatization process. They can be grouped into two categories: changes of the corruptive provisions of the rules and improvement of the conduct of the competent authorities in the detection and prosecution of criminal offenses in the privatization process. New Law on Privatization ("Official Gazette of RS" No. 83/2014) was adopted in order to improve the legal provisions of the privatization process and eliminate the deficiencies that have led to numerous abuses. The adoption of the new law represents the beginning of implementation of the Action Plan for implementation of the Strategy, which provides a number of other measures to improve these areas. In the Republic of Serbia, the police, prosecution and courts use different systems for monitoring criminal cases. In practice, such an approach creates a number of problems. The police keep statistical records according to the number of reported crimes; the prosecution according to the number of reported persons; whereas the court statistics is kept according to the number of cases. Such record keeping is not suitable for measuring the progress and the level of efficiency of the criminal justice system, neither for setting up criminal policy. The goal of establishing a unique records keeping system or an electronic record for criminal offenses with elements of corruption is, inter alia, the precise systematization and classification of data as well as regular control and information exchange. One of the tasks this information system has to correspond to is to establish a uniform system of reporting on corruption and organized crime. By achieving this goal, the Ministry of Justice shall have the ability to produce reliable annual report on cases with elements of corruption, which contain all the relevant information about the course of the investigation, the progress of the criminal proceedings and their outcome. Mutually compatible forms in the police, courts and prosecutors’ offices should also include the possibility of monitoring cases of proactive conduct, acting upon the reports of the Agency, State Audit Institution, Tax Administration, and Administration for public procurement, etc. The legal framework for conducting financial investigations and tracing criminal proceeds is regulated by the Law on Seizure and Confiscation of the Proceeds from Crime ("Official Gazette of RS", no. 32/2013). Also, the Criminal Procedure Code ("Official Gazette of RS", no. 72/2011, 101/2011, 121/2012, 32/2013, 45/2013 and 55/2014) provides for special investigative techniques that are used to facilitate tracking of the proceeds from crime. Competent authority for the implementation of financial investigation is the Financial Investigation Unit, responsible for financial investigation at the Ministry of Interior, while the Directorate for Administration of Seized Assets is responsible for the management of seized assets within the Ministry of Justice. The National Anti-Corruption Strategy for the period of 2013-2018, provides for measures to improve the implementation of financial investigations and management of seized assets. It is necessary, inter alia, to improve the efficiency of relevant institutions, records keeping and information exchange at the national and international level. Pursuant to the Constitution of the Republic of Serbia, the following categories of persons shall enjoy immunity: MPs, the President of the Republic, the President and members of the Government, the judges of the Constitutional Court, judges, public prosecutors and deputy public prosecutors, the Ombudsman, members of the High Judicial Council and State Prosecutorial Council. Parliamentary immunity includes substantive immunity (immunity from liability and the procedural immunity. A judge may not be detained in proceedings instituted for a criminal offense committed in the performance of judicial functions without the approval of the High Judicial Council. Member of High Judicial Council shall enjoy immunity as a judge. A public prosecutor and deputy public prosecutor cannot be held responsible for the opinions expressed in the exercise of prosecutorial functions, unless it is a criminal offense of violating the law by the public prosecutor or deputy public prosecutor. A public prosecutor and deputy public prosecutor may not be deprived of liberty in proceedings instituted for a criminal offense committed in the exercise of prosecutorial function or service, without the approval of the competent committee of the National Assembly. Member of the State Prosecutorial Council shall enjoy immunity as a prosecutor. A judge of the Constitutional Court shall enjoy immunity as a deputy. The Constitutional Court decides on his/her immunity. The Republic of Serbia has a legal framework that guarantees a wide range of public access to information of public importance, which is a fundamental right in a democratic society. The implementation of regulations in this area, in connection with the respect of the right to personal data protection and the presumption of innocence, still represents a challenge. Exposure of the details of investigations based on anonymous sources of information that was "leaked" from police action or criminal prosecution, may jeopardize the investigation, undermine the presumption of innocence and violate the right to privacy. In such cases, the absence of adequate response against persons who have exposed sensitive and confidential information from the investigation is notable. The aim of the regulations on personal data protection is the protection of fundamental human rights, which requires that the information can only be obtained in accordance with the law - under strict conditions and for the purposes defined by law. Therefore, it is necessary to strengthen internal control mechanisms and sanctioning to prevent the disclosure of confidential information to the media. Practical implementation of the planned measures shall represent an indicator of progress in the fight against corruption. Therefore, it is necessary to collect relevant data on the extent and methods of implementation of the envisaged measures in order to determine their effect and anticipate next steps for systematic fight against corruption in high-risk areas. A large part of the necessary reforms relates to the establishment of an appropriate legal, institutional and administrative framework. Upon the establishment of the above key grounds for the fight against corruption in high-risk areas, the relevant indicator of progress will be consistent application of established mechanisms in practice. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.IMPLEMENTATION OF ANTI-CORRUPTION MEASURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.1.1. Broaden the political and institutional ownership, including high level coordination, of the fight against corruption and identify clear high level institutional leadership in the implementation of the anti-corruption strategy in particular; |  |  |  |  |  | Coordination of implementation of anti-corruption measures established at the highest political level, along with political and institutional accountability of high level institutional leadership for the implementation of strategic measures in the fight against corruption. |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia; - Degree of implementation of measures and activities from the Action Plans, based on the report of the Anti-Corruption Agency; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.1.1.1. | Amending the Decision which established the Coordination Body for the implementation of the Action Plan for the Implementation of the National Anti-Corruption Strategy in the Republic of Serbia in the period 2013- 2018 by extending the competencies of the Government’s Coordination Body to the coordination of implementation of this Action Plan for Chapter 23, Subchapter fight against corruption. |  |  | -Government of the Republic of Serbia -Ministry of Justice (State secretary in charge of anti corruption) |  | IV quarter of 2014. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Decision on extension of competencies of Coordination Body for implementation of National Anti-Corruption Strategy adopted. |  |  |  |  |  |
| 2.1.1.2. | Organizing regular bi-annual meetings of the Coordination Body, presided by the Prime Minister (political level), quarterly and bilateral meetings, presided by the State Secretary of the Ministry of Justice (political and technical level, Group for coordination of the implementation of the National Anti-Corruption Strategy) in order to monitor implementation of the obligations stipulated in the Action plans. Meetings of the coordination bodies are open to the public and participation of civil society organizations. |  |  | -Ministry of Justice (State secretary in charge of anti- corruption) -Group for Coordination of the implementation of the National Anti-Corruption Strategy |  | Continuously |  | Budget of the Republic of Serbia 30.878 € In 2014 - 6.176 € In 2015 - 6.176 € In 2016 - 6.176 € In 2017 - 6.176 € In 2018 - 6.176 € |  | Publishing of reports from meetings of the Coordination Body on the website of Ministry of Justice. Reports of Anti-Corruption Agency on the monitoring the implementation of the National Anti-corruption Strategy for period 2013-2018 reviewed. |  |  |  |  |  |
| 2.1.1.3. | Strengthening of capacities of the Group for coordination of the implementation of the National Anti-Corruption Strategy, in accordance with previously prepared Needs Assessment. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) |  | IV quarter of 2015. |  | Budget of the Republic of Serbia, 31.913 € In 2016 - 10.638 € In 2017 - 10.638 € In 2018 - 10.638 € |  | Report on Needs Assessment. In accordance with Needs Assessment, capacities of the Group for coordination of the implementation of the National Anti- Corruption Strategy strengthened. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| - Ensure systematic consideration of the recommendations of the Anti-Corruption Council; |  |  |  |  |  | Systematic consideration of the recommendations of the Anti-Corruption Council ensured; |  |  |  | - Number of reviewed recommendations (stated in Annual report on work of Anti-Corruption Council) which have been taken into consideration by the Government and other competent state authorities during implementation of measures in the field of fight against corruption; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.1.2.1. | Government includes all reports of Anti-Corruption Council and reviews reports as part of daily agenda. |  |  | -Government of the Republic of Serbia |  | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Records from Government’s sessions adopted. |  |  |  |  |  |
| 2.1.2.2. | Inclusion of Anti-Corruption Council in legislative procedure concerning regulations which, according to Council’s assessment, bear a risk of corruption. Members of the Council are required to take active participation in the operation of working groups as members or observers. |  |  | - Authorized proposing authorities of laws |  | Continuously. |  | Budget of the Republic of Serbia, 43.211 € In 2014 - 8.642 € In 2015 - 8.642 € In 2016 - 8.642 € In 2017 - 8.642 € In 2018 - 8.642 € |  | Council takes active participation in legislative procedure. |  |  |  |  |  |
| 2.1.2.3. | The Republic Public Prosecutor's Office draws up annual reports on conduction of activities in compliance with reports of Anti-Corruption Council and submits reports to the Government. |  |  | -The Republic Public Prosecutor’s Office -Government of the Republic of Serbia |  | Continuously. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | The Republic Public Prosecutor's Office drawn up annual reports on conduction of activities in compliance with reports of Anti-Corruption Council and submitted reports to the Government. |  |  |  |  |  |
| 2.1.2.4. | Strengthening budgetary and staff capacities of Anti-Corruption Council. |  |  | -Government of the Republic of Serbia |  | I quarter of 2015. |  | Budget of the Republic of Serbia 127.650 € In 2015 - 31.913 € In 2016 - 31.913 € In 2017 - 31.913 € In 2018 - 31.913 € |  | Government issued decree on appointment of members of Anti-Corruption Council issued. Higher degree of administrative support of General Secretariat of the Government. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.1.3. Ensure legal alignment with the EU Acquis - including as regards the definitions of active and passive corruption – and with the UN Convention against Corruption (UNCAC); |  |  |  |  |  | Ensured legal alignment with the EU Acquis and UNCAC in field of fight against corruption including as regards the definitions of active and passive corruption. |  |  |  | - Positive opinion of European Commission stated in annual progress report on Serbia; - GRECO reports on evaluation; - Reports of UN Office on Drugs and Crime on compatibility with UNCAC. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.1.3.1. | Conduct comprehensive analysis of compatibility of anti-corruption legislation with EU Acquis and international standards in order to identify deficiencies of legal framework of fight against corruption. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) |  | IV quarter of 2015. |  | Total- 4.030.878 € Budget of the Republic of Serbia -30.878 € In 2015 IPA 2013 Total - 4.000.000 € In 2015 1.600.000€ In 2016 -1.600.000€ In 2017 - 800.000 € |  | Analysis conducted. |  |  |  |  |  |
| 2.1.3.2. | Adopt amendments and supplements to legal framework of fight against corruption in line with the comprehensive analysis of compatibility of anti-corruption legislation with EU Acquis and international standards in order to identify deficiencies of legal framework of fight against corruption from item 2.1.3.1. and in line with identified deficiencies. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) - National Assembly |  | IV quarter of 2016 |  | Total - 32.628 € Budget of the Republic of Serbia - 30.878 €, TAIEX- 1.750 € In 2016 |  | Amendments and supplements to the law adopted. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.1.4. Clarify the co-ordination and co-operation between the different actors in charge of implementing and monitoring the action plan |  |  |  |  |  | Different factors in charge of implementation and monitoring of the implementation of the Action plan comprehend their role in relation to implementation and monitoring of implementation of the Action plan. |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia; - Degree of implementation of measures and activities from Action plans, based on the report of the Anti-Corruption Agency. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.1.4.1. | Adoption of amendments and supplements to the Law on the National Assembly in order to introduce obligation of the Government to submit (at least once a year) report on implementation of National Assembly’s conclusions which have been adopted upon taking into consideration of the reports of the Agency. Government is required to submit the aforementioned reports within the 6 months following the adoption of the aforementioned conclusions by National Assembly whereas National Assembly is required to review the Government’s report at the session. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) - National Assembly |  | I quarter of 2015. |  | Budget of the Republic of Serbia- 48.650 € In 2015. |  | Adopted Law on amendments and supplements to the Law on National Assembly. |  |  |  |  |  |
| 2.1.4.2. | Adopt amendments and supplements to Law on Anti-Corruption Agency introducing the following: - report on implementation of the Strategy has to be submitted separately from annual report on work of Agency -stakeholders from Action plan are required to submit to the Agency: A) bi-annual reports on implementation and B) documentation which prove that activities from Action plan are implemented -entitlement of Agency to require data from stakeholders and, if necessary, to require oral argumentation from stakeholders in relation to submitted data - entitlement of Agency with the right to submit opinion concerning implementation of Strategy and Action plan to stakeholders or state authority that elected and appointed manager of the stakeholder -Proscribing misdemeanor- if liable person in the stakeholder does not submit report or if, without good reason, does not comply with Agency’s request for oral arguments concerning additional data. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) - National Assembly |  | IV quarter of 2014. |  | Budget of the Republic of Serbia 48.650 € In 2014. |  | Adopted law amending Law on Anti-Corruption Agency. . |  |  |  |  |  |
| 2.1.4.3. | Draw up Rules of Procedures for implementation of Action plan for implementation of National Anti-corruption Strategy for period 2013-2018. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) |  | I quarter of 2015. |  | Budget of the Republic of Serbia 1.000 € In 2015. |  | Drawn up Rules of Procedures for implementation of Action plan for implementation of National Anti-corruption Strategy for period 2013-2018. |  |  |  |  |  |
| 2.2. PREVENTION OF CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| - Clarify the mandate of ACA ensuring that its staffing level matches the tasks it is asked to perform. Further improve its efficiency through and amended legal basis and strengthen its administrative capacity, allowing it to better perform its coordinating role inter alia by ensuring that it is better connected, including through databases, to various agencies and that its reports, complaints and recommendations receive an adequate follow up; ensure effective and operational monitoring mechanisms |  |  |  |  |  | Improved efficiency of Anti-corruption Agency in exercising its competencies through an amended legal basis, strengthen its administrative capacity and ensured better connectivity to various agencies and state authorities. |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia; - Annual report on work of Anti-Corruption Agency; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.1.1. | Amend the Law on Anti-corruption Agency based on the performed analysis on the Anti-Corruption Agency’s competencies in order to ensure Agency’s efficiency in dealing with: - assets declaration and incomes of public office holders -prevention of conflict of interest -control of financing the political activities -supervision over implementation of integrity plans and -supervision over implementation of Strategy and Action plan. |  |  | - Anti-Corruption Agency (Director) - National Assembly |  | I quarter of 2015. |  | Budget of the Republic of Serbia -55.697 € In 2015. IPA 2013 (Budgeted in activity 1.2.2.1) |  | Adopted law which amends Law on Anti-Corruption Agency based on the results of the conducted analysis on competencies of Anti-Corruption Agency. |  |  |  |  |  |
| 2.2.1.2. | Conduct midterm analysis of the competencies of the Anti-Corruption Agency in order to ensure Agency’s efficiency in dealing with: - assets declaration and incomes of public office holders -prevention of conflict of interest -control of financing the political activities -supervision over implementation of integrity plans and -supervision over implementation of Strategy and Action plan |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -With the participation of Civil Society Organizations |  | II quarter of 2015 |  | Total- 10.392 € Budget of the Republic of Serbia- 8.642 €, TAIEX- 1.750 € In 2015. |  | Midterm analysis of the competencies of the Anti-Corruption Agency conducted. . |  |  |  |  |  |
| 2.2.1.3. | Monitoring the implementation of Law of Anti-Corruption Agency and acting of all state bodies in line with the report of the Agency. |  |  | -Ministry of Justice (State secretary in charge of corruption) -Anti-Corruption Agency |  | Continuously |  | Budget of the Republic of Serbia 1.064 € In 2014 - 213 € In 2015 - 213 € In 2016 - 213 € In 2017 - 213 € In 2018 - 213 € |  | Annual report on implementation of Law published on the web page of the Ministry of Justice. Annual report on operation of Anti-Corruption Agency. Report on progress of the Republic of Serbia issued by European Commission. |  |  |  |  |  |
| 2.2.1.4. | Strengthening staff capacities of Anti-Corruption Agency, based on previously conducted analysis of current staff capacities, in particular concerning: -organizational capacities -number of employees -degree of competence in order to align it with the competencies proscribed in Law of amendments and supplements to the Anti-Corruption Agency. The same activity under 1.2.2.6. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Ministry of Finance (State secretary in charge of anti-corruption) -Anti-Corruption Agency’s Board for fight against corruption (Director, Deputy Director) |  | For analysis: II quarter of 2016 For acting according to analysis: IV quarter of 2017 |  | Budget of the Republic of Serbia Currently unknown IPA 2013 Budgeted in activity 2.1.3.1 |  | Analysis conducted. Amended Rules on internal organization and systematization of jobs in Anti-Corruption Agency. Vacancies filled in accordance with amended Rules. |  |  |  |  |  |
| 2.2.1.5. | Interconnectedness of data bases for criminal investigations ensured i.e. secured system for electronic exchange of information between public prosecutors’ offices, police, Customs administration, Anti-Corruption Agency and other relevant state authorities which have data bases of high importance for anti-corruption prevention. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Anti-Corruption Agency |  | IV quarter of 2016. |  | Budget of the Republic of Serbia8.642 €, In 2016. IPA 2013 Budgeted in activity 2.1.3.1. |  | Interconnectedness of data bases ensured. |  |  |  |  |  |
| 2.2.1.6. | Conduct mandatory introductory training of new employees in Anti-Corruption Agency, as well as training of current employees concerning new legislative solutions and operational mechanisms. |  |  | -Anti-Corruption Agency |  | One year from entering into force of law amending Law on Anti-Corruption Agency. |  | IPA 2013 twinning Total - 2.000.000 € In 2016 –800.000 € In 2017 –800.000 € In 2018 –400.000 € |  | Conducted education of employees in Anti-Corruption Agency concerning new legislative solutions and operative mechanisms. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.2. Ensure an effective implementation of the legislation on the control of political party financing and the financing of electoral campaigns, in particular by issuing effective sanctions in cases of failures to report and proven irregularities; |  |  |  |  |  | Law on control of financing of political activities is implemented efficiently in particular in part dealing with implementation of sanctions for conduction not complying with provisions of the law. |  |  |  | 1.Positive opinion of European Commission on progress of Serbia; 2.Report on control of political activities issued by Anti-Corruption Agency; 3.Number of initiated and finalized misdemeanor procedures and other proceedings; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.2.1. | Quality analysis of implementation of Law on financing of political activities in particular measures which sanction noncompliance with the Law: -number of filed misdemeanour charges -number of decisions of misdemeanour courts (adjourn the case, final) -conduction of misdemeanour courts, Anti-Corruption Agency |  |  | -Ministry of Justice (State secretary) -Anti-Corruption Agency’s Board for fight against corruption (Director, Deputy Director) -Misdemeanour court (President) |  | I quarter of 2015. |  | IPA 2013, twinning Budgeted in activity 2.2.1.6. |  | Report on conducted analysis. |  |  |  |  |  |
| 2.2.2.2. | Adoption of amendments and supplements to Law on Financing of Political Activities in order to clarify and separate duties of Agency, State Audit Institution and other relevant state authorities in the process of control of political activities and subjects in order to clarify duties and mechanisms for transparency of financing of political subjects in accordance with quality analysis on implementation of Law on Financing of Political Activities from item 2.2.2.1. |  |  | -Ministry of Finance (State secretary) -Participation of Civil Society Organizations -National Assembly |  | IV quarter of 2015. |  | Budget of the Republic of Serbia- 48.900 € In 2016. IPA 2013, twinning Budgeted in activity 2.2.1.6. |  | Adopted amendments and supplements to Law on Financing of Political Activities. |  |  |  |  |  |
| 2.2.2.3. | Proscribe in the program of revision compulsory revision of parliamentary political parties on the republic level and introduction of duty of director of Tax administration to state donors of financial resources and other services to political subjects, in annual or extraordinary plan of tax control, in compliance with report of Agency on financing political activities and subjects. |  |  | -Ministry of Finance (State secretary) -National Assembly |  | III quarter of 2016. |  | Budget of the Republic of Serbia 48.900 € In 2016. |  | Adopted amendments and supplements to Law on Financing of Political Activities. |  |  |  |  |  |
| 2.2.2.4. | Monitoring of implementation of Law on Financing Political Activities. |  |  | -Ministry of Finance (State secretary) -Anti-Corruption Agency |  | Continuously, commencing from 2016. |  | Budget of the Republic of Serbia 638 € In 2016 - 213 € In 2017 - 213 € In 2018 - 213 € |  | Annual report published on Ministry of Finance’s web page. Report of Anti-Corruption Agency on financing of political activities and election campaign. |  |  |  |  |  |
| 2.2.2.5. | Strengthening the capacities of Anti-Corruption Agency for process of control of financing political activities, based on the analysis from item 2.2.1.2. of Action plan, and with consent of Ministry of Finance Linked with activity 2.2.1.4. of Action plan. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Ministry of Finance (State secretary in charge of anti-corruption) -Anti-Corruption Agency’s Board for fight against corruption (Director, Deputy Director) |  | For analysis: II quarter of 2016 For acting according to analysis: IV quarter of 2017 |  | Budget of the Republic of Serbia, Currently unknown |  | Amended Rules on internal organization and systematization of vacancies in Anti-Corruption Agency in line with the analysis from item 2.2.1.1. and 2.2.1.1. Vacancies filled. |  |  |  |  |  |
| 2.2.2.6. | With approval of the Ministry of Finance, strengthening of staff capacities of State Audit Institution in order to efficiently conduct revision of parliamentary political parties, based on previously conducted analysis of capacities in particular concerning organizational structure, number of employees, degree of competence. |  |  | -Ministry of Finance (State secretary in charge of anti-corruption) |  | II quarter of 2016 |  | Budget of the Republic of Serbia Currently unknown |  | Amended Rules on internal organization and systematization of vacancies in line with the analysis. Vacancies filled. |  |  |  |  |  |
| 2.2.2.7. | Establishing mechanisms of continuous education and providing information to the political entities obliged to act in accordance with the Law on the Financing Political Activities. |  |  | -Anti-Corruption Agency (Director, Deputy Director) |  | One year from entering into force of Law amending Law on financing of political activities. |  | Budget of the Republic of Serbia IPA 2013, twinning Budgeted in activity 2.2.1.6. |  | Education and informing of political subjects (which are obliged to operate in accordance with Law on financing of political activities) conducted. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.3. Improve the legal and administrative framework to prevent and deal with conflicts of interest. Ensure the concept is well understood at all levels; |  |  |  |  |  | The legal and administrative framework to prevent and deal with conflicts of interest improved. Ensured that the concept is well understood at all levels. |  |  |  | - Positive opinion of European Commission on progress of Serbia; - Annual report on operation of Anti-Corruption Agency; - Number of initiated and finalized misdemeanor and other proceedings; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.3.1. | Conduct midterm analysis of Anti-Corruption Agency’s competencies in order to ensure Agency’s efficiency in dealing with: - assets declaration and incomes of public office holders -prevention of conflict of interest -control of financing the political activities -supervision over implementation of integrity plans and -supervision over implementation of Strategy and Action plan (Measure from item 2.2.1.1. of Action plan). |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Anti-Corruption Agency (Director) |  | II quarter 2015. |  | Budget of the Republic of Serbia - TAIEX- Budgeted in activity 2.2.1.2. In 2015. |  | Analysis of competencies of Anti-Corruption Agency conducted. |  |  |  |  |  |
| 2.2.3.2. | Amending Law on Anti-Corruption Agency in accordance with conducted analysis. The same activity under item 2.2.1.1. |  |  | - Anti-Corruption Agency -Participation of Civil Society Organizations - National Assembly |  | I quarter of 2015. |  | Budget of the Republic of Serbia TAIEX Budgeted in activity 2.2.1.1. |  | Adopted Law on amendments and supplements to the Law on Anti-Corruption Agency. |  |  |  |  |  |
| 2.2.3.3. | Conducting professional education of employees in Sector for preventing conflict of interest in Anti-Corruption Agency concerning amendments and supplements to the Law on conflict of interest. Coordinate activity with item 2.2.1.6. |  |  | -Anti-Corruption Agency, Sector for preventing conflict of interests |  | I quarter of 2015 (concurrently with the amendments to the Law) |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Education conducted. |  |  |  |  |  |
| 2.2.3.4. | Conduct Feasibility study on regulation of legal framework for prevention of conflict of interest in public administration. |  |  | -Ministry of Public Administration and Local-Self-government (State secretary) |  | IV quarter of 2015. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Conducted Feasibility study |  |  |  |  |  |
| 2.2.3.5. | Regulate by law prevention of conflict of interest of employees in public administration, based on the results of Feasibility study from item 2.2.3.4. |  |  | -Ministry of Public Administration and Local-Self-government (State secretary) -Participation of Civil Society Organizations - National Assembly |  | IV quarter of 2016. |  | Budget of the Republic of Serbia 55.697 €, In 2016. |  | Adopted law that regulates prevention of conflict of interest of employees in public administration, based on the results of analysis. |  |  |  |  |  |
| 2.2.3.6. | Monitoring implementation of legal provisions concerning prevention of conflict of interests of employees in public administration from item 2.2.3.5. |  |  | -Ministry of Public Administration and Local-Self-government (State secretary) |  | Continuously, commencing from entering into force of provisions of law from item 2.2.3.5. |  | Budget of the Republic of Serbia 426 € In 2017 - 213 € In 2018 - 213 € |  | Published annual report on web page of Ministry of Public Administration and Local-Self-government |  |  |  |  |  |
| 2.2.3.7. | Conduct professional education in public administration in connection to issues of prevention of conflict of interests. |  |  | -Ministry of Public Administration and Local-Self-government (State secretary) |  | Continuously, commencing from entering into force of provisions of law from item 2.2.3.5. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Conducted professional education in public administration in connection to issues of prevention of conflict of interests. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.4.Look into and adequate and institutional solution to effectively address cases of illicit enrichment; |  |  |  |  |  | Cases of illicit enrichment are efficiently resolved according to adequate legal and institutional framework. |  |  |  | - Positive opinion by European Commission on Serbia’s progress - Number of initiated and finalized misdemeanor and other procedures. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.4.1. | Conduct analysis of legal and institutional framework in order to clarify ramifications of „illicit enrichment“ (criminal, administrative or misdemeanor ramifications) and based on the results of the analysis revise the current regulations or adopt new |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Anti-Corruption Agency (Director) - Ministry of Finance (State secretary in charge of anti-corruption) - National Assembly |  | II quarter of 2016. |  | Budget of the Republic of Serbia 57.542 €, In 2016. IPA 2013 Budgeted in activity 2.1.3.1. |  | Conducted analysis of legal and institutional framework in order to clarify ramifications of „illicit enrichment“ (criminal, administrative or misdemeanor ramifications)and based on the results of the analysis current regulations revised or new adopted. |  |  |  |  |  |
| 2.2.4.2. | Monitoring implementation of amended law from item 2.2.4.1. along with obligation of courts and public prosecutors’ offices of general and special jurisdiction, to deliver reports on number of initiated and completed proceedings. Ministry of Justice draws up uniform report and publishes it on the web page. |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) |  | Continuously, commencing from entering into force of law from item 2.2.4.1. |  | Budget of the Republic of Serbia, 426 €, In 2017 - 213 € In 2018 - 213 € |  | Prepared and published report on the web page of the Ministry of Justice. Annual report of Anti-Corruption Agency. |  |  |  |  |  |
| 2.2.4.3. | Training of all competent state authorities in accordance with published analysis and amendments to the law from item 2.2.4.1. Police Prosecutor's office Courts Anti- corruption Agency |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Ministry of Finance (State secretary in charge of anti-corruption) -Judicial Academy (Director) |  | Continuously, commencing from entering into force of law from item 2.2.4.1. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Conducted trainings of all competent state authorities in accordance with published analysis and amendments to the law from item 2.2.4.1 |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.5. Improve the free access to information rules and their practical implementation, inter alia, with regard to information on privatization deals, public procurement, public expenditures or donations from abroad to political parties, including as regards information considered 'sensitive'; |  |  |  |  |  | Regulation in the field of free access to information are improved, their implementation is improved, inter alia, in regards to privatization, public procurement, public expenditures and donations from abroad to political subjects. |  |  |  | - Positive opinion on progress of Serbia issued by European Commission; - Number of initiated and finalized procedures before Commissioner; - Annual report on work of Commissioner; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.5.1. | Conduct analysis of implementation of Law on free access to information of public importance, to date in particular emphasizing the following areas: -privatization - public procurement -public expenditures -foreign donations to political subjects Capacity building of the Commissioner based on previously conducted analysis of current staff capacities in particular: -organizational structure -number of employees -degree of competencies; in order to harmonize it with competencies proscribed in Law on amendments and supplements to the Law on free access to information of public importance |  |  | -Commissioner for Information of Public Importance and Personal data Protection -Ministry of Justice (State secretary in charge of anti-corruption) -Ministry of Public Administration and Local-Self-government (State secretary) - Ministry of Finance (State secretary) |  | Analysis I quarter of 2015. Strengthening staff capacities: IV quarter of 2016. |  | Budget of the Republic of Serbia Analyses - 8.642 € In 2015. Strengthening staff capacities - cost currently unknown |  | Conducted analysis of implementation of Law on free access to information of public importance, to date. Vacancies filled in accordance with amended Rulebook. |  |  |  |  |  |
| 2.2.5.2. | Adopt amendments to Law on free access to information of public importance based on analysis of implementation of Law on free access to information of public importance to date, in particular emphasizing areas: -privatization - public procurement -public expenditures -foreign donations to political subjects conducted in item 2.2.5.1. |  |  | -Republic secretariat for legislature (Director) -Partner institution: - Commissioner for Information of Public Importance and Personal data Protection - National Assembly |  | IV quarter of 2015. |  | Total- 50.659 € Budget of the Republic of Serbia - 48.909 €, TAIEX- 1.750 € In 2015. |  | Adopted amendments to Law on free access to information of public importance and personal data protection. . |  |  |  |  |  |
| 2.2.5.3 | Monitoring of implementation of Law of free access to information of public importance |  |  | -Commissioner for Information of Public Importance and Personal data Protection |  | Continuously, commencing from 2016. |  | Budget of the Republic of Serbia - 638 € In 2016 - 231 € In 2017 - 231 € In 2018 - 231 € |  | Overview of current state in annual report issued by Commissioner for Information of Public Importance and Personal data Protection. |  |  |  |  |  |
| 2.2.5.4. | Conduct trainings for officials in charge of deciding on requests for free access to information, in accordance with case law and international standards |  |  | -Human resources -Commissioner for Information of Public Importance and Personal data Protection |  | Continuously |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Trainings conducted. |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.6.Take steps to depoliticize the public administration, to strengthen its transparency and integrity, including through strengthening internal control and audit bodies; |  |  |  |  |  | Public administration has been depoliticized and transparent, with strengthened integrity of public administration and internal control and audit bodies. |  |  |  | - Positive opinion of European Commission on Serbia’s progress; - Number of officials in public administration who are employed or promoted in accordance with merits system; - Percentage of state authorities which have internal audit body - Harmonized finance management to INTOSAI standards of internal control. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 2.2.6.1. | Conduct analysis of the system of accountability and transparency in the work of the public administration system and establish the direction of the development of civil service systems in public administration based on unique principles (depoliticization, professionalism, merits, etc.). |  |  | - Ministry of Public Administration and Local Self-government (state secretary in charge of anti-corruption) -CSOs participation |  | IV quarter of 2015. |  | Budget of the Republic of Serbia 30.878 €, In 2015. IPA 2013 Budgeted in activity 2.1.3.1. |  | Analysis conducted and principles in the work of the public administration system and the direction of the development of civil service systems in public administration established n based on unique principles (depoliticization, professionalism, merits, etc.). |  |  |  |  |  |
| 2.2.6.2. | Establish an objective and precise criteria for employment and promotion in the public sector in line with the principles of transparency and competitiveness pursuant to the analysis referred to under item 2.2.6.1. |  |  | - Ministry of Public Administration and Local Self-government (state secretary in charge of anti-corruption) -High Civil Service Council - Directorate for Human Resource Management -Civil Society Organization’s s participation |  | II quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 2.2.6.1. |  | Amendments and supplements to the law governing the status of civil servants and employees in various segments of the public administration adopted, according to the analysis referred to under item 2.2.6.1. |  |  |  |  |  |
| 2.2.6.3. | Implement transparent tender procedures for all of the civil servants holding position in the state administration. |  |  | - Ministry of Public Administration and Local Self-government (state secretary) |  | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Tender procedures implemented. |  |  |  |  |  |
| 2.2.6.4. | Develop mechanisms to monitor the implementation of the Code of Conduct for civil servants. |  |  | - High Civil Service Council -Ministry of Public Administration and Local Self-government (state secretary in charge of anti-corruption) |  | IV quarter of 2015. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Mechanisms to monitor the implementation of the Code of Conduct for civil servants developed. |  |  |  |  |  |
| 2.2.6.5. | Adopt the law governing the position of internal auditors and provide functional and operational independence of the internal audit and define the principles of financial management and controls, as well as the function, and positions at the Central Harmonization Unit. |  |  | - Ministry of Finance (state secretary) - National Assembly |  | IV quarter of 2016. |  | Budget of the Republic of Serbia 48.900 € In 2016. |  | Law governing the position of internal auditors adopted or amended. |  |  |  |  |  |
| 2.2.6.6. | Introduce program budgeting. |  |  | - Ministry of Finance (state secretary) |  | I quarter of 2015. |  | Budget of the Republic of Serbia Completed Activity requiring insignificant costs |  | Program budgeting introduced. |  |  |  |  |  |
| 2.2.6.7. | Strengthen staff capacities of the Central Harmonization Unit. |  |  | - Ministry of Finance (state secretary) |  | IV quarter of 2015. |  | Budget of the Republic of Serbia Currently unknown |  | Amended Rulebook on job classification Positions filled. |  |  |  |  |  |
| 2.2.6.8. | Increase the number of trained managers and employees in the public administration on the basis and importance of financial management and control, and increase the number of qualified internal auditors. |  |  | - Ministry of Finance (state secretary) |  | IV quarter of 2015. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Work plan of the Central Harmonization Unit. Reports on conducted training delivered. Number of newly trained managers and employees in the public administration and certified internal auditors in relation to 2013. |  |  |  |  |  |
| 2.2.6.9. | Establish the fund to enable postgraduate and vocational training and scholarships for employees in the public administration to participate in educational programs of the European universities and educational centers through the IPA 2013 project. |  |  | - Ministry of Public Administration and Local Self-government |  | IV quarter of 2015 – IV quarter of 2018. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Number of employees in the public administration participating in training. |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |
| 2.2.7.Adopt and implement the new law on whistle-blowing and take the necessary steps to make the system of whistle-blower protection more effective in practice; |  |  |  |  | Established new legal framework for protection of whistle-blowers and ensured its efficient implementation in practice. |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings for the protection of whistle-blowers; |  |  |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES |  | RESULT |  |  | IMPLEMENTATION STATUS |  |
| 2.2.7.1. |  | Adopt the law and bylaws on Whistle-blowers in line with international standards. | - Ministry of Justice (state secretary in charge of anti- corruption) -CSOs participation. - National Assembly |  | IV quarter of 2014. |  |  |  | Budget of the Republic of Serbia 71.386 € In 2014. |  | Law and bylaws on Whistle-blowers adopted in line with international standards. |  |  |  |  |
| 2.2.7.2. |  | Provide technical conditions for effective implementation of the Law on Whistle-blowers. | - Ministry of Justice (state secretary) -Partners: Ministry of Interior -Republic Public Prosecutors’ Office -Supreme Court of Cassation |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Technical conditions for effective implementation of the Law on whistle-blowers established. |  |  |  |  |
| 2.2.7.3. |  | Develop and implement a training program for the implementation of the Law on the protection of whistle blowers for judges acting in cases of protection of whistle-blowers Develop and implement a training program for the implementation of the Law on the protection of whistle blowers for employees in public administration. | -Judicial Academy - Ministry of Justice (state secretary in charge of anti- corruption) - High Civil Service Council |  | Training of judges: IV quarter of 2014. Training of employees in public administration: IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Training programs for judges and employees in public administration developed and implemented. |  |  |  |  |
| 2.2.7.4. |  | Conduct a campaign to raise awareness about the importance of whistle-blowers and use of channels for reporting illegal actions. | - Ministry of Justice (state secretary in charge of anti- corruption) |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Campaign conducted. |  |  |  |  |
| 2.2.7.5. |  | Monitor the implementation of the Law on whistle blowers through the preparation of the annual report of the ministry of justice made ​​on the basis of periodic reports of the competent authorities on cases of acting in relation to the whistle blowers. | - Ministry of Justice (state secretary) |  | Annually, commencing from I quarter of 2016. |  |  |  | Budget of the Republic of Serbia 638 € In 2016 - 213 € In 2017 .- 213 € In 2018 - 213 € |  | Report of the Ministry of Justice developed and published with detailed statistics. |  |  |  |  |

| RECOMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |
| --- | --- | --- | --- | --- | --- | --- |
| 2.2.8. Implement measures to strengthen the control system for public procurement and monitor their effects |  |  | Conducted measures to strengthen the control system for public procurement and monitor their effects. |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia - Annual supervision report of the Administration for Public Procurement, Annual report of the Republic Commission for the Protection of Rights in Public Procurement and Annual report of the State Audit Institution. - Number of initiated and finalized misdemeanor and other proceedings for breaches of the Law on Public Procurement. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT | IMPLEMENTATION STATUS |
| 2.2.8.1. | Conduct an analysis of the effects of implementation of all mechanisms to monitor, supervise and control public procurement and make corrections through amendments to the Law on Public Procurement in accordance with the findings and give recommendations in respect to other regulations. | - Administration for Public Procurement | Amendments to the Law on Public Procurement: II quarter of 2015. Amendments to other regulations: IV quarter of 2015. | Budget of the Republic of Serbia 57.543 € In 2015. | Analysis of the effects of implementation of all mechanisms to monitor, supervise and control public procurement, as well as other measures set in other regulations conducted. Recommendations regarding other regulations provided to the competent bodies. |  |
| 2.2.8.2. | Amend and supplement the Law on Public Procurement in order to remove obstacles to the full implementation of the measures to monitor, supervise and control the Law. | - Administration for Public Procurement -Government of the Republic of Serbia - National Assembly | II quarter of 2015. | Budget of the Republic of Serbia Budgeted in activity 2.2.8.1. | Law on Amendments and supplements the Law on Public Procurement adopted. |  |
| 2.2.8.3. | Strengthen staff and technical capacity of the Administration for Public Procurement based on conducted analysis of existing capacity especially in terms of: -organizational structure - the number and position of employees -level of training -technical capacity. | - Ministry of Public Administration and Local Self-government -Ministry of Finance - Administration for Public Procurement | Analysis: II quarter of 2015. Strengthening staff capacity: IV quarter of 2017. | Budget of the Republic of Serbia - Analysis - 8.642 € In 2015. Strengthening staff capacity – cost currently unknown | Analysis conducted. Modified staff plan and amended Rulebook on job classification in the Administration for Public Procurement. Positions filled. |  |
| 2.2.8.4. | Establish unique database on the measures taken to monitor, supervise and control public procurement by all relevant institutions, as well as the outcomes of these measures, managed by the Administration for Public Procurement. | - Administration for Public Procurement | IV quarter of 2015. | Budget of the Republic of Serbia - 8.642 € In 2015. | Data base established. |  |
| 2.2.8.5. | Monitoring the implementation of the measures of supervision and control in public procurement | - Administration for Public Procurement Republic Commission for the Protection of Rights in Public Procurement | Continuously, commencing from 2016. | Budget of the Republic of Serbia 638 € In 2016 .- 213 € In 2017 - 213 € In 2018 - 213 € | Report of the Administration for Public Procurement on supervision over the implementation of the Law on Public Procurement. Report of the Republic Commission for the Protection of Rights in Public Procurement. |  |
| 2.2.8.6. | Conduct training for police officers, prosecutors and judges to efficiently prosecute cases of corruption in public procurement. | - Administration for Public Procurement - Republic Commission for the Protection of Rights in Public Procurement -Judicial Academy | Continuously | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. | Training conducted. |  |
| 2.2.8.7. | Improve Public Procurement Portal by introducing new features to further enhance the transparency of public procurement procedures and advance public participation in monitoring budget spending. | - Administration for Public Procurement | IV quarter of 2015. | Budget of the Republic of Serbia - 8.642 € In 2015. | Public Procurement Portal advanced by activating new features to further enhance the transparency of public procurement procedures. |  |

| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2.9. Adopt specific measures to prevent and sanction corruption in privatization deals and more broadly to address private sector corruption and improve the transparency and accountability of state-owned and state controlled companies |  |  |  |  |  |  |  |  |  |  |  | Prevention and sanctioning of corruption in the private sector, particularly in the privatization process is performed through concrete measures establishing transparency and accountability, particularly in commercial entities owned or controlled by the state. |  |  |  |  |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Reports of the Anti-Corruption Council; - Number of initiated and finalized criminal proceedings for corruption in the private sector. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  |  |  |  | FINANCIAL RESOURCES |  |  |  |  | RESULT |  |  | IMPLEMENTATION STATUS |
| 2.2.9.1. |  |  |  | Government includes all the reports of the Anti-corruption Council in the agenda. Activity referred to under 2.1.2.1. |  | - Government of the Republic of Serbia |  |  |  |  |  | Continuously |  |  |  |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  |  |  | Adopted minutes from the sessions of the Government. |  |  |  |
| 2.2.9.2. |  |  |  | Conduct analysis of the risk of corruption in implementation of the new laws on bankruptcy and privatization, as well as the Law on public- private partnership and the Law on public companies. Adopt amendments and supplements to the laws in line with the results of the analysis. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) - Anti-Corruption Council - Anti-Corruption Agency - National Assembly |  |  |  |  |  | Analysis: II quarter of 2015. Amendments and supplements: IV quarter of 2015. |  |  |  |  |  |  | Budget of the Republic of Serbia 71.136 € In 2015. |  |  |  |  | Analysis conducted. Amendments and supplements to the law adopted. |  |  |  |
| 2.2.9.3. |  |  |  | Develop criteria for objective and transparent selection of directors, management boards and supervisory boards of the public companies. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) - Participation of CSOs |  |  |  |  |  | IV quarter of 2015 |  |  |  |  |  |  | Budget of the Republic of Serbia 8.892 € In 2015. |  |  |  |  | Criteria developed. |  |  |  |
| 2.2.9. 4. |  |  |  | Establish internal control in all public companies. |  | - All public companies. |  |  |  |  |  | IV quarter of 2015. |  |  |  |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Internal control established in all public companies, which is confirmed in Annual report of the Central Harmonization Unit. |  |  |  |
| 2.2.9.5. |  |  |  | Strengthen capacities of State Audit Institution for the control of public companies on the basis of prior analyses on the staff capacities, particularly relating to organizational structure, number of employees, level of training, for the purpose of effective implementation of revision of the parliamentary political parties referred to under item 2.2.2.6. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) - State Audit Institution |  |  |  |  |  | Analysis: IV quarter of 2015. Strengthening capacities: II quarter of 2016. |  |  |  |  |  |  | Budget of the Republic of Serbia Budgeted in activity 2.2.2.6. |  |  |  |  | Capacities strengthened. Analysis conducted. |  |  |  |
| 2.2.9.6. |  |  |  | Comprehensive analysis of the work and the needs of the Privatization Agency and amendments to the regulatory framework in line with the analysis. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) - Privatization Agency |  |  |  |  |  | Analysis: IV quarter of 2015. Amendments to the regulatory framework: II quarter of 2016. |  |  |  |  |  |  | Budget of the Republic of Serbia 71.136 € In 2016. |  |  |  |  | Analysis and amendments to the regulatory framework conducted. |  |  |  |
| 2.2.9.7 |  |  |  | Comprehensive analysis of the work and the needs of the Commission for Protection of Competition and amendments to the regulatory framework in line with the analysis. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) |  |  |  |  |  | Analysis: IV quarter of 2015. Amendments to the regulatory framework: II quarter of 2016. |  |  |  |  |  |  | Budget of the Republic of Serbia 71.136 € In 2016. |  |  |  |  | Analysis and amendments to the regulatory framework conducted. |  |  |  |
| 2.2.9.8. |  |  |  | Comprehensive analysis of the work and the needs of the Securities Commission and amendments to the regulatory framework in line with the analysis. |  | - Ministry of Commerce (state secretary in charge for anti-corruption) |  |  |  |  |  | Analysis: IV quarter of 2015. Amendments to the regulatory framework: II quarter of 2016. |  |  |  |  |  |  | Budget of the Republic of Serbia 71.136 € In 2016. |  |  |  |  | Analysis and amendments to the regulatory framework conducted. |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |
| 2.2.10. Further develop, implement and assess the impact of specific measures to tackle corruption in other particularly vulnerable areas, such as health, taxation, education, police, customs and the local administration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Assessment of the measures against corruption in the field of health, tax, education, police, customs and local government indicates that they are improved and fully implemented. |  |  |  |  |  |  |  |  | 1. Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; 2. The degree of fulfilment of the measures and activities in the areas identified in the Action Plan, based on the report of the Anti-Corruption Agency. 3. Reports of the Anti-Corruption Council. |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES |  |  |  |  | RESULT |  |  | IMPLEMENTATION STATUS |
| 2.2.10.1. |  |  |  |  | Conduct analysis of the legislative framework in the field of health care system in terms of risk of corruption. |  |  |  |  | - Ministry of Health (state secretary) |  |  |  |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.2. |  |  |  |  | Amend legislative framework in line with the guidelines resulting from the conducted analysis of the legislative framework in the field of health care system in terms of risk of corruption referred to under item 2.2.10.1. |  |  |  |  | - Ministry of Health (state secretary) - National Assembly |  |  |  |  | II quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Amendments to the laws adopted. |  |  |  |
| 2.2.10.3. |  |  |  |  | Conduct analysis of the existing control mechanisms in the health system and strengthen them in line with the analysis. |  |  |  |  | - Ministry of Health (state secretary) - Council for Health |  |  |  |  | Analysis: IV quarter of 2015. Strengthening control mechanisms: Continuously |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. Control mechanisms strengthened. |  |  |  |
| 2.2.10.4. |  |  |  |  | Conduct analysis of the staff capacity in the inspection bodies in the health sector. |  |  |  |  | - Ministry of Health (state secretary) |  |  |  |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.5. |  |  |  |  | Strengthen capacity of the staff in the inspection bodies in the health sector based on the results of the analysis. |  |  |  |  | - Ministry of Health (state secretary) |  |  |  |  | II quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Capacities strengthened. Revised Rulebook on job classification. Positions filled. |  |  |  |
| 2.2.10.6. |  |  |  |  | Introduce national health account into the health system. |  |  |  |  | - Ministry of Health (state secretary) |  |  |  |  | II quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | National health account introduced. |  |  |  |
| 2.2.10.7. |  |  |  |  | Conduct analysis on the conflict of interest in the health system and adopt the rules for prevention of conflict of interest in line with the feasibility study on establishment of the legal framework for the prevention of conflict of interest in public administration referred to under item 2.2.3.4. |  |  |  |  | - Ministry of Health (state secretary) |  |  |  |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted and rules for prevention of conflict of interest adopted in line with the analysis. |  |  |  |
| 2.2.10.8. |  |  |  |  | Amend the Law on Chambers of Health Workers and harmonize regulations of the chambers of health workers with amendments in the law in line with the guidelines resulting from the analysis of the legislative framework in the field of health care system in terms of risk of corruption referred to under item 2.2.10.2. |  |  |  |  | - Ministry of Health (state secretary) - Chambers of the Health Care Workers - National Assembly |  |  |  |  | II quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Law on Amendments and Supplements to the Law on Chambers of Health Workers adopted. Regulations of the chambers of health workers harmonized with the Law. |  |  |  |
| 2.2.10.9. |  |  |  |  | Adopt legislation or amend existing legislation to establish a system of unique identification tax number. |  |  |  |  | - Tax Administration |  |  |  |  | IV quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Law adopted or existing legislation amended to establish a system of unique identification tax number. |  |  |  |
| 2.2.10.10. |  |  |  |  | Conduct training of employees on new solutions in the law on unique identification tax number, develop the Guidelines on the implementation of the law governing unique identification tax number and deliver them to the employees. |  |  |  |  | - Tax Administration |  |  |  |  | II quarter of 2017. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Report on realization of training, number of participants. Guidelines on the implementation of the law governing unique identification tax number developed and delivered. |  |  |  |
| 2.2.10.11. |  |  |  |  | Strengthen capacities of the staff in the Tax Administration to effectively implement the system of e-taxes. |  |  |  |  | - Tax Administration |  |  |  |  | IV quarter of 2015. |  |  |  | Budget of the Republic of Serbia Costs will be specified by the submission of the final draft AP. |  |  |  |  | Capacities strengthened. |  |  |  |
| 2.2.10.12. |  |  |  |  | Strengthen capacities of the internal control department at Tax Administration. |  |  |  |  | - Tax Administration |  |  |  |  | IV quarter of 2015. |  |  |  | Budget of the Republic of Serbia Costs will be specified by the submission of the final draft AP. |  |  |  |  | Capacities strengthened. |  |  |  |
| 2.2.10.13. |  |  |  |  | Monitor the established system of corruption risk management/integrity plan and develop appropriate systems of indicators of corruption. |  |  |  |  | - Tax Administration |  |  |  |  | Continuously |  |  |  | Budget of the Republic of Serbia 638 € In 2016 - 213 € In 2017 - 213 € In 2018 - 213 € |  |  |  |  | Annual report of the Tax Administration. |  |  |  |
| 2.2.10.14. |  |  |  |  | Develop an action plan to meet the recommendations of the OECD report „Strengthening Integrity and Fighting Corruption in Education “in 2012. |  |  |  |  | - Ministry of Education (state secretary) |  |  |  |  | II quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Action plan developed. |  |  |  |
| 2.2.10.15. |  |  |  |  | Conduct analysis of the criteria necessary for a successful process of accreditation and inspection of work in higher education. |  |  |  |  | - National Council for Higher Education - Commission for Accreditation and Quality Assurance |  |  |  |  | II quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.16. |  |  |  |  | Establish the accreditation process and subsequent inspection of the work of public and private higher education institutions on the basis of clear, objective, transparent and pre-established criteria, based on performed analysis, through the improvement of the work of the Commission for Accreditation and Quality Assurance. |  |  |  |  | - Commission for Accreditation and Quality Assurance |  |  |  |  | II quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Accreditation process based on clear, objective, transparent and pre-established criteria established. |  |  |  |
| 2.2.10.17. |  |  |  |  | Improve the transparency of the process of registration, exams, assessment and evaluation of knowledge in all educational institutions so as to change the legal framework with the aim of objectifying procedures and criteria of entry. |  |  |  |  | - Ministry of Education |  |  |  |  | IV quarter of 2016. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Report developed and published at the website. |  |  |  |
| 2.2.10.18. |  |  |  |  | Improve the legal framework in the field of inspection in education and strengthen staff capacity. |  |  |  |  | - Ministry of Education |  |  |  |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Amendments and supplements to the law adopted and capacity strengthened. |  |  |  |
| 2.2.10.19. |  |  |  |  | Review all valid contracts and requests for conclusion of the lease of part of premises of educational institutions. |  |  |  |  | - Ministry of Education - Republic Directorate for Property |  |  |  |  | II quarter of 2015. |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Report on all the reviewed valid contracts and requests developed and published at the website of the Ministry of Education. |  |  |  |
| 2.2.10.20. |  |  |  |  | Conduct analysis on the conflict of interest and discretionary powers of managers of educational institutions in line with the feasibility study on establishment of the legal framework for prevention of conflict of interest in public administration referred to in item 2.2.3.4. |  |  |  |  | - Ministry of Education |  |  |  |  | II quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.21. |  |  |  |  | Conduct analysis of the operations and actions of the Internal Control: - in terms of functionality, organization, capacity and relationship between preventive and repressive measures, the number, the extent of staff training and methodology in certain cases. |  |  |  |  | - Ministry of Interior |  |  |  |  | II quarter of 2015. |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.22. |  |  |  |  | Conduct analysis of the legal framework regulating the work of the internal control of the Ministry of Interior with proposals to amend existing laws and regulations or adopt new if necessary. |  |  |  |  | - Ministry of Interior |  |  |  |  | II quarter of 2015. |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.23. |  |  |  |  | Establish legal framework that will regulate the operations of the sector of internal control of the Ministry of Interior in line with the analysis of the legal framework regulating the work of the internal control of the Ministry of Interior with proposals to amend existing laws and regulations or adopt new if necessary, referred to under item 2.2.10.22. |  |  |  |  | - Ministry of Interior - National Assembly |  |  |  |  | II quarter of 2016. |  |  |  | Budget of the Republic of Serbia 55.697 € In 2016. |  |  |  |  | Amendments and supplements to the law adopted. |  |  |  |
| 2.2.10.24. |  |  |  |  | Develop mechanisms to strengthen the integrity of the police officers: a) Develop risk analysis for each position with respect to the integrity of police officers; b) Create the conditions for the normative regulation, strengthening the integrity of the police officers (amendments to the Law on Police, bylaws, procedures and methodologies); v) Changes in the organizational part resulting from the normative framework (creating the conditions for implementation of the laws and regulations) to ensure the necessary human and material resources to warrant procedures and methodology enabling a higher level of integrity in the police. |  |  |  |  | - Ministry of Interior |  |  |  |  | For item а): II quarter of 2015. For item b): II quarter of 2016. For item c) IV quarter of 2016. |  |  |  | a) Budget of the Republic of Serbia 8.642 € In 2015. b) and c) IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Analysis conducted. Laws and bylaws amended. Changes in organizational structure performed in line with the analysis. |  |  |  |
| 2.2.10.25. |  |  |  |  | Strengthen the capacity of the internal control for the purpose of suppression of corruption in the police in accordance with the performed analysis and amended normative framework in line with the activity referred to under item 2.2.10.23. |  |  |  |  | - Ministry of Interior |  |  |  |  | II quarter of 2016. Gradually per year until 2018. |  |  |  | Capacity building - Budget of the Republic of Serbia – costs currently unknown Training IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Capacities strengthened. Rulebook on job classification amended (the number of systematized jobs in accordance with the established standard 1% of total number) Positions filled (80 % of systematized jobs by 2018,) |  |  |  |
| 2.2.10.26. |  |  |  |  | Continuous training of staff in the Department of internal control and all employees of the Ministry of Interior in relation to the integrity. |  |  |  |  | - Ministry of Interior - Criminalistics Police Academy |  |  |  |  | Continuously |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Training performed. |  |  |  |
| 2.2.10.27. |  |  |  |  | Amend the Law on Police and the Regulations on job classification and internal organization of the Ministry of Interior to establish effective coordination mechanisms of the key stakeholders involved in suppression of corruption at the strategic, tactical and operational level. |  |  |  |  | - Ministry of Interior - National Assembly |  |  |  |  | IV quarter of 2015. |  |  |  | Budget of the Republic of Serbia 71.136 € In 2015. |  |  |  |  | Law on amendments and supplements adopted and bylaws adopted. |  |  |  |
| 2.2.10.28. |  |  |  |  | Establish an organizational unit for fight against corruption in the Criminal Police Directorate, which shall directly cooperate with the anti-corruption units at public prosecutors’ offices, . Establish separate organizational units within the Criminal Police Directorate in Belgrade and Criminal Police Directorates in Novi Sad, Kragujevac, and Niš and designate contact persons in the other local police directorates. |  |  |  |  | - Ministry of Interior |  |  |  |  | II quarter of 2016. |  |  |  | Budget of the Republic of Serbia Currently unknown |  |  |  |  | Organizational units established. |  |  |  |
| 2.2.10.29. |  |  |  |  | Establish coordination of the work between the following units: the Criminal Police Directorate in Belgrade and Criminal Police Directorates in Novi Sad, Kragujevac, and Niš, referred to in item 2.2.10.28., and anti-corruption departments at the Higher Public Prosecutor's Offices. |  |  |  |  | - Ministry of Interior - Republic Public Prosecutor's Offices |  |  |  |  | IV quarter of 2016. |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  |  |  | Coordination of the work established. |  |  |  |
| 2.2.10.30. |  |  |  |  | Conduct comprehensive analysis of the risk for corruption in the normative framework of the system of customs. |  |  |  |  | - Customs Administration - Ministry of Finance (state secretary) |  |  |  |  | II quarter of 2015. |  |  |  | Budget of the Republic of Serbia 8.642 е In 2015. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.31. |  |  |  |  | Amend legislative framework in line with the conducted analysis of the risk for corruption in the normative framework of the system of customs referred to under item 2.2.10.30. |  |  |  |  | - Ministry of Finance (state secretary) - Customs Administration - National Assembly |  |  |  |  | IV quarter of 2016. |  |  |  | Budget of the Republic of Serbia 48.900 € In 2016. |  |  |  |  | Amendments and supplements to the law adopted. |  |  |  |
| 2.2.10.32. |  |  |  |  | Conduct training of the staff at customs in line with new regulations referred to under item 2.2.10.31. |  |  |  |  | - Customs Administration |  |  |  |  | IV quarter of 2017. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Training conducted. |  |  |  |
| 2.2.10.33. |  |  |  |  | Strengthen capacities of the Department of Internal Control. |  |  |  |  | - Customs Administration |  |  |  |  | Continuously |  |  |  | Budget of the Republic of Serbia Cost currently unknown |  |  |  |  | Capacities strengthened. Rulebook on job classification amended. Positions filled. |  |  |  |
| 2.2.10.34. |  |  |  |  | Install video surveillance in customs offices and border crossings with centralized recorder of Signal in the Customs Administration and the ability of the Customs Administration to access video surveillance in each object in the real time. |  |  |  |  | - Customs Administration |  |  |  |  | IV quarter of 2018. |  |  |  | Budget of the Republic of Serbia (Budgeted in Chapter 24) Costs will be specified by the submission of the final draft AP. |  |  |  |  | Video surveillance installed. |  |  |  |
| 2.2.10.35. |  |  |  |  | Conduct analysis of the normative framework regulating local self-government in relation to risks of corruption. |  |  |  |  | - Ministry of Public Administration and Local Self-government (state secretary) |  |  |  |  | IV quarter of 2015. |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.2.10.36. |  |  |  |  | Develop models of local action plans for local self-government units and autonomous provinces. |  |  |  |  | - Anti-Corruption Agency |  |  |  |  | IV quarter of 2015. |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Models developed. |  |  |  |
| 2.2.10.37. |  |  |  |  | Assemblies of the autonomous provinces and local self-governments adopt local action plans and form a permanent working body for monitoring and implementation of local action plans |  |  |  |  | - Assemblies of autonomous provinces and local self-governments |  |  |  |  | IV quarter of 2016. |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  |  |  | Local action plans developed. |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 2.2.11. Ensure that civil society is involved in the anticorruption agenda |  |  |  |  |  |  |  |  |  |  |  |  |  | Civil society is involved in the anticorruption agenda. |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Annual report of the Office for Cooperation with Civil Society; - Number of measures against corruption which are carried out in partnership between CSOs and state authorities. - Number of joint programs implemented |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |
| 2.2.11.1. |  |  | Conduct a joint campaign to encourage and increase the participation of citizens in the fight against corruption. |  |  |  |  | - Office for Cooperation with Civil Society |  |  |  |  |  | Continuously |  |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  | Joint campaigns periodically organized. |  |  |  |  |  |
| 2.2.11.2. |  |  | Amend the Law on State administration in the part relating to transparency and cooperation with civil society organizations and other relevant legislation for the purpose of alignment of the standards of cooperation between state authorities and civil society with the Council of Europe standards and United Nations Convention against corruption agree in accordance with the performed analysis of deficiencies. |  |  |  |  | - Ministry of Public Administration and Local Self-government (state secretary) - Republic Secretariat for Legislation - Office for Cooperation with Civil Society - National Assembly |  |  |  |  |  | IV quarter of 2015. |  |  |  |  | Budget of the Republic of Serbia 48.900 € In 2015. |  |  | Law on amendments and supplements to the Law on State administration adopted. |  |  |  |  |  |
| 2.2.11.3. |  |  | Develop a monitoring methodology for the implementation of programs / projects financed from the budgetary resources and in particular monitor their implementation in the field and expenditure of financial funds for prevention of improper expenditure of funds. |  |  |  |  | - Office for Cooperation with Civil Society |  |  |  |  |  | IV quarter of 2015. |  |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  | Methodology developed. |  |  |  |  |  |
| 2.2.11.4. |  |  | Implement public calls for allocation of funds to the CSOs for projects in the field of anti-corruption for the initiatives at national and local level, as well as for media initiatives in the field of fight against corruption. |  |  |  |  | - Office for Cooperation with Civil Society |  |  |  |  |  | Continuously |  |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  | Number of implemented public calls. |  |  |  |  |  |
| 2.3. REPRESSION OF CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.3.1. Review the economic crime section of the criminal code with a view to provide alternatives to the offence of abuse of office; |  |  |  |  |  |  |  |  |  |  |  | Section of the Criminal Code regulating the chapter on criminal offenses against the economy is aligned with the EU standards, especially with regard to the criminal offense of abuse of office. |  |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Positive GRECO assessment; - Number of prosecuted persons for criminal offences against the economy. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  |  |  |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  |  | IMPLEMENTATION STATUS |
| 2.3.1.1. |  |  |  | Conduct analysis of the need for alignment of the Criminal Code with the EU standards and conduct a case study of the implementation of the chapter on criminal offenses against the economy. |  | - Ministry of Justice (state secretary in charge of anti- corruption) |  |  |  |  |  | IV quarter of 2014. |  |  |  |  |  |  | Budget of the Republic of Serbia 8.642 € In 2014. |  | Analysis and case study conducted. |  |  |  |  |  |  |
| 2.3.1.2. |  |  |  | Amend the Criminal Code in order to specify criminal offences of corruption and against the economy in line with the analysis of the need for alignment of the Criminal Code with the EU standards and conducted case study of the implementation of the chapter on criminal offenses against the economy referred to under item 2.3.1.1. |  | - Ministry of Justice (state secretary in charge of anti- corruption) - National Assembly |  |  |  |  |  | IV quarter of 2015. |  |  |  |  |  |  | Budget of the Republic of Serbia 71.136 € In 2015. |  | Law on amendments and supplements to the Criminal Code adopted. |  |  |  |  |  |  |
| 2.3.1.3. |  |  |  | Monitor the implementation of the CC with the obligation of the police, public prosecutors and courts to submit annual statistical reports on initiated and concluded proceedings to the Ministry of Justice. Ministry of Justice prepares a single annual report and publishes it on the website. |  | - Ministry of Interior - Republic Public Prosecutors’ Office - Supreme Court of Cassation - Ministry of Justice (state secretary in charge of anti- corruption) |  |  |  |  |  | Continuously |  |  |  |  |  |  | Budget of the Republic of Serbia 638 € In 2016 - 213 € In 2017 - 213 € In 2018.- 213 € |  | Annual report published. |  |  |  |  |  |  |
| 2.3.1.4. |  |  |  | Conduct training of judges and prosecutors to implement Criminal Code. |  | - Judicial Academy (director) |  |  |  |  |  | Continuously, commencing from entry into force of the Law on Amendments and Supplements to the Criminal Code |  |  |  |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  | Training conducted. |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |
| 2.3.2. Ensure independent, effective specialized investigation/prosecution bodies, in particular through: – Proposing and implementing measures to strengthen the independence of all investigative and judicial bodies dealing with investigations into corruption so as to effectively protect from undue political pressure; – Providing adequate resources (including budget, staffing and specialized training) to all investigation and judicial authorities involved in the fight against corruption; – Improving the cooperation and information exchange between authorities involved in the fight against corruption, including also tax and other only indirectly linked authorities, through a better inter-connection of databases and by establishing a secure platform of communication; – Fully implementing the new FATF recommendations and stepping up the capacity to run complex financial investigations in parallel with criminal investigations, including through strengthening the special unit in the Ministry of Interior and ensuring adequate training; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Independent, effective and specialized investigation/prosecution is fully insured, and in particular through: - Proposing and implementing measures to strengthen the independence of the investigative and judicial authorities working on the investigation of corruption in order to effectively protect them from undue political pressure, -Providing adequate resources (including budget, staff, specialized training) to all investigative and judicial authorities involved in the fight against corruption, -Improvement of cooperation and exchange of information between the authorities involved in the fight against corruption, including the tax authorities and other indirectly linked bodies, through a better interconnection of databases and the establishment of a secure platform for communication, -Fully implementing the new recommendations of the FATF and strengthening capacity to conduct complex financial investigations in parallel with criminal investigations, as well as the strengthening of the special units of the Ministry of Interior and the provision of adequate training. |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings for criminal offences of corruption. |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  |  |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |
| 2.3.2.1. |  |  | Analysis of the organizational structure, capacity and powers of state bodies in the fight against organized crime and corruption in order to achieve efficiency and strengthen the independence of all relevant institutions. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Prosecutors’ Office for Organized Crime - Ministry of Interior (state secretary) - High Judicial Council - State Prosecutorial Council - Republic Public Prosecutor |  |  |  |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  | Analysis performed. |  |  |  |  |
| 2.3.2.2. |  |  | Provide mutual database connectivity for criminal investigation and a safe system of electronic information exchange between public prosecutor's offices, the police, the Customs Department, Tax Administration, Anti-Corruption Agency and other relevant bodies that have databases of importance to combating corruption. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Ministry of Interior - State Prosecutorial Council - Republic Public Prosecutor - Anti-Corruption Agency |  |  |  |  |  |  |  | IV quarter of 2016. |  | IPA 2013 Budgeted in activity 2.2.1.5. |  |  |  | Database connectivity established. |  |  |  |  |
| 2.3.2.3. |  |  | Amend the Law on Organization and Jurisdiction of State Authorities in the fight against organized crime, corruption and other particularly serious criminal offences, in order to systematically organize the work of special investigative teams, using the necessary methods for increasing efficiency in the prosecution of criminal offences. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Republic Public Prosecutor - Prosecutors’ Office for Organized Crime - National Assembly |  |  |  |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia 48.900 € In 2015. |  |  |  | Law on amendments and supplements to the Law on Organization and Jurisdiction of State Authorities in the fight against organized crime, corruption and other particularly serious criminal offences adopted. |  |  |  |  |
| 2.3.2.4. |  |  | Introduce the team of economic forensics as a part of the Public Prosecutors’ offices and other authorities where necessary. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Republic Public Prosecutor - Prosecutors’ Office for Organized Crime |  |  |  |  |  |  |  | I quarter of 2016. |  | Budget of the Republic of Serbia IPA 2013 Costs currently unknown for both sources |  |  |  | Law on amendments and supplements to the Law on Organization and Jurisdiction of State Authorities in the fight against organized crime, corruption and other particularly serious criminal offences adopted. |  |  |  |  |
| 2.3.2.5. |  |  | Develop and monitor the implementation of a comprehensive strategy improving the efficiency of financial investigation. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) |  |  |  |  |  |  |  | Continuously, commencing from 2016. |  | Budget of the Republic of Serbia 9.281 €, In 2016 - 3.094 е In 2017 - 3.094 е In 2018 - 3.094 е |  |  |  | Strategy improving the efficiency of financial investigation adopted. Reports on the extent of implementation of the strategy published at the website of the Ministry of Justice. |  |  |  |  |
| 2.3.2.6. |  |  | Implementation of the Financial Action Task Force (FATF) recommendations in the relevant regulations of the RS in accordance with previously prepared analysis. See recommendation number 5 in chapter 24, subchapter organized crime. Link with Chapter 24, activity 6.2.5.2.) |  |  |  |  |  | - Ministry of Finance (state secretary) - Administration for Prevention of Money Laundering (director) - Ministry of Justice (state secretary) |  |  |  |  |  |  |  | II quarter of 2016. |  | Budget of the Republic of Serbia (Budgeted in Chapter 24, activity 6.2.5.2.) |  |  |  | FATF recommendation implemented. |  |  |  |  |
| 2.3.2.7. |  |  | Strengthening the capacity of the Department for financial investigation of the Ministry of Interior RS, based on the results of the analysis performed. |  |  |  |  |  | - Ministry of Interior |  |  |  |  |  |  |  | III quarter of 2015. |  | Budget of the Republic of Serbia Calculation shall be performed after conducted analysis |  |  |  | Strengthened capacities Amended Rulebook on job classification Positions filled. |  |  |  |  |
| 2.3.2.8. |  |  | Conduct professional training of employees focusing on a mechanism of information exchange at the international level in accordance with the Framework Decision 2006/960 for the purpose of effective seizure, confiscation and asset management. |  |  |  |  |  | - Ministry of Interior |  |  |  |  |  |  |  | IV quarter of 2015. |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  | Training conducted. |  |  |  |  |
| 2.3.2.9. |  |  | Continuous training of police and prosecutors for conducting financial investigations, monitoring cash flows, proactive approach and special investigative techniques. |  |  |  |  |  | - Judicial Academy - Criminalistics – Police Academy |  |  |  |  |  |  |  | Continuously, commencing from entry into force of the regulations in which FATF recommendations are implemented |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  | Training conducted. |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |
| 2.3.3. Effectively investigate all allegations of corruption in privatization cases and ensure full transparency and accountability to avoid such cases in the future |  |  |  |  |  |  |  |  |  |  |  |  | All allegations of corruption in privatization cases are effectively investigated preventive measures are undertaken to ensure full transparency and accountability in acting. |  |  |  |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings against responsible persons for illegal actions carried out in privatization of state-owned capital. |  |  |  |
| ACTIVITIES |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  |  |  | FINANCIAL RESOURCES |  |  |  |  | RESULT |  |  | IMPLEMENTATION STATUS |
| 2.3.3.1. | Conduct analysis with the aim to establish a system of regular and mandatory coordination between the Council for the Fight against Corruption, Agency for Privatization and appropriate government agencies and state authorities for the purpose of establishing proactive approach in retention of risk of corruption in the field. |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Agency for Privatization (director) - Ministry of Commerce (state secretary) - Anti-Corruption Agency (director) |  |  |  |  |  | II quarter of 2015. |  |  |  |  |  | Budget of the Republic of Serbia 8.642 € In 2015. |  |  |  |  | Analysis conducted. |  |  |  |
| 2.3.3.2. | Amend the regulations on the basis of prior analysis from item 2.3.3.2 in the privatization process. |  |  |  |  |  | - Ministry of Commerce (state secretary) - National Assembly |  |  |  |  |  | . II quarter of 2016. |  |  |  |  |  | Budget of the Republic of Serbia 48.900 € In 2016. |  |  |  |  | Regulations amended on the basis of prior analysis of the risk of corruption in the privatization process. |  |  |  |
| 2.3.3.3. | Design and implement programs of mutual professional development of authorities participating in the process of privatization and authorities responsible for the prevention and prosecution of the cases of corruption. |  |  |  |  |  | - Judicial Academy (director) - Ministry of Commerce (state secretary) - Ministry of Finance (state secretary) - Anti-corruption Agency (director, deputy director) |  |  |  |  |  | Continuously, commencing from the II quarter of 2016. |  |  |  |  |  | IPA 2013 Budgeted in activity 2.1.3.1. |  |  |  |  | Training conducted. |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |
| 2.3.4. Improve the collection of unified statistics on corruption, distinguishing clearly between different types of criminal activities and allowing for a detailed assessment of length of the cases, outcome etc.; |  |  |  |  |  |  |  |  |  |  |  |  | Established system for collection of unified statistics on corruption, distinguishing clearly between different types of criminal offences, length of the cases, outcome of the proceedings, etc. |  |  |  |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings against responsible persons for criminal offences of corruption; - Improved statistical data analysis of the proceedings for criminal offences of corruption. |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  |  |  | TIMEFRAME/DEADLINE |  |  |  |  |  | FINANCIAL RESOURCES |  |  |  |  | RESULT |  |  | IMPLEMENTATION STATUS |
| 2.3.4.1. |  |  |  | Amend the positive regulations in order to establish unique methodology for data collection, records keeping and statistical reporting on criminal offences of corruption. Activity linked with 1.3.8.1. |  | - Ministry of Justice (state secretary in charge of anti- corruption) - National Assembly |  |  |  |  |  |  | II quarter of 2015. |  |  |  |  |  | Budget of the Republic of Serbia 48.900 € In 2015. |  |  |  |  | Amendments to the regulations adopted. |  |  |  |
| 2.3.4.2. |  |  |  | Establish unique records keeping (electronic register) for criminal offenses with an element of corruption, in accordance with the law governing the protection of personal data. |  | - Ministry of Justice (state secretary in charge of anti- corruption) |  |  |  |  |  |  | IV quarter of 2015. |  |  |  |  |  | PACS project Costs will be specified by the submission of the final draft AP. |  |  |  |  | Records keeping established. |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.5. Ensure that the legislative and institutional framework enables effective seizure, confiscation and management of the proceeds of crime resulting in an increased number of seizures and confiscations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Legislative and institutional framework enable effective seizure, confiscation and management of the proceeds of crime resulting in an increased number of seizures and confiscations |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia. - Number of decisions on seizure and confiscation and value of seized and confiscated assets derived from criminal activity. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.3.5.1. |  | Adoption of the Law on Amendments and Supplements to the Law on Seizure and Confiscation of the Proceeds from Crime in accordance with the previously conducted analysis aimed at improvement of efficiency. |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets (director) - National Assembly |  |  |  |  | IV quarter of 2015. |  | Budget of the Republic of Serbia 48.900 € In 2015. |  | Law on Amendments and Supplements to the Law on Seizure and Confiscation of the Proceeds from Crime adopted. |  |  |  |  |  |  |  |
| 2.3.5.2. |  | Conduct a comparative legal analysis on efficient mechanisms for seizure and confiscation of assets and select an appropriate model. |  |  |  |  |  |  |  |  | - Ministry of Interior - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for seized property |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia 8.642 € In 2015. |  | Analysis performed. |  |  |  |  |  |  |  |
| 2.3.5.3. |  | Adoption of bylaws to regulate records keeping, management of seized assets and value assessment. |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets (director)) |  |  |  |  | II quarter of 2016. |  | Budget of the Republic of Serbia 8.642 € In 2015. |  | Bylaws adopted. |  |  |  |  |  |  |  |
| 2.3.5.4. |  | Strengthening the material and technical capacities of the Directorate for Administration of Seized Assets through the purchase of software for recording seized property. |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets (director) |  |  |  |  | II quarter of 2016. |  | Budget of the Republic of Serbia Costs currently unknown |  | Software installed. |  |  |  |  |  |  |  |
| 2.3.5.5 |  | Strengthen the capacity of the Directorate for Administration of Seized Assets through employment and training, particularly in the part relating to the management of property seized from legal entities. |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets |  |  |  |  | Continuously |  | Budget of the Republic of Serbia Costs currently unknown |  | Training conducted. |  |  |  |  |  |  |  |
| 2.3.5.6. |  | Advance international cooperation by signing contracts with the Directorates in the region and the EU. |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets |  |  |  |  | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Number of contracts concluded with the Directorates in the region and in the EU. |  |  |  |  |  |  |  |
| 2.3.5.7. |  | Strengthen capacity by recruiting new staff and training current staff |  |  |  |  |  |  |  |  | - Ministry of Justice (state secretary in charge of anti- corruption) - Directorate for Administration of Seized Assets |  |  |  |  | Continuously |  | Budget of the Republic of Serbia Costs currently unknown |  | Training conducted and positions filled. |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.6. Review the system of immunities, by ensuring that effective procedures for lifting of immunities are in place so that they do not hamper criminal investigations into allegations of corruption and crime |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Provisions on immunity are reviewed and amended to ensure efficient procedure for deciding on immunity, which do not hamper criminal proceedings in corruption and other crimes. |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of cases of lifting immunity; |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.3.6.1. | Conduct analysis of the deficiencies in regulations and revision of regulations with regard to: - persons enjoying immunity - scope of immunity и -proceedings to lift immunity. |  |  |  |  |  |  |  |  |  | - Parliament of the Republic of Serbia |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia 8.642 € In 2015. |  | Analysis conducted. |  |  |  |  |  |  |  |
| 2.3.6.2. | Changes in regulations so as to cover all categories of persons enjoying immunity and redefine procedures of lifting immunity in accordance with the analysis of the deficiencies in regulations and revision of regulations with regard to: - persons enjoying immunity - scope of immunity и -proceedings to lift immunity, referred to under item 2.3.6.1. |  |  |  |  |  |  |  |  |  | - Government of Republic of Serbia - National Assembly |  |  |  |  | IV quarter of 2015. |  | Budget of the Republic of Serbia 48.900 € In 2015. |  | Amendments to the regulations adopted. |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.7. Propose measures for law enforcement and the judiciary to prevent leaks to the media of confidential information regarding the investigations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Measures to prevent leeks to the media of confidential information regarding the investigations are established and effectively implemented. |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of proceedings for illegal distribution of information to the media about active investigation procedures. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.3.7.1. | Conduct analysis of the current situation (normative, organizational and functional), identifying weaknesses and risks (level of data accessibility for the exact determination of availability in relation to time and content) |  |  |  |  |  |  |  |  |  | - Ministry of Interior - Republic Public Prosecutors’ Office |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia 8.642 € In 2015. |  | Analysis conducted. |  |  |  |  |  |  |  |
| 2.3.7.2. | Proposal of amendments or the adoption of new regulations and procedures aimed at introducing control and oversight mechanisms in line with the analysis of the current situation (normative, organizational and functional), identifying weaknesses and risks (level of data accessibility for the exact determination of availability in relation to time and content) referred to in item 2.3.7.1. |  |  |  |  |  |  |  |  |  | - Ministry of Interior - Republic Public Prosecutors’ Office - Ministry of Justice (state secretary in charge of anti-corruption) |  |  |  |  | IV quarter of 2015. |  | Budget of the Republic of Serbia - 48.900 € In 2015. |  | Amended or adopted new regulations and procedures in line with the analysis referred to in item 2.3.7.1. |  |  |  |  |  |  |  |
| 2.3.7.3. | Develop an "ideal model" for the detection of offenders and proving criminal offence of disclosing official secrets ("leaking information to the media"). Link with activities 2.3.4.1, 2.3.4.2 и 2.2.10.24 |  |  |  |  |  |  |  |  |  | - Ministry of Interior - Republic Public Prosecutors’ Office |  |  |  |  | II quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activities 2.3.4.1. 2.3.4.2. and 2.2.10.24 |  | Model for the detection of offenders and proving criminal offence of disclosing official secrets developed. |  |  |  |  |  |  |  |
| 2.3.7.4. | Revise the rules governing criminal, disciplinary and all other types of liability and increase levels of IT protection by creating a so-called early warning system and alarm system. |  |  |  |  |  |  |  |  |  | - Ministry of Interior - Republic Public Prosecutors’ Office - National Assembly |  |  |  |  | IV quarter of 2015. |  | Budget of the Republic of Serbia 48.650 € In 2015. |  | Regulations revised and the level of IT protection increased. The so called early warning system and alarm system established. |  |  |  |  |  |  |  |
| 2.3.7.5. | Monitor sanctioning of violations of regulations preventing disclosure of confidential information, along with the prepared analysis on the implementation of regulations and recommendations. |  |  |  |  |  |  |  |  |  | - Ministry of Interior - Republic Public Prosecutors’ Office |  |  |  |  | Continuously, commencing from entry into force of internal acts |  | Budget of the Republic of Serbia 1.225 € In 2016 - 408 € In 2017 - 408 € In 2018 - 409 € |  | Number of cases of violation of regulations preventing disclosure of confidential information. Conducted analysis on implementation with the recommendations. |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.8. Conduct a mid-term review at the end of 2015 as well as an impact assessment in 2018 of the results generated by the 2013 Strategy and its revised action plan against the overall corruption situation in Serbia. Define on that basis and where needed measures to cover the remaining period up until accession |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Conducted a mid-term analysis at the end of 2015 and impact assessment in 2018 in conjunction with the results of the strategy in 2013 and its revised action plan in relation to the overall situation in the field of ​​corruption in Serbia. Defined measures including the remaining period up to accession. |  |  |  | 1.The positive assessment of the European Commission's annual report on the progress of Serbia; 2. The degree of fulfillment of measures and activities in these areas defined in the Action Plan, based on the report of Anti-corruption Agency; 3. Reports of the Council for the fight against corruption. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  |  |  |  |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.3.8.1. | Analyze the results achieved by implementing the Action Plan for the Implementation of the National Strategy for the Fight against Corruption for the period from 2013 to 2018, and possibly propose their amendments. |  |  |  |  |  |  |  |  |  | - Ministry of Justice |  |  |  |  | IV quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Development of the analysis and evaluation of the degree of fulfilment of the Action Plan for the implementation of the strategy and possibly the proposed amendments. |  |  |  |  |  |  |  |
| 2.3.8.2. | Evaluate the results achieved by the implementation of the National Strategy for the Fight against Corruption for the period from 2013 to 2018 and the accompanying action plans and compare them with the overall situation with regard to corruption in Serbia. On that basis, define the necessary measures for the remaining period up to accession. |  |  |  |  |  |  |  |  |  | - Ministry of Justice |  |  |  |  | IV quarter of 2018. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Estimated results of the implementation of the Strategy and action plans and the necessary measures for the remaining period up to accession defined. |  |  |  |  |  |  |  |

| 3. FUNDAMENTAL RIGHTS |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CURRENT STATE: |  |  |  |  |  |  |  |  |  |  |  |
| The Republic of Serbia will continue to improve its legal and normative framework for the protection and promotion of fundamental rights, in line with the EU Acquis, European and international standards and best practices. Prohibition of torture, degrading and ill-treatment and punishment In the field of prevention and prohibition of torture and ill- treatment, the Republic of Serbia plans to strengthen the capacity of the Ombudsman, particularly with regard to its role as a National Preventive Mechanism, through the provision of the necessary number and structure of employees for the efficient performance of duties. Also, by establishing specific communication channels between police officers, NPM and civil society organizations, it is planned to increase the level of coordination and raise general awareness about the necessity of full elimination of all forms of torture. Through initial and continuous training for police officers, staff at the institutes for enforcement of criminal sanctions and enforcement judges, a higher level of expertise and awareness of the necessity to establish zero torture tolerance shall be achieved. The existence of adequate infrastructure at the institutes for enforcement of criminal sanctions is an important aspect of the prevention of torture, hence the Republic of Serbia plans to invest considerable efforts to build new institutes for enforcement of criminal sanctions during the implementation period of the Action Plan for Chapter 23, and restore the existing facilities. In addition to the renewal of the facilities, considerable attention will be paid to the improvement of conditions in the Special Prison Hospital in Belgrade. In addition to the infrastructure of the institutes for enforcement of criminal sanctions, significant efforts will be made to improve the infrastructure of the detention facilities in police stations. The problem of overcrowding in the institutes for enforcement of criminal sanctions will be addressed on two tracks, both through infrastructure investments as well as through the development and further improvement of the system of alternative sanctions. In the formulation of measures for the prevention and suppression of torture and ill-treatment, special attention is paid to the Recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment i.e. the implementation of the recommendations is the main focus of all activities in this area. Freedom of thought, conscience and religion In the domain of freedom of thought, conscience and religion, it is necessary to conduct a detailed comparative analysis of the legal status of churches and religious communities, taking into account the specificities of European legal tradition in this domain and cultural characteristics of the region Serbia belongs to. The analysis will be based on the idea proclaimed in the Constitution of the Republic of Serbia, which states that churches and religious communities are equal and free to independently regulate their internal organization, religious affairs, to perform religious rites. The neighboring countries of the Republic of Serbia will represent the paradigm for this analysis, given that they have already met the criteria for membership in the EU. The abovementioned approach is based on the cultural similarities of the countries in the region and the fact that the same religious communities are extended across these countries, but also given the need to use the know-how of countries that have already experienced the process of integration. Following the performed analysis, all necessary measures to implement the recommendations of the analysis will be undertaken to enable full alignment with the identified standards and best practices. Freedom of expression, including freedom and pluralism of the media Through consistent implementation of a set of new media laws that came into force in the beginning of August 2014, full withdrawal of the state from media ownership will be achieved, which is one of the main strategic objectives of the Strategy for Development of Public Information System in the Republic of Serbia in 2011. Frequent threats and violence against journalists have been recognized as a serious threat to freedom of expression and media pluralism. In order to overcome this challenge, it is necessary to strengthen coordination between all competent authorities and raise awareness on the importance of the protection of journalists, both through training and prioritization of these cases, which will represent the key focus in the following period. Information leaks regarding planned and ongoing criminal investigations have been perceived as a serious threat to the efficiency of the investigation, the presumption of innocence and privacy of personal data. It is planned to end these negative practices through the development of new operational procedures, capacity building through training and effective coordination of the competent authorities. Principle of anti-discrimination and position of socially vulnerable groups In the following period, the Republic of Serbia plans to achieve full alignment the Law on anti-discrimination with the EU Acquis . Through planned adoption of the Action Plan for the implementation of the Strategy of Prevention and Protection Against Discrimination for the period from 2014 to 2018, and its consistent implementation and active monitoring, improvement of the position of the most vulnerable social groups will be achieved. Through dedicated work, the Commissioner for Protection of Equality, as a central national body specialized in combating all forms and types of discrimination and prevention of discrimination, led to a significant increase of awareness on discrimination. Strengthening its capacity in the forthcoming period is necessary in order to additionally improve the protection and prevention of discrimination. Positive progress has been made in improving the situation of the LGBTI community. This will continue through the implementation of the section of the Action Plan for the implementation of the Strategy of Prevention and Protection Against Discrimination for the period from 2014 to 2018, which refers precisely to this vulnerable group, as well as through ongoing consistent implementation of the Law on anti-discrimination. Through the development of a model of community policing and continuous cooperation with the representatives of the LGBTI community by designating contact persons, the work on the improvement of safety of all members of the LGBTI community will continue. In the forthcoming period, the good practice of raising awareness about the prohibition of all forms of discrimination and methods for its prevention is planned to continue, which will be achieved through a series of educational roundtables, training of citizens and civil servants, and printing and distributing manuals for recognizing and responding to discrimination. Gender equality In the forthcoming period, the Republic of Serbia plans to pay due attention to the promotion of the principle of gender equality, both at strategic and legislative level, as well as to strengthen capacity of the institutions and their mutual coordination. The Government of the Republic of Serbia recently established a Coordinating Body for gender equality that will address all the related issues and coordinate the work of state administration in relation to gender equality, in order to ensure that all the available mechanisms operate in an efficient and consistent manner. In the forthcoming period, the Republic of Serbia will develop a new strategic framework for the protection of gender equality, establishing in this way a new foundation to advance implementation of gender equality in practice. In addition to the adoption of new strategies in this field, the Republic of Serbia shall endow the necessary efforts to align with the Istanbul Convention, in particular through analysis and the necessary amendments to the current legislative framework for the protection of women against violence. Rights of the child The work of the Council for the Rights of a Child will be intensified to achieve a higher level of coordination of all state bodies responsible for the implementation of strategic documents in the field of the rights of a child. In addition, through an inclusive and transparent process, a new strategic framework for the protection of children from violence will be developed, in order to carry on with the development and improvement of the existing framework, based on the previous experiences. The work on increasing the number of children who benefit from family support measures will be continued, in order to reduce the necessity to use alternative care, the placement of children in residential institutions or foster care, whereas in the case of necessity to use alternative care, placement in the family-like environment in the local community will be emphasized, while gradually increasing the availability of different alternative care options, selected on the basis of each individual case. Efforts will be made to strictly control and reduce the number of children placed in residential institutions. For the purpose of full implementation of the European standards, the work on improvement of the juvenile justice system will be continued, in particular by enabling that the number of children who benefit from the child-oriented judiciary increases annually through the wider use and the introduction of new educational orders, adjusted preparation for release, performed by trained judicial and other professionals, better infrastructure and wider use of alternative sanctions. Procedural safeguards The establishment of a functioning free legal aid system shall commence by the adoption of the Law on Free Legal Aid and its implementing bylaws. Introduction of this system will significantly facilitate access to justice for all citizens and particularly those who are most vulnerable. The amendments and supplements to the Criminal Procedure Code will enable full harmonization with EU directives in the field of procedural safeguards, enabling additional guarantees for the exercise of the right of suspects or accused persons to access a lawyer, the right to information and the right to interpretation and translation. The amendments to the normative framework will also be performed to achieve full alignment with the Directive 2012/29 / EU regarding the rights, support and protection of victims of crime / injured parties. Through the establishment of victim support services, another aspect of access to justice shall be improved. Also, through a series of trainings for all relevant stakeholders, the necessary capacities for full implementation of the new procedural safeguards shall be strengthened. Position of national minorities With regard to the position of national minorities, the Republic of Serbia plans to draft an Action Plan for the implementation of legislation in the field of national minorities. The above-mentioned Action Plan will focus on the implementation of the existing legal framework, which has been rated as very good, but with inconsistent levels of implementation. In the process of development of the abovementioned Action Plan, the Republic of Serbia will focus on the relevant recommendations set out in the Third opinion of the Advisory Committee on Serbia in the context of the Council of Europe Framework Convention for the Protection of National Minorities. In all stages of this extremely important strategic document, major importance will be dedicated to full inclusion of all stakeholders, i.e. the councils of national minorities, civil society organizations and all relevant public authorities. The principle of transparency will be respected at all stages of design, implementation and monitoring over the implementation of this Action Plan. As part of the efforts to improve the situation of the Roma minority, a new multi-annual strategy and action plan for improving the living conditions of Roma will be developed in the forthcoming period. In the development of these strategies, the experience in implementation of the previous strategy as well as comparative legal experience of our partners in the EU will be utilized. The aforementioned strategy will focus on the most important areas of life, particularly paying attention to the following areas: personal documents, comprehensive measures of protection against discrimination, compliance with international standards in the forced evictions, equal access to health and social care, equal access to education and equal access the labor market. Along with the strategy, a detailed action plan will be developed to enable its effective implementation. Position of refugees and internally displaced persons In the forthcoming period, significant efforts will be made to improve the living conditions of refugees and internally displaced persons. Significant financial resources will be invested to resolve housing problems of the most vulnerable families, particularly those who are still placed in collective centers, both through to the construction of new housing units and the provision of necessary construction materials. The provision of complementary measures aimed at sustainable integration of refugees through programs aimed at the economic empowerment will continue. The introduction of a free legal aid system available to refugees and internally displaced persons will enable a higher degree of legal certainty and facilitate access to personal documents through the procedures prescribed by the Law on non-contentious proceedings, aimed at elimination of "legally invisible persons" through the registration and provision of identity documents. Measures against Racism and Xenophobia In the field of combating racism and xenophobia, in the following period measures will be undertaken in terms of legislative alignment with the Framework Decision 2008/913 / JHA on suppression of certain forms and expressions of racism and xenophobia by means of criminal law. Through amendments to the criminal legislation, compliance with paragraphs (c) and (d) of Article 1 of the aforementioned decision will be ensured, envisaging punishment of public approval, denial or gross trivialization of genocide, crimes against humanity and war crimes, as well as public approval, denial or gross trivialization of the crime in a way that can lead to violence or hatred against persons or groups of persons who are linked by common race, colour, religion, ancestry, nation or ethnicity. Also, by amending the criminal offense of violation of equality (Article 128), in order to include its execution on the grounds of sexual orientation or gender identity to limit or deny the rights of any person, a higher degree of protection and prevention of hate crimes will be achieved. Through the training of judges, prosecutors and police officers, improved knowledge and skills necessary for the effective prosecution of hate crimes will be provided, whereas the development and dissemination of educational materials, organization of annual forums and implementation of active media campaign will lead to a higher level of tolerance necessary for successful hate crime prevention. Through the selection of new members and intensification of the work of the Action Team for development and implementation of a Strategy and Action Plan to combat violence and misbehavior at Sports Events, the supervision over the implementation of the Strategy will be enhanced, providing in this way adequate update the Action Plan for the implementation of this strategy. Personal data protection Through the development of detailed tables of concordance of the current Law on personal data protection with the EU Acquis in this field, a solid analytical basis for the amendments to the Law on Personal Data Protection shall be provided, providing a higher level of protection of personal data as well as full harmonization in this field. The adoption of bylaws that accompany the Law on Amendments to the Law on Personal Data Protection will enable full functionality and consistent implementation of these laws. Amendments and supplements to the Law on Personal Data Protection will lead to changes in responsibilities and organization of the Commissioner for Information of Public Importance and Personal Data Protection, and in accordance with these changes it will be necessary to develop a new Rulebook on internal organization and job systematization and implement it in order to strengthen the capacity of the Commissioner. |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. PROHIBITION OF TORTURE AND INHUMAN OR DEGRADING TREATMENT OR PUNISHMENT |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |
| 3.1.1 Fully implement the recommendations provided by the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment (CPT) |  |  |  |  | Implementation of the Recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment results in full elimination of torture and inhuman or degrading treatment or punishment and preconditions for its effective prevention |  |  |  |  | - Report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment stating significant progress of Serbia in terms of implementation of the recommendations of the CPT - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia's in the part referring to prevention of torture and inhuman or degrading treatment or punishment - A higher percentage of alternative sanctions ascertained in the report of the National Bureau of Statistics; - Report of the Ombudsman concluding effective application of alternative sanctions; - Report of the Ombudsman stating significant progress of Serbia in terms of implementation of the recommendations of the CPT - Report of the National Mechanism for the Prevention of Torture stating significant progress of Serbia in terms of implementation of the recommendations of the CPT |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 3.1.1.1. | Revise the normative framework of the Ministry of Interior governing the treatment of detainees and persons remanded in custody. The same activity under item 3.3.1.19. |  | - Ministry of Interior |  | III and IV quarter of 2015. | Total- 19.035 € Budget of the Republic of Serbia-17.285 € TAIEX- 1.750 € in 2015. |  |  |  | Amendments and supplements to the normative framework of the Ministry of Interior governing the treatment of detainees and persons in custody adopted. |  |
| 3.1.1.2. | Introduce a system of mandatory education for new police officers and continuous education for current police officers regarding the treatment of detainees and persons remanded in custody in accordance with international standards in the field of human rights, professional ethics and acting in high risk situations. The same activity under item 3.3.1.20 |  | Ministry of Interior |  | II quarter of 2016. | Total -7.750 € Budget of the Republic of Serbia- 6.000 € TAIEX-1.750 € In 2016. - 3.750 € In 2017. - 2.000 € In 2018. - 2.000 € |  |  |  | Conducted training for 200 police officers on an annual basis; Decreased number of complaints about the conduct of police officers towards detainees and persons remanded in custody. |  |
| 3.1.1.3. | Construction, renovation and equipping of facilities for detention in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman) The same activity under item 3.3.1.21. |  | - Ministry of Interior |  | Continuously, commencing from IV quarter of 2015. | Budget of the Republic of Serbia IPA 2015 Currently unknown expecting data from Ministry of Interior |  |  |  | Constructed and restored facilities for detention in accordance with the recommendations of the CPT ; Necessary equipment for detention facilities purchased in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman). |  |
| 3.1.1.4 | Strengthening the supervision mechanism at the Ministry of Interior for the implementation of standards of police conduct in the field of torture prevention through; - training of the members of the Commission for the implementation of standards of police conduct in the field of torture prevention in order to effectively perform their duties; - training of the detention units’ directors in order to effectively monitor police conduct; -training of police officers working in the police stations in order to prevent any prohibited treatment; - improvement of records in detention units ; - unexpected visits to places of detention in order to control the implementation of the recommendations of the National Mechanism for the Prevention of Torture; - introduction of clear procedures of treatment of detainees and persons remanded into custody to ensure the exercise of their rights (e.g. the right to access to a lawyer, contact with close relatives, the right to health care). The same activity under item 3.3.1.22. |  | - Ministry of Interior |  | Continuously, commencing from IV quarter of 2015. | Total -21.192 € Budget of the Republic of Serbia -19.442 € TAIEX - 1.750 € IPA2015 In 2015. - 6.611 € In 2016. - 4.861 € In 2017. - 4.861 € In 2018. - 4.859 € |  |  |  | Capacities of the supervision mechanism at the Ministry of Interior in the field of torture prevention strengthened through: Conducted training on the prevention of torture; Improved coordination of the Ombudsman and non-governmental sector; Unexpected visits to places of detention carried out regularly; Established procedures for treatment of detainees and persons remanded into custody ensuring the exercise of their rights; Established procedures for records keeping on the and detained persons and persons remanded into custody and forms developed. |  |
| 3.1.1.5. | Intensify cooperation with the National Mechanism for the Prevention of Torture by holding regular meetings and reporting on actions undertaken pursuant the recommendations of the National Mechanism for the Prevention of Torture . The same activity under item 3.3.1.23. |  | - Ministry of Interior |  | Continuously | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  |  | Cooperation between the Ministry of Interior and National Mechanism for the Prevention of Torture intensified. |  |
| 3.1.1.6. | Intensify cooperation between the Ministry of Interior with state authorities, national mechanism for the prevention of torture and civil society organizations in the field of torture prevention through: - Organization of workshops and discussions on the prohibition of torture in police, unprofessional behavior of police officers and respect for the rights of detained persons and persons remanded into custody; - Establishment of a practice of the Ministry of Interior to report in writing on the measures taken in accordance with the recommendations of civil society organizations. - Raising awareness on prevention of torture in the police among police officers and provision of information to the public on the rights of detainees and persons remanded into custody. The same activity under item 3.3.1.24. |  | - Ministry of Interior |  | Continuously, commencing from I quarter of 2015. | Budget of the Republic of Serbia-5.404 € In 2015. - 1.351 € In 2016. - 1.351 € In 2017. - 1.351 € In 2018. - 1.351 € |  |  |  | Cooperation between the Ministry of Interior with state authorities, national mechanism for the prevention of torture and civil society organizations intensified. Workshops and discussions on the prohibition of torture in police and awareness raising organized. Signed cooperation protocols between the Ministry of Interior and civil society organizations. Ministry of Interior regularly reports on undertaken measures in accordance with the recommendations of civil society organizations. Awareness raising campaign conducted. |  |
| 3.1.1.7. | Development of a methodology for the prosecution and the police to investigate cases of abuse and torture in order to conduct effective investigations into allegations of ill-treatment and torture by police. The same activity under item 3.3.1.25. |  | -Ministry of Interior |  | I quarter of 2016. | Total- 123.452€ Budget of the Republic of Serbia- 1.702 € OECD mission to the Republic of Serbia - 121.750 € In 2016. |  |  |  | Document on methodology to investigate allegations of ill-treatment and torture by police drafted. |  |
| 3.1.1.8. | Construction of new buildings and departments in order to improve living conditions in prisons: - Initiate the construction of prisons in Pancevo and Kragujevac. - Finalization of works on the construction of prisons in Pancevo and Kragujevac enabling the start of their operation, pursuant to the construction plan. The same activity under item 3.3.1.1. |  | - Administration for enforcement of criminal sanctions |  | Initiation of construction: IV quarter 2015 Finalization of works: 2018. | Total - 35.481.000 Development Bank of the Council of Europe, EU (IPF3)- 35.000.000 €, Budget of the Republic of Serbia 481.000 € In 2015. - 2.108.330 € In 2016. - 2.103.330 € In 2017. - 3.353.330 € In 2018. - 32.647.000 € |  |  |  | Prisons in Pancevo and Kragujevac constructed. |  |
| 3.1.1.9. | Reconstruction of existing accommodation capacity of the current institutions in accordance with European standards and their alignment with existing standards, including the following institutions District Prison in Belgrade District Prison in Uzice Criminal Correctional Facility Valjevo Criminal Correctional Facility Zabela Criminal Correctional Facility Ćuprija Criminal Correctional Facility Niš Correctional Facility for Women Pozarevac Correctional Educational Facility Krusevac Special Prison Hospital Belgrade The same activity under item 3.3.1.2. |  | - Administration for enforcement of criminal sanctions |  | By the end of 2018. | Total -8,089,790 € The donation of the Kingdom of Norway – Costs will be specified by the submission of the final draft AP. IPA2013- 2.565.000 € Budget of the Republic of Serbia 5,524,790 € In 2015. - 1.203.130 € In 2016. - 3.163.830 € In 2017. - 3.722.830 € |  |  |  | Reconstruction of accommodation capacities of the current institutions in accordance with European standards finalized. |  |
| 3.1.1.10. | Ensure more effective judicial review and supervision over the rights of individuals deprived of liberty by establishing sustainable system of provision of information to individuals deprived of liberty on the content of their rights and protection mechanisms in the proceedings before the enforcement judge. The same activity under item 3.3.1.7. |  | - Administration for enforcement of criminal sanctions |  | Continuously, commencing from I quarter of 2015. | Total -75.404 € Budget of the Republic of Serbia - 3.404 € OSCE mission - 72.000 € In 2015. - 72.851 € In 2016. - 851 € In 2017. - 851 € In 2018. - 851 € |  |  |  | More effective judicial review and supervision over the rights of individuals deprived of liberty secured by regular provision of information to individuals deprived of liberty on the content of their rights and protection mechanisms in each case. |  |
| 3.1.1.11. | Conduct training of staff for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. The same activity under item 3.3.1.11. |  | - Administration for enforcement of criminal sanctions |  | Continuously, commencing from I quarter of 2015. | Total - 1.007,500 € Budget of the Republic of Serbia - 57.500 € IPA 2013 Total- 950.000 € In 2015. - 750.000 € In 2016. - 257.500 € |  |  |  | Staff training conducted. Relevant staff improved their knowledge and skills for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. |  |
| 3.1.1.12. | Analysis of the functioning of the system for enforcement of criminal sanctions. The same activity under item 3.3.1.8 |  | - Administration for enforcement of criminal sanctions |  | IV quarter of 2015. | Budget of the Republic of Serbia- 17.285 € In 2015. |  |  |  | Analysis of the functioning of the system for enforcement of criminal sanctions conducted, including recommendations for its improvement. |  |
| 3.1.1.13. | Further reduction of hospital beds in health institutions specialized in psychiatry; in Serbia, there is a total of five, one of which has the status of the clinic (on the territory of Vojvodina there are 3) by an average of 10% per annum. |  | Ministry of Health |  | Continuously, commencing from I quarter of 2015. | Budget of the Republic of Serbia No calculations of infrastructure costs - reallocation of resources in the health system |  |  |  | Reduction of hospital beds in health institutions specialized in psychiatry performed by an average of 10% per annum. |  |
| 3.1.1.14. | Further transformation of hospital beds with the ultimate goal to continue the use of beds in these hospitals primarily for psychosocial rehabilitation, gerontopsychiatry and forensic psychiatry , namely measures of compulsory treatment and confinement. |  | Ministry of Health |  | Continuously, commencing from I quarter of 2015. | Budget of the Republic of Serbia No calculations of infrastructure costs - reallocation of resources in the health system |  |  |  | Active transformation of hospital beds enabling their use for psychosocial rehabilitation, gerontopsychiatry and forensic psychiatry , or measures of compulsory treatment and confinement |  |
| 3.1.1.15. | Continuous implementation of the provisions of the Rulebook on detailed conditions for the application of physical restraint and isolation of persons with mental disorders who are treated in psychiatric institutions and control of the implementation. |  | Ministry of Health |  | Continuously | Budget of the Republic of Serbia- 53.188 € In 2014. - 10.638 € In 2015. - 10.638 € In 2016. - 10.638 € In 2017. - 10.638 € In 2018. - 10.638 € |  |  |  | Continuous implementation of the provisions of the Rulebook ensures adequate implementation of the procedures of physical restraint and isolation of persons with mental disorders, which is noted in the report of the National mechanism for the prevention of torture |  |
| 3.1.1.16. | Strengthening of mental health services in the community through: - Establishment of centers for mental health in the community; - Provision of diversified services available to numerous individuals; - Establishment of cooperation with all health institutions at all levels of health care through information exchange and the establishment of a single patient referral system from primary to other levels of health care; - Continuing education of general practitioners in mental health |  | Ministry of Health Civil Society organizations |  | Continuously, commencing from I quarter of 2015. | Budget of the Republic of Serbia No calculations of infrastructure costs - reallocation of resources in the health system |  |  |  | Improved mental health protection in the community through: - Established centers for mental health in the community; - Availability of diversified mental health protection services; - Unique patient referral system from primary to other levels of health care established and implemented. - Number of conducted trainings annually. |  |
| 3.1.1.17. | Establishment of a practice of prioritizing the treatment of persons with mental disabilities in the community and through brief hospitalization in psychiatric wards of general hospitals. |  | Ministry of Health |  | Continuously, commencing from I quarter of 2015. | Budget of the Republic of Serbia No calculations of infrastructure costs - reallocation of resources in the health system |  |  |  | Treatment of persons with mental disabilities in the community prioritized. |  |
| 3.1.1.18. | Implementation of continuous training for employees in health care institutions for treatment of individuals with mental health problems and judge in the non- proceedings in regard to: - the practical application of the provisions of the Law on the Protection of Persons with Mental Disabilities and the rulebooks - international standards and best practices in the field of protection of rights, treatment, involuntary hospitalization and treatment in the community of persons with mental health problems. |  | Ministry of Health |  | Continuously | Budget of the Republic of Serbia 12.000 € In 2014. - 2.400 € In 2015. - 2.400 € In 2016. - 2.400 € In 2017. - 2.400 € In 2018. - 2.400 € |  |  |  | Number of conducted trainings annually. Improved knowledge and skills of employees in health care institutions and judge in the non-contentious proceedings in regarding international standards and best practices in the field of protection of rights, treatment, involuntary hospitalization and treatment in the community of persons with mental health problems |  |
| 3.2. POSITION OF THE OMBUDSMAN, THE PROVINCIAL OMBUDSMAN AND LOCAL OMBUDSMEN |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.2.1. Strengthen the capacity of the Ombudsman (in particular in view of his role as national prevention mechanism ), the provincial and local Ombudsmen services |  |  |  | The capacity of the Ombudsman, the Provincial Ombudsman-Ombudsman and the local services of the Ombudsman are strengthened and these institutions perform duties in their competence in full capacity. The Ombudsman acts as a national mechanism for the prevention of torture in accordance with the Optional Protocol to the Convention against Torture - formed a separate organizational unit of the NPM with an adequate number of employees and full organizational, functional and financial independence |  |  |  |  | - The report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment stating that the capacity of the Ombudsman, the provincial ombudsman and local ombudsman service are significantly enhanced. - Annual Report of the Ombudsman noting the improvement of the capacity of the Ombudsman, especially with regard to the national preventive mechanism for torture |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.2.1.1 | Strengthening the capacity of the professional service of the Ombudsman in accordance with the adoption of the Rulebook on organization and job systematization at the technical service of the Ombudsman, upon the obtained consent of the National Assembly, securing the necessary number and structure of employees for efficient performance of the competencies of the Ombudsman and in particular the responsibilities related to the National Prevention Mechanism. |  | - Ombudsman | IV quarter of 2014. |  | Budget of the Republic of Serbia- 8.642 € In 2014. |  |  | Capacities of the professional service of the Ombudsman strengthened in accordance with the new systematization, based on the need to strengthen the administrative capacity necessary for operation of the Ombudsman |  |  |
| 3.2.1.2. | Enable the premises for adequate long-term placement of the Ombudsman |  | - Government of the Republic of Serbia | IV quarter of 2014. |  | Budget of the Republic of Serbia- 369.728 € In 2015. - 92.432 € In 2016. - 92.432 € In 2017. - 92.432 € In 2018. - 92.432 € |  |  | Adequate long-term placement of the Ombudsman secured and functional. |  |  |
| 3.2.1.3. | Amend and supplement the Law on Ombudsman |  | - Ministry of State Administration and Local Self-government - Ombudsman -National assembly | I quarter of 2015. |  | Budget of the Republic of Serbia- 48.900 € In 2015. |  |  | Law on amendments and supplements to the law on Ombudsman enabling increased autonomy and improvement of the efficiency of the Ombudsman adopted. |  |  |
| 3.2.1.4. | Adoption of the new Rulebook on organization and job systematization at the technical service of the Ombudsman in line with the amendments and supplements to the Law on Ombudsman |  | - Ombudsman | II quarter of 2015. |  | Budget of the Republic of Serbia- 8.642 € In 2015. |  |  | New Rulebook on organization and job systematization at the technical service of the Ombudsman in line with the amendments and supplements to the Law on Ombudsman adopted. |  |  |
| 3.2.1.5. | Amend and supplement the Law on local self-government in order to strengthen the role of the Local Ombudsman |  | - Ministry of State Administration and Local Self-government -National assembly | II quarter of 2015. |  | Budget of the Republic of Serbia- 48.900 € In 2015. |  |  | Law on amendments and supplements to the Law on local self-government strengthening the role of the Local Ombudsman adopted. |  |  |
| 3.2.1.6. | Regularly monitor the effectiveness of acting of the state authority bodies of in the process of control initiated by the Ombudsman. |  | - Government of the Republic of Serbia - Controlled body - Ombudsman | Continuously |  | Budget of the Republic of Serbia- 159.563 € In 2014. - 31.913 € In 2015. - 31.913 € In 2016. - 31.913 € In 2017. - 31.913 € In 2018. - 31.913 € |  |  | The Ombudsman and state authority bodies actively cooperate in the process of monitoring the effectiveness of acting of the state authority bodies. |  |  |
| 3.2.1.7. | Regularly monitor the effectiveness of acting of the state authority bodies in line with the recommendations of the National Prevention Mechanism |  | - Government of the Republic of Serbia - Controlled body - National Prevention Mechanism | Continuously |  | Budget of the Republic of Serbia- 106. 375 € In 2014. - 21.275 € In 2015. - 21.275 € In 2016. - 21.275 € In 2017. - 21.275 € In 2018. - 21.275 € |  |  | National Prevention Mechanism and state authority bodies actively cooperate in the process of monitoring the effectiveness of acting of the state authority bodies in line with the recommendations of the National Prevention Mechanism |  |  |
| 3.3. PRISON SYSTEM |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.3.1. Further improve prison conditions and take measures to reduce the prison population, in particular alternative sanctions could be further explored. Take measures to effectively reduce ill treatment in police custody. |  |  |  | Living conditions in prisons improved in terms of accommodation, health care, training of convicted individuals, advanced staff training, and judicial review over the exercise of the rights of individuals deprived of liberty, supervision over the implementation of sanctions and improved treatment programs for convicted individuals and vulnerable categories of convicted individuals. Implemented measures to reduce the prison population, particularly through the widespread use of alternative sanctions. Measures to effectively reduce ill treatment in police custody undertaken. |  |  |  |  | - Report of the Ombudsman indicating the improvement of living conditions in prisons and the number of ill treatment in police custody decreased. - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia's in the part referring to the prison system - A higher percentage of the implementation of alternative sanctions noted in the Report of the Republic Institute for Statistics - Report of the Ombudsman indicating effective implementation of alternative sanctions - Positive assessment of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment - Report of the National Mechanism for the Prevention of Torture, which concludes a significant positive progress. |  |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.3.1.1. | - Construction of new buildings and departments in order to improve living conditions in prisons: Initiate the construction of prisons in Pancevo and Kragujevac. - Finalization of works on the construction of prisons in Pancevo and Kragujevac enabling the start of their operation, pursuant to the construction plan. The same activity under item 3.1.1.8. | - Administration for enforcement of criminal sanctions |  | Initiation of construction: IV quarter 2015 Finalization of works: 2018 |  | Development Bank of the Council of Europe, EU (IPF3) Budget of the Republic of Serbia Budgeted in activity 3.1.1.8. |  |  | Prisons in Pancevo and Kragujevac constructed |  |  |
| 3.3.1.2. | Reconstruction of existing accommodation capacity of the current institutions in accordance with European standards and their alignment with existing standards, including the following institutions District Prison in Belgrade District Prison in Uzice Criminal Correctional Facility Valjevo Criminal Correctional Facility Zabela Criminal Correctional Facility Ćuprija Criminal Correctional Facility Niš Correctional Facility for Women Pozarevac Correctional Educational Facility Krusevac Special Prison Hospital Belgrade The same activity under item 3.1.1.9. | - Administration for enforcement of criminal sanctions |  | By the end of 2018. |  | The donation of the Kingdom of Norway IPA Budget of the Republic of Serbia Budgeted in activity 3.1.1.9. |  |  | Reconstruction of accommodation capacities of the current institutions in accordance with European standards finalized |  |  |
| 3.3.1.3. | Conduct analysis on achievement and impact of the Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions for the period of 2010 - (31.12.2014) 2015. | - Administration for enforcement of criminal sanctions |  | I and II quarter of 2015 |  | Budget of the Republic of Serbia- 30.878 € In 2015. |  |  | Analysis of realization and impact of the Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions for the period of 2010 – (31.12.2014) 2015 conducted and key obstacles in its implementation identified. |  |  |
| 3.3.1.4. | Develop new multiannual Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions in line with the results of the analysis | - Administration for enforcement of criminal sanctions |  | III quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.3.1.3. |  |  | New multiannual Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions developed in line with the results of the analysis. |  |  |
| 3.3.1.5. | Draft Action plan for the implementation of Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions followed by establishment of effective mechanism for monitoring the implementation of the Action Plan. | - Administration for enforcement of criminal sanctions |  | IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.3.1.3. |  |  | Action plan for the implementation of Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions developed; Effective mechanism for monitoring the implementation of the Action Plan established. |  |  |
| 3.3.1.6. | Conduct training of enforcement judges in the field of: - rights of individuals deprived of liberty - contemporary trends in enforcement of criminal sanctions -recognized standards in treatment and post penal support | - Administration for enforcement of criminal sanctions |  | Continuously, commencing from IV quarter of 2014. |  | Budget of the Republic of Serbia- 6.000 € In 2014. - 1.200 € In 2015. - 1.200 € In 2016. - 1.200 € In 2017. - 1.200 € In 2018. - 1.200 € |  |  | Enforcement judges improved their knowledge through training on: - rights of individuals deprived of liberty - contemporary trends in enforcement of criminal sanctions -recognized standards in treatment and post penal support |  |  |
| 3.3.1.7. | Ensure more effective judicial review and supervision over the rights of individuals deprived of liberty by: - Establishing sustainable system of provision of information to individuals deprived of liberty on the content of their rights and protection mechanisms in the proceedings before the enforcement judge. The same activity under item 3.1.1.10. | - Administration for enforcement of criminal sanctions |  | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.3.1.10. |  |  | More effective judicial review and supervision over the rights of individuals deprived of liberty secured by regular provision of information to individuals deprived of liberty on the content of their rights and protection mechanisms in each case. |  |  |
| 3.3.1.8. | Analysis of the functioning of the system for enforcement of criminal sanctions. The same activity under item 3.1.1.12. | - Administration for enforcement of criminal sanctions |  | IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.3.1.11. |  |  | Analysis of the functioning of the system for enforcement of criminal sanctions conducted including recommendations for its improvement.. |  |  |
| 3.3.1.9. | Development of a plan to expand competencies of the enforcement judge | - Ministry of Justice - Administration for enforcement of criminal sanctions |  | I quarter of 2016. |  | Budget of the Republic of Serbia- 8.642 € In 2016. |  |  | A plan to expand competencies of the enforcement judge developed. |  |  |
| 3.3.1.10. | Amend the Law on enforcement of criminal sanctions in order to expand competencies of the enforcement judge | - Ministry of Justice - Administration for enforcement of criminal sanctions -National assembly |  | I quarter of 2017. |  | Budget of the Republic of Serbia 8.642 € In 2017. |  |  | Amendments to the Law on enforcement of criminal sanctions adopted |  |  |
| 3.3.1.11. | Conduct training of staff for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. The same activity under item 3.1.1.11. | - Administration for enforcement of criminal sanctions |  | Continuously, commencing from I quarter of 2015. |  | IPA 2013 Budget of the Republic of Serbia Budgeted in activity 3.1.1.11. |  |  | Staff training conducted. Relevant staff improved their knowledge and skills for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. |  |  |
| 3.3.1.12. | Amend and supplement criminal legislation in order to introduce new forms and types of alternative measures and sanctions and align with European standards in this area | - Ministry of Justice |  | I quarter of 2016. |  | Budget of the Republic of Serbia- 17.285 € In 2016. |  |  | Amendments and supplements to the criminal legislation introducing new forms and types of alternative measures and sanctions and aligning with European standards in this area adopted |  |  |
| 3.3.1.13. | Reorganization of existing services for the treatment and alternative sanctions within the Administration for enforcement of criminal sanctions by establishing special department for alternative sanctions in accordance with the new job classification. | - Administration for enforcement of criminal sanctions |  | IV quarter of 2015. |  | Budget of the Republic of Serbia- 255.300 € In 2016. - 86.100 € In 2017. - 86.100 € In 2018. - 86.100 € |  |  | A special department for alternative sanctions within the Administration for enforcement of criminal sanctions established. |  |  |
| 3.3.1.14. | Establishment of the entire network of offices for alternative sanctions by opening 9 new offices for alternative sanctions, namely: - by opening 3 offices by the end of 2014. - by opening 6 offices by the end of 2015. | - Administration for enforcement of criminal sanctions |  | Opening 3 offices: IV quarter of 2014 Opening 6 offices: IV quarter of 2015. |  | Budget of the Republic of Serbia- 772.500 € In 2014. - 154.500 € In 2015. - 154.500 € In 2016. - 154.500 € In 2017. - 154.500 € In 2018. - 154.500 € |  |  | 9 new offices for alternative sanctions operational by the end of 2015. |  |  |
| 3.3.1.15. | Conduct training for holders of judicial functions and new commissioners for alternative sanctions. | - Administration for enforcement of criminal sanctions - Judicial academy |  | Continuously |  | Budget of the Republic of Serbia- 6.000 € In 2014. - 1.200 € In 2015. - 1.200 € In 2016. - 1.200 € In 2017. - 1.200 € In 2018. - 1.200 € |  |  | Training for holders of judicial functions, and new commissioners for alternative sanctions, conducted. |  |  |
| 3.3.1.16. | Develop Rulebook on supervision and regular reporting on effective implementation of alternative sanctions. | - Administration for enforcement of criminal sanctions |  | III and IV quarter of 2015 |  | Total- 10.392 € Budget of the Republic of Serbia- 8.642 € TAIEX - 1.750 € In 2015. |  |  | Rulebook on supervision and regular reporting on effective implementation of alternative sanctions developed. |  |  |
| 3.3.1.17. | Signing Protocol on cooperation of the offices for alternative sanctions and local self-government units for the purpose of strengthening cooperation and establishing conditions for successful social reintegration of convicted individuals upon release. | - Administration for enforcement of criminal sanctions - Representatives of local self-government |  | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Protocol on cooperation of the offices for alternative sanctions and local self-government units for the purpose of strengthening cooperation and establishing conditions for successful social reintegration of convicted individuals upon release signed. |  |  |
| 3.3.1.18. | Conduct analysis of the current situation regarding: - detention units of the Ministry of Interior (human, technical, and spatial capacities) - normative framework of the Ministry of Interior regulating the treatment of detainees and persons remanded in custody - identify weaknesses and risks in the treatment of the detainees and persons in custody. | - Ministry of Interior |  | I and II quarter of 2015. |  | Total- 17.189 € Budget of the Republic of Serbia- 15.439 € TAIEX– 1.750 € In 2015. |  |  | The analysis of the current situation conducted with recommendations: - for legislative framework amendments; - improvement of the conditions in detention; - for addressing weaknesses and risks in treatment of detainees and persons in custody. |  |  |
| 3.3.1.19. | Revise the normative framework of the Ministry of Interior governing the treatment of detainees and persons remanded in custody. The same activity under item 3.1.1.1. | - Ministry of Interior -National assembly |  | III and IV quarter of 2015. |  | Budget of the Republic of Serbia TAIEX Budgeted in activity 3.1.1.1. |  |  | Amendments and supplements to the normative framework of the Ministry of Interior governing the treatment of detainees and persons in custody adopted. |  |  |
| 3.3.1.20. | Introduce a system of mandatory education for new police officers and continuous education for current police officers regarding the treatment of detainees and persons remanded in custody in accordance with international standards in the field of human rights, professional ethics and acting in high risk situations.. The same activity under item 3.1.1.2. | Ministry of Interior |  | II quarter of 2016. |  | Budget of the Republic of Serbia TAIEX Budgeted in activity 3.1.1.2. |  |  | - Conducted training for 200 police officers on an annual basis; -Decreased number of complaints about the conduct of police officers towards detainees and persons remanded in custody |  |  |
| 3.3.1.21. | Construction, renovation and equipping of facilities for detention in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman) The same activity under item 3.1.1.3. | - Ministry of Interior |  | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia IPA 2015 Budgeted in activity 3.1.1.3. |  |  | Constructed and restored facilities for detention in accordance with the recommendations of the CPT ; Necessary equipment for detention facilities purchased in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman). |  |  |
| 3.3.1.22. | Strengthening the supervision mechanism at the Ministry of Interior for the implementation of standards of police conduct in the field of torture prevention through; - training of the members of the Commission for the implementation of standards of police conduct in the field of torture prevention in order to effectively perform their duties; - training of the detention units’ directors in order to effectively monitor police conduct; -training of police officers working in the police stations in order to prevent any prohibited treatment; - Improvement of records in detention units ; - Performing unexpected visits to places of detention in order to control the implementation of the recommendations of the National Mechanism for the Prevention of Torture; - Introduction of clear procedures of treatment of detainees and persons remanded into custody to ensure the exercise of their rights (e.g. the right to access to a lawyer, contact with close relatives, the right to health care). The same activity under item 3.1.1.4. | - Ministry of Interior |  | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia TAIEX IPA2015 Budgeted in activity 3.1.1.4. |  |  | - Capacities of the supervision mechanism at the Ministry of Interior in the field of torture prevention strengthened through: -Conducted training on the prevention of torture; - Improved coordination of the Ombudsman and non-governmental sector; - Unexpected visits to places of detention carried out regularly; - Established procedures for treatment of detainees and persons remanded into custody ensuring the exercise of their rights; - Established procedures for records keeping on the and detained persons and persons remanded into custody and forms developed. |  |  |
| 3.3.1.23. | Intensify cooperation with the National Mechanism for the Prevention of Torture by holding regular meetings and reporting on actions undertaken pursuant the recommendations of the National Mechanism for the Prevention of Torture . The same activity under item 3.1.1.5. | - Ministry of Interior |  | Continuously |  | Budget of the Republic of Serbia Budgeted in activity 3.1.1.5. |  |  | Cooperation between the Ministry of Interior and National Mechanism for the Prevention of Torture intensified. |  |  |
| 3.3.1.24. | Intensify cooperation between the Ministry of Interior with state authorities, national mechanism for the prevention of torture and civil society organizations in the field of torture prevention through: - Organization of workshops and discussions on the prohibition of torture in police, unprofessional behavior of police officers and respect for the rights of detained persons and persons remanded into custody; - Establishment of a practice of the Ministry of Interior to report in writing on the measures taken in accordance with the recommendations of civil society organizations. - Raising awareness on prevention of torture in the police among police officers and provision of information to the public on the rights of detainees and persons remanded into custody. The same activity under item 3.1.1.6. | - Ministry of Interior |  | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.1.1.6. |  |  | Cooperation between the Ministry of Interior with state authorities, national mechanism for the prevention of torture and civil society organizations intensified. Workshops and discussions on the prohibition of torture in police and awareness raising organized. Signed cooperation protocols between the Ministry of Interior and civil society organizations. Ministry of Interior regularly reports on undertaken measures in accordance with the recommendations of civil society organizations. Awareness raising campaign conducted. |  |  |
| 3.3.1.25. | Development of a methodology for the prosecution and the police to investigate cases of abuse and torture in order to conduct effective investigations into allegations of ill-treatment and torture by police. The same activity under item 3.1.1.7. | Ministry of Interior |  | I quarter of 2016. |  | Budget of the Republic of Serbia OECD mission to the Republic of Serbia Budgeted in activity 3.1.1.7. |  |  | Document on methodology to investigate allegations of ill-treatment and torture by police drafted. |  |  |
| 3.4. FREEDOM OF THOUGHT, CONSCIENCE AND RELIGION |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.4.1. Ensure state neutrality towards the internal affairs of religious communities and further ensure that the right of persons belonging to a national minority to equal access to religious institutions, organizations and associations is consistently guaranteed in both legislation and its implementation in line with independent bodies recommendations. |  |  |  | State neutrality towards the internal affairs of religious communities ensured and right of persons belonging to a national minority to equal access to religious institutions, organizations and associations ensured and consistently guaranteed. |  |  |  |  | - Positive opinion of the European Commission in the Annual Progress Report on Serbia in the part referring to freedom of confession - Report of the Ombudsman noting progress in achieving freedom of thought, conscience and religion; - Regular reports of the monitoring body |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.4.1.1. | Conduct comparative legal expert analysis regarding the regulation of the status of churches and religious communities in order to establish specific criteria on the basis of best practices of the EU member states in the region (e.g. Romania, Croatia, Slovenia, Hungary) and implement solutions adopted in the region. |  | - Administration for cooperation with churches and religious communities | I and II quarter of 2015. |  | Budget of the Republic of Serbia - 9.574 € In 2015. |  |  | Comparative analysis of best practices of the European Union member states in the region in terms of regulation of the status of churches and religious communities conducted. |  |  |
| 3.4.1.2. | Implementation of recommendations arising from the analysis of best practices of the European Union member states in the region in terms of regulation of the status of churches and religious communities. |  | - Administration for cooperation with churches and religious communities | Continuously, commencing from III quarter of 2015. |  | Budget of the Republic of Serbia Currently unknown until finalization of the analysis. |  |  | Recommendations arising from the analysis of best practices of the European Union member states in the region in terms of regulation of the status of churches and religious communities implemented. |  |  |
| 3.4.1.3 | Presentation of the results of the analysis to the employees at the Ministry of Justice and Administration for cooperation with churches and religious communities |  | - Ministry of Justice | III quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | The results of the analysis presented to the employees at the Ministry of Justice and Administration for cooperation with churches and religious communities at the workshop. Participants improved their knowledge with regard to EU best practices in regulation of the status of churches and religious communities. |  |  |
| 3.4.1.4 | Strengthen administrative capacities by training for the employees at the Ministry of Justice (sector for normative affairs and register of churches and religious communities), |  | - Administration for cooperation with churches and religious communities - Ministry of Justice | III and IV quarter of 2015. |  | Budget of the Republic of Serbia- 300 € In 2015. |  |  | Administrative capacities at the Ministry of Justice (sector for normative affairs and register of churches and religious communities) strengthened through training. |  |  |
| 3.4.1.5. | Strengthen administrative capacities of the Administration for cooperation with churches and religious communities by hiring 3 new staff in line with the existing job classification. |  | - Administration for cooperation with churches and religious communities | - 2017. |  | Budget of the Republic of Serbia- 63.825 € In 2017. - 31.913 € In 2018. - 31.913 € |  |  | Administrative capacities of the Administration for cooperation with churches and religious communities strengthened by hiring 3 new staff . |  |  |
| 3.4.1.6. | Establishment of a mechanism for regular monitoring of the status of churches and religious communities |  | - Ministry of Justice | IV quarter of 2015. |  | Budget of the Republic of Serbia- 11.523 € In 2015. - 2.881 € In 2016. - 2.881 € In 2017. - 2.881 € In 2018. - 2.881 € |  |  | Mechanism for regular monitoring of the status of churches and religious communities established. |  |  |
| 3.5. FREEDOM OF EXPRESSION AND FREEDOM AND PLURALISM OF MEDIA |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.5.1. Ensure protection of journalists against threats and violence, in particular through effective investigations and deterrent sanctioning of past attacks. |  |  |  | More efficient protection of journalists against threats and violence ensured through improvement of the system of preventive measures undertaken for the purpose of protecting journalists and prioritization of investigations of threats and violence against journalists in order to effectively sanction past attacks. |  |  |  |  | - Positive opinion of the European Commission in the Annual Progress Report on Serbia in the part relating to higher extent of protection of journalists against threats and violence - Positive report of the Ombudsman in the part relating to higher extent of protection of journalists against threats and violence - Increased number of indictments raised against persons who jeopardized the safety of journalists. - Report of the Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.5.1.1. | Analyze the relevant provisions of the Criminal Code in order to assess the need for amendments and supplements that would lead to a higher level of protection for journalists from threats of violence. |  | - Working group established by the Ministry of Justice | IV quarter of 2015. |  | Total- 32.628 € Budget of the Republic of Serbia- 30. 878 € TAIEX - 1.750 € In 2015. |  |  | Analysis of the Criminal Code developed including recommendations for establishment of a more efficient protection of journalists against threats and violence. |  |  |
| 3.5.1.2. | Continuation of the work of the Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists and provision of regular reports. |  | - Government of the Republic of Serbia - Commission for consideration of the facts that were obtained in the investigations that were conducted on the killings of journalists | Continuously |  | Budget of the Republic of Serbia- 11.523 € In 2014. - 2.305 € In 2015. - 2.305 € In 2016. - 2.305 € In 2017. - 2.305 € In 2018. - 2.305 € |  |  | Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists actively operates and provides regular reports. |  |  |
| 3.5.1.3. | Amendments and supplements to the Rules of procedure on Administration of Public Prosecutions in terms of keeping records of offenders of the criminal offences against journalists and designation of these criminal offences as a priority in acting. |  | - Minister of Justice | I and II quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.2.1.12. |  |  | Amendments and supplements to the Rules of procedure on Administration of Public Prosecutions prioritizing the acting upon criminal offences against journalists adopted. |  |  |
| 3.5.1.4. | Drafting and signing of a cooperation agreement of the Republic Public Prosecutor's Office and the Ministry of Interior, stipulating acting in the investigation of threats and violence against journalists as a priority in order to improve the efficiency of the investigation of the attacks on journalists and prosecute the perpetrators. |  | - Republic Public Prosecutor's Office - Ministry of Interior | II quarter 2015 |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Cooperation agreement between Republic Public Prosecutor's Office and the Ministry of Interior improving the efficiency of the investigation of the attacks on journalists and prosecute the perpetrators signed. |  |  |
| 3.5.1.5. | Improve the system of preventive measures undertaken for the purpose of protection of journalists from threats of violence by: - Analysis of the risk of vulnerability of journalists conducted in cooperation with representatives of journalists’ associations. - Continuously monitoring of the situation in the printed and electronic media in order to determine the risk of vulnerability of journalists. |  | - Ministry of Interior (police directorate) | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia- 85.100 € In 2015. - 21.275 € In 2016. - 21.275 € In 2017. - 21.275 € In 2018. - 21.275 € |  |  | System of preventive measures undertaken for the purpose of protection of journalists improved in cooperation with representatives of journalists’ associations. Quarterly reporting on the situation in the printed and electronic media in order to determine the risk of vulnerability of journalists. |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.5.2. Review and amend the legislative and institutional framework for the protection of media freedom by implementing the Media strategy with a view to appropriately regulating state funding and putting an end to control of media by the State. Take urgent measures to stop threats and violence against journalists as well as media leaks related to ongoing or planned criminal investigations. |  |  |  | Improved legal and institutional framework for the protection of media freedoms. Achieved full withdrawal of state ownership of the media. Greater extent of protection of journalists' safety achieved. Absence of unauthorized disclosure of information related to ongoing or planned criminal investigations to the media. |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia in the part relating to media freedom and safety of journalists. - Positive report of the Ombudsman in the part relating to a higher level of protection of media freedoms. - Periodic Report of the Sector for media and information of the Ministry for culture and information - Fewer cases of media leaks about ongoing or planned criminal investigations. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.5.2.1. | Organization of a conference to promote a new set of media laws: Law on Public Information, Law on Electronic Media Law on public service media |  | - Ministry for culture and information | IV quarter 2014. |  | IPA 2012 “Strengthening media freedoms” Budgeted in Chapter 10 |  |  | Conference organized, conclusions from the Conference published. |  |  |
| 3.5.2.2. | Efficient monitoring the implementation of the set of media laws and periodic reporting. |  | - Ministry for culture and information | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia 42.550 € In 2015. - 10.638 € In 2016. - 10.638 € In 2017. - 10.638 € In 2018. - 10.638 € |  |  | Reports of the Ministry for culture and information publicly available. |  |  |
| 3.5.2.3. | Conduct an analysis of the effects of the Strategy for the Development of Public Information System (2011-2016). |  | - Ministry for culture and information | I and II quarter of 2015. |  | Budget of the Republic of Serbia- 30.878 € In 2015. |  |  | An analysis of the effects of the Strategy for the Development of Public Information System (2011-2016) conducted and key obstacles in its implementation identified. |  |  |
| 3.5.2.4. | Develop a new multiannual Strategy for the Development of Public Information System. |  | - Ministry for culture and information | IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.5.2.3. |  |  | A new multiannual Strategy for the Development of Public Information System developed. |  |  |
| 3.5.2.5. | Develop Action Plan for implementation of a new multiannual Strategy for the Development of Public Information System. |  | - Ministry for culture and information | I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 3.5.2.3. |  |  | Action Plan for implementation of a new multiannual Strategy for the Development of Public Information System developed. |  |  |
| 3.5.2.6. | Develop and sign the Cooperation Agreement among the Public Prosecutors' Office, Ministry of Interior and relevant associations of journalists (contact points, information exchange on events that do not constitute criminal offences, problem identification, etc.). |  | - Republic Public Prosecutors' Office (Public Prosecutor) - Ministry of Interior (Minister) - Presidents of the associations of journalists | II quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Cooperation Agreement among the Public Prosecutors' Office, Ministry of Interior and representative/relevant associations of journalists establishing a higher level of safety protection of journalists signed. |  |  |
| 3.5.2.7. | Develop Communication Strategy of the public prosecutors' offices with the media aimed at defining relationship, methods and scope of communication. |  | - Republic Public Prosecutors' Office (department for public relations) | II quarter of 2015. |  | Budget of the Republic of Serbia - 8.642 € In 2015. |  |  | Communication Strategy of the public prosecutors' offices with the media developed. |  |  |
| 3.5.2.8. | Develop Communication Strategy of the Ministry of Interior with the media aimed at defining relationship, methods and scope of communication. |  | - Ministry of Interior | II quarter of 2015. |  | Budget of the Republic of Serbia- 8.642 € In 2015. |  |  | Communication Strategy of the Ministry of Interior with the media aimed at defining relationship, methods and scope of communication developed. |  |  |
| 3.5.2.9. | Amendment and supplements to the Code of Ethics and the Rules of the disciplinary proceedings and disciplinary responsibilities of public prosecutors and deputy public prosecutors in the part relating to the accountability of public prosecutors and deputy public prosecutors for unauthorized communication of information about ongoing or planned investigations to the media. |  | - State Prosecutorial Council-president, Republic Prosecutors Office (deputy public prosecutor) | II and III quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.6.4. |  |  | Amendment and supplements to the Code of Ethics and the Rules of the disciplinary proceedings and disciplinary responsibilities of public prosecutors and deputy public prosecutors adopted. |  |  |
| 3.5.2.10. | Amendment and supplements to the law governing internal affairs stipulating that unauthorized communication to the media represents serious breach of duty |  | - Ministry of Justice - National Assembly | II quarter of 2015. |  | Budget of the Republic of Serbia- 48.900 € In 2015. |  |  | Amendments and supplements to the law governing internal affairs stipulating that unauthorized communication to the media represents serious breach of duty adopted. |  |  |
| 3.5.2.11. | Amendment and supplements to the Code of Police Ethics and law governing internal affairs in the part relating to the responsibility of police officers for unauthorized communication of information about ongoing or planned investigations to the media. |  | - Ministry of Interior - Government of the Republic of Serbia | II quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.1.6.3. |  |  | Amendment and supplements to the Code of Police Ethics and Regulation on disciplinary responsibility of the Ministry of Internal Affairs adopted |  |  |
| 3.5.2.12. | Amendments and supplements to the bylaws governing the procedures of confidentiality and safety of planning and conducting criminal investigations in order to improve the privacy and protection of police procedures for the planning and implementation of criminal investigations. |  | - Ministry of Interior | II quarter of 2016. |  | Budget of the Republic of Serbia- 8.642 € In 2016. |  |  | Amendments and supplements to the bylaws governing the procedures of confidentiality and safety of planning and conducting criminal investigations in order to improve the privacy and protection of police procedures for the planning and implementation of criminal investigations adopted |  |  |
| 3.5.2.13. | Adopt a by-law which establishes procedures for issuing statements of police officers to the media. |  | - Ministry of Interior | II quarter of 2016. |  | Budget of the Republic of Serbia- 8.642 € In 2016 |  |  | By-law which establishes procedures for issuing statements of police officers to the media adopted. |  |  |
| 3.5.2.14. | Conduct training for public prosecutors, deputy public prosecutors, police officers and representatives of relevant associations of journalist, with regard to: - prevention of media leaks related to ongoing or planned criminal investigations prevention of media leaks related to respect for privacy with regard to vulnerable persons (victims, children) |  | - Ministry of Justice - Ministry of Culture and Information - Republic Public Prosecutors’ Office | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia - 3.600 € In 2016. - 1.200 € In 2017. - 1.200 € In 2018. - 1.200 € IPA 2012 “Strengthening media freedoms” Budgeted in Chapter 10 |  |  | Training for public prosecutors, deputy public prosecutors, police officers and representatives of relevant associations of journalist conducted. Participants improved their knowledge to prevent media leaks related to ongoing or planned criminal investigations and prevention of media leaks related to respect for privacy with regard to vulnerable persons (victims, children). |  |  |
| 3.6. PRINCIPLE OF NON-DISCRIMINATION AND SOCIAL POSITION OF VULNERABLE GROUPS |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.6.1. Complement the anti-discrimination strategy with a credible action plan, including actions to foster gender equality and a mechanism to monitor its implementation. Strengthen the institutional capacity of the bodies active in this area, improve their cooperation and ensure more effective follow up from the law enforcement bodies to possible violations, enhance awareness and support measures, especially on employment and public representation of women. Particular focus should be put on ending discrimination of the LGBTI community and respecting their rights and freedoms; Adopt the Law aiming at protecting persons with mental disabilities in institutions of social welfare |  |  |  | Action plan for the implementation of anti-discrimination strategy adopted; the status of women and gender equality improved along with the establishment of an effective mechanism to monitor the situation in the field of discrimination. The position of the LGBT community promoted and the respect of their rights and freedoms secured. Legal safeguards for persons in specialized institutions reinforced in line with international human rights standards. Provision of adequate care and living conditions for residents and the parallel development of community-based care services in line with the UN Convention on the Rights of Persons with Disabilities. |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia in the part relating to anti-discrimination - Positive report of the Ombudsman in the part relating to anti-discrimination - Positive peer review report on anti-discrimination - Reports on the Government provided to relevant committees of the National Assembly - Reports and completed questionnaires of the CEDAW Committee of the United Nations, ascertaining the progress of Serbia - Report of the Group of Experts of the Council of Europe for the prevention of violence against women and domestic violence GREVIO confirming Serbia's progress. - Annual report of the Commissioner for the Protection of Equality stating progress of Serbia in the field of anti-discrimination - Report of the European Commission against Racism and Intolerance (ECRI) noting improved situation with regard to discrimination - Number of held and prohibited public gatherings. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.6.1.1. | Adoption of the Action Plan for the implementation of the Strategy for prevention and protection from discrimination. |  | - Government of the Republic of Serbia | IV quarter of 2014. |  | Budget of the Republic of Serbia- 30.878 € In 2014. |  |  | Action Plan for the implementation of the Strategy for prevention and protection from discrimination adopted. |  |  |
| 3.6.1.2. | Establishment and start of operations of the body for monitoring and supervision over the implementation of the Strategy and Action Plan for prevention and protection from discrimination. |  | - Government of the Republic of Serbia | II quarter of 2015. |  | Budget of the Republic of Serbia- 9.218 € In 2015. - 2.305 € In 2016. - 2.305 € In 2017. - 2.305 € In 2018. - 2.305 € |  |  | Body for monitoring and supervision over the implementation of the Strategy and Action Plan for prevention and protection from discrimination established and provides regular reports. |  |  |
| 3.6.1.3. | Conduct an analysis of the current implementation of the Law on Prohibition of Discrimination in particular in terms of: -volume of exceptions to principle of equal treatment; - definition of indirect- discrimination; - obligations related to ensuring reasonable accommodation for employees with disabilities. |  | - Commissioner for the Protection of Equality | III-IV quarter of 2015. |  | Budget of the Republic of Serbia - 8.642 € In 2015. |  |  | Analysis of the implementation of the Law on Prohibition Discrimination conducted and key obstacles in its implementation identified. |  |  |
| 3.6.1.4. | Amendments and supplements to the Law on Prohibition of Discrimination to fully align with the EU Acquis and in particular with regard to: -volume of exceptions from the principle of equal treatment, - definition of indirect discrimination - obligation to provide the reasonable accommodation for employees with disabilities. |  | - Working group established by the Ministry of Labor, Employment, Veterans and Social Affairs - Partner organization - Commissioner for the Protection of Equality -National assembly | I quarter of 2016. |  | Budget of the Republic of Serbia- 8.642 € In 2016. |  |  | Amendments and supplements to the Law on Prohibition of Discrimination adopted, enabling full alignment with the EU Acquis , in particular with regard to: volume of exceptions from the principle of equal treatment, - definition of indirect discrimination - obligation to provide the Reasonable accommodation for employees with disabilities. |  |  |
| 3.6.1.5. | Conduct a detailed analysis of the alignment of criminal justice legislation with Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) |  | -Ministry of Justice | III quarter of 2015. |  | Budget of the Republic of Serbia - 30.878 € In 2015. |  |  | A detailed analysis of the alignment of criminal justice legislation with Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) conducted including recommendations for the amendments to the legislative framework. |  |  |
| 3.6.1.6. | Amend the Criminal Code in line with the analysis of alignment with the provisions of the Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) |  | -Ministry of Justice -National assembly | I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 3.6.1.5. |  |  | Amendments to the Criminal Code in line with the analysis of alignment with the provisions of the Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) |  |  |
| 3.6.1.7. | Analysis of the effects of the National Strategy for improving the status of women and promoting gender equality ("Official Gazette RS ", No. 15/09). |  | - Working group established by the Coordination body for gender equality | I and II quarter of 2015. |  | Budget of the Republic of Serbia- 30.878 € In 2015. |  |  | Analysis of the effects of the National Strategy for improving the status of women and promoting gender equality performed and key obstacles to its implementation identified |  |  |
| 3.6.1.8. | Preparation and adoption of a new multi-annual strategy and Action Plan for the empowerment of women and promotion of gender equality for the period after the 2015, in line with recommendations from the analysis of the effects of the previous National Strategy for improving the status of women and promotion of gender equality. |  | - Working group established by the Coordination body for gender equality | IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.6.1.7. |  |  | New multi-annual strategy and Action Plan for the empowerment of women and promotion of gender equality for the period after the 2015 adopted. |  |  |
| 3.6.1.9. | Strengthening the capacities of the Unit for Gender Equality of the Ministry competent for social protection through staff training in order to effectively coordinate implementation and monitoring of gender equality policies in particular in relation to: - Implementation of the Council of Europe Convention on preventing and combating violence against women and domestic violence; - Monitoring the implementation of the Concluding Observations of the UN Committee on the Elimination of Discrimination against Women |  | - Ministry of Labor, Employment, Veterans and Social Affairs - Commissioner for the Protection of Equality | I and II quarter of 2016. |  | Budget of the Republic of Serbia - 300 € In 2016. |  |  | Training of the staff at the Unit for Gender Equality of the Ministry competent for social protection conducted and their capacity strengthened with regard to: - Implementation of the Council of Europe Convention on preventing and combating violence against women and domestic violence; - Monitoring the implementation of the Concluding Observations of the UN Committee on the Elimination of Discrimination against Women. |  |  |
| 3.6.1.10. | Strengthening the capacity of the Office of Human and Minority Rights, for the purpose of monitoring the implementation of the Strategy for prevention and protection against discrimination through the recruitment of 2 new employees. |  | - Office of Human and Minority Rights | I and II quarter of 2016. |  | Budget of the Republic of Serbia - 63.825 € In 2016. - 21.275 € In 2017. - 21.275 € In 2018. - 21.275 € |  |  | Capacity of the Office of Human and Minority Rights strengthened through employment of new staff in order to efficiently monitor the implementation of the Strategy for prevention and protection against discrimination |  |  |
| 3.6.1.11. | Strengthening the capacity of the Commissioner for the Protection of Equality in accordance with the existing job classification. |  | - Commissioner for the Protection of Equality | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia Cost currently unknown. |  |  | Capacity of the Commissioner for the Protection of Equality strengthened in accordance with the existing job classification. |  |  |
| 3.6.1.12. | Monitoring the implementation of the Law on Anti-discrimination |  | -- Commissioner for the Protection of Equality | Continuously |  | Budget of the Republic of Serbia - 265.938 € In 2014. - 53.188 € In 2015. - 53.188 € In 2016. - 53.188 € In 2017. - 53.188 € In 2018. - 53.188 € |  |  | Current situation described in the annual report of the Commissioner for the Protection of Equality. |  |  |
| 3.6.1.13. | Conduct regular training and professional development of employees in the institution of the Commissioner for Protection of Equality in order to improve their work through: - knowledge building on work, practice and acting of other equality bodies, amendments to national legislation and international standards. |  | -Staff administration service - Commissioner for the Protection of Equality | Continuously |  | Budget of the Republic of Serbia- 6.000 € In 2014. - 1.200 € In 2015. - 1.200 € In 2016. - 1.200 € In 2017. - 1.200 € In 2018. - 1.200 € |  |  | Training conducted and professional development sessions held. |  |  |
| 3.6.1.14 | Development and distribution of a manual ​​on identification and effective suppression of discrimination cases in Serbian and minority languages for: - judges -public prosecutors and deputy public prosecutors, - police officers, -employees in the state administration and local self-government |  | - Office of Human and Minority Rights - Commissioner for the Protection of Equality - Office for Cooperation with Civil Society | I and II quarter of 2017. |  | IPA 2015 Budget of the Republic of Serbia Currently unknown |  |  | Manual ​​on identification and effective suppression of discrimination cases developed and distributed in all courts, prosecutors' offices and police departments, as well as local self-government units. |  |  |
| 3.6.1.15. | Development and distribution of a manual ​​on identification of discrimination cases and available mechanisms for protection of rights in Serbian and minority languages for the citizens and particularlz vulnerable groups.. |  | - Office of Human and Minority Rights - Commissioner for the Protection of Equality - Office for Cooperation with Civil Society | I and II quarter of 2017. |  | IPA 2015 Budget of the Republic of Serbia Currently unknown |  |  | Manual ​​on identification of discrimination cases and available mechanisms for protection of rights developed and distributed in the premises of the local self- government units, educational institutions, health centers and hospitals |  |  |
| 3.6.1.16. | Conduct media promotional campaign and organize roundtables aimed at promoting the Manual for identification and effective suppression of discrimination cases s and the Manual for identification of cases of discrimination and available mechanisms for protection of rights. |  | - Commissioner for the Protection of Equality - Office for Cooperation with Civil Society - Office of Human and Minority Rights | III and IV quarter of 2017. |  | IPA 2015 Budget of the Republic of Serbia Currently unknown |  |  | Media campaign conducted and roundtables aimed at promoting the Manual for identification and effective suppression of discrimination cases s and the Manual for identification of cases of discrimination and available mechanisms for protection of rights organized. |  |  |
| 3.6.1.17. | Organize workshops for journalists aimed at preventing incitement to discrimination through media. |  | - Ministry for culture and information - Commissioner for the Protection of Equality - Representative Association of Journalists - Civil society organizations | III and IV quarter of 2015. |  | Budget of the Republic of Serbia - 600 € In 2015. |  |  | Workshops for journalists in order to prevent incitement to discrimination through media organized. |  |  |
| 3.6.1.18 | Continue the development of a model of community policing, particularly in multi-ethnic and multicultural communities, by implementing security prevention in partnership with other state and local entities and contributing to the development of tolerance in society. |  | - Ministry of Interior - Ministry of State Administration and Local Self-government | Continuously, commencing from I quarter of 2015. |  | Total- 36.320 € Budget of the Republic of Serbia- 34.570 € TAIEX- 1.750 € In 2015. – 10.393 € In 2016. - 8.643 € In 2017. - 8.643 € In 2018. - 8.641 € |  |  | Established model of community policing, particularly in multiethnic and multicultural communities and in partnership with other state and local entities. |  |  |
| 3.6.1.19 | Appointment of police officers as contact points for the socially vulnerable groups in order to foster cooperation and protect their safety at national and regional level and, if required, in smaller urban areas and work to improve cooperation between police representatives and associations of socially vulnerable groups. |  | - Ministry of Interior - Vulnerable groups’ associations | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Police officers as contact points for the socially vulnerable groups appointed and started operating. |  |  |
| 3.6.1.20. | Continuously hold meetings of the police with representatives of socially vulnerable groups, the LGBT community and civil society organizations to foster sensitization and enhance co-operation and foster prevention to ensure security and protection of human and minority rights. |  | -Ministry of Interior - Civil society organizations | Continuously, commencing from IV quarter of 2014. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Through active cooperation and regular meetings with police representatives, socially vulnerable groups, LGBT community and civil society organizations, established mutual relations of trust and improved preventive action in achieving security and protection of human and minority rights. |  |  |
| 3.6.1.21 | Adoption of the law on peaceful assembly, in order to to align with Article 11 of the European Convention of Human Rights and fundamental freedoms and Article 12 of the charter of Fundamental Rights of the European Union, in particular as regards the right to freedom of peaceful assembly, locations for holding a public assembly, responsibilities of the organizer of a public assembly and reasons for banning and suspension of a public assembly. |  | - Ministry of Interior -National assembly | II quarter of 2015. |  | Budget of the Republic of Serbia- 71.386 € In 2015. |  |  | Law on peaceful assembly adopted, enabling full alignment with Article 11 of the European Convention of Human Rights and fundamental freedoms and Article 12 of the charter of Fundamental Rights of the European Union, in particular as regards the right to freedom of peaceful assembly, locations for holding a public assembly, responsibilities of the organizer of a public assembly and reasons for banning and suspension of a public assembly. |  |  |
| 3.6.1.22. | Conducting training of police officers in terms of keeping order at public gatherings and other mass events in accordance with international instruments for the protection of human rights. |  | -- Ministry of Interior | Commencing from IV quarter of 2017. |  | Budget of the Republic of Serbia- 6.000 € In 2017. - 3.000 € In 2018. - 3.000 € |  |  | Police officers improved their skills on keeping order at public gatherings and other mass events in accordance with international instruments for the protection of human rights, through conducted training. |  |  |
| 3.6.1.23 | Conduct an analysis of best practices in the EU in the field of protection of persons with mental disabilities in institutions of social protection with the aim to identify the best model for legislative regulation of this area. This activity will be elaborated in detail in Chapter 19 |  | - Ministry of Labor, Employment, Veterans and Social Affairs |  |  | Budgeting in Chapter 19 |  |  |  |  |  |
| 3.6.1.26. | Strengthen the oversight of living conditions in social care institutions and psychiatric hospitals This activity will be elaborated in detail in Chapter 19 |  | - Ministry of Labor, Employment, Veterans and Social Affairs |  |  | Budgeting in Chapter 19 |  |  |  |  |  |
| 3.6.1.27. | Strengthen social integration of persons with disabilities This activity will be elaborated in detail in Chapter 19 |  | - Ministry of Labor, Employment, Veterans and Social Affairs |  |  | Budgeting in Chapter 19 |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.6.2. Improve the protection and enforcement of rights of the children and of persons with disabilities, including by strengthening the relevant institutions, ensuring better cooperation between the judiciary and the social sector and by fully implementing legislation on juvenile justice in line with EU standards. |  |  |  | Improved protection and enforcement of rights of children and persons with disabilities by strengthening of relevant institutions ensuring better cooperation between the judiciary and the social sector. Social protection system implements solutions that give priority to family support while providing support for children at risk, or provide community living for people with disabilities. The judicial system applies adopted policies and regulations that ensure respect for the principle of the best interests of the child in accordance with EU standards. |  |  |  |  | 1. A continuous increase in the number of children who benefit from family support measures (target - 1,000 families and 2,500 children by 2017 – With regard to intensive family support services (including min.30% of children with disabilities), the target is 2,000 families and 5000 by 2020 for family support services) which prevents the need for the use of alternative care or placement of children in residential institutions or foster care 2. Children who are in need for alternative care are placed in the local community, family type, with an increase in the availability of different options xx% annually (Concept of shared care introduced into the system and operational; increase in the number of children beneficiaries of family housing as shared care; continuous increase in the number of children with disabilities in kinship and foster families 3. Options of alternative aging are selected based on individual situations and needs of each child in accordance with international standards. 4. Number of children and people with disabilities who use institutional care services decreases (target - decrease by 15% by 2017. for children and 5% for adults), 5. The number of children entering institutions for the first time is strictly controlled and supervised, and decreases from year to year, in accordance with defined criteria for institutionalization; target: reduced number of requests by 30% by 2017. 6. The number of children who benefit from the child-oriented-justice increases annually - Implementation of diversion orders increased – percentage of implementation in the total number of criminal charges for criminal offenses committed by juveniles, target 15% by 2017. - implementation of new alternative sanctions: target: 40% by 2018. - improved conditions for the juveniles deprived of liberty (especially those in custody) by 2018 through access to quality education and improved contents for leisure time. - clear procedures established and implemented for the preparation of juveniles for release. - the right of the child to express his or her opinion in accordance with international standards is monitored in judicial proceedings, especially concerning civil guardianship, care or violence and data on implementation is available to the public. 7. Increased availability of community services for people with disabilities and families at risk 8. The report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment noting positive developments in Serbia regarding the rights of children deprived of liberty 9. Positive report of the Ombudsman in the part relating to the rights of children and persons with disabilities. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.6.2.1. | Improve the work of the Council for the Rights of the Child and ensure its role in monitoring the effects of the reforms and further policy making, including through adequate resources to effectively monitor and track implementation of the action plans and strategies in the area of rights of the child. |  | - Ministry of Labor, Employment, Veterans and Social Affairs | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia - 24.702 € In 2015. - 6.176 € In 2016. - 6.176 € In 2017. - 6.176 € In 2018. - 6.176 € |  |  | Council for the Rights of the regularly and efficiently monitors the reforms and provides regular reports. |  |  |
| 3.6.2.2. | Organizing support services for children, adults and older people with intellectual disabilities and their families, in order to prevent institutionalization by: - Organization of day care - Organization of inclusive workshops - Inclusion of children with developmental disabilities who are at risk of separation from families in existing services in the community - Organization of services for the early rehabilitation of children with disabilities and provision of support to remain in family - Organization of a network of clubs with inclusive content in local communities for children, adults and elderly people with intellectual disabilities and their parents - Organization of workshops for parents focusing on responsible parenthood and participation in the rehabilitation of children with disabilities. |  | - Ministry of Labor, Employment, Veterans and Social Affairs - Federation of Associations for Helping Individuals with Mental Disabilities | Continuously, commencing from II quarter of 2015. |  | IPA2013 Total - 2.300.000 € In 2015. - 920.000 € In 2016. - 920.000 € In 2017. - 460.000 € |  |  | Support services for children, adults and older people with intellectual disabilities and their families organized in order to prevent institutionalization by: - Organization of day care - Organization of inclusive workshops - Inclusion of children with developmental disabilities who are at risk of separation from families in existing services in the community. - provision of services for the early rehabilitation of children with disabilities and support to remain in family provided. - A network of clubs with inclusive content organized in local communities. - Workshops for parents focusing on responsible parenthood and participation in the rehabilitation of children with disabilities organized. |  |  |
| 3.6.2.3. | Piloting centers for family support in order to: -Target population of multiply deprived communities (paying particular attention to the availability for Roma families and children) -Support a parent who suffers domestic violence -Support children at risk of dropping out of school -Support families at risk of separation (children and parents) -Support children victims of crime -Support children with disabilities from vulnerable families and at risk of placement in institution. |  | - Ministry of Labor, Employment, Veterans and Social Affairs - UNICEF | 2015-2016 |  | IPA 2013 – EU (UNICEF) Budgeted in activity 3.6.2.2. |  |  | Family support centers established in 4 cities in the context of the transformation of institutions Defined standards for intensive family support services Established financing system of intensive family support services. |  |  |
| 3.6.2.4. | Improvement of the system of cash benefits for vulnerable families of children with disabilities in accordance with the principles of social inclusion, through amendments to the Law governing financial support for families with children |  | - Ministry of Labor, Employment, Veterans and Social Affairs - UNICEF | 2015-2018 |  | IPA 2013 – ЕU (UNICEF ) Budgeted in activity 3.6.2.2. |  |  | Regulations revised in accordance with the principles of social (functional) approach to disability Amendments to the Law governing financial support for families with children adopted. Capacity building plan for the implementation of the new assessment system and administration harmonized. |  |  |
| 3.6.2.5. | Improving foster care system by increasing the availability and quality of services for children with disabilities and their families through: - strengthening the capacity of regional centers for foster care (Centers for foster care and adoption) and centers for social work, - development of procedures and guidelines for foster care as shared care between foster and biological families - development of a respite foster care |  | - Ministry of Labor, Employment, Veterans and Social Affairs - UNICEF - Regional fostering centers (Centers for foster care and adoption) | 2015-2017 |  | IPA 2013 – EU (UNICEF) Budgeted in activity 3.6.2.2. |  |  | Foster care as a shared care approach defined through the normative framework. Specialized guidance and capacity building programs relating to foster care and the concept of shared care are published and accredited Centers for foster care and centers for social work are used as a shared care mechanism through which families with children with disabilities receive additional support. |  |  |
| 3.6.2.6. | Improve the quality of work with inpatient service users to enable more efficient engagement in the community through: - Provision of psychosocial support for social reintegration - Organization of contacts outside of the institution and participation in local support services such as day care centers and clubs - Participation in cultural and sporting events and camps |  | - Ministry of Labor, Employment, Veterans and Social Affairs | Continuously |  | Budget of the Republic of Serbia Costs currently unknown. IPA 2015 Costs will be specified by the submission of the final draft AP. |  |  | The quality of work with inpatient service users improved to enable more efficient engagement in the community. |  |  |
| 3.6.2.7. | Evaluation of existing resources in large and small residential institutions for children and drafting recommendations on the methods of their use in the process of transition from institutional to community care |  | - Ministry of Labour, Employment, Veterans and Social Affairs -UNICEF -institutions | 2015-2018 |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Plans to reduce the accommodation capacity in two large residential institutions developed and adopted Funding for their implementation defined |  |  |
| 3.6.2.8. | Strengthen capacity of providers of social services in accordance with the processes of deinstitutionalization and system decentralization by organizing staff training for the provision of psychosocial support for service users’ reintegration. |  | - Ministry of Labor, Employment, Veterans and Social Affairs | Continuously, commencing from II quarter of 2015. |  | Budget of the Republic of Serbia - 1.200 € In 2015. - 300 € In 2016. - 300 € In 2017.- 300 € In 2018. - 300 € |  |  | Capacity of providers of social services strengthened in accordance with the processes of deinstitutionalization and system decentralization by organizing staff training for the provision of psychosocial support for service users’ reintegration through conducted training. |  |  |
| 3.6.2.9. | Improving the system of case management in the centers for social work in order to focus treatment planning on support to families at risk of separation instead of an institutionalization-oriented approach |  | - Ministry of Labour, Employment, Veterans and Social Affairs - UNICEF - Regional fostering centers (Centers for foster care and adoption) | 2015-2017 |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Case management system improved in centers for Social Work. Guidelines for centers for Social Work to support families at risk of separation developed. Report on the implementation of the guidelines prepared. Reduction by 30% in the number of referrals to institutional placement of children by the Centers for Social Work through the application of revised procedures. |  |  |
| 3.6.2.10. | Adopt amendments and supplements to the Law on Juveniles in order to: - Review the type and system of criminal sanctions for juveniles: - Introduce a broader spectrum of specific obligations; - Introduce the new diversion orders; - Comply with the provisions of the new Criminal Procedure Code - (primarily in relation to the stage of the procedure and the altered role of the officials in the procedure in the specific procedural stages). |  | - Ministry of Justice -National assembly | I and II quarter of 2015. |  | Budget of the Republic of Serbia - 71.386 € In 2015. |  |  | Amendments and supplements to the Law on Juveniles adopted enabling simplified and efficient implementation of diversion orders. |  |  |
| 3.6.2.11. | Improve the work of the Juvenile Justice Council in order to achieve the coordination of state bodies, the judiciary and the non-governmental sector in dealing with juvenile offenders. |  | - Ministry of Justice - Minister - Supreme Court of Cassation - President | I and II quarter of 2015. |  | Budget of the Republic of Serbia- 24.702 € In 2015. - 6.176 € In 2016. - 6.176 € In 2017. - 6.176 € In 2018. - 6.176 € |  |  | Council for the monitoring and improvement of work of the bodies in criminal proceedings and the enforcement of criminal sanctions against juveniles holds regular sessions. Biannual report of the Juvenile Justice Council published. |  |  |
| 3.6.2.12. | Increasing use of diversionary orders and prioritizing restorative approach to juvenile offenders to ensure their social reintegration and reduce recidivism rates, by: - Piloting the draft by-law governing implementation of diversionary schemes in Belgrade, Nis, Novi Sad and Kragujevac - Defining the role of the guardianship authority as the organization responsible for the implementation of diversionary schemes - Defining mechanisms for long-term funding of diversionary schemes - Improving the use of alternative sanctions. - Better data collection measures implemented with introduction of any new mechanisms to monitor effectiveness over time and document impact on children |  | - Ministry of Justice | Continuously, commencing from IV quarter of 2014. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Use of diversionary schemes increased. Percentage of implementation of diversion orders in the total number of criminal charges for criminal offenses committed by juveniles (target: 15% by the end of 2017 and 20% by 2020). The role of social protection systems specified, including through the promotion of the guardianship procedures. The issue of funding implementation of diversion orders regulated. Percentage of the use of specific obligations increased, target: 25% by 2017. |  |  |
| 3.6.2.13. | Adopt bylaws specifying the implementation of diversionary schemes in line with the approach placing the implementation of diversionary schemes in the context of community responsibility. |  | - Ministry of Justice | III and IV quarter of 2015. |  | Budget of the Republic of Serbia- 8. 642 € In 2015. |  |  | Bylaws specifying the implementation of diversionary schemes adopted. |  |  |
| 3.6.2.14. | Sign and implement local memoranda of cooperation in implementation of diversionary schemes involving the sectors of education, social protection, health, local self-government, economy and civil society. |  | - Ministry of Justice - UNICEF | 2016 |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Local memoranda of cooperation in implementation of diversionary schemes involving the sectors of education, social protection, health, local self-government, economy and civil society signed in 10% of municipalities by 2016 and 40% of municipalities by 2018 and implemented. |  |  |
| 3.6.2.15. | Conduct training and support continued certification of judges and prosecutors in contact with juvenile offenders; |  | - Judicial Academy | Continuously |  | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. |  |  | Judges and prosecutors who handle juvenile cases attended training at the Judicial Academy and are licensed to work with juveniles. |  |  |
| 3.6.2.16. | Define practical guidelines for interviewing children, based on best practices of EU countries and provide conditions for the uniform application of protective measures of children victims / witnesses in criminal proceedings to avoid secondary victimization. |  | - Ministry of Justice - UNICEF - Judicial Academy - High Judicial Council - State Prosecutorial Council - Ministry of Interior | III and IV quarter of 2015. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Practical guidelines for interviewing children, based on best practices of EU countries defined, adopted and available to the experts in the judicial system and guardianship body, as the conditions for the uniform application of protective measures of children victims / witnesses in criminal proceedings provided. Mechanism for the implementation of guidelines established. |  |  |
| 3.6.2.17. | Conduct training and informative sessions for police officers, public prosecutors and deputy public prosecutors, judges and employees of Centers for Social Work, on the protection of children victims / witnesses in criminal proceedings in order to avoid secondary victimization and distribute educational materials. |  | - Ministry of Labour, Employment, Veterans and Social Affairs - Ministry of Justice - UNICEF - Judicial Academy - High Judicial Council - State Prosecutorial Council - Ministry of Interior | IV quarter of 2015. to III quarter of 2017. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Training on the protection of children victims / witnesses in criminal proceedings conducted within the Judicial Academy training programs and educational materials distributed. Participants improved skills in dealing with children victims / witnesses in criminal proceedings in order to avoid secondary victimization |  |  |
| 3.6.2.18. | Strengthen staff capacity of the Administration for enforcement of criminal sanctions in order to improve the treatment of juveniles through continuous staff training in all the institutions housing juvenile offenders. |  | - Administration for enforcement of criminal sanctions | IV quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.1.1.11. |  |  | Staff capacity of the Administration for enforcement of criminal sanctions strengthened with regard to treatment of juveniles. |  |  |
| 3.6.2.19. | Establishment of the department and construction of accommodation facilities for the enforcement of the measure of mandatory psychiatric treatment and custody in a medical institution imposed to minors. |  | - Administration for enforcement of criminal sanctions | IV quarter of 2017. |  | Kingdom of Norway donation Budgeted in activity 3.1.1.9. |  |  | Accommodation facilities for the enforcement of the measure of mandatory psychiatric treatment and custody in a medical institution constructed. |  |  |
| 3.6.2.20. | Develop and implement specialized treatment programs and programs for release preparation of juvenile offenders |  | - Administration for enforcement of criminal sanctions | Continuously, commencing from IV quarter of 2015. |  | Kingdom of Norway donation Budgeted in activity 3.1.1.9. |  |  | Specialized treatment programs and programs for release preparation of juvenile offenders developed and implemented in all institutions housing juvenile offenders. |  |  |
| 3.6.2.21. | Improve the protection of children in civil and administrative court proceedings by establishing uniform case law in terms of children's rights to express their opinion and the right to have that opinion taken into account in the court proceedings |  | - Supreme Court of Cassation | I quarter of 2016 to IV quarter of 2017. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Protection of children in civil and administrative court proceedings by establishing uniform case law in terms of children's rights to express their opinion and the right to have that opinion taken into account in the court proceedings improved. Current system of monitoring and records keeping advanced to include data on the child’s opinion and how it was taken into account. |  |  |
| 3.6.2.22. | Introduction of post-traumatic counselling and support for children victims / witnesses in criminal proceedings in the context of family support services that are developed in the social protection system under item 3.6.2.3. of this plan, which includes children victims of crime in the group of beneficiaries. |  | - Ministry of Justice - Republic Public Prosecutors’ Office - Supreme Court of Cassation - High Judicial Council | I quarter of 2016 to IV quarter of 2017. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Post-traumatic counselling and support for children victims / witnesses in criminal proceedings introduced within centers for family support and services clearly defined. |  |  |
| 3.6.2.23. | Improving regulations and practices for managing data in the courts by records keeping in compliance with the principle of 'best interests of the child' in civil proceedings |  | - Ministry of Justice | Continuously |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Regulations and practices for managing data in the courts by records keeping in compliance with the principle of 'best interests of the child' in civil proceedings improved. |  |  |
| 3.6.2.24. | Supply equipment for the premises for the children and other particularly vulnerable victims in Higher court in Belgrade, Nis, Novi Sad, Vranje and Basic court in Leskovac |  | - Ministry of Justice | IV quarter of 2014. |  | IMG, Kingdom of Norway donation 632.000 € In 2014. |  |  | Equipment for the premises for the children and other particularly vulnerable victims in Higher court in Belgrade, Nis, Novi Sad, Vranje and Basic court in Leskovac supplied and utilized. |  |  |
| 3.6.2.25. | Conduct analysis of results and identify obstacles to the implementation of the National Strategy for the Prevention and Protection of Children from Violence 2008-2015 |  | - Working group established by the Ministry of Labour, Employment, Veterans and Social Affairs | III and IV quarter of 2015. |  | Budget of the Republic of Serbia- 30.878 € In 2015. |  |  | Analysis of results and identification of obstacles to the implementation of the National Strategy for the Prevention and Protection of Children from Violence 2008-2015 conducted. |  |  |
| 3.6.2.26. | Develop new multiannual strategic framework for prevention and protection of children from violence |  | - Working group established by the Ministry of Labour, Employment, Veterans and Social Affairs | I quarter of 2016. |  | Budget of the Republic of Serbia-30.878 € In 2016. |  |  | New multiannual strategic framework for prevention and protection of children from violence developed and adopted, including financial plan for its implementation. |  |  |
| 3.6.2.27. | Develop Action plan for new multiannual Strategy for prevention and protection of children from violence with a monitoring mechanism for efficient supervision over the implementation of the Strategy. |  | - Ministry of Labor, Employment, Veterans and Social Affairs | II quarter of 2016. |  | Budget of the Republic of Serbia- 15.439 € In 2016. |  |  | Action plan for new multiannual strategy for prevention and protection of children from violence developed and adopted. |  |  |
| 3.6.2.28. | Improvement of the existing General Protocol for the protection of children from abuse and neglect in order to align with EU best practices. |  | - Working group established by the Ministry of Labor, Employment, Veterans and Social Affairs - UNICEF | I and II quarter of 2016. |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | The existing General Protocol for the protection of children from abuse and neglect improved and aligned with EU best practices and its implementation is monitored. |  |  |
| 3.6.2.29. | Development of new special protocols for the protection of children from abuse and neglect and establishment of conditions for their mandatory implementation , particularly in the areas of: Acting of judicial authorities to protect children from abuse and neglect Protection of children in institutions of social care from abuse and neglect Acting of police officers to protect children from abuse and neglect Protection of children from abuse and neglect in the health care system Protection of children and students from violence, abuse and neglect in educational institutions. |  | - Ministry of Justice - Ministry of Labour, Employment, Veterans and Social Affairs - Ministry of Education - Ministry of Interior - Ministry of Health | III and IV quarter of 2016 (harmonization of the protocol) 2017 (harmonization of sectorial bylaws). |  | IPA 2013 – ЕU UNICEF Budgeted in activity 3.6.2.2. |  |  | Special protocols to protect children from abuse and neglect developed and their implementation is monitored. The adoption of sectorial bylaws establishing mechanism for their mandatory implementation. |  |  |
| 3.6.2.30 | Establishment of a mechanism for resolving cases of missing infants from maternity hospitals in relation to the decision of the ECHR Zorica Jovanovic vs. Serbia (no. 21794/08) to enable all parents in similar situations to get adequate answers and compensation. |  | - Ministry of Health - Ministry of Interior - Ministry of Justice | I and II quarter of 2015. |  | Budget of the Republic of Serbia- 8.642 € In 2015. |  |  | Mechanism for resolving cases of missing infants from maternity hospitals established. |  |  |
| 3.7. PROCEDURAL GUARANTEES |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |
| 3.7.1. Strengthen procedural safeguards in line with EU standards |  |  |  |  | Functional free legal aid system established and greater guarantees recognized for the suspect or accused persons to exercise the right to have access to a lawyer, the right to information and the right to interpretation and translation The principle of the right to a fair trial is effectively implemented. Access to justice is guaranteed through the establishment of a functional free legal aid system established and greater guarantees recognized for the suspect or accused persons to exercise the right to have access to a lawyer, the right to information and the right to interpretation and translation in line with the relevant EU Acquis . The same applies to minimum standards on rights, support and protection of victims of crime. |  |  |  | - Positive opinion of the European Commission stated in Annual Progress Report on Serbia relating to access to justice - Positive report of the Ombudsman relating to access to justice and free legal aid - Reports from international and non-governmental organizations and CEPEJ; - Statistical data in the Annual report of the Ministry of Justice on the number of beneficiaries, proceedings in which free legal aid was provided and costs of the provision of free legal aid. - Increased number of requests for exercising the right to free legal aid in 2016. - Increased number of suspect or accused persons exercising the right to have access to a lawyer. - The average duration of court proceedings (per subject). |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.7.1.1. | Adopt Draft Law on Free Legal Aid. |  | - Ministry of Justice -National assembly |  | I quarter of 2015. |  | Total - 104.013 € Budget of the Republic of Serbia -102.263 € and international aid (MDTF) - 1.750 € |  | Law on Free Legal Aid adopted. |  |  |
| 3.7.1.2. | Adopt by-laws relating to the implementation of the Law on Free Legal Aid. |  | - Ministry of Justice |  | II and III quarter of 2015. |  | Total-36.319 € Budget of the Republic of Serbia - 34.569 € and international aid (MDTF) - 1.750 € In 2015. |  | Adopted by-laws relating to the implementation of the Law on Free Legal Aid. |  |  |
| 3.7.1.3. | Anticipate effective allocation of budget to fund the free legal aid system, in particular when it comes to obligations of the local self-government units. |  | - Ministry of Finance |  | Continuously, commencing from III quarter of 2015. |  | Budget of the Republic of Serbia Financial calculation are currently being developed, it’s a matter of complex financing scheme and a new law |  | Effective allocation of budget to fund the free legal aid system anticipated. |  |  |
| 3.7.1.4. | Monitor and analyze the results of implementation and the cost of the new Law on Free Legal Aid. |  | - Ministry of Justice |  | Continuously, commencing from I quarter of 2016. |  | Total- 885.165 € Budget of the Republic of Serbia - 127.650 € and international aid (MDTF)- 757.515 € In 2016. - 345.556 € In 2017. - 345.556 € In 2018. - 194.053 € |  | Analysis of the results of implementation and the cost of the new Law on Free Legal Aid performed. |  |  |
| 3.7.1.5. | Conduct training of free legal aid providers in relation to the start of implementation of the Law on Free Legal Aid. |  | - Ministry of Justice |  | Continuously, commencing from II quarter of 2015. |  | International aid (MDTF) Budgeted in activity 3.7.1.4. |  | Training of free legal aid providers in relation to the start of implementation of the Law on Free Legal Aid conducted. |  |  |
| 3.7.1.6. | Conduct a campaign to provide information to citizens about the Law on Free Legal Aid. |  | - Ministry of Justice |  | Continuously, commencing from II quarter of 2015. |  | International aid (MDTF) Budgeted in activity 3.7.1.4. |  | Campaign to provide information to citizens about the Law on Free Legal Aid conducted. |  |  |
| 3.7.1.7 | Adopt Draft Law on protection of right to a fair trial |  | - Ministry of Justice -National assembly |  | I quarter of 2015. |  | Budget of the Republic of Serbia 71.136 € In 2015. |  | Draft Law on protection of right to a fair trial adopted. |  |  |
| 3.7.1.8. | Continuously monitor the exercise of the right to a trial in reasonable time through implementation and improvement of the judicial reform |  | - Commission for the implementation of the National Judicial Reform Strategy for the period 2013-2018 |  | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Commission for the implementation of the National Judicial Reform Strategy for the period 2013-2018, based on the relevant institutions reports provides recommendations to competent bodies to undertake measures to resolve identified problems. |  |  |
| 3.7.1.9. | Conduct an analysis of alignment of normative framework with EU Acquis and standards in the field of procedural safeguards, with particular emphasis on comparative experiences and best practices at EU level and identify the necessary changes |  | - Ministry of Justice - Supreme Court of Cassation - Republic public prosecutors’ office -Ministry of Interior |  | IV quarter of 2015. |  | Total-19.035 € Budget of the Republic of Serbia - 17.285 € ТАIEX- 1.750 € In 2015. |  | Analysis with recommendations to improve procedural safeguards developed. |  |  |
| 3.7.1.10. | Adopt the Criminal Procedure Code amendments based on the recommendations in the analysis to align with: - Directive 2013/48/EU on the right of suspect or accused persons to have access to a lawyer, in terms of strengthening the right of suspects and accused persons to access to a lawyer without delay and before any questioning by investigators in criminal proceedings and proceedings by the European arrest warrant. - Directive 2010/64/EU on the right to interpretation and translation, in order to precisely define the withdrawal from the right to translation - Directive 2012/13/EU on the right to information, in order to improve the exercise of the right to information. |  | - Ministry of Justice - National Assembly |  | I quarter of 2016. |  | TAIEX Budget of the Republic of Serbia Budgeted in activity 3.7.1.9 |  | Criminal Procedure Code amendments adopted enabling alignment with the stated directives. |  |  |
| 3.7.1.11. | Regularly monitor the implementation of the amendments and supplements to the Criminal Procedure Code with regard to procedural safeguards. Link with the measures in recommendation 1.3.10. |  | - Commission for monitoring the implementation of the Criminal Procedure Code - Commission for the implementation of the National Judicial Reform Strategy for the period 2013-2018 |  | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Reports on the implementation of the amendments and supplements to the Criminal Procedure Code with regard to procedural safeguards publicly available. |  |  |
| 3.7.1.12. | Amend and supplement Criminal Procedure Code in order to provide temporary legal aid granted without undue delay after deprivation of liberty and before any questioning by the police, other law enforcement authorities or court authority for the purposes of criminal proceedings which involve a suspect or defendant. |  | - Ministry of Justice - National Assembly |  | I quarter of 2016. |  | Budget of the Republic of Serbia - 8.642 € In 2016. |  | Amendments to the Criminal Procedure Code adopted enabling temporary legal aid in criminal proceedings. |  |  |
| 3.7.1.13. | Conduct training of the police officers, prosecutor's and deputy prosecutors and judges in terms of stronger procedural safeguards. |  | - Judicial academy |  | Continuously, commencing from II quarter of 2016. |  | Budget of the Republic of Serbia and donations. Budgeted in activity 1.3.1.7. |  | Training conducted. Knowledge of the police officers, prosecutor's and deputy prosecutors and judges in terms of stronger procedural safeguards improved. |  |  |
| 3.7.1.14. | Design a ‘Letter of Rights’ that shall be provided to an arrested person, suspect or an accused person by the police/prosecution. |  | - Ministry of Justice - Republic public prosecutors’ office - Supreme Court of Cassation |  | I quarter of 2017. |  | Budget of the Republic of Serbia - 8.642 € In 2017. |  | Letter of Rights on designed. |  |  |
| 3.7.1.15. | Distribute „Letter of Rights” in all police stations and prosecutor's offices in: - Serbian language - language of national minorities in the communities in which they live - English language |  | - Ministry of Justice |  | II quarter of 2017. |  | Budget of the Republic of Serbia Currently unknown |  | Letter of Rights distributed in all police stations and prosecutor's offices and used for informing persons about their rights. |  |  |
| 3.7.1.16. | Conduct an analysis of normative framework for the implementation of minimum standards concerning the rights, support and protection of victims of crime / injured parties in accordance with Directive 2012/29/EU |  | - Ministry of Justice |  | IV quarter 2015. |  | Total-59.293 € Budget of the Republic of Serbia- 57.543 € TAIEX- 1.750 € In 2015. |  | Analysis with recommendations for amendments to the normative framework developed. |  |  |
| 3.7.1.17. | Amend normative framework in order to effectively implement minimum standards concerning the rights, support and protection of victims of crime / injured parties in accordance with Directive 2012/29/EU and in line with the analysis. |  | - Working group established by the Ministry of Justice -National assembly |  | I and II quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 3.7.1.16. |  | Normative framework aligned with the Directive 2012/29/EU. |  |  |
| 3.7.1.18 | Conduct training for judges, prosecutors and police officers on the implementation of minimum standards regarding the rights, support and protection of victims in accordance with Article 25 of Directive 2012/29 / EU |  | - Judicial Academy |  | Continuously commencing from III quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. |  | Judges, prosecutors and police officers improved their skills regarding the implementation of minimum standards regarding the rights, support and protection of victims in accordance with Article 25 of Directive 2012/29 / EU. |  |  |
| 3.7.1.19. | Establish services for support to the victims, witnesses and injured parties in all higher courts. |  | - Supreme Court of Cassation - High Judicial Council |  | 2018. |  | Budget of the Republic of Serbia Currently unknown |  | Services for support to the victims, witnesses and injured parties established in all higher courts. |  |  |
| 3.7.1.20. | Establish services for support to the victims, witnesses and injured parties in the respective prosecutors’ offices (25 higher, POC, WCP) |  | - Republic public prosecutors’ office |  | 2018. |  | Budget of the Republic of Serbia Currently unknown |  | Services for support to the victims, witnesses and injured parties established in the respective prosecutors’ offices. |  |  |
| 3.8. POSITION OF NATIONAL MINORITIES |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.8.1. Adopt through an inclusive process specific action plan focused on the effective implementation of existing rights of national minorities, taking into account the recommendations issued in the third Opinion on Serbia in the context of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities |  |  |  | A specific action plan taking into account the recommendations issued in the third Opinion on Serbia in the context of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities, focused on the effective implementation of existing rights of national minorities adopted through an inclusive process and implemented. |  |  |  |  | - Report of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities. - Report of the body competent for the implementation a specific action plan focused on the effective implementation of existing rights of national minorities. - Annual report of the Commissioner for Equality noting improvements in the field of protection of national minorities’ rights. - Report of the Ombudsman in the part relating to the position of national minorities stating that there has been progress with regard to protection of national minorities' rights. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.8.1.1. | Adopt a specific action plan for the implementation of the existing normative framework for the protection of national minorities, taking into account the relevant recommendations issued in the third Opinion of the Advisory Committee of the Council of Europe on Serbia in the context of the Framework Convention for the Protection of National Minorities, focusing in particular on achieving following aims: - Enabling increased participation of national minorities in the bodies of state administration and multi-ethnic police force; - Strengthening effective participation of numerically smaller national minorities in the electoral process; - Upgrading the National Councils of National Minorities; - Enabling a flexible access to statistical data on national minorities; - Enable more efficient acting in accordance with the recommendations of the Ombudsman, Provincial Ombudsman and Commissioner for the Protection of Equality in all cases affecting the rights of persons belonging to national minorities and providing simple access of persons belonging to national minorities to all institutions ; - Permanently resolve the situation of “legally invisible” persons; - Strengthening inter-ethnic communication; - Improve effectiveness of the criminal justice system in terms of sanctioning hate crimes and raising awareness on the importance of prosecuting hate crimes; - Ensure full and proper implementation of the rules currently applicable for the use of minority languages, registration of names in minority languages, official communication with public authority bodies and as regards the display of topographical indications in minority languages; - Ensure harmonized exercise of the right to education in minority languages; - Strengthening cooperation among national minorities in local self-government units; - Ensure effective implementation of the new media laws, particularly with regard to media rights of the national minorities. |  | Multi-sectoral working group composed of representatives of all relevant ministries, established by the Ministry of State Administration and Local Self-government. | IV quarter of 2015. |  | Budget of the Republic of Serbia- 30.878 € In 2015. |  |  | A specific action plan taking into account the recommendations issued in the third Opinion on Serbia in the context of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities, focused on the effective implementation of existing rights of national minorities adopted. |  |  |
| 3.8.1.2. | Reinstate the work of the Council for national minorities, including participation of the representatives of all national minorities, aimed at effective exercise of the rights of national minorities |  | - Government of the Republic of Serbia | II quarter of 2015. |  | Budget of the Republic of Serbia - 18.527 € In 2015. |  |  | The work of the Council for national minorities reinstated. |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.8.2. Serbia should start preparations for adopting at the end of 2014 a new multi-annual strategy and action plan to improve living conditions of Roma, including actions to ensure their registration, comprehensive measures on non-discrimination, ensure compliance with international standards on forced evictions and access to guaranteed socio-economic rights and dedicate additional financial assistance to implement the current and future Roma strategy in particular regarding education and health measures |  |  |  | New multi-annual strategy and action plan to improve living conditions of Roma adopted through an inclusive process and implemented. |  |  |  |  | 1. Positive opinion of the European Commission stated in the Annual Progress Report on Serbia's in the part referring to the position of Roma national minority 2. Annual report of the Ombudsman on implementation of the strategy to improve living conditions of Roma 3. Annual report of the Team for Social Inclusion and Reduction of Poverty stating that living conditions of Roma have improved. 4. Report of the Council for the Advancement of Roma and the Decade of Roma Inclusion on the implementation of the Strategy for Advancing the position of Roma |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.8.2.1. | Conduct an analysis on the effects of the Strategy for Advancing the position of Roma in the Republic of Serbia |  | - Ministry of Labor, Employment, Veterans and Social Affairs - Office for Human and Minority Rights - Government of the Republic of Serbia – Team for Social Inclusion and Reduction of Poverty | II quarter of 2015. |  | Total-37.878 € Budget of the Republic of Serbia - 30.878 € ТAIEX - 7.000 € In 2015. - 18.939 € In 2016. - 18.939 € |  |  | Analysis on the effects of the Strategy for Advancing the position of Roma in the Republic of Serbia conducted. |  |  |
| 3.8.2.2. | Develop a new strategy for Advancing the position of Roma in the Republic of Serbia, with active participation of Roma representatives and dedication of financial resources for its implementation, focusing in particular on the following areas: - Issuing personal documents/ registration - Comprehensive anti-discrimination measures - Compliance with international standards on forced evictions - Equal access to health care and social protection - Equal access to education - Equal access to labour market - Improvement of living conditions |  | Multi-sectorial working group comprised of representatives from all relevant ministries | IV quarter of 2015. |  | ТAIEX Budget of the Republic of Serbia Budgeted in activity 3.8.2.1. |  |  | A new strategy for Advancing the position of Roma in the Republic of Serbia developed and financial resources for its implementation secured. |  |  |
| 3.8.2.3. | Develop Action Plan for the implementation of the new strategy for Advancing the position of Roma in the Republic of Serbia |  | Multi-sectorial working group comprised of representatives from all relevant ministries | I quarter of 2016 |  | Budget of the Republic of Serbia Budgeted in activity 3.8.2.1. |  |  | Action Plan for the implementation of the new strategy for Advancing the position of Roma in the Republic of Serbia adopted and implemented. |  |  |
| 3.8.2.4. | Monitoring the achievement of the objectives of a new Strategy for Improving the Situation of Roma in the Republic of Serbia through the continuous work of the Council for the Advancement of Roma and the Decade of Roma Inclusion |  | Council for the Advancement of Roma and the Decade of Roma Inclusion | Continuously, commencing from I quarter of 2016. |  | Budget of the Republic of Serbia- 18.527 € In 2016. - 6.176 € In 2017. - 6.176 € In 2018. - 6.176 € |  |  | Council for the Advancement of Roma and the Decade of Roma Inclusion provides regular reports and gives recommendations for overcoming potential obstacles in the implementation of the Strategy and Action Plan. |  |  |
| 3.9. POSITION OF REFUGEES AND INTERNALLY DISPLACED PERSONS |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.9.1. Improve the situation of refugees and IDPs by ensuring their full access to rights, including civil documentation and housing solutions for the most vulnerable ones. |  |  |  | Position of refugees and internally displaced persons improved by ensuring their full access to rights, including civil documentation and housing solutions for the most vulnerable ones. |  |  |  |  | - Final Report of the Regional Programme for housing refugees - The number of housing solutions - Annual Report of the Commissioner for Refugees and Migration - Report of the Ombudsman in the part relating to the position of national minorities stating significantly improved situation with regard to the position of refugees and internally displaced persons. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.9.1.1. | Providing permanent housing solutions for refugees through the implementation of the Regional Programme for housing refugees. |  | - Commissioner for Refugees and Migration - Regional Programme for housing refugees | Continuously, until 2018. |  | Multi donor Regional Housing Fund Planed funds for Serbia from Multi donor Regional Housing Fund amount to 300.000.000€ The dynamics currently unknown, as they depend on individual schemes. |  |  | Permanent housing solutions for refugees provided through the implementation of the Regional Programme for housing refugees. |  |  |
| 3.9.1.2. | Provide free legal aid in order to ensure full access to rights including personal documents for internally displaced persons and refugees. |  | - Ministry of Justice | Continuously, commencing from II quarter of 2015. |  | Budget of the Republic of Serbia Currently unknown (Pending Preparation of detailed calculation which depends on concrete solutions of Law, which will be known by the moment of sending Draft Law to the Government of Serbia.) |  |  | Law on Free Legal Aid adopted and implemented. |  |  |
| 3.9.1.3. | Effective implementation of the Law on Non-contentious proceedings especially in the part related to the provision of civil documentation of undocumented persons. |  | - Ministry of Public Administration and local self-government | Continuously |  | Budget of the Republic of Serbia. Activity requiring insignificant costs |  |  | Proceedings related to the provision of civil documentation to undocumented persons effectively implemented. |  |  |
| 3.9.1.4. | Improvement of the living conditions of internally displaced persons while in displacement by: - Aid allocation to improve housing conditions; - Provision of building materials to start construction of real estate; - Aid allocation for the purchase of village house with garden; - Aid allocation for obtaining and construction of prefabricated houses and other residential premises; - Aid allocation for resolving the issue of informal collective centers. |  | - Commissioner for Refugees and Migration | Continuously |  | Budget of the Republic of Serbia Budgeted in activity 3.9.1.1. |  |  | The living conditions of internally displaced persons improved while in displacement. |  |  |
| 3.9.1.5. | Providing complementary measures aimed at sustainable integration of refugees through programs for economic empowerment through income generating activities |  | - Commissioner for Refugees and Migration | Continuously |  | Budget of the Republic of Serbia Budgeted in activity 3.9.1.1. |  |  | Sustainable integration of refugees facilitated. |  |  |
| 3.9.1.6. | Establishment of a mechanism for regular monitoring of the exercise of the rights of Roma internally displaced persons in cooperation with the health mediators, educational assistants, to assess their equal exercise of rights and potential improvements. |  | - Body competent for monitoring Strategy for Advancing the position of Roma in the Republic of Serbia | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Mechanism for regular monitoring of the exercise of the rights of refugees and internally displaced persons established and regularly reports. |  |  |
| 3.9.1.7. | Conduct an information campaign to raise awareness of refugees and internally displaced persons to ensure their social integration and awareness on the mechanisms available for the exercise of rights. |  | - Commissioner for Refugees and Migration - CSOs | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.9.1.1. |  |  | Information campaign to raise awareness of refugees and internally displaced persons to ensure their social integration and awareness on the mechanisms available for the exercise of rights conducted. |  |  |
| 3.10. MEASURES AGAINST RACISM AND XENOPHOBIA |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.10.1. Ensure adequate prosecution of perpetrators of hate crime. Monitor the effects of the implementation of the strategy (2013 – 2018) for combating violence and misbehavior at sport events and take corrective measures where needed. |  |  |  | Adequate prosecution of hate crime ensured. The effects of the implementation of the strategy (2013 – 2018) for combating violence and misbehavior at sport events regularly monitored and corrective measures undertaken where needed. |  |  |  |  | 1. Annual Progress Report on Serbia stating that Serbia has made progress in prosecuting hate crime. 2. Positive opinion in the Peer review stating that Serbia has made progress in prosecuting hate crime 3. Report of the European Committee for Racism and Tolerance stating that Serbia has made progress in prosecuting hate crime; 4. Annual statistics report Republic Public Prosecutors’ Office 5. Annual statistics report Ministry of Interior 6. Report of the Action Team for development and implementation of a Strategy and Action Plan to combat violence and misbehavior at Sports Events |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.10.1.1. | Amend and supplement the Criminal Code to align with the Framework Decision of the Council 2008/913/JHA of 28 November 2008 Article 1 (paras (c and d) |  | - Ministry of Justice -National assembly | I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 2.3.1.2. |  |  | Criminal Code amended and supplemented to align with the Framework Decision of the Council 2008/913/JHA of 28 November 2008 Article 1 (paras c and d). |  |  |
| 3.10.1.2. | Amend and supplement the Criminal Code - supplement the criminal offence of Violation of Equality (Article 128), introducing that this offence can be committed if citizen’s rights are limited or denied due to the sexual orientation or gender identity |  | - Ministry of Justice -National assembly | I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 2.3.1.2. |  |  | Criminal Code amended and supplemented. |  |  |
| 3.10.1.3. | Conduct joint training of the judges, prosecutors and deputy prosecutors and police officers, to advance their knowledge and skills for efficient suppression of hate crime |  | - Judicial Academy | Continuously, commencing from II quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 1.3.1.7. |  |  | Joint training conducted. Judges, prosecutors and deputy prosecutors and police officers, advanced their knowledge and skills for efficient suppression of hate crime. |  |  |
| 3.10.1.4. | Raise awareness on elimination of hate crime through: - Development and distribution of educational material - Organization of annual roundtables - Active media campaign |  | - Office for Human and Minority Rights | Continuously, commencing from II quarter of 2015. |  | IPА 2013- Total- 203. 440 € In 2015. - 50.860 € In 2016. - 50.860 € In 2017. - 50.860 € In 2018. - 50.860 € |  |  | - educational material distributed - annual roundtables organized - Media campaign conducted |  |  |
| 3.10.1.5. | Improve the work of the Action Team for development and implementation of a Strategy and Action Plan to combat violence and misbehavior at Sports Events through: - appointment of new members, - regular meetings. |  | - Government of the Republic of Serbia | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | The decision on the appointment of new members of the Action Team for development and implementation of a Strategy and Action Plan to combat violence and misbehavior at Sports Events adopted. Regular meetings of the Action Plan to combat violence and misbehavior at Sports Events take place. |  |  |
| 3.10.1.6. | Monitor the implementation of the Action Plan for the implementation of the Strategy Against Violence and Misbehavior at Sports Events and develop the report with recommendations for potential updating of the Action plan |  | - Action Team to develop and implement a strategy and action plan to combat violence and misbehavior at Sports Events | Continuously, commencing from I quarter of 2015. |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  |  | Report with recommendations for potential updating of the Action plan. |  |  |
| 3.10.1.7. | Update Action Plan for the implementation of the Strategy Against Violence and Misbehavior at Sports Events (2013-2018) in line with recommendations from the report on implementation of the Action Plan. |  | - Action Team to develop and implement a strategy and action plan to combat violence and misbehavior at Sports Events | II quarter of 2015. |  | Budget of the Republic of Serbia -638 € In 2015. |  |  | Action Plan for the implementation of the Strategy Against Violence and Misbehavior at Sports Events (2013-2018) updated in line with recommendations from the report on implementation of the Action Plan. |  |  |
| 3.11. PERSONAL DATA PROTECTION |  |  |  |  |  |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |
| 3.11.1. Ensure legislative and constitutional alignment with the Acquis in the area of protection of personal data and allow for assessment through the preparation of the relevant transposition tables; ensure sufficient financial and human resources to the Commissioner for Information of Public Importance and Personal Data Protection. |  |  |  | Legislative alignment with the Acquis in the area of protection of personal data ensured. Commissioner for Information of Public Importance and Personal Data Protection has sufficient financial and human resources to work. |  |  |  |  | - Positive opinion of the European Commission stated in Annual Progress Report on Serbia relating to personal data protection. - Positive report of the Commissioner for Information of Public Importance and Personal Data Protection. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |
| 3.11.1.1. | Draft tables of concordance of the normative framework of the Republic of Serbia in the field of personal data protection. |  | - Ministry of Justice | IV quarter of 2014. |  | Total- 32.628 €€ Budget of the Republic of Serbia - 30.878 € PLAC expert 1.750 € In 2014. |  |  | Tables of concordance of the normative framework in the field of personal data protection with the Acquis prepared. |  |  |
| 3.11.1.2. | Amend and supplement the Law on personal data protection in line with tables of concordance. |  | - Ministry of Justice - National Assembly | III quarter of 2015. |  | Budget of the Republic of Serbia Budgeted in activity 3.11.1.1. |  |  | Law on personal data protection aligned with the Acquis. |  |  |
| 3.11.1.3. | Adopt relevant bylaws for the implementation of the Law on personal data protection |  | - Ministry of Justice | I quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in activity 3.11.1.1. |  |  | Bylaws for the implementation of the Law on personal data protection adopted. |  |  |
| 3.11.1.4. | Strengthen the human resource capacity of the Commissioner for Information of Public Importance and Personal Data Protection based on prior analyzes of existing human capacity especially in terms of: -organizational structure -number of employees -level of training so that they coincide with the competencies prescribed by the Law on Amendments to the Law on personal data protection. |  | - Ministry of Justice - Ministry of Finance - Commissioner for Information of Public Importance and Personal Data Protection | Analysis: IV quarter of 2015. Acting in line with the analysis: I quarter of 2016. |  | Budget of the Republic of Serbia Analysis budgeted in activity 3.11.1.1. Dynamics and extent of strengthening capacity- costs currently unknown depends on the analysis |  |  | Conducted analysis. Revised Rulebook on internal organization and job classification of the Commissioner for Information of Public Importance and Personal Data Protection. Filled jobs in accordance with the amended job classification. |  |  |

This title, without prejudice to the status of Kosovo, is in accordance with UN resolution 1244 and the decision of the International court of Justice on Kosovo’s declaration of independence