REPUBLIC OF SERBIA NEGOTIATION GROUP FOR CHAPTER 23 ACTION PLAN CHAPTER 23 JUDICIARY AND FUNDAMENTAL RIGHTS July 2022

TABLE OF CONTENTS

INTRODUCTION........................................................................................................................	3

JUDICIARY ...............................................................................................................................	11

FIGHT AGAINST CORRUPTION ...........................................................................................	285

FUNDAMENTAL RIGHTS ......................................................................................................	467

ANNEX ………………………………………………………………………………………	894

INTRODUCTION

- Need for the revision of the Action Plan for Chapter 23 and commitment to European values

The Action Plan for Chapter 23 was adopted on 27 April 2016 by the Government of the Republic of Serbia. It is clear that, after four years of its implementation, the Action Plan requires a revision, a review of what has been achieved, for the purpose of defining the next steps that need to be taken in order to fully meet the Screening Report recommendations as well as Interim Benchmarks.

A revision of the Action Plan for Chapter 23 is needed to:

- Make an overview of activities that clearly indicate the future direction (with the setting of new realistic deadlines);

- Make interventions in the formulation of activities so that they properly reflect the recommendations from the screening report and Interim Benchmarks

- Remove the observed difficulties in the implementation and monitoring of the implementation of activities.

The Ministry of Justice and the Negotiating Group for Chapter 23 revised the Action Plan so that activities can be divided into several groups:

- normative regulation and harmonization (amendments to the Constitution, amendments to the legislative framework, adoption of strategic documents - other strategies and action plans, guidelines, instructions) at different levels and by different stakeholders;

- strengthening the institutional and administrative capacities of all institutions involved in the process of implementation of the activities, their mutual cooperation and communication;

- improvement of skills and competences through the implementation of appropriate training programs, including raising awareness in specific areas.

During the revision process, the aim was for the interventions to properly reflect the recommendations of the Screening Report and Interim Benchmarks, taking into account the assessment of the fulfillment of the activities provided by the Council for the implementation of the Action Plan for the negotiations for Chapter 23, the contributions provided by the responsible entities listed in the Action Plan for Chapter 23, as well as the difficulties encountered in the implementation and monitoring of the implementation of activities.

In the review process, we believe that the Action Plan should reflect Serbia's commitment to align its legal acts and procedures in the area of judiciary, anti-corruption and fundamental rights with EU acquis, which largely consists of generally accepted European and international standards, expressed through the documents and bodies of the EU, UN and the CoE, particularly Venice Commission, but also GRECO, CEPEJ, Consultative Council European Judges, the Consultative Council of European Prosecutors and the European Judicial Council Network. While implementing these standards it was important, as well, to consider the legal heritage of the Republic of Serbia, as well as socio-economic factors conditioning the applicability of the solutions that provide good results in other legal systems.

- Methodology and course of revision of the Action Plan for Chapter 23

The Government of the Republic of Serbia expresses its deep commitment to the reform process in the rule of law as it is aware that it represents the core value of each democratic society and one of the key areas of European Union policy. Having that in mind, the Republic of Serbia is putting a great attention to the fulfilling commitments prescribed within the Chapter 23 – Judiciary and Fundamental Rights. At the third EU-Serbia Intergovernmental Conference held in Brussels on 18 July 2016, the Republic of Serbia opened negotiating chapter 23 and chapter 24. The opening of these chapters represented a crucial step in the Republic of Serbia's European integration process, because the aim of these chapters is alignment with the acquis in the rule of law domain.

Following the EC recommendations from the Screening Report for Chapter 23 based on conclusions from the Explanatory and Bilateral Screening meetings and after the wide consultations with all relevant stakeholders and civil society, in April 2016 the Government of the Republic of Serbia adopted the Action Plan for the implementation of Chapter 23 (AP23), previously approved by the European Commission. Precisely one of the recommendations of the EC for Serbia was to deliver one or more detailed action plans with a coordinated schedule, clear goals and timelines, as well as the necessary institutional framework and adequate cost estimates and financial allocations in the following areas: the judiciary, the fight against corruption and fundamental rights. After the adoption of the AP CH23 in July 2016 accession negotiations on Chapter 23 commenced. At the abovementioned Conference EU General Position on Accession Negotiations with the Republic of Serbia was presented, including 50 interim benchmarks (IBM) for Chapter 23 defined to assess further progress of Serbia.

Most of the activities established within the Action Plan for the implementation of Chapter 23 are being carried out continuously with the success and progress. However, there are also activities with whose implementation some difficulties have arisen. The decision on the revision of the Action plan was made upon the conclusion that after four years of its implementation, the Action Plan requires an audit with an overview of what has been achieved and the definition of the next steps that need to be taken in order to fully meet the recommendations from the Screening Report, i.e. that are fit for purpose, now supplemented with the interim benchmarks, with prescribed realistic timelines.

The following steps were taken in terms of revising a document:

- The Interim Benchmarks have been added in the document. Where possible, recommendations as the basis for defining the activities have been deleted from the document and corresponding interim benchmarks have been listed instead along with relevant activities belonging to the specific Interim Benchmark. Where the recommendation has not been fully fulfilled or its content does not fully coincide with the Interim Benchmark, the recommendation has remained and is now supplemented by corresponding Interim Benchmark;

- Each subchapter begins with an introduction and a description of what has been done. Through an overview of the current state of play by subchapters, the introductory part describes the activities that have been fully implemented, and which are therefore deleted from the Action Plan (table);

- The activities that were partially implemented are described through the introductory parts, while the part of the activities that was not realized is predefined and retained in the Action plan (table);

- Continuous activities, i.e. activities for which the deadline for the implementation is stated as “continuous” are retained in the Action Plan;

- Activities that have not been implemented, with the necessary changes, are retained in the Action Plan;

- New activities are added where it was necessary to respond to the Interim Benchmark;

- Impact indicators / results have been improved at the level of the entire Action Plan;

- Deadlines for the implementation of individual activities have been revised and realistically set.

On 13 February 2018 the first meeting of the Negotiation Group for Chapter 23 was held on the topic of the possible revision of the Action Plan. On that occasion all participants were informed that revision would be made through the correction of existing activities and possibly addition of the new ones where necessary but without changing the essence and the structure of the current Action plan. Also, all stakeholders were invited to submit an internal analysis of the state of implementation of their activities with proposals of the next steps. On the basis of internal analysis provided by stakeholders and the regularly quarterly reports of the Council for the implementation of the Action Plan for the negotiations for Chapter 23 the working (zero) draft of the revised AP23 was made. Simultaneously, bilateral meetings were held with representatives of stakeholders in all three sub-chapters.

On 13 December 2018 the working (zero) draft of the revised AP CH23 was submitted to all stakeholders responsible for its implementation for further discussion. Second meeting of the Negotiation Group for Chapter 23 was held on 17 December 2018 in order to constructively discuss the interventions made in the revised AP CH23. Almost all stakeholders sent their writing comments on the text and several more bilateral meetings with the institutions were organized where needed. Following the implementation of the suggestions made by the institutions, the first draft of the revised Action Plan was published on the website of the Ministry of Justice on 21 January 2019. The draft was published with the public call for the civil society organizations and public at large to submit proposals and suggestions. At the same time, the public call was published by the Office for cooperation with civil society as well.

In order to have the opportunity to exchange the views and to clarify all procedural and substantive aspects of the revision, on 6 February 2019 the Ministry of Justice organized the roundtable supported by the IPA 2015 project “EU for Justice – Support to Chapter 23” where the official presentation of the document was delivered. The round table gathered representatives of relevant Serbian institutions, civil society organizations, and international partners. The presentation was followed by lively and fruitful debate of all participants. The same day, Serbian and English versions of the presentation was put on the web site of the Ministry of Justice.

The Ministry of Justice received more than 25 written comments from the various state authorities and civil society organizations. Particular attention has been paid to the joint comments of the NKEU which was composed of the conclusions and suggestions of several civil society organizations within NKEU. The separate meetings with NKEU were organized on 20 February and 19 April 2019 with an aim to discuss all three Subchapters. The First Draft of the Revised AP CH23 was thoroughly discussed in a constructive atmosphere. The meeting was particularly beneficial, given that a number of comments prepared by the CSOs were addressed and clarified, while certain changes of the AP were explained.  All received comments and submitted suggestions have been reviewed. During the development of the second draft of the revised Action Plan for Chapter 23, the Report on the conducted public consultations has been made as well. The report presents what suggestions were made during the public consultations, whether and in what way those suggestions were integrated into the draft of the AP CH23 and the reasons why some of the suggestions were not accepted. This draft of the revised Action Plan for Chapter 23 together with the Report on the conducted public consultations was published and sent to the European Commission.

After receiving the opinion of the European Commission in October 2019, its comments have been thoroughly analyzed and forwarded to the relevant state authorities within the Chapter 23. Also, for the sake of respect for the principles of inclusivity and transparency, they were also forwarded to the NKEU for information and timely preparation for the continuation of the consultation process.

On 22 October 2019 the meeting of the Negotiation Group for Chapter 23 was held on the topic of the implementation of EC comments. The institutions were asked to submit written contributions which would address EC recommendations regarding activities related to specific institution.

The draft of the revised Action Plan for Chapter 23 was shared with civil society organizations for the second round of consultations. On 27 December 2019 (Fundamental Rights) and 25 February 2020 (Judiciary and Anti-corruption), the meetings with NKEU were held in order to discuss all three subchapters from the third draft of the revised Action Plan for Chapter 23. After receiving and reviewing the new joint comments of the NKEU, the draft was revised again implementing the suggestions. The new Report on the conducted public consultations has been prepared and published as well. On the basis of all written contributions, the conclusion from the meetings held afterwards with institutions and the civil society, the work on the final version of the Revised Action plan for the implementation of Chapter 23 continued in order to improve the text and align it with the EC comments and recommendations. In parallel, the constructive and fruitful dialogue with the EC was conducted with the aim to clarify all relevant issues.

It should be underlined that the process of the adjustment of the final draft has been conducted with fully inclusiveness and with continuing communication and cooperation with all stakeholders and institutions responsible for the implementation of the activities.

In the process of drafting the Action Plan for Chapter 23 in 2016, the negotiating Group for Chapter 23 followed the principles of full transparency and inclusiveness. The current process of the revision of this Action Plan is following the same path respecting the same principles. In that respect, Serbia will closely pay attention to IBM from the EU Common Position, that is, throughout the document, “Serbia will fully recognise the importance of inclusive and evidence-based policy-making and of making the best use of civil society expertise and therefore to engage in inclusive consultations on legislative and policy proposals with civil society and other stakeholders and to ensure systematically access to information.”

- Mechanisms for implementation of the Action Plan

3.1. Subjects responsible for monitoring the implementation of the Action Plan

The responsibility for monitoring the implementation of the activities envisaged in the Action Plan will be entrusted to the Coordination Body for implementation of the Action Plan for Chapter 23 (hereinafter: Coordination Body). Expert and administrative- technical support to the Coordination Body will be provided by the Secretariat of the Coordination Body for implementation of the Action Plan for Chapter 23 (hereinafter: Secretariat).

Government of the Republic of Serbia shall render the Decision on establishing of the Coordination Body together with the adoption of the revised Action Plan. Government shall appoint members of the Coordination Body among the highest rank public office holders/ heads of institutions in charge of the implementation of the main portion of the activities from the Action Plan. Every member of the Coordination Body shall be accompanied with deputy member. Minister of Justice shall be President of the Coordination Body. Detailed rules and procedures of work of the Coordination Body shall be arranged by the Rules of Procedure of the Coordination Body.

Coordination Body:

- Monitors implementation of the Action Plan;

- Analyses and discusses draft Reports on implementation of the Action Plan;

- Adopts Reports on implementation of the Action Plan;

- Reports to the European Commission, Government of the Republic of Serbia and the National Assembly on implementation of the Action Plan;

- Defines recommendation for improvements of the implementation of the Action Plan;

- Initiates an Early Warning Mechanism in case of delays or other problems in the implementation of the Action Plan;

Coordination Body semi-annually reports on the implementation of the Action Plan to:

- The European Commission through the Ministry of European Integration;

- The European Integration Chamber of the National Assembly;

- Government of the Republic of Serbia.

Reports on the implementation of the Action Plan shall be publicly available on the Ministry of Justice Webpage.

The Coordinating Body meets at least four times a year. The meetings of the Coordination Body are attended by representatives of the Secretariat. At the invitation of the Coordination Body, sessions may also be attended by representatives of other institutions and bodies responsible for the implementation of the Action Plan that do not have representatives in the membership of the Coordination Body, as well as representatives of other institutions and bodies whose presence is important for the more efficient work of the Coordinating Body.

The constituent session of the Coordination Body shall be held no later than 30 days after the establishment of the Coordination Body. The members of the Coordination Body are not compensated for their work.

The Secretariat of the Coordination Body for the implementation of the Action Plan for Chapter 23 is the expert body that provides expert and administrative-technical support to the Coordinating Body. Independent experts with proven experience in the field of Chapter 23 shall be appointed to the Secretariat.

The Secretariat provides expert support to the Coordinating Body by:

- Analysis of the collected and consolidated data on the implementation of the Action Plan;

- Conducting a preliminary evaluation of the results of the implementation of the Action Plan in accordance with the indicators and Interim Benchmarks;

- Establishing a list of critical points in the implementation of the Action Plan under the Early Warning Mechanism;

- Adoption and an effective implementation of the Methodology for monitoring and evaluating the results of the implementation of the Action Plan and the training of focal points in institutions responsible for implementation of the Action Plan;

- Needs Assessment and initiation of the updates and revision of the Action Plan;

The Secretariat provides administrative support to the Coordinating Body by:

- Initiating and coordination of the collection, unification and processing of data on the implementation of the Action Plan;

- Drafting reports on the implementation of the Action Plan, as well as draft decisions of the Coordination Body;

- Timely publishing reports and other relevant information related to the implementation of the Action Plan;

- Organization of sessions of the Coordination Body, meetings of the Coordination Body with civil society organizations, as well as training of focal points.

The Secretariat begins its work within 30 days since the establishment of the Coordination Body. The funds for the work of the Secretariat shall be allocated from the donor projects and/or the Budget of the Republic of Serbia and the members of the Secretariat appointed accordingly.

3.2. The role of civil society in monitoring the implementation of the Action Plan

Bearing in mind that the mechanisms of cooperation with the civil society, created during the screening process, the preparation of the Action Plan and the monitoring of its implementation before the revision, resulted in significant progress terms of transparency and inclusiveness, but also showed certain shortcomings. After the adoption of the revised Action Plan, an improved consultation mechanism with civil society in the process of monitoring the implementation of the Action Plan will be developed. This new improved consultation mechanism will include the coordination with the Convent, as the body which gathers the representatives of high number of the civil society Organizations.

Not later than 30 days after the establishment of the Coordination Body, the Office for Cooperation with Civil Society will announce a public call for systematic, continuous and institutionalized inclusion of civil society organizations in the process of monitoring the implementation of the Action Plan for Chapter 23, which will include the establishment of an expert platform for continuous dialogue with the Coordination Body and institutions in charge of implementing the Action Plan. This will include, among others, at least semi-annual debates and round tables with representatives of relevant stakeholders to discuss reports on the implementation of the Action Plan and other relevant issues.

In addition to this, the Negotiating Group for Chapter 23, the Coordination Body and the Secretariat will continue to use consultative mechanisms that showed the great capacity and results in the previous period of the implementation of the Action Plan, including the announcement of public calls for submitting suggestions and comments on drafts of relevant documents.

3.3. The Early Warning Mechanism in case of delays and/or problems in implementation of the Action Plan

Within the scope of preparation of draft Reports on implementation of the Action Plan, the Secretariat prepares a dedicated report or appendix to the draft Report outlining critical points in implementation of the Chapter 23 Action Plan. This document would inform and urge the Coordination Body’s actions under the early warning mechanism.

Where institutions (not represented in the Coordination Body) face difficulties in implementing activities envisaged in the Chapter 23 Action Plan, their representatives shall be invited to the Coordination Body’s sessions for further discussion of the shortcomings and necessary measures.

The Coordination Body shall establish the follow-up reporting procedure of measures taken to address the issues that triggered the early warning mechanism.

In cases where reports in accordance with the follow up reporting procedure show that there is no progress or progress is not satisfactory, the Coordination Body shall inform the Government outside of the regular reporting timeframe in order to initiate the Government’s intervention aimed at fostering implementation of the Action Plan.

3.4. Monitoring and evaluation mechanism: relationship between the Action Plan for Chapter 23 and the Judicial Development Strategy for the period 2020-2025

The process of drafting Judicial Development Strategy for the period 2020-2025 and the process of revision AP 23 are two parallel processes, and their content is as far as possible harmonized. These simultaneous processes are being seen as an opportunity to improve the quality of each aspect of these strategic documents including the mechanism for their monitoring and reporting. The main goal is to establish a coordination of implementation of the strategic framework. This will help us avoid the earlier dualism of strategic documents in the sector of judiciary, which was highlighted as a problem in the previous analyses and reports of domestic authorities and institutions.

Monitoring of the implementation of the measures from the Judicial Development Strategy for the period 2020-2025 will be placed under the responsibility of the body charged with monitoring the implementation of the activities in the Action Plan for Chapter 23- the Coordination Body for implementation of the Action Plan for Chapter 23 and in accordance with the methodology provided for in this strategic document in order to avoid duplication of work and unnecessary burdens in reporting by the same institutions. Expert and administrative- technical support to the Coordination Body will be provided by the Secretariat of the Coordination Body for implementation of the Action Plan for Chapter 23, currently performed by the Council for AP 23 consisted of external experts/consultants.

Such an approach should result in achieving the maximum efficiency of the mechanism for monitoring the development of the judiciary, providing objective reports and strengthening accountability for the results of development and implementation of reforms with the relevant stake holders.

The deadlines set by the AP23 will be the deadlines for implementing the measures in the Strategy. The same applies to the impact indicators at the level of the recommendation, and the Interim Benchmark and the indicators of the results at the level of measure or activity. The results indicators are set in relation to each activity individually, so as to facilitate the way in which the implementation of the Action Plan is monitored, in quantitative and qualitative terms.
MONITORING & EVALUATION MECHANISM

GOVERNMENT OF THE REPUBLIC OF SERBIA

COORDINATION BODY FOR THE IMPLEMENTATION OF AP CH23

Discusses, adopts and submits reports on the AP CH 23 implementation

Stakeholders in charge of the implementation of AP CH23

Working bodies in charge of the monitoring of national strategic documents related to CH 23

quarterly

Semiannual

Semiannual

CIVIL SOCIETY ORGANISATIONS

NATIONAL ASSEMBLY- CHAMBER FOR EU INTEGRATIONS

EUROPEAN COMISSION

MINISTRY OF EUROPEAN INTEGRATION

Semiannual

Semiannual

quarterly

SECRETARIAT OF THE COORDINATION BODY FOR THE IMPLEMENTATION OF AP CH23

Analyses performance reports, prepares draft reports and decisions of the Coordination Body and conducts pre evaluation

- JUDICIARY

CURRENT STATE OF PLAY

Legislative and institutional framework for the judiciary in the Republic of Serbia comprises the following:

National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 57/13);

Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 71/13, 55/14 and 106/16);

The Constitution of the Republic of Serbia ("Official Gazette of the RS", No. 98/06);

Law on the Constitutional Court ("Official Gazette of the RS", No. 109/07, 99/11, 18/13 –Decision of the Constitutional Court, 40/15 and 103/15);

Law on the High Judicial Council ("Official Gazette of the RS", No. 116/08, 101/10, 88/11 and 106/15);

Law on the State Prosecutorial Council ("Official Gazette of the RS", No. 116/08, 101/10, 88/11 and 106/15);

Law on Judges ("Official Gazette of the RS", No. 116/08, 58/09 – decision of the Constitutional court, 104/09, 101/10, 8/12 – decision of Constitutional court, 121/12 and 101/13, 106/15, 63/16- decision of the Constitutional court and 47/17);

The Law on Public Prosecutor’s Office ("Official Gazette of RS", No. 116/08, 104/09, 101/10, 78/11 – state law, 101/11, 38/12 – decision of the Constitutional court, 121/12 and 101/13, 106/15 и 63/16 – decision of the Constitutional court);

Law on Organization of Courts ("Official Gazette of the RS", No. 116/08, 104/09, 101/10, 31/11 – state law, 78/11 – state law, 101/11 and 101/13, 106/15, 40/15 –state law, 13/16, 108/16, 113/17 and 65/18 – decision of the Constitutional court);

Law on the Seats and Territorial Jurisdictions of Courts and Public Prosecutors’ Offices ("Official Gazette of the RS", No. 101/13);

Law on the Judicial Academy ("Official Gazette of RS", No. 104/09 and decision of Constitutional court No. 32/14 – decision of the Constitutional court and 106/15);

Criminal Procedure Code ("Official Gazette of the RS", No. 72/11, 101/11, 121/12, 32/13, 45/13 and 55/14);

Civil Procedure Law ("Official Gazette of the RS", No. 72/11 49/13 – decision of Constitutional court, 74/13 – decision of Constitutional court, 55/14);

Law on Non-Contentious Proceedings ("Official Gazette of the RS", No. 25/82 and 48/88 and "Official Gazette of the RS", No. 46/95 – state law, 18/05 – state law, 85/12, 45/13 – state law and 55/14, 6/15 и 106/15 – state law);

Law on Enforcement and Security ("Official Gazette of the RS", No.106/15, 106/16 – authentic interpretation and 113/17 – authentic interpretation and 54/2019);

Law on Public Notaries ("Official Gazette of the RS", No. 31/11, 85/12, 19/13, 55/14 – state law and 106/15);

Law on Mediation ("Official Gazette of the RS", No. 55/14);

Law on the Bar Exam ("Official Gazette of the RS", No. 16/97);

Law on Misdemeanors ("Official Gazette of the RS", No. 65/13, 13/16 and 98/16 – decision of Constitutional court);

Law on the Public Attorney's Office ("Official Gazette of the RS", No. 55/14).

The institutional framework encompass: the High Judicial Council, the (High) State Prosecutorial Council, Ministry of Justice, Judicial Academy, Supreme Court of Cassation, four appellate courts, 25 higher courts, 66 basic courts with 29 court units, Misdemeanor court of appeal with three departments, 44 misdemeanor courts, Commercial Court of Appeal, 16 commercial courts, Administrative Court with three departments, the Republic Public Prosecutor’s Office, four appellate public prosecutors’ offices, 25 higher public prosecutors’ offices, 58 basic public prosecutors’ offices. The judicial system in the Republic of Serbia, as of January 1st 2020, encompasses 2703 judges, 68 public prosecutors and 716 deputy public prosecutors.

National Assembly of the Republic of Serbia had enacted the National Judicial Reform Strategy for the period 2013-2018 on July 1st 2013, which had determined priorities, strategic goals and strategic guidelines of reform measures. The Government of the Republic of Serbia had adopted an Action plan for implementation of the Judicial Reform Strategy for the period 2013- 2018 on July 31st which had envisaged concrete measures and activities for implementation of strategic objectives, defined the deadlines and competent authorities for its implementation and financial sources. Following adoption of the Action plan for Chapter 23, the Government passed the Conclusion on the adoption of the revised Action Plan for the implementation of the National Judicial Reform Strategy in December 2016.

The Strategy had envisaged independence, impartiality, competence, accountability and efficiency of the judiciary, as five basic principles and defined priorities, strategic objectives and strategic guidelines of reform measures.

The National Judicial Reform Strategy for the period 2013-2018 had stipulated implementation of measures aimed at improvement of impartiality, ethics and integrity of the judicial office holders as well as at the alignment and complete accessibility to the case law and the full realization of the right to the natural judge. The same strategic document had also stipulated the establishment of a system of appointment and promotion of judges and public prosecutors according to clear, objective and criteria determined in advance. Following measures in the reform of Judicial Academy had been set forth as the strategic approach: Improving initial and continuously training of judges’ and public prosecutors’ associates and assistants, and judicial office holders as well as of representatives of legal professions, along with the system of development of a comprehensive annual training programs and assessment of attendees. In order to achieve these objectives, a comprehensive analysis of the position and directions of the development of the Judicial Academy had been conducted. In that purpose, the Judicial Academy adopted the Strategic Plan for the Development of the Judicial Academy for the period 2016-2020 which set four main goals: further strengthening the capacity of the Judicial Academy in order to achieve an effective training and research institution; development of sustainable training programs for the holders of judicial functions, both for initial and continuous training; supporting the development of a system of appointment and promotion of judges and public prosecutors according to clear, objective and criteria system; further networking and external strengthening of the cooperation with partners.

On the requirement of the first IBM for an impact assessment of the National Judicial Reform Strategy 2013-2018 and following the fact that the National Judicial Reform Strategy for the period 2013-2018 expired at the end of 2018, the assessment of its implementation has been done with the support of USAID Rule of Law Project. The USAID document “Assessment of the implementation of the National Judicial Reform Strategy 2013-2018 from November 2018 is the result of a process of consultation and research in the area of judicial reform. The aim of this assessment was to contribute to a better understanding of the reforms that have been implemented so far, as well as to point out the possible directions of future strategic activities in the field of judicial reform. Within each principle of the NJRS 2013-2018, the implementation of measures and activities for achieving the defined goals and guidelines of the reform was analyzed in detail, which gave decision-makers a clear insight into the status of the achieved results under individual guidelines and measures from the respective Action plan.

The USAID Assessment gave an overview of the most important areas of progress made during the implementation of the Strategy, areas where progress has been made and areas that require additional efforts. The development of the new Judicial Development Strategy (JDS) for the period 2020-2025 was preceded by this assessment and the new strategic document will rely on the assessment of the previous one, its advantages and disadvantaged experienced during implementation.

The development of the new Judicial Development Strategy (JDS) for the period 2020-2025 began timely in January 2019 when the Ministry of Justice formed a Working Group that drafted and adopted the first draft of the document at the meeting held on 24 April 2019. As part of the consultative process that was conducted, four round tables were held on May 22 in Kragujevac, June 4 in Novi Sad, June 6 in Nis and June 24 in Belgrade, where the Working Text of the Judicial Development Strategy for 2020-2025 was presented. At the same time, all interested stakeholders were invited to submit further suggestions and proposals until 15 July 2019. After the analysis and implementation of the received comments and suggestions, a new version of the Working Text of the Judicial Development Strategy for the period 2020-2025 was published on the website of the Ministry of Justice at the end of July 2019. Also, a Report on the course and results of consultations with interested stakeholders was published. The Committee on Legal System and State Bodies of the Government, at the proposal of the Ministry of Justice, adopted Conclusion 05 No: 021-11621 /2019 from 21 November 2019, authorizing the holding of a public debate on the Draft of National Judicial Development Strategy (NJDS) for the period 2020-2025. The Public Debate was conducted from 21 November to 10 December 2019. The Ministry of Justice collected and the consolidated the opinions of the State authorities. The Report on the Public Debate was published on the Ministry of Justice's website.

The National Assembly adopted the Law on the Planning System of the Republic of Serbia (“Official Gazette of RS”, No 30/18) on 19 April 2018. The Law came into force on 28 April 2018 and applies as of 29 October 2018. The motive for adopting this law was the need to establish an efficient, transparent, coordinated and realistic planning system for the Republic of Serbia, autonomous provinces and local self-government units. Passage of the Law on Planning System was followed by the adoption of the Regulation on Public Policy Management Methodology, Regulatory Impact Assessment and Contents of Individual Documents.

Judicial Development Strategy for the period 2020-2025 was drafted to be in line with the relevant strategic principles contained in the Law on the Planning System of the Republic of Serbia. During the drafting process, Articles 23 and 49 of the Law were considered since the documents drawn up in the process of accession negotiations of the Republic of Serbia to the European Union are considered a special type of planning documents and are drafted in accordance with the legal framework for conducting accession negotiations, or in form, with content, according to the procedure and within the deadlines provided by the methodological recommendations of the EC and in accordance with the needs arising from the accession process, and therefore may contain special elements not prescribed by the Law on the Planning System of the Republic of Serbia.

With regards to the Action Plan for the JDS, the Law on the Planning System (Article 18, paragraph 7) leaves the possibility to regulate the implementation of strategies through several action plans with a shorter implementation period. Accordingly, JDS 2020-2025 will be partly implemented through a revised Chapter 23 Action Plan aimed at reaching transitional benchmarks. It is expected that, during the implementation of the Strategy, the Republic of Serbia in the negotiation process for accession to the European Union will receive the final benchmarks, which will be contained in the new, or subsequently revised, Action Plan for Chapter 23. Implementation and monitoring of the JDS 2020-2025 will be consolidated in this way. For these reasons, monitoring the implementation of JDS 2020-2025 will be the responsibility of the body in charge of monitoring the implementation of AP23 and in accordance with the methodology foreseen by that strategic document, and in full compliance with the standards defined in the Law on Planning System of the Republic of Serbia, which provides for ex-post analysis of the effects of the strategy no later than 120 days after the end of each third year from the date of adoption, as well as the final report to be submitted no later than six months after the end of the strategy's implementation.

Pursuant to Article 77 of the Law on State Administration, as well as the procedural and methodological framework contained in the Law on the Planning System of the Republic of Serbia, the process of adoption of the JDS 2020-2025 was preceded by a lengthy and comprehensive consultative process involving all judicial institutions, professional associations, civil society organizations and the group of external experts in the field of justice.

Reform activities in the Republic of Serbia will continue to be based on the new Judicial Development Strategy for the period 2020-2025. Strategic goals from the JDS 2020-2025 will follow the determination of Serbia for full membership in the EU. Thus, in the next five-year period, the strengthening of the independence and autonomy, impartiality, efficiency, competence and accountability of the judiciary, as well as the strengthening the public confidence in the work of the judiciary, will be priority of all stakeholders. As the process of the revision of the Action plan for Chapter 23 and of drafting Judicial Development Strategy for the period 2020-2025 are being conducted simultaneously, a particular attention was given to obtain two strategic documents dealing with judiciary that will be complementary and harmonized among themselves. The highest level of coherence of the two strategic documents is important not only regarding envisaged key activities, but also in respect of monitoring and evaluation mechanism that will be established in order to facilitate the oversight of the implementation of the reform.

The table composed of the Comparative analysis that presents which activities in the AP23 will implement which measure of the new JDS 2020-2024 can be found as annex I of this document.

INDEPENDENCE /IMPARTIALITY /ACCOUNTABILITY/ PROFESSIONALISM/COMPETENCE/EFFICIENCY

Concerning the independence of judiciary, the National Judicial Reform Strategy for the period 2013-2018 had identified the need of amending the Constitution in the part which deals with the interference of legislative and executive powers in the process of appointment and dismissal of judges, court presidents, public prosecutors and deputy public prosecutors, elected members of the High Judicial Council and State Prosecutorial Council, and the need for strengthening the role and status of Judicial Academy, as mechanism for entry to judiciary.

Although due to various reasons deadlines concerning constitutional changes prescribed at the APCH23 have not been fully met, in previous years the Republic of Serbia made substantial progress as regards the revision of its Constitution in order to strengthen the independence and accountability of the judiciary.

The base for the commencement of the process regarding the constitutional amendments was the Analysis of the Constitutional Framework on the Judiciary in the Republic of Serbia done by the Working Group consisted of the professors of Constitutional law. This Working group was esablished by the Commission for the Implementation of the National Justice Reform Strategy for the period 2013-2018 on which session the Analisis was presented and discussed. On 29 November 2016 the Supreme Court of Cassation organised the conference devoted to the presentation of the Analysis. The Conference was attended by the presidents of all courts in the Republic of Serbia, representatives of the Working Group, representatives of the MoJ, international Organizations and institutions, professional associations and the non-governmental sector.

On 19 May 2017 the Ministry of Justice in cooperation with the Office for Cooperation with Civil Society had issued a public invitation for the participation of civil society Organizations in a consultative process inviting the non-governmental sector to submit its proposals for amending the Constitution in the part relating to the judiciary. In order to ensure full transparency the proposals were published in the websites of the Ministry of Justice and Office for Cooperation with Civil Society. All of the proposals regarding constitutional changes in judiciary were analysed, the offered solutions for the future amandements were compared and they were taken into account during a drafting of the working texts of the constitutional amendments. As a part of the Consultative Process the MоJ organised six roundtables in the period from July to November 2017. After a series of roundtables organized throughout Serbia where the most important topics related to the future amendments were discussed and in consultation with the expert of the Council of Europe, the first Working Version of the Draft Amendments to the Constitution of the Republic of Serbia was drafted and published on the website of the Ministry of Justice on January 22, 2018. All interested stakeholders (as well as public in large) had been invited to submit their opinions and reasoned comments regarding the Working text and the new roundtable series was organised. In line with received comments and suggestions, and on the basis of the conclusions from the public debate, the Working text has been revised by the Ministry. The second version of the Draft Amendments to the Constitution was published on April 13, 2018 and sent to the Venice Commission on opinion. At the plenary session held on June 22, 2018, the Venice Commission adopted the opinion on the Working Draft Amendments to the Constitution of the Republic of Serbia in the field of judiciary.  Since the APCH23 clearly stipulates that constitutional changes have to be done in accordance with the European standards as promulgated by the Venice Commission, the recommendations given in the Opinion have been implemented in the revised working draft of the amendments and such a third text was published on September 11, 2018 by the MoJ. Taking into account the views and suggestions of representatives of relevant state authorities, professional associations and civil society at the round table held on September 18, as well as the conclusions from the Analysis of the Constitutional Framework on the Judiciary in the Republic of Serbia, the Ministry of Justice revised the third working text of the constitutional amendments and published the final fourth version on October 15, 2018.

The Venice Commission on 22nd October published the Secretariat Memorandum on the compatibility of the draft Amendments to the Constitutional Provisions on the Judiciary as submitted by the Ministry of Justice of Serbia on 12 October 2018 (CDL-REF(2018)053) with the Venice Commission’s Opinion on the draft Amendments to the Constitutional Provisions on the Judiciary (CDL-AD(2018)011). In the Memorandum the Venice Commission concluded that the recommendations formulated by the Venice Commission in its opinion were followed by Serbian authorities in the final draft Amendments to the Constitutional Provisions on the Judiciary.

Transparency and inclusiveness of all stakeholders including civil society and professional Organizations were the guiding principles for the Ministry throughout the entire process of drafting the amendments as the basis for initiation of the official procedure that will be continued in the Parliament.

The official procedure commenced at the end of 2018. The Government has established on its 113th session held on 29 November 2018 the Proposal for Amendments to the Constitution of the Republic of Serbia and made a conclusion, pursuant to Article 203 paraph 1 of the Constitution of the Republic of Serbia and Article 142 of the Rules of procedure of the National Assembly ("Official Gazette of RS”, 20/12 – corrigendum) to propose to the National Assembly amendments to the Constitution of the Republic of Serbia. The Government submitted a Proposal for Amending the Constitution of the Republic of Serbia to the National Assembly on 30 November 2018.

At its 111th sitting, held on 14 June 2019, the Committee on Constitutional and Legislative Issues of the National Assembly discussed this Proposal and established that the Proposal had been submitted by a proposer authorised by the Constitution and that it had been submitted in a prescribed form, which the Committee reported to the National Assembly where the official process now will be continued.

Having in mind the importance of the alignment of the subsequent judicial legislation with new constitutional provisions, the Ministry of Justice has already formed four Working groups (Working group for the preparation of the Draft Law on Judicial Academy; Working group for the preparation of the Draft Law on High Judicial Council, the Draft Law on Court Organization and Draft Law on Judges; Working group for the preparation of the Draft Law on High Prosecutorial Council and the Draft Law on Public Prosecution; Working group for the division of the competences between the Ministry of Justice and Judicial and Prosecutorial Councils) which have started to meet and work. Their task is, on the one hand, to harmonize the judicial legislation with the future amendments to the Constitution, and, on the other hand, to improve current legislative solutions where it is recognized as necessary and welcoming. The Venice Commission will be consulted on this legislation and its opinion will be valuable for taking next steps.

During the period of the implementation of the APCH23 and the NJRS 2013-2018 the National Assembly appointed the remaining court presidents at the proposal of the High Judicial Council. Presently, the procedure for the nomination and the election of the candidates for the court presidents is being conducted regularly, according to law, without delay and with a clear selection procedure applied. Improved rules for evaluating professional performance of judges and public prosecutors have been adopted and are being successfully applied. Through the legislative changes and new bylaws, clear, measurable and objective criteria were defined for appointment to the function and evaluation of work of judges and public prosecutors. Progress has also been made in terms of transparency in that field, primarily through the availability of information relevant to the process and evaluation results on the High Judicial Council and State Prosecutorial Council websites. Since the adoption of the Rulebook on criteria, standards, procedures and authorities for the assessment of the work of judicial assistants by High Judicial Council in 2016, the position of the judicial assistants has been improved to some extent as well.

The greatest progress at general has been made related to the transparent functioning of the High Judicial Council and State Prosecutorial Council, as bodies guaranteeing the independence and autonomy of courts and judges, public prosecutors and deputy public prosecutors. Namely, through the amendments and supplements to laws and adoption of bylaws, the publicity and transparency of work of the Councils has been significantly improved, making the judiciary and its work seem more accessible to the professional, as well as the general public.

When it comes to transfer of competences from the Ministry of Justice to the High Judicial Council and the State Prosecutorial Council, Serbia has seriously taken into account the changes that have taken place in the previous four years, since 2016 until present date, especially meaning the following: the reasons for the repetitive delays in the application of the provisions of the Law on Organization of Courts; the Decision of 25 October 2018 by which the Constitutional Court finally ruled that the provisions of Article 32 of the Law on Organization of Courts regarding transfer of competences were not in conformity with the Constitution; MDTF Functional Review 2014 for the Judiciary, part Finance – recommendation 34 which states the needs to “Clarify the division of financial responsibilities in key areas of the budget. Articulate definitions of capital and current expenditures, and clarify which institution is responsible for each. Clarify the division of financial responsibilities for the costs of legal procedure between the courts and PPOs. Improve coordination with service providers (i.e. prison facilities, attorneys, expert witnesses, and enforcement agents). Clarity and coordination would improve the effectiveness of resource allocation by the High Judicial Council, State Prosecutorial Council and the Ministry of Justice. It would also improve operational efficiency and minimize unnecessary disruptions, reduce arrears and prevent duplicating and equivocation among courts and PPOs”; NJRS 2013-2018 Strategic Guideline 1.2.2: “Analysis and division of competences between the High Judicial Council and State Prosecutorial Council on one side and the Ministry of Justice on the other in regards to competences related with the budget”; as well as the Opinion No.2 of the CCJE, which refers to the efficiency of the judiciary and to article 6 of the European convention on human rights. The same logic is followed by the ENCJ in the Report 2015-2016 Funding of the Judiciary. Among other recommendations in this Report, the one is that the “courts must be resourced to a level which enables them to discharge their obligation to provide an effective and efficient system for the delivery of justice. Each State should therefore allocate adequate resources, facilities and equipment to the courts to enable them to function in accordance with the standards laid down in Article 6 of the European Convention on Human Rights and to enable judges and court staff to work efficiently.” Also, recommendation No.2 of the Report is “to ensure and strengthen the separation of powers, the Council for the Judiciary, or a body on which the Judiciary is represented, should be closely involved and fully informed at all stages in the budgetary process and should have an opportunity to express its views about the proposed budget to Parliament.”

With this approach, Serbia has not moved away from its previously assumed commitments from 2016, but rather tries to explore and propose the most efficient system of material and financial arrangement, which would provide the judiciary with adequate resources for efficient operation. International standards allow each state to make a decision on the most suitable manner of financing of the judiciary and to regulate this issue by law. In the Revised AP23 the activities will finally lead to fully demarcate what is the jurisdiction of Ministry of Justice, Supreme Court of Cassation, High Judicial Council,  and State Prosecutorial Council, taking into account the Constitutional Court arguments, therefore, without prejudice in any way to the principle of separation of powers and without prejudice to the independence of the judicial branch of government.

With the proposed activities from 1.1.3.1. to 1.1.3.4. under the IBM 1.1.3. Serbia will secure the most efficient system of material and financial arrangement, which would provide the judiciary with adequate resources for efficient operation, all in accordance with the international standards allowing “each state to make a decision on the most suitable manner of financing of the judiciary and to regulate this issue by law.”

Therefore, the working group for the division of the competences between Ministry of Justice and both Councils (established in January 2019) will propose the sustainable legislative solution regarding transfer of competences from the Ministry of Justice to the High Judicial Council, the Republic Public Prosecutor’s Office and State Prosecutorial Council, which will be in line with the Venice Commission opinion, but also in line with the international standards in the respected area of budgeting.

For the purpose of the establishment of an effective mechanism allowing the Councils to react against political interferences, The High Judicial Council, at the session held on 25 October 2016, adopted amendments to the Rules of Procedure of the High Judicial Council that stipulates the procedures of public reactions of the High Judicial Council in cases of political interference in the judiciary. Also, the State Prosecutorial Council adopted the Regulation on work of the State Prosecutorial Council in March 2017, which established the institute of the Commissioner for autonomy, stipulated that this function will be performed by the Deputy President of State Prosecutorial Council and prescribed the procedure of the State Prosecutorial Council public reactions in cases of political influence to work of public prosecution office, regularly (once in a year) and extraordinary (if needed). The Deputy of the President of State Prosecutorial Council started to perform duties of the Commissioner for autonomy in April 2017 and is being very active since then. The Commissioner for autonomy proceeded in several cases, he has been filing reports to the State Prosecutorial Council and has been informing the public on cases of forbidden influence to work of the public prosecution office, where, in opinion of certain prosecutorial office holders, were endangered independence of the public prosecution office and professional integrity of prosecutorial position holders.

In order to raise awareness that refraining from commenting court decisions (in particular by politicians) is an important component of strengthening the full respect of court decisions, the Government has adopted the Conclusion for passing the Code of conduct for Members of the Government of the Republic of Serbia, which regulates commenting judicial decisions and procedures in January 2016. The National Assembly has adopted the Code of conduct for members of Parliament (MPs) relating to restrictions on commenting on judicial decisions and proceedings in July 2017. In accordance with the new Law on Police (Article 45, paragraph 3) on the proposal of the Ministry of Interior, the Government of the Republic of Serbia adopted a completely new Police Code of Ethics. In this regard, the new Code of Police Ethics contains the general norm "Protection of official information" which prescribes that police officers do not disclose and do not use, without an authorization, data which they acquire in service or in connection to the service, and especially those which could threaten legal proceedings or the rights of third parties.

When it comes to the aforementioned Screening Report Recommendation which states: „Establish a clear procedure for both Councils to react publicly in cases of political interference in the judiciary and prosecution – and this recommendation refers to both Councils and their reaction in cases of political influence in the judiciary and prosecution” and Recommendation: “Ensure the full respect of court decisions including by raising the awareness that criticizing decisions, in particular by politicians puts the independence at risk – and this recommendation refers to the Parliament, Government or other state officials who should have full respect of court decisions and proceedings that are ongoing” and the respective IBM (1.1.4. and 1.1.5.): “Serbia establishes an effective mechanism allowing the Councils to react against political interferences and establishes an initial track record of fully respecting judicial decisions and refraining from public comments on the work of courts by officials and politicians”, some new activities have been proposed with the aim to ensure an effective mechanism for the Councils to react in the event of eventual pressure on the judiciary, but also to establish an effective follow up to breaches by members of parliament and government of their duty to refrain from public comments.

By introducing new activities 1.1.5.1. and 1.1.5.2. Serbia will greatly improve the environment around judiciary. Holding regular / quarterly meetings is a good way and proper mechanism to promote and raise awareness, conduct and respect the rules of conduct of all when it comes to court proceedings, court decisions and their commenting. In proposing new activities the CCJE Opinion No. 21 was followed, where it is stated in paragraph 57: “In principle, the judiciary must accept that criticism is part of the dialogue between the three powers of state and with society as a whole, where free and diverse media plays an indispensable role. However, there is a clear line between freedom of expression and legitimate criticism on the one hand, and disrespect and undue pressure against the judiciary on the other. Politicians, others in public positions and the media, particularly in pending cases and during political campaigns, might use simplistic, populist, or demagogic arguments and deliberately misinform the public to make irresponsible criticisms of the judiciary and do not respect the presumption of innocence. Consequently, this may also create an atmosphere of public mistrust in the judiciary and can in some cases infringe the principle of a fair trial as set out in Article 6 of the European Convention on Human Rights”. Such opinion is also linked to paragraphs 52 and 53 of the CCJE Opinion No.18 on the position of the judiciary and its relationship with the other powers of state in a modern democracy. There is also ECtHR practice that supports such approach. In this section, Serbia will include in the program of the Judicial Academy the implementation of training programs regarding the introduction of European standards relating to separation of powers and perception that other state powers should refrain from public comments on individual judicial cases in the context of respect of judiciary’s independence. This approach would also be in line with the Opinion no. 21 of the CCJE on preventing corruption among judges: “64. … Notwithstanding any intention to restrict the justified comments by the public about the work of courts, the role of protecting the constitutional position of the judiciary lies not only with judges but also with representatives of the executive and legislative powers, representatives of civil society, the media and so on. Public criticism of the judiciary should always comply with the requirements set out by Article 10(2) of the ECHR and paragraph 18 of CM/Rec(2010)12.”

A system for monitoring and promoting processing of misdemeanor cases of public violations of presumption of innocence (art. 73 from Law Public information and Media) as well as tracking records concerning this type of proceedings provided by the Supreme Court of Cassation, in cooperation with the Misdemeanor Court of Appeal, has successfully been established.

Civil society and professional associations are continuously involved in defining future steps in the reform process, as well as in monitoring the implementation of reforms. From the very beginning of the current process of constitutional amendments, the Ministry of Justice, with the support of the Office for cooperation with civil society, has involved civil society Organizations and professional associations in its work by means of public calls and a series of round tables organised throughout Serbia. Despite some disagreements during the public  debate caused by the significance and the delicacy of the topic, the civil society Organizations and professional associations gave a great contribution in this process. The final version of the Working Draft Amendments to the Constitution of the Republic of Serbia in the field of judiciary published on October 15, 2018 was the result of the implementation of large number of suggestions made by the civil society Organizations and professional associations. Also, the examples of good cooperation with the civil society in the previous period was joint engagement in the development of the new Judicial Development Strategy for the period 2020-2025 as well as the work on the National strategy on the rights of victims and witnesses of crime - for the period 2020-2025 and its acompanying Action plan.

Ethics Committee within High Judicial Council had been established in April 2016. The High Judicial Council adopted the Rules of Procedure of the Ethics Committee in September 2018. Judges can find relevant information regarding violation of provisions of Code of Ethics on the internet site of the High Judicial Council, via decisions of High Judicial Council in this matter. All decisions are anonymized. The State Prosecutorial Council has established Ethics Committee in April 2014 and adopted the Rules of Procedure of the Ethics Committee in July 2018. At the same session the State Prosecutorial Council established the Working group for amendment of the Code of Ethics so drafting of the text is in course, and it will be followed by guidelines for its implementation. The future step which demands legislative changes as a precondition will be the transformation of ethics committees into the permanent bodies within the Councils.

The legal framework and transparency of its implementation have been improved to a certain degree during the implementation of the APCH23 and the NJRS 2013-2018 with regard to the work of disciplinary bodies within the Councils. Disciplinary bodies of the High Judicial Council file yearly report to the High Judicial Council regarding their work. These reports can be found on internet site of the High Judicial Council. The Disciplinary Prosecutor also yearly submits the annual reports to the State Prosecutorial Council. The proposal of the improvement of the legal framework on disciplinary responsibility for judges and public prosecutors, based on the analysis findings, will be one of the tasks of the formed Working groups for the alignment of the subsequent judicial legislation with new constitutional provisions.

Seminars on ethics are part of the regular program of continuous education conducted by the Judicial Academy, and within it, cycles of education are being conducted annually for judges, public prosecutors and deputy public prosecutors. Through these numerous trainings and the availability of relevant materials on the High Judicial Council and State Prosecutorial Council websites, awareness of the rules of ethics and mechanisms of disciplinary responsibility is raised.

It is obvious that efficient justice system could not be managed without comprehensive case management system and that is why a much effort is given to finish roll-out of modern efficient system for courts of general jurisdiction (named SAPS) in close cooperation with EU. SAPS software enables management of cases that covers the entire course and life cycle of the case, from filing an initial act to final decision and archiving. Republic of Serbia has a clear vision of a modern e-system with centralized case management systems accompanied by appropriate hardware infrastructure and a clear legal framework of laws and court rules governing the usage. Although this commitment is just becoming documented through appropriate strategic acts, at the operational level, it is already being realized through various procurement for the data center equipment upgrade, secure network providing, adequate equipment for user, regular trainings of employees in various relevant fields and engagement in realization of relevant projects related to overcoming organizational, technical and legal constrains.

Activities related to training of users and providing of equipment are by their nature, activities that are carried out continuously and have found their place in the coming period. The activities carried out for the purpose of uniform data entry have been carried out and the plan identifies those that will achieve the same objective at the general level.

Central to the ICT justice system is The Judicial Informational System (PIS) for the purpose of electronic data exchange between judicial bodies and other government institutions, Ministry of Justice developed and implemented the Judicial Information System. The Judicial Information System caused significant improvements regarding speed and cost of processes. Through the Judicial Information System, all courts, public prosecutors, notaries and public enforcement officers can electronically check data from the Central Registry for Compulsory Social Security (data on compulsory social insurance paid by the employer for a certain period of time); Misdemeanor records (convictions); Administration for the Enforcement of Criminal Sanctions (whether a person is serving a sentence in a prison); Ministry of Internal Affairs (data on residence and residence history, criminal evidence); Birth registers (data from birth registers, deceased, married); Business Registry Agency (data on natural and legal persons associated with companies, and the history of their functions); The Republic Geodetic Authority (searching for data on whether a person owns a real estate on the territory of the RS); General jurisdiction courts (Register of persons deprived of parental right, Register of persons participants in proceedings); Pension and Disability Insurance Fund (Data on paid pensions, assistance and care benefits and physical impairment benefits); Register of real estate transactions containing data on notarial records and solemnization by contracts on real estate transactions, data on notaries public making records or confirming the deeds, data on courts performing verification of the entry into the Registry; National Bank of Serbia (Single Register of Accounts for Legal Persons and Entrepreneurs, Register of Received Decisions and Register of Enforcement Debtors) and Tax administration. According to Ministry of Justice statistics, since the commencement of the system operation users made 4.000.000 electronic inquiries. It speeds up average court proceeding length for approximated period from 3 to 6 months. It is used by employees of the courts, prosecutor's offices, offices of public bailiffs and notaries. Providing users with click-through data for which they had to make written submissions send by post and process written submissions, as being the biggest contributor to ICT accelerating and facilitating procedures.

Also, the e-filing system was established with the vision to serve citizens and professionals as a means of delivering documents and insight into court cases. In the coming period, it is expanding to new types of court proceedings. Furthermore, Business Intelligence tools are implemented through interconnection with case management system in courts of general jurisdiction so advances statistical tool are available for analytics and as future means for reports on court data.

In September 2017 Judicial Efficiency Improvement Project (JEP) expert’s team developed and proposed over 80 tickets for the AVP application to stop the bad and invalid data entry into the AVP database. The implementation of the developed methodology was fully realized in 2017 and 2018. These tickets concern various types of common mistakes during data entry, harmonization with current Court rules book and Criminal procedure code and missing registries in electronic form. During 2017, trainings were held and the validation of software on data entry forms was significantly improved, which in this way allowed to drastically reduce the number of incorrect data in the databases in the courts.

In September 2018 functionality of electronic scheduling of the hearings and data collection on the adjournments and the reasons for them are developed and implemented within the AVP application for the basic courts, the higher courts, the commercial courts and Commercial Appellate Court. In the future this activity will be transformed into the activity of monitoring the reasons why the hearings are delayed.

Through Judicial Efficiency Improvement Project (JEP), Ministry of Justice has successfully developed and implemented the formula for evaluating cases by weight in twenty higher and basic courts in Serbia. In order to distribute cases evenly in cases of criminal, civil and labour disputes, the formula has been successfully identified and specifically assigned to judges for cases requiring more work. List of implemented courts with formula for evaluating cases by weight: Basic court in Zrenjanin, Basic and Higher court in Novi Sad, Basic and Higher court in Kragujevac, Basic court in Valjevo, Basic court in Cacak, Basic court in Leskovac, Basic court in Kraljevo, Basic court in Sombor, Basic court in Vranje, Basic court in Sremska Mitrovica, Basic court in Pozarevac, Basic court in Sabac, Basic court in Negotin, Basic court in Uzice, Basic and Higher court in Nis, Third Basic court in Belgrade and Higher court in Subotica. This formula is intended to be improved and to be more widely implemented.

On the basis of the Analysis of ICT systems in terms of hardware and software from September 2017, the process of establishing the hardware infrastructure is continuing, which is the main prerequisite for the introduction of centralized systems in courts and prosecutor's offices and modern services with the exchange of data and documents between authorities and services to citizens and the economy to the judiciary. In parallel with the preparation of the hardware, the legal framework is being prepared and prepared through amendments to the court rules and other regulations for a greater volume of digitization.

The justice sector is also pursuing reforms towards interoperability of the system with state authorities outside the justice sector, and therefore "Pronep" and "eZiO" applications are being developed to serve the submission of data and documents to the cadaster and tax administration and control over the work of the professions.

Hopefully, after goals settled here future reforms will keep pace with the most developed countries in terms of the development of applied technologies, especially enrichment with Artificial Intelligence and Machine Learning. To set such a goal, the coming years are filled with work on establishing a sustainable basis for a more advanced ICT system in the justice sector.

During the implementation of the APCH23, significant efforts have been made to improve the competence of the holders of judicial functions. A great attention has been dedicated in trainings of the representatives of new judicial professions, such as public enforcement officers, public notaries, mediators, and of the other judicial staff as well. Judicial Academy adopted numerous acts that regulate the training dynamics and contribute to its quality. New programs of continuous training were established, and the capacities of the Judicial Academy were significantly improved.

The National Assembly had passed the Law on Amendments to the Law on the Judicial Academy in December 2015. Amendments to the Law on Judicial Academy provided as follows: the Judicial Academy would be able to implement the professional advanced studies programs intended for the enforcement officers, public notaries, public notaries’ assistants and public notaries' junior clerks/trainees, based on the contract made with the Chamber of Enforcement Officers, i.e. Chamber of Public Notaries; Program Council composition was extended by including the representative of the initial training users’; the final exam board composition was determined and the fee of mentors engaged in the initial training program would be aligned to the fee paid to the mentors engaged in the programs intended for judicial and prosecutorial assistants and trainees; it was provided that the  initial training attendance would be regarded as an experience in the legal field and it was determined in which cases the permanent training would be obligatory (shift in specialized training, major modification of regulations, introduction of new working methods, resolving inefficient performance of judges and the public prosecutor assistants discovered by evaluation of their work results).

The National Assembly had passed the Law on Amendments to the Law on Judges in May 2015. By means of modifications and amendments to the Law on Judges the rules were prescribed on the basis of which the High Judicial Council would particularly evaluate the completed initial training at the Judicial Academy and determine the candidates’ competence and training for the first appointment to the judicial post in basic court and misdemeanor court verified in an exam organized by the High Judicial Council. The candidates who completed initial training with the Judicial Academy are exempted from the obligatory exam and the criteria for competence and qualification evaluation for judicial position is the final exam grade achieved in the basic training at the Academy.

The National Assembly had passed the Law on Amendments to the Law on Public Prosecution, in December 2015. By means of modifications and amendments to the Law on Public Prosecution the rules were prescribed on the basis of which the State Council of Prosecutors would particularly evaluate the completed initial training at the Judicial Academy and determine the candidates’ competence and qualification for the first appointment to the post of the deputy public prosecutor, prescribing that the competence of the candidate running for the deputy public prosecutor post for the first time would be  verified in an exam organized by the  State Council of Prosecutors. The candidates who completed initial training with the Judicial Academy are exempted from the obligatory exam and the criteria for competence and qualification evaluation for judicial position is the final exam grade achieved in the basic training at the Academy.

In 2019 the tenth generation of (35) beneficiaries of the initial training of the Judicial Academy has been enrolled. The Judicial Academy has started to apply live broadcasting during the whole entrance exam, including the written part. In the aim of transparency, this method of activity implementation has been realised firstly during the entrance exam for the judicial and prosecutorial trainees. Within USAID's Judicial Academy support program following systems have been developed during the period of the implementation of the APCH23: a system for the selection and improvement of mentors and lecturers and a system of new evaluations of mentors' work as well as initial training beneficiaries. A new web portal of the Judicial Academy was established, and the Judicial Academy has created a database of decisions of the ECHR under the name e-JURIS / e-CASE which was formed as an e-ACADEMY module. Adequate building for permanent accommodation of the Judicial Academy was obtained on 9th April 2015 by Serbian Government decision and its renovation started in January 2019 with the support of EU funded projects. The new premises should fully correspond to the needs of the Judicial Academy.

Activity regarding the development of monitoring system concerning quality of initial, continuous and specialized training that implies bidirectional evaluation system that would allow the assessment of the results of training or degree of advancement of knowledge of the participants, as well as the assessment of the quality of the program and trainers has being successfully implemented. Cooperation with the Institute for quality assurance of education only asserted our belief that it is necessary to well determine strategic planning. Both initial and continuous educations are conducted at the Judicial Academy since its establishment. At initial education, candidates are evaluated by mentors and at the end of education they are passing the final exam, simulation of trial, evaluated by the commission. Continuous education is being evaluated through standard questionnaires, evaluating the following aspects, quality of lecturers and conditions of work.

The Academy Program Council determined priority topics for education annually based on, among other things, performance evaluation. The programs are regularly being submitted to the High Court Council and the State Prosecutorial Council for adoption, and they are also having in mind performance evaluations when approving the programs.

A significant step in dealing with the problem of large number of backlog cases was the adoption of the Unified Backlog Reduction Program in the Republic of Serbia in December 2013 and the Special Program of Measures for Reduction of Old Enforcement Cases in the Courts in the Republic of Serbia for the period from 2016-2020. Teams in charge of reduction of backlogged cases were established in all courts. After that, in August 2016, the President of the SCC passed the Amended Unified Backlog Reduction Program in the Republic of Serbia for the period 2016-2020. The fact that this is a recognized and acknowledged measure is reflected in the APCH23, since the Unified Backlog Reduction Program is considered a dynamic document, which is why it needs to be “amended and improved in accordance with the initial results of its application and based on the conclusions from the regular sessions of the Working Group for the implementation of the Unified Backlog Reduction Program”. In the following period, in cooperation with the Judicial Academy, a training program for judges’ skills should be further developed – case management and drafting of an individual judge’s plan for reduction of backlog cases. The Working Group for monitoring the application of the Amended Unified Backlog Reduction Program at the meeting held on 24 October 2019 concluded that the trend of backlog reduction is continuous, but that in the same time in almost all courts there was an increase in the number of cases received.

Regarding efficiency and the relieving, the burden off the courts, the significant step was made by introducing the system of bailiff/enforcement officers and the public notary system into the Serbian judiciary. As at 1 January 2020, a total of 197 public notaries and 226 public enforcement officers were appointed. The Chambers of Public Notaries and the Chamber of enforcement officer have also been established and since then they both have very active role in the promotion of these relatively new judicial professions in the Republic of Serbia. The Judicial Academy is in charge of the organization of the trainings for the representatives of public notaries and bailiffs on basis of the agreements signed between the Chambers and the Judicial Academy. Memorandum on Cooperation was signed between the Judicial Academy and the Chamber of Enforcement Agents for the purpose of training of enforcement agents on 21 March 2015. Memorandum on Cooperation was signed between the Judicial Academy and the Chambers of Public Notaries for the purpose of training of public notaries on 22 March 2015.

The Law on Amendments of the Law on Enforcement and Security („Official Gazette of the Republic of Serbia“, Nos. 106/15, 106/16 – Authentic interpretation, 113/17 - Authentic interpretation and 54/19 - hereinafter: “Law”) was adopted by the National Assembly of the Republic of Serbia on July 26th 2019 and its implementation started on January 1st 2020. The Law brings new solutions for the existing problems occurred in practice as well as the implementation of the new models that are not recognised by the current law. It is worth mentioning that one of the biggest novelties will be implementation of the new model related to the sale procedure of immovable and movable property of the enforcement debtor (e-auction). This model as such gives a lot of possibilities in the manner of saving of time, implementation of protective or enforceable measures and which is important this model increases number of buyers and provide the judicial system with the high level of regularity. It should be also mentioned that the procedure of service of documents will be improved by implementation of the electronic board for service of documents (hereinafter: Electronic board) in all courts in the territory of the Republic of Serbia. The Electronic board is centralized application that will be available on the single web address, where all documents issued by the courts or public enforcement officers will be published, and it will be possible to search documents by using the filters. Therefore, this will be the unique electronic board that will cover all courts in the territory of the Republic of Serbia. Furthermore, the Law prescribes the summary proceedings in commercial cases, changes in the field that regulates the legal remedies, changes of the principle of proportionality in order to make this principle stronger, change of the current law in order to prevent the accumulation of costs in the enforcement proceedings, as well as changes of jurisdiction of the public enforcement officers. The Law also prescribes the provisions related to the remaining backlog cases and in that respect new rules are proposed in order to make efficient and suitable solution. In that respect the Minister of Justice and the president of the Supreme Court of Cassation have signed the Guidelines for the implementation of the Law that identify measures and activities which should be carried out. In order to explain specific steps that should be taken relevant trainings of the enforcement judges were held (four training sessions for court presidents and enforcement judges from basic and commercial courts in December 2019).

By the decision of the Minister of Justice, the new Tariff related to the work of the public enforcement officers, the Rulebook on the Procedure of Voluntary Settlement of Monetary Claim before the Enforcement Proceedings is Launched, the Rulebook on Standards of the Professional Behaviour of the Public Enforcement Officer and the amendments to the Rulebook on Model of Keeping Record on Enforcement and Security Proceedings and Financial Conducting of Business of the Public Enforcement Officers, Reporting Model, Content of the Report on Work of the Public Enforcement Officers and the Model of Dealing with the Archive were adopted.

For the purpose of application of provisions of the competences of notaries to act as a trustee of the court, the Ministry of Justice, Supreme Court of Cassation and High Judicial Council have enacted on 13 May 2016 “Instructions for the Implementation of Provisions of Arts. 30a and 110a of the Law on Non-Contentious Procedure and Art. 98 of the Law on Notary System”, enabling the extension of notary competences to inheritance proceedings, thereby alleviating courts of this non-contentious judicial workload.

The Ministry of Justice continuously monitor and analyse judicial statistics related to the entrusting of the implementation of inheritance proceedings and undertaking of actions in non-contentious proceedings. Regarding the transferal of non-judicial non-contentious cases to notaries, the positive trend is constant.

Following the analysis of appropriate solutions for improving the registration process in the real estate cadastre, i.e. for the improvement of the legal framework for cooperation of notaries, courts and enforcement officers with the Republic Geodetic Authority, the National Assembly has adopted the Law on procedure of registration with the Cadaster and Leads („Official Gazette RS“, No. 41/18) dated on 31 May 2018. Based on the mentioned law, the Government of the Republic of Serbia has adopted the Regulation on the mechanisms for delivery of documents in the procedure of registration with the Cadaster and the mechanisms of issuing of the Cadaster extract electronically (“Official Gazette RS number: 50/18”) dated on 29 June 2018.

According to the Law on Certification of Signatures, Manuscripts and Transcripts ("Official Gazette of RS", No. 93/14, 22/15 and 87/2018) since March 1st 2017 the public notaries have taken over new responsibilities and duties.

During the period of the implementation remaining by-laws and Chamber regulations have been adopted and the harmonization with the valid provisions of the Law on Public Notaries has been completed.

On 24 December 2019, by virtue of Article 119 of the Law on Notaries and of Article 15 of the Programme of Training of Notaries, the Executive Board of the Chamber adopted the Plan of Implementation of the Programme of Training of Notaries for 2020, all for the purpose of establishing of the continuous professional improvement of notaries, notary assistants, associates, and notary interns and the standardization of the notary practice.

The Supreme Court of Cassation in December 2016 adopted Rulebook on the replacement and omission (pseudonymization and anonymization) of data in court decisions. Rules governing the method of substitution and omission of information in judicial decisions of the Supreme Court of Cassation, including the method and techniques of anonymization / pseudonymization in decisions in electronic and written form are defined by this document. The regulations in relation to the rules of anonymity of court decisions were adopted at the level of all appellate courts as well.

The activities of the Supreme Court of Cassation regarding the improvement of the consistency of the jurisprudence have been continued. Having in mind that the final version of the Working Draft Amendments to the Constitution of the Republic of Serbia gives a special place to this topic, the Working groups for the alignment of the subsequent judicial legislation with new constitutional provisions, will develop a proposal for more detailed regulation of this issue.

A continuous increase of mediation referrals and mediation proceedings has been noted since the enacting of the Law on Mediation in Dispute Resolution (“Official Gazette of RS” no. 55/2014) and, in particular, since the issuing of the Joint Guidelines for the Improvement of Mediation in the Republic of Serbia on June 28th, 2017 by the Supreme Court of Cassation, the High Judicial Council and the Ministry of Justice. The issuing of the Joint Guidelines has been followed by various promotional activities by the Ministry of Justice and the Judicial Academy, and notable efforts by certain courts. Various protocols have been concluded following the Joint Guidelines, such as the Protocol on Cooperation between the Higher and Basic Courts in Niš, on the one hand, and the Public Utility Company JKP Niš; Protocol on Cooperation to Enhance the Use of Commercial Mediation between the Serbian Chamber of Commerce and the Commercial Court of Appeal; Guidelines for the Promotion of the Procedure for Concluding and Implementing Out-of-Court Settlement in Procedures for the Protection of the Right to Trial in a Reasonable Time, etc.

Mediation continues to be promoted by the Ministry of Justice at various seminars, conferences and other relevant national and international fora. Most significantly, the Republic of Serbia was among the 46 first signatories of the United Nations Convention on International Settlement Agreements Resulting from Mediation in Singapore, on 7 August 2019. The Singapore Convention applies to international settlement agreements resulting from mediation, concluded by parties to resolve a commercial dispute, and is expected to have the same impetus on the development of mediation as the New York Convention had on international arbitration.

Nonetheless, the statistics show that greater demand for mediation must be made in order to achieve the objective of the 2008 Mediation Directive. Namely, of the 411 mediators who filed their Annual Reports to the Ministry of Justice for 2019, 124 stated that they mediated in 2019, 34 of which mediated in cooperation with a co-mediator. Based on these reports, during 2019, 569 mediation agreements were concluded (agreements to enter into mediation), while 403 cases successfully finished with the conclusion of a settlement agreement. Pursuant to the reports of mediators, in 266 proceedings the case was referred to mediation by the court. Most of the mediation procedures were conducted on the territory of the Court of Appeal in Belgrade (34.7%), while 29% were conducted on the territory of the Court of Appeal in Niš, 19.4% on the territory of the Court of Appeal in Novi Sad, and 14.5% on the territory of the Court of Appeal in Kragujevac. Therefore, the number of mediations compared to the number of initiated civil procedures remains under 1%.

By December 30, 2019, 1.349 mediators have been registered by the Ministry of Justice, out of which more than a third is from the City of Belgrade (477), followed by Niš (136), Novi Sad (131) and Kragujevac (65). There are 277 lawyer-mediators (1/4th of all mediators) and the licenses are issued also to the following predominant categories: 29 judges, 6 judicial associates, 10 enforcement officers, 832 graduate lawyers and two Ombudsman. No proposals for revoking of licenses of mediators have been submitted to date to the Ministry of Justice Commission for Revocation of Mediation Licenses. With respect to training, 17 organizations received licenses for conducting training for mediators, but only 12 organizations conducted training, with the total number of participants being 2,941.

With respect to legislative changes, the Law on Amendments to the Law on Peaceful Labour Dispute Resolution, enacted in June 28th, 2018, significantly expanded the scope of the Republic Agency for Peaceful Settlement of Labour Disputes in accordance with its acquired experiences and practices. The competence for individual labour disputes with respect to arbitration was also expanded to include the disputes arising from: payment of salaries/wages, allowance of salaries/wages in accordance with the law, payment of severance pays during retirement, working hours and exercising rights to annual leave. An important novelty in the Law is the precise wording that the arbitrator should in the course of the proceedings indicate to the parties in the dispute the possibility of an amicable settlement of the dispute.

Moreover, the Law on Amendments and Supplements to the Law on Court Fees ("Official Gazette of RS", no. 95/2018), applicable from 1 January 2019, further encourages parties to resolve their disputes by amicable means, through mediation, negotiated settlement, court settlement or any other amicable way. These amendments postpone the collection of court fees in order to leave the parties the opportunity to once again consider the amicable resolution of the dispute, once the court proceedings have been initiated. Through these provisions, the state offers financial incentives to the parties to consider other viable dispute resolution options early in the court proceedings by exempting them from paying all relevant court fees if they achieve a settlement by the time of the first hearing.

Recognizing the need for coordinated, joint, continued multi-annual efforts to establish a viable and sustainable mediation system, the Ministry of Justice has initiated a strategic approach to improving the use of mediation in August 2018 by addressing other institutions, such as the National Bank of Serbia and the Agency for Amicable Dispute Resolution, so as to seek to together find best ways to improve the use and quality of mediation in the fields of their respective competences. Moreover, the Working Group for drafting of amendments to the Law on Mediation in Dispute Resolution and accompanying bylaws was established in 2018 and has since January 2019 worked intensively on a new legal framework, supported by EU funded projects, with the main objectives of improving the availability and quality of mediators, and increasing the number of mediations, i.e. finding modalities which would allow for achieving the objective of the 2008 Mediation Directive.

The implementation of the Criminal Procedure Code from 2011 has been successfully monitored, particularly within the work of the Commission for the Implementation of the NSRP 2013-2018. The quarterly reports on the implementation of the new Criminal Procedure Code elaborated by the RPPO have been widely discussed at the meetings of the Commission for the Implementation of the NSRP 2013-2018. The introduction of the prosecutorial investigation and the institutes of the deferring criminal prosecution and the plea agreement have made a criminal system much more efficient.  At this point in time, the working group will be formed to do fine tuning of the provisions and propose corrective measures where needed.

WAR CRIMES

The legal framework in Serbia encompass:

Law on Organization and Competence of Government Authorities in War Crimes Proceedings („Official Gazette of the RS“ No. 67/03, 104/2009, 101/11- state law 6/15) established an institutional framework for the prosecution of war crimes; Criminal Code (“Official Gazette of RS”, No 121/12, 104/13, 108/14 and 94/16 );

Criminal Procedure Code (“Official Gazette of RS” No. 72/11, 101/11, 121/12, 32/13,45/13 and 55/14);

Law on Mutual Legal Assistance in Criminal Matters (“Official Gazette of RS” No.20/2009);

Law on Protection program for participants in Criminal Proceedings („Official Gazette of the RS“ No. 85/2005);

Law on Cooperation with the ICTY („Official Gazette of the SRJ“ No. 18/2002, and “Official Gazette of SCG” No. 16/2003);

Law on Migration Management („Official Gazette of the RS“ No. 107/2012);

Decision on Establishing the Commission for Missing Persons of the Government of the Republic of Serbia („Official Gazette of the RS“ No. 49/06, 73/06, 116/06, 53/10 and 108/12);

Memorandums on cooperation concluded between the state authorities of the Republic of Serbia with the competent authorities of the countries of the region (Croatia, Bosnia and Herzegovina, Montenegro) and Protocol on cooperation with EULEX, with the purpose of direct cooperation, and more efficient exchange of information regarding war crimes and perpetrators. Jurisdiction for War Crimes in Serbia: 1) Criminal offences from art. 370 through 386 of the Criminal Code; 2) serious violations of International Humanitarian Law committed in the territory of the former Yugoslavia since January 1st 1991 stipulated in the Statute of the International Criminal Tribunal for the Former Yugoslavia; 3) Criminal offence from Art. 333 of the Criminal Code - assistance to the perpetrator after the commission of crime, if committed in relation to criminal offences from point 1) and 2) of this Article.

Institutional framework consists of: 1) Ministry of Interior, War Crimes Investigation Service; 2) Ministry of Interior, Protection unit; 3) War Crimes Prosecutor’s Office; 4) Higher Court, War Crime Department; 5) Appellate Court in Belgrade, Crime Department; 6) Victims and Witnesses assistance and support Section; 7) Commissariat for Refugees and Migration, Sector for Admission, Accommodation and Care, Readmission and Permanent Solutions, Department for Missing Persons (as administrative - technical support to the Commission for Missing Persons).

The Government of the Republic of Serbia was of the opinion that it is necessary to adopt a strategy to prosecute war crimes at the national level, whose objectives and activities would provide a comprehensive and clear strategic framework for improving all areas where problems have been identified, as a clear reflection of the undeniable commitment of the Republic of Serbia to the effective punishment of war crimes. On February 20th 2016, the Government of the Republic of Serbia has adopted the National Strategy for Prosecution of War Crimes 2016-2020 (“Official Gazette RS”, No.19/16), expressing its full support to all local judicial and executive bodies involved in the process of investigating, raising indictments for the war crimes, as well as all international and local organizations that monitor and report on these proceedings as independent observers.

In order of monitoring of the National Strategy, on August 26th 2017 by the decision of the Government of the Republic of Serbia, the Working body for Monitoring of the Implementation of the National Strategy was established. The members of the Working body are representatives of all institutions relevant for the implementation of the National Strategy. The working body develops conclusions and recommendations to competent institutions, and it submits its reports on the implementation of the Strategy on a quarterly basis to the Secretariat for the Implementation of the Action Plan for Chapter 23 and to the Government of the Republic of Serbia. Eight reports were adopted so far, covering the period until October 2019. The reports are published on the web page of the Ministry of Justice.

The draft version of the Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023 was presented at the expert meeting that was held on March 12th 2018 at the premises of the Office of the War Crime Prosecutor in Belgrade. The meeting was attended by the judges, prosecutors, lawyers, representatives of all state bodies involved in prosecution of war crimes. Additionally, the Office of the prosecutor of the Mechanism for International Criminal Tribunals gave its full support to the working version of the Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023. The Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023 was adopted at the Office of the War Crimes Prosecutor management board meeting of 04 April 2018.

A new War Crime Prosecutor was elected by the National Assembly of Republic of Serbian on 15 May 2017 after what she took over the duty of the War Crime Prosecutor on 31 May 2017. The War Crime Prosecutor`s Office team currently consists of nine deputy war crimes prosecutors. Additionally, since 01 November 2018, a military analyst has been engaged as part of the War Crime Prosecutor`s Office team. The capacity building of the War Crimes Prosecutor's Office is constantly in progress.

The system of training/education in the area of International Criminal Law for the related judges and prosecutors has been established, bearing on mind that the implementation of the training schemes on international criminal law for deputy prosecutors and assistant prosecutors started from 2018.

Research into the ICTY/ IRMCT archives – including the databases of the ICTY/ IRMCT Prosecutor's Office – continued throughout the period of the implementation of the APCH23. The War Crime Prosecutor`s Office Liaison Officer is responsible for the the identification of evidentiary items and other relevant documents, their verification for use in cases handled by the War Crime Prosecutor`s Office and their timely delivery to this Office.

The cooperation between the Prosecutor's Office and the War Crime Investigation Service has been improved. The War Crimes Prosecutor's Office formed joint investigation teams with members of the War Crime Investigation Service, having introduced a new methodology in the work. The joint teams hold regular meetings for the purpose of efficient operational treatment. The Prosecutor's Office established working procedures between the War Crimes Prosecutor's Office and the Service, which are necessary for the purpose of harmonizing activities during the procedure in each case.

The strengthening institutional and administrative capacities of the War Crime Investigation Service within the Ministry of Interior Affairs by receiving adequate accommodation facilities - more working premises and adequate space for storing files in the physical form as well as new official vehicles, improved the efficiency of the Service.

The Government of the Republic of Serbia issued a decision dated 8 June 2006 (“Official Gazette RS”, Nos. 49/06, 73/06, 116/06, 53/10 и 108/12) on forming a Commission for the consideration of facts that have arisen during investigations conducted on the occasion of murder of journalists, including murders that were committed during the armed conflict in former Yugoslavia in the period from 1991 until 1995, and murders that were committed in the territory of Kosovo and Metohija in the period from 01 January 1998 until 31 December 2000. The United Nations Committee on Enforced Disappearances commended the Republic of Serbia for its measures so far undertaken in the areas of relevance for the issue of missing persons and pointed to the need for further harmonization of the normative framework with the Convention for the Protection of All Persons from Enforced Disappearance.

The form and contents of the War Crime Prosecutor`s Office web presentation have been improved in order to update the public on the ongoing War Crime Prosecutor`s Office activities related to particular cases, on the implementation of relevant strategic documents and on other developments of importance for the work of this Office. Due to its multiple advantages, the War Crime Prosecutor`s Office web page – with its continuous improvements – is the major source of information and a reliable instrument for the presentation of data relevant to the War Crime Prosecutor`s Office  performance, free and accessible at any time. In order to check if all war crimes reports have been properlly addressed, the War Crime Prosecutor`s Office prepared a report on its overall performance further to the crime reports received since 2003. The report was presented at the War Crime Prosecutor`s Office official website and thus made available to the public.

The Supreme Court of Cassation regularly publishes decisions on war crimes cases on its website. Also, a review of the criminal policy in war crimes proceedings for 2015, 2016 and 2017 is published on the website of the High Court in Belgrade.

The Witness Protection Unit has been granted a status of a special unit of police by the Decree on Special and Special Police Units ("Official Gazette of RS" No. 47/18 of 20.06.2018 and 59/18 of 31.07.2018) and reorganization of the WPU was carried out. Within the Ministry of the Interior – General Police Directorate, the new official premises have been adapted and fully adapted to the needs of the Witness Protection Unit. By adopting the Regulation on special and special units of the police, positions in the WPU were systematized, cataloging was done, general and special conditions for the filling of these positions were determined, and job descriptions were also made for each workplace. By those by-laws, the employment procedure in the WPU determinates the obligation of selection testing, as well as the completion of specialist training for work in the Unit. In the future period, in accordance with the procedure prescribed in above mentioned by-laws the fulfillment of work positions in the WPU will be conducted in the Department for operative procedures, for direct work with the protected persons, as well as police psychologist and the social sciences expert which would create the conditions for the Unit to independently carry out tasks related to psychological and social support to witnesses and close persons to them. Upon the completion of the project WINPRO, the WPU will independently and in cooperation with the relevant organizational unit, continue to train police officers in accordance with the Training program.

In compliance with the Act on Personal Data Protection, the War Crime Prosecutor`s Office has taken measures for the protection of data against unauthorized access, publishing or any other abuse. All members of the War Crime Prosecutor`s Office staff have signed the statement on the preservation of secret and confidential data within the meaning of the Data Secrecy Act and other legal / by-legal documents. A binding instruction on the protection and preservation of secret / confidential information, which is included in this statement, has been handed in to all employees. The instruction includes the overview of the applicable substantive regulations concerning the handling of secret / confidential data, obligation of the protection / preservation of such data, and the list of the criminal law provisions concerning the conduct of elected, appointed and employed staff members in contravention of their legally prescribed obligations. The implementation of relevant legal and by-legal acts governing this area is continuously supervised in order to ensure full confidentiality of the investigations and witness accounts.

Two important regional conferences considering, inter alia, the topic of sentencing policy of the war crimes were held during the period of the implementation of the APCH23. First expert meeting has been held on December 11th, 2015 where the representatives of all relevant institutions in the area of war crimes investigation and proceeding from region and ICTY took part in the discussion. Second regional conference on the subject "Cooperation, criteria and standards in the persecution of perpetrators of war crimes" has been held from 20th to 22nd May 2019 in Belgrade. The High Delegations of the Prosecutor's Offices of Bosnia and Herzegovina, the Federation of BiH, the Brčko District, the Una-Sana Canton, the State Attorney's Office and the Special Prosecutorial Offices of the Republic of Croatia, the Special Prosecution Office of Montenegro, the War Crimes Prosecutor's Office of the Republic of Serbia and the Prosecutor's Office of the Mechanism have participated at this Regional Conference. The conference was organised by the War Crimes Prosecutor's Office of the Republic of Serbia  and UNDP in cooperation with the United Kingdom and Italy. The Conference participants gave the following joint statement on the main conclusions and commitments which has been published in the website of the War Crime Prosecutor Office. The participants agreed that there is still a need for more war crimes proceedings in the conflicts on the territory of the former Yugoslavia and that cooperation between their prosecutors is crucial for achieving this goal. In a desire to significantly improve existing cooperation, the participants agreed to identify specific cases that would be suitable for transfer between their prosecutors' offices, and to start the necessary conversations in this regard. It was also concluded that it is necessary to raise the level of confidence of victims in regional cooperation. To this end, the Prosecution of the MICT will, if necessary, assist the Regional Prosecutor's Offices in the work on the taken cases. The Prosecutor's Offices from Bosnia and Herzegovina, Montenegro and Serbia expect the Prosecution of the IRMCT to continuously assist in strengthening their capacities and support in the exercise of the mandates entrusted to them. Finally, the participants emphasized the importance of regular communication between their prosecutors. One of the conclusions also was that it is necessary to organise periodicaly  regional trainings of public  prosecutors on which the regulations and jurisprudence from all countries will be presented, and which will be the opportunity to exchange opinions and remove the decisions that make the problem in practice, as proposed by the representative of the Prosecutor's Office of Bosnia and Herzegovina. In parallel, the War Crimes Prosecutor's Office of the Republic of Serbia adopted its conclusions related particularly to the question of proportionality of sentences and a sentencing policy. It is noted that one of the challenges that must be overcome is the equalization of the jurisprudence regarding the punishment of war crimes perpetrators, in the ICTY (IRMCT) and in the countries in the region, and overcoming the problems that have arisen in connection with this issue.

- JUDICIARY

| 1.1. INDEPENDENCE |  |  |
| --- | --- | --- |
| INTERIM BENCHMARK | OVERALL RESULT | IMPACT INDICATOR |
| 1.1.1. Serbia adopts new Constitutional provisions bearing in mind the Venice Commission recommendations, in line with European standards and based on a wide and inclusive consultation process. Serbia subsequently amends and implements the Laws on the Organization of Courts, on Seats and Territorial Jurisdiction of Courts and Public Prosecutors’ Offices, on Judges, on Public Prosecutor’s Office, on the High Judicial Council and on the State Prosecutorial Council as well as the Law on Judicial Academy | Adopted new Constitution and judicial laws aligned with new Constitution in a process in which the representatives of the judiciary and the profession were actively and equally involved, taking into account the recommendations of the Venice Commission and European standards, ensures the independence of the judiciary from political influence, maximally restricting influence of legislative and executive powers in the process of recruitment, selection, appointment, transfer and termination of the judge’s office, presidents of the courts, and (deputy) public prosecutors, and which must be based on precise criteria. Constitution and judicial laws guarantee, to all candidates, without discrimination, entrance in the judiciary based on merit-based objective criteria, fair in selection procedures, open to all suitably qualified candidates and transparent in terms of professional and public scrutiny. The role of the High Judicial Council and the State Prosecutorial Council in terms of the management of the judiciary, as well as in the supervision and control of the judiciary has been strengthened; their composition encompasses at least 50% of members from the ranks of judges and public prosecutors; Elected members of the High Judicial Council and the State Prosecutorial Council are elected by their peers and represent different levels of jurisdiction. | - The judiciary in the Republic of Serbia is completely independent which is confirmed in the positive opinion of the Venice Commission on the new Constitution and the legal provisions relating to the judiciary; - Judges and prosecutors are elected on the basis of their expertise and merit, which has an overall positive impact on the quality and efficiency of the judiciary; - The High Judicial Council and the State Prosecutorial Council successfully manage the judiciary with adequate financial resources, competent and professional personnel elected with necessary competences, selected based on clear criteria, while respecting the principles of transparency and accountability; - All of the above is confirmed in the positive Annual report of the European Commission's on the progress of the Republic of Serbia, including the improvement of the provisions of the Constitution. |

| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  | IMPLEMENTATION STATUS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1.1.1. | Conducting procedure for Constitutional amendments in the area of judiciary (Article 203 Constitution of RS and Art. 142-149 Rules of Procedure of the National Assembly), which implies the following steps: Submitting proposal for the amendments to the Constitution, with an explanation of the proposal by an authorized proponent (Article 142 par.1 of the Rules of Procedure) Determination of the authorized committee whether the proposal for the amendments to the Constitution is submitted by authorised proposer and in the prescribed form (Article 142 par.1 of the Rules of Procedure) Debating in the National Assembly the submitted proposal at its sitting (Article 143 par.1 of the Rules of Procedure) Decision of the National Assembly on the proposal for the amendment to the Constitution (Article 143 par.3 of the Rules of Procedure) Determination of the authorized committee of the draft proposal of an act on the amendments to the Constitution, with explanation, and a draft constitutional law for its implementation (Article 144 par.1 of the Rules of Procedure) Decision of the authorized committee on organizing public hearings on proposed acts and notification of the Speaker of the Parliament on the decision to hold public hearings (Art. 83 and 84 of the Rules of Procedure) Harmonization of the draft amendments to the Constitution and the proposal of the constitutional law for its implementation after held public hearings Resending draft amendments to the Constitution to Venice Commission if there is any change in substance compared with the text that has been already examined and approved by the Venice Commission Submitting a proposal for the amendments to the Constitution and the draft of the constitutional law for its implementation to the Speaker of the National Assembly (Article 145, paraf.1 of the Rules of Procedure) Discussion and a decision-making on the proposal for the amendments to the Constitution and on the proposal of the constitutional law for its implementation by a two-third majority of the total number of deputies of the National Assembly (Article 203 par.5 of the Constitution and Article 146 of the Rules of Procedure) Conducting a referendum Decision of the National Assembly on promulgation of the act amending the Constitution and a decision on promulgation of the constitutional law for implementation of the amendments to the Constitution (Article 148 of the Rules of Procedure) | Government of the Republic of Serbia (authorized representatives from the ministry in charge of judiciary) National Assembly (Authorized committee on constitutional and legislative issues) National Assembly (Sitting of the Assembly) |  |  |  |  | IV quarter 2021 | Budget RS 560.543 € Referendum costs and other related costs are unknown at this moment the Committee on Constitutional and Legislative Issues of the National Assembly discussed this Proposal and established that the Proposal had been submitted by a proposer authorised by the Constitution and that it had been submitted in a prescribed form, which the Committee reported to the National Assembly where the official process now will be continued. |  |  | The Act on the amendment of the Constitution and Constitutional Law promulgated and in line with the Venice Commission opinion |  | Activity is being successfully implemented The proposed amendments to the Constitution have been confirmed at the referendum on January 16, 2022. At the Tenth Special Session, held on February 9th, 2022, the National Assembly of the Republic of Serbia passed the Act amending the Constitution of the Republic of Serbia and the Constitutional Law implementing the Act amending the Constitution of Serbia, which are in line with the Venice Commission. |  |  |  |  |  |  |
| 1.1.1.2. | Work on harmonization of a set of judicial laws with the Constitution, preparation of working texts on changes and supplements to the Law on Organization of Courts, Law on Seats and territorial Jurisdiction of Courts and Public Prosecutors’ Offices, Law on Judges, Law on Public Prosecutor’s Office, Law on High Judicial Council, Law on State Prosecutorial and Law on Judicial Academy and drafting set of judicial laws, which specifically implies: - Establishment of working groups for drafting working texts of changes to the set of judicial laws - drafting of judicial laws and organizing public hearings in order to make remarks on drafts - harmonization of working texts of the set of judicial laws with remarks after holding public hearings - submitting a draft judicial legislation to the Venice Commission for the opinion - Full alignment of draft laws with the opinion of the Venice Commission - Acceptance of the draft laws and determining a draft law by the Government for the submission to the National Assembly | Working groups formed by the Ministry of Justice, comprising of all relevant representatives from the Ministry, High Judicial Council, State Prosecutorial Council, Supreme Court of Cassation, Republic Public Prosecutor`s Office, Judicial Academy and professors of law universities, representatives from civil society and professional associations Government of the Republic of Serbia |  |  |  |  | I - II quarter 2022 | Budget of the Republic of Serbia and TAIEX IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € USAID Project „Rule of Law“ 40.000 $ |  |  | Working groups formed Working texts of relevant legislation elaborated and public hearings held in accordance with regular procedure (the Law on the Planning System of the Republic of Serbia) Working texts of relevant legislation harmonized with the conclusions from public debates Draft proposal elaborated and set of legislation sent to the Venice Commission for its opinion Venice Commission opinion obtained Proposal of the relevant legislation elaborated in accordance with the Venice Commission opinion |  |  | Activity is being successfully implemented On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |  |  |  |  |  |
| 1.1.1.3. | Adoption of the new set of legislation in the National Assembly: - Law on Organization of Courts - Law on Seats and territorial Jurisdiction of Courts and Public Prosecutors’ Offices - Law on Judges - Law on Public Prosecutors Office - Law on the High Judicial Council - Law on the State Prosecutorial Council - Law on Judicial Academy | National Assembly |  |  |  |  | II quarter 2022 | Budget of the Republic of Serbia Calculation according to individual laws stated within individual activities from this AP |  |  | Set of legislation adopted, through a transparent process, in which the representatives of the judiciary and the profession were actively and equally involved, with a broadly established consultative process and organized public hearings |  |  | Activity is not implemented. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |  |  |  |  |  |
| 1.1.1.4. | Election of new composition of the High Judicial Council and State Prosecutorial Council | High Judicial Council State Prosecutorial Council National Assembly |  |  |  |  | In line with transitional and final provisions of the relevant legislation | Budget of the Republic of Serbia 851 € in 2022 |  |  | New composition of the High Judicial Council and the State Prosecutorial Council in place |  |  | Activity is not implemented. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |  |  |  |  |  |
| 1.1.1.5. | Adoption of by-laws referring, but not limited, to: - Rules of Procedure of the High Judicial Council - Rules of Procedure of the State Prosecutorial Council - Rulebooks on the bodies and procedure for evaluating the work of judges and (deputy) public prosecutors - Regulations on the work of the permanent working bodies of the High Judicial Council and the State Prosecutorial Council (disciplinary bodies, ethics committees, election commissions, appeal commissions, evaluation performance commissions of judges and prosecutors) - Rules on Procedure of Managing Board and Program Council of the Judicial Academy | Ministry of Justice High Judicial Council State Prosecutorial Council Supreme Court of Cassation Republic Public Prosecutor’s Office Judicial Academy |  |  |  |  | IV quarter 2022 | Budget of the Republic of Serbia Calculation according to individual laws stated within individual activities from this AP |  |  | By-laws adopted by respective institutions |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |  |
| 1.1.2. Serbia establishes an initial track record of implementing a fair and transparent system based on merit for the management of the careers of judges and prosecutors including recruiting, evaluating and promoting judges and prosecutors based on periodic, professional performance assessment (including at senior level) |  |  |  |  |  |  | Established fair and transparent system, in which both Councils are accountable for decision making for promotion, deployment and dismissal of judges and public prosecutor’s functions, based on periodic professional assessment of judges’ and public prosecutors’ performance A system of monitoring and evaluation of the application of adopted standards in practice established |  |  |  | - Serbia has a comprehensive career advancement system for judges and public prosecutors, including the election and dismissal of judges, performance evaluation, promotion, disciplinary responsibility, demotion, dismissal, etc.in a way that guarantees the independence (internal and external) and the impartiality of the entire judicial system; - Evaluation of the work of judges, public prosecutors, as well as judicial and prosecutorial assistants is regularly conducted and promotion is based on competence and merit, which has an overall positive effect on the quality and efficiency of justice which is confirmed in the positive evaluation issued by European Commission in Annual Progress Report on Serbia; - Positive evaluation stated in the Report of the High Judicial Council for monitoring results of judicial laws’ implementation; - Positive evaluation stated in the Report of the State Prosecutorial Council for monitoring results of judicial laws’ implementation. |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |  |  |
| 1.1.2.1. | Adoption of by-laws on criteria and measurement for the election of judges and court presidents, for promotion and termination of judicial function and the function of the court president and their publication on the website of the High Judicial Council |  |  | High Judicial Council |  |  | IV quarter 2022 | Budget of the Republic of Serbia 8.642 € |  |  | By-laws on criteria and measurement for the election of judges and court presidents, for promotion and termination of judicial function and function of the president of court adopted. Internal acts published on the website of the High Judicial Council and accessible to the public |  |  |  |  |  |  |  |  |
| 1.1.2.2. | The High Judicial Council makes decisions on the election, promotion and termination of judicial function and the function of the court presidents, by applying new legislative solutions and by-laws on the election, promotion and termination of judicial function and the function of the court presidents |  |  | High Judicial Council |  |  | Continuously, commencing from IV quarter 2022 | Budget of the Republic of Serbia Negligible cost activity |  |  | The High Judicial Council makes decisions on the election, promotion and termination of the judicial function and the function of the president of the court Decisions of the High Judicial Council on the election, promotion and termination of the judicial function and the function of the president of the court, with the reasoning, published on the website of the Council |  |  |  |  |  |  |  |  |
| 1.1.2.3. | Adoption of by-laws on criteria and measurement for the election of the holders of public prosecutors offices, for their promotion and termination of the prosecutorial function and their publication on the website of the State Prosecutorial Council |  |  | State Prosecutorial Council |  |  | IV quarter 2022 | Budget of the Republic of Serbia 8.642 € IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000€) |  |  | By-laws on criteria and measurement for election to the public prosecutor's office, for promotion and termination of the public prosecutor's office adopted Internal acts published on the website of the State Prosecutorial Council and accessible to the public |  |  |  |  |  |  |  |  |
| 1.1.2.4. | The State Prosecutorial Council makes decisions on the election, promotion and termination of holders of prosecutorial function, by applying new legislative solutions and by-laws on the election, promotion and termination of prosecutorial function |  |  | State Prosecutorial Council |  |  | Continuously, commencing from IV quarter 2022 | Budget of the Republic of Serbia Negligible cost activity |  |  | The State Prosecutorial Council makes decisions on the election, promotion and termination of the public prosecutor's office Decisions of the State Prosecutorial Council on the election, promotion and termination of the public prosecutor's office, with the reasoning, published on the website of the Council |  |  |  |  |  |  |  |  |
| 1.1.2.5. | The High Judicial Council is publishing detailed information on the evaluation process of judges on its website and promotes the importance of performance evaluation and its impact on career development with all courts |  |  | High Judicial Council All courts |  |  | Continuously | Budget of the Republic of Serbia Negligible cost activity |  |  | Detailed information on the importance of the performance evaluation process and the impact on the career development available to judges on the website of the High Judicial Council and all courts in Serbia |  |  |  |  | Аctivity is being successfully implemented. The Commission for the Evaluation of the Work of Judges and Court President held 3 sessions in the period from April 01st 2022 to Jun 30th t 2022, at which decisions were made on the regular evaluation work of 48 judges at permanent tenure and extraordinary evaluation of work of 76 judges. The Council has started activities aimed at improving the process of evaluating the work of judges, as well as at strengthening the capacities of the Judicial Academy to adequately respond to the training needs of judges, especially in terms of referring judges to training as a result of the evaluation of their work. In this regard, at the session of the High Judicial Council, held on June 30th the Council made a decision that one judge, after the evaluation process was given an "unsatisfactory" grade, should be sent to the Judicial Academy for mandatory training. In accordance with paragraph 1, article 26b of the Rulebook on criteria, standards, procedures and bodies for evaluating the work of judges and Court presidents. At the website of the High Judicial Council www.vss.sud.rs the decisions of the Council on the changing of members in the Commissions for conducting the evaluation procedure and determining the evaluations of the work of judges and court presidents, as well as statistical data on the number of judges evaluated and evaluation marks they got, are published. Which, among other things, ensures the transparency of the work of the Council. |  |  |  |
| 1.1.2.6. | The State Prosecutorial Council is publishing detailed information on its website and promotes the importance of evaluation of the work of public prosecutors and deputy public prosecutors and its impact on career development with all PPOs |  |  | State Prosecutorial Council All PPOs |  |  | Continuously | Budget of the Republic of Serbia Negligible cost activity |  |  | Detailed information on the importance of the performance evaluation process and the impact on the career development available to public prosecutors on the website of the State Prosecutorial Council and all PPO`s in Serbia |  |  |  |  | Аctivity is being successfully implemented. The State Council of Prosecutors is at the session held on February 8, 2022. made a decision on extraordinary evaluation of holders of public prosecutor's office, who applied for the position of Deputy Public Prosecutor in the Special Department for Suppression of Corruption in the Higher Public Prosecutor's Office in Belgrade and the Higher Public Prosecutor's Office in Novi Sad. |  |  |  |
| 1.1.2.7. | The High Judicial Council, within the scope of its competences, establishes its working body in charge of monitoring the effects of the implementation of judicial laws regarding recruitment, evaluation and promotion of judges and preparation of the report with the recommendations for the improvement of such processes |  |  | High Judicial Council |  |  | III quarter 2020 for the establishment of the working body Continuously, commencing from IV quarter 2020 for the preparation of reports | Budget of the Republic of Serbia 31.914 €: In 2020.- 10.638 € In 2021.- 10.638 € In 2022.- 10.638 € IPA 2016 Project “Support to the High Judicial Council” 1.500.000 € |  |  | The working body established Reports prepared and presented to the High Judicial Council Number of recommendations for the improvement issued |  |  |  |  | Аctivity is partially implemented. The Council formed a working body to monitor the effects of the implementation of judicial laws, which includes elected members of High Judicial Council from the ranks of judges. |  |  |  |
| 1.1.2.8. | The High Judicial Council, through its working body, analysis the effects of the implementation of judicial laws regarding recruitment, evaluation and promotion of judges, based on periodic, professional performance assessment |  |  | High Judicial Council |  |  | Continuously, Twice a year: II and IV quarter | Budget of the Republic of Serbia Budgeted within the activity 1.1.2.7. |  |  | Number of joint meetings held between the working body and the High Judicial Council Number of recommendations for the improvement implemented by the High Judicial Council until next reporting cycle |  |  |  |  | Activity is being successfully implemented. The implementation of this activity has been suspended until the adoption of new laws - the Law on Judges and the Law on the High Judicial Council, the amendments of which are ongoing, and the deadline for adoption is February 2023. |  |  |  |
| 1.1.2.9. | The State Prosecutorial Council, within the scope of its competences, establishes its working body in charge of monitoring the effects of the implementation of judicial laws regarding recruitment, evaluation and promotion of public prosecutors and preparation of the report with recommendations for the improvement of such processes |  |  | State Prosecutorial Council |  |  | III quarter 2020 for the establishment of the working body Continuously, commencing from IV quarter 2020 for the preparation of reports | Budget of the Republic of Serbia IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1.500.000€) |  |  | The working body established Reports prepared and presented to SPC Number of recommendations for the improvement issued |  |  |  |  | Activity is being successfully implemented. At its session held on April 23, 2021, the State Prosecutorial Council formed two working groups: 1. Working Group for monitoring judicial laws 2. Working Group for training programs The Working Group for Monitoring Judicial Laws held its first session in June 2021, at which it was decided to urgently analyze the effects of the application of judicial laws concerning the election, evaluation and promotion of public prosecutors and deputy public prosecutors, and based on periodic professional performance appraisals. At the request of the Working Group, the Appellate Public Prosecutor's Offices submitted their reports containing opinions and constructive proposals for amending judicial laws related to the selection, evaluation and promotion of public prosecutors. Also, for a better and more comprehensive analysis, experts from the project "Support to the Prosecutorial System" (IPA 2017) were hired. The experts made a comparative analysis, taking into account the positive regulations in this area of 5 European Union countries, namely: France, Austria, Italy, Slovenia and Croatia, and submitted them to the Working Group. The working group analyzed the submitted reports in detail, prepared a comprehensive report and submitted them to the State Prosecutorial Council. |  |  |  |
| 1.1.2.10. | The State Prosecutorial Council, through its working body, analysis the effects of the implementation of judicial laws regarding recruitment, evaluation and promotion of public prosecutors, based on periodic, professional performance assessment |  |  | State Prosecutorial Council |  |  | Continuously, Twice a year: II and IV quarter | Budget of the Republic of Serbia Budgeted within the activity 1.1.2.9. |  |  | Number of joint meetings held between the working body and the SPC Number of recommendations for the improvement implemented by the SPC until next reporting cycle |  |  |  |  | Activity is being successfully implemented. See 1.1.2.9. |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |  |
| 1.1.3. Serbia provides an adequate administrative capacity to the Judicial and Prosecutorial Councils and provides them with their own budget |  |  |  |  |  |  | The High Judicial Council and the State Prosecutorial Council successfully manage the judiciary with adequate financial resources and personnel elected with a clear mandate, while respecting the principles of transparency and accountability |  |  |  | - Increased structure and number of employees in the Administrative office of High Judicial Council according to new systematization, especially based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with the new constitutional and legal solutions; - Increased structure and number of employees in the Administrative office of the State Prosecutorial Council, according to new systematization, especially based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with the new constitutional and legal solutions; - High Judicial Council independently proposes and executes its own budget; - State Prosecutorial Council independently proposes and executes its own budget; - Sessions of the High Judicial Council and the State Prosecutorial Council are, as a rule, open to the public; - Decisions of the High Judicial Council and the State Prosecutorial Council are reasoned; - Reports on the work of the High Judicial Council and the State Prosecutorial Council are published on their websites; - Clear procedures for institutional responsibility of the High Judicial Council and the State Prosecutorial Council are established. |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  |  |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.1.3.1. | Changes to the Law on High Judicial Council, the Law on Organization of Courts and the Law on Ministries, with the aim to clarify the division of competences in key areas of the budget and judiciary administration between the High Judicial Council and the Ministry in charge of judicial affairs in order to strengthen the judicial independence in Organizational and budgetary performance |  | Ministry of Justice High Judicial Council Supreme Court of Cassation National Assembly |  |  |  | II quarter 2022 | Budget of the Republic of Serbia 151.652 €: Preparation of legislation: 30.878 € Discussion and adoption of legislation: 120.774 €. |  |  | The Law on High Judicial Council, the Law on Organization of Courts and the Law on Ministries changed Effectiveness of resource allocation improved Operational efficiency of the judiciary improved |  |  |  |  | Activity is being successfully implemented On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |  |  |  |
| 1.1.3.2. | Changes to the Law on State Prosecutorial Council, the Law on Public Prosecutors Office and the Law on Ministries, with the aim to clarify the division of competences in key areas of the budget and prosecution administration between the State Prosecutorial Council and the Ministry in charge of judicial affairs in order to strengthen the prosecution autonomy in Organizational and budgetary performance |  | Ministry of Justice State Prosecutorial Council Republic Public Prosecution National Assembly |  |  |  | II quarter 2022 | Budget of the Republic of Serbia 71.136 €: Preparation of legislation: 30.878 €; Discussion and adoption of legislation: 40.258 € IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000€) |  |  | The Law on State Prosecutorial Council, the Law on Public Prosecutors Office and the Law on Ministries changed Effectiveness of resource allocation improved Operational efficiency of the PPOs improved |  |  |  |  | Activity is being successfully implemented On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |  |  |  |
| 1.1.3.3. | Strengthening the capacities of the Administrative office of the High Judicial Council, in line with a new systematization act, especially in the field of the analytical, statistical and managerial capacities |  | High Judicial Council |  |  |  | Continuously | Budget of the Republic of Serbia The amount will be known after the job systematization is made |  |  | Capacities of the Administrative Office of High Judicial Council strengthened, in line with a new systematization act, especially in the field of the analytical, statistical and managerial capacities |  |  |  | Аctivity is being successfuly implemented Based on the Conclusion of the Commission for giving consent for new employment and additional employment with users of public funds, number: 112-635 / 2022 of January 31st , 2022, the High Judicial Council was approved for employment as a civil servant in the Group for Evaluation the work of judges and court presidents. The submitted Staff Plan Proposal for 2022, number: 110-00-7 / 2021-01 of March 25th, 2022, was approved by the Ministry of Finance (number: 401-001-12750 / 2021-03 of April 5th, 2022). The proposed staffing plan for 2022 envisages that the High Judicial Council will employ 10 more executors by the end of 2022, so that the total number of employees for an indefinite period would be 51, as follows: 3 civil servants in position, 44 civil servants in executive jobs and 4 employees/Clarks. Action Plan for the Implementation of the Judicial Development Strategy for the period 2022-2025., the High Judicial Council envisages the following dynamics of employment (2022-10 executors; 2023-10 executors and 2024-6 executors). On June 8th 2022 a public competition was announced for the filling of a position for administrative and technical affairs, classified as a clerk, Group for evaluating the work of judges and presidents of courts, Sector for status issues of judges and lay judges - 1 executor. On the basis of the Act of the Commission for granting consent for new employment and additional employment with users of public funds, number: 112-635/2022 of January 31st , 2022, the High Judicial Council was given consent for the employment of a clerk in the Evaluation Group work of judges and court presidents. The election procedure and all activities related are ongoing, i.e. they are conducted in accordance with legal provisions. |  |  |  |  |
| 1.1.3.4. | Strengthening the capacities of Administrative office of the State Prosecutorial Council, in line with the new systematization act, especially in the field of analytical, statistical and managerial capacities |  | State Prosecutorial Council |  |  |  | Continuously | Budget of the Republic of Serbia The amount will be known after the job systematization is made |  |  | Capacities of Administrative office of the State Prosecutorial Council strengthened, in line with new systematization act, especially in the field of the analytical, statistical and managerial capacities |  |  |  | Activity is being successfully implemented By a decision of March 15, 2022, the State Council of Prosecutors hired for an indefinite period of time a candidate who applied for the position of administrative expert support for evaluating the work of public prosecutors and deputy public prosecutors with the title of clerk. At the session held on March 29, 2022, the State Council of Prosecutors adopted the Rulebook on Internal Organization and Systematization of Workplaces in the Administrative Office of the State Council of Prosecutors. The Rulebook envisages an increase in the number of executive positions for one position, clerk, in the Department of Personnel and General Affairs, and for the existing three executive positions, provides for the promotion of civil servants by title, bearing in mind that they meet the requirements for the required position experience, all with the aim of strengthening the capacity of the Administrative Office of the State Prosecutors' Council. On March 30, 2022, the State Council of Prosecutors announced a public competition for the filling of an executive position in the title of advisor, in the Department for Status Issues and Holders of the Public Prosecutor's Office and Preparation of Regulations. The decision of the State Council of Prosecutors dated June 23, 2022. In 2008, a candidate who applied for the position of advisor in the Department for Status Issues and Holders of the Public Prosecutor's Office and the Preparation of Regulations was hired for an indefinite period of time. |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |  |
| 1.1.4. Serbia establishes an effective mechanism allowing the Councils to react against political interferences and establishes an initial track record of fully respecting judicial decisions and refraining from public comments on the work of courts by officials and politicians |  |  |  |  |  |  | High Judicial Council and State Prosecutorial Council react according to clear and in-advance established procedures in case of political interference in the judiciary. |  |  |  | - Essentially reduced perception of political interference in the work of judicial instances, both among judicial officers and the citizens; - Improved transparency of the High Judicial Council and the State Prosecutorial Council and their cooperation with the media; - Initial track record established. |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |  |  |
| 1.1.4.1. | Amending the Rules of Procedure of the High Judicial Council in order to: - prescribe clear procedure for public reacting of the High Judicial Council against political interferences - introduce an effective mechanism in keeping track record in the High Judicial Council on cases of political interference in the judiciary - prescribe procedure of reporting, including periodicity of reporting on cases of political interference in the judiciary |  |  |  |  | High Judicial Council | IV quarter of 2020 | Budget of the Republic of Serbia 8.642 € |  |  | Rules of Procedure of the High Judicial Council amended High Judicial Council acts in line with the Rules of Procedure which stipulates clear procedures for public reacting in cases of political interference in the judiciary |  |  |  | Аctivity is being successfully implemented. At the session of the High Judicial Council held on March 3th, the Report on Work was submitted by the judge competent to act in cases of undue influence on the work of judges and the judiciary for 2021. During the period from April 1st to June 30th, 2022, four judges, who considered that their work was under the undue influence, submitted a request to the judge who is appointed to act in accordance with Article 27a of the Rules of Procedure. The procedure for these requests is ongoing. |  |  |  |  |
| 1.1.4.2. | Analysis of the work of the Commissioner for Autonomy and, if necessary, amending the Rules of Procedure of the State Prosecutorial Council in order to enhance the work and capacity of the Commissioner |  |  |  |  | State Prosecutorial Council | IV quarter of 2020 | Budget of the Republic of Serbia IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000€) |  |  | Analysis of the work of the Commissioner for Autonomy conducted Rules of Procedure of the State Prosecutorial Council amended accordingly State Prosecutorial Council acts in line with the Rules of Procedure which stipulates clear procedures for public reacting in cases of political interference in operation of public prosecutor’s office |  |  |  | Аctivity is being successfully implemented. On February 25, 2022, the Commissioner for Independence submitted a report to the State council of prosecutors on the illicit influence on the holders of the public prosecutor's office for the period from April 23 to December 31, 2021. |  |  |  |  |
| 1.1.4.3. | Regular and periodic reporting and extraordinary addressing of the High Judicial Council to the public, regarding the possible existence of political interference on the work of the judiciary |  |  |  |  | High Judicial Council Supreme Court of Cassation | Continuously Reporting once a year as part of the Annual Report Need basis addressing | Budget of the Republic of Serbia 7.659 € In 2020. – 2.553 € In 2021. – 2.553 € In 2022. – 2.553 € |  |  | Report on the High Judicial Council actions regarding the possible existence of a political influence on the work of the judiciary published Number of extraordinary addressing to the public |  |  |  | Activity is being successfully implemented. On February 3rd, the High Judicial Council issued a statement informing the public that on the High Judicial Council session held on October 14, decision no. 021-05-00049 / 2021-01 was adopted that that the portal "Directno RS" had an undue influence on the work of Judge of the First Basic Court in Belgrade, who is acting in family relationship cases Supreme Court of Cassation received the Award for contribution to the public right to know in the category of the highest public authorities, which is awarded by Commissioner for Information of Public Importance and Personal Data Protection on the occasion on the ,,Right to know’’Day. Internet web-site of the Court (http://www.vk.sud.rs) is regularly updated on daily-basis with current information on the work of Court (news, case law database, information on public procurement, legal views, conclusions, selected sentences, contentious legal issues, activities aimed at unifying court jurisprudence, general regulationsof the Court, Data Base of the European Court of Human Rights jurisprudence and anonymized court decisions). Supreme Court of Cassation has published in 2021, 25 press releases on the internet website of the Court, some of which being forwarded to the printed and electronic media. 120 requests for free access to information of public importance were received, of which 65 requests were submitted by citizens, 6 by media, 5by non-governmental organizations and other citizens’ associations and 44 requests by others (lawyers, institutions). A total of 120 requests were submitted until December 31, 2021 and all requests were answered within the deadline provided in legislation. The data published in the Information Booklet ( http://www.vk.sud.rs ) have been updated for five times. |  |  |  |  |
| 1.1.4.4. | Regular and periodic reporting and extraordinary addressing of the State Prosecutorial Council to the public, regarding the possible existence of political influence on the work of the prosecution |  |  |  |  | State Prosecutorial Council Republic Public Prosecution | Continuously Reporting once a year as part of the Annual Report Need basis addressing | Budget of the Republic of Serbia 7.659 € In 2020. – 2.553 € In 2021. – 2.553 € In 2022. – 2.553 € |  |  | Report on the State Prosecutorial Council actions regarding the possible existence of a political influence on the work of the prosecution published Number of extraordinary addressing to the public |  |  |  | Activity is being successfully implemented. In 2021, so far, the Commissioner has acted in 7 cases. So far, 6 cases have been resolved, of which in one case, due to a physical attack on a public prosecutor, the Commissioner issued a press release calling on the competent institutions to take measures within their competence in order to secure the public prosecutor. He also called on the media and public figures to give their statements in the recognition of the public prosecutor's office as a state body that works effectively on the suppression of criminal acts. Furthermore, in four cases the Commissioner found that there was no undue or any other undue influence, while in one case it was found that the Commissioner was not competent to act. |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |  |
| 1.1.5. Serbia establishes an effective mechanism allowing the Councils to react against political interferences and establishes an initial track record of fully respecting judicial decisions and refraining from public comments on the work of courts by officials and politicians. |  |  |  |  |  |  | Judicial decisions are fully respected, whereas awareness, that criticizing decisions puts the judicial independence at risk, has been raised. |  |  |  | Judicial decisions as well as court work and prosecution work are fully respected by public officials and politicians. |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  |  |  | IMPLEMENTATION STATUS |  |
| 1.1.5.1. | Establish a monitoring mechanism through holding quarterly joint meetings between representatives of ethics boards/committees of the High Judicial Council, State Prosecutorial Council, National Assembly and the Government of the Republic of Serbia in order to raise awareness of public officials and politicians for full respect of judicial decisions and work of courts and PPOs and that criticizing decisions puts the judicial independence at risk |  |  |  | High Judicial Council State Prosecutorial Council National Assembly / Ethics Committee Government of the Republic of Serbia / Ethics Committee |  | IV quarter 2020 for the establishment of the monitoring mechanism Continuously, commencing from IV quarter 2020 for holding quarterly meetings |  | Budget of the Republic of Serbia 17.285 € |  |  | Monitoring mechanism established Quarterly meetings scheduled and held regularly |  |  |  |  |  | Activity is being successfully implemented. At the initiative of the Ethics Committee of the High Judicial Council, the first joint meeting of representatives of the ethics committees of the High Judicial Council, the StateProsecutorial Council and the Ethics Committee of the National Assembly of the Republic of Serbia was held on June 7, 2022. During the meeting, the participants got to know each other about the work of the Commitees, they presented their experiences from the previous work and presented the challenges they face. The representative of the Ethics Committee of the High Judicial Council informed the attendees that the Ethics Committee had developed a model of the new Rulebook on the work of the Ethics Committee of the High Judicial Council and submitted it to the Council for consideration. At the session held on June 9th, 2022, the Council adopted the Rulebook on the work of the Ethics Committee of the High Judicial Council ("Official Gazette of the Republic of Serbia", number 68/22 of June 26, 2022). At the end of the meeting, the participants expressed their willingness to establish a good practice of regularly holding joint meetings of ethics committee representatives in order to implement activities 1.1.5.2. From the Chapter 23 Action Plan. In this way, they will work to establish an effective monitoring mechanism for full compliance with court decisions that will enable the High Judicial Council and the State Prosecutorial Council to react against political interference and in relation to public commenting on court decisions. |  |
| 1.1.5.2. | The joint group of representatives of all ethics boards/committees from 1.1.5.1. prepares quarterly reports on the conclusions and recommendations for future improvements in the area of full respect for judicial independence and autonomy |  |  |  | High Judicial Council / Ethics Board State Prosecutorial Council /Ethics Board National Assembly / Ethics Committee Government of the Republic of Serbia / Ethics Committee |  | Continuously, quarterly reports |  | Budget of the Republic of Serbia Budgeted within the activity 1.1.5.1. |  |  | Quarterly reports provided and made public Quarterly reports presented to the High Judicial Council, State Prosecutorial Council, National Assembly and Government of the Republic of Serbia |  |  |  |  |  |  | Activity is being successfully implemented. Reports are prepared regularly after each organized meeting from activity 1.1.5.1. |
| 1.1.5.3. | Drawing up of an electronic brochure on the standards for full respect of judicial decisions and the work of courts and PPOs by public officials and politicians and putting the electronic brochure on the websites of the respective institutions |  |  |  | Ministry of Justice and National Assembly (Republic Secretariat for Legislation) with the support of the High Judicial Council and the State Prosecutorial Council |  | IV quarter 2020 |  | Budget of the Republic of Serbia 7.659 €: |  |  | Drawn up electronic brochure on the standards for full respect of judicial decisions and the work of courts and PPOs by public officials and politicians Publication of the electronic brochure on the websites of the respective institutions Number of visits to the links with electronic brochures Number of documents downloaded from the links with electronic brochures |  |  |  |  |  |  | Activity is being successfully implemented. The publication “Guide for Judges and Prosecutors Ethical Aspects of the Use of Social Networks”, prepared within the joint project of the European Union and Council of Europe “Strengthening Independence and Accountability of Judiciary”, was published on the Council’s website. The Guide was created on the basis of a comprehensive survey in which elected members of the High Judicial Council participated. The Guide’s authors are Council of Europe’s experts and the author of the introductory speech is Omer Hadžiomerović, President of the Ethics Committee of the High Judicial Council. The Guide is intended for holders of judicial functions as users because it contains mapping of potential risks they encounter when using social networks and it also contains practical tips for dealing with the most common challenges. See activity 1.2.2.10. – data on implementation. Additionally, the European Union and the Council of Europe have created a brochure „Full respect of judicial decisions and work by public officials and civil servants. The author of the introductory speech is the Minister of Justice. |
| 1.1.5.4. | Introduction of the standards in the program of the Judicial Academy relating to separation of powers and perception that other state powers should refrain from public comments on individual judicial cases in the context of respect of judiciary’s independence and the implementation of such training programs |  |  |  | Judicial Academy High Judicial Council State Prosecutorial Council Partners (associations of journalists and civil society Organizations) |  | Continuously, once a year through annual program of continuous and initial training of the Judicial Academy |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. (3.083.301€) Donor support (Projects of the Council of Europe) |  |  | Curriculum of the program developed Number of trainings held Number of participants trained Evaluation (through pre-test and post-test) of the participants of the trainings demonstrates the increased awareness and knowledge on the European standards relating to separation of powers and perception that other state powers should refrain from public comments on individual judicial cases in the context of respect of judiciary’s independence and autonomy |  |  |  |  |  |  | Аctivity is being successfully implemented. During the first quarter 2022, two trainings were conducted on the topic: ‘’Identification and protection from inappropriate influence on judges- advanced training of trainers’’, in Belgrade and Novi Sad, for a total of 44 participants. Also, in the reporting period, one two-day online seminar was held, for a total of 32 participants, on the topic: ‘’Basic communication skills.’’ During the second quarter 2022 four one-day trainings were conducted on the topic: ‘’Identification and protection from inappropriate influence on judges- advanced training of trainers’’, in Belgrade, Niš, Kragujevac and Novi Sad, for a total of 63 participants. |
| 1.1.5.5. | Organizing workshops for journalists in order to adopt European standards and national rules in the area of full respect for judicial independence and autonomy, compliance with court decisions and reporting on court proceedings |  |  |  | High Judicial Council State Prosecutorial Council Partners (associations of journalists and civil society Organizations) |  | Continuously |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. (3.083.301 €) IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000€) USAID Project „Rule of Law“ – 50.000 $ |  |  | Number of the workshops for journalists planned and held Number of journalists invited and participated in the workshops Evaluation (through pre-test and post-test) of the participants of the trainings demonstrates the increased awareness and knowledge on the European standards and national rules for full respect for judicial independence and autonomy, compliance with court decisions and reporting on court proceedings |  |  |  |  |  |  | Аctivity is being successfully implemented. Within the project of the Council of Europe and the EU "Strengthening the Independence and Accountability of the Judiciary" and in cooperation with the High Judicial Council and the State Prosecutorial Council from 9 to 11 March, in Vrdnik were organized a workshop entitled "Towards a new partnership of justice and media “. The workshop was organized in order to improve the relationship between courts and public prosecutor's offices on the one hand and journalists specializing in judicial issues on the other, as well as work on further steps to increase the capacity of the media to report on justice. Within the project of the Council of Europe and the EU "Strengthening the Independence and Accountability of the Judiciary", from March 29 to 30, , a training for spokespersons from the area of the Appellate Court in Novi Sad was organized in Vrdnik, aimed at improving the knowledge and skills of spokespersons to work with traditional and digital media. |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 1.1.6. Serbia fully recognizes and exploits the benefits of civil society expertise and therefore engages in a real and systematic dialogue with civil society |  |  |  |  |  |  | Civil society and professional associations are involved in defining the further steps in the reform process and in monitoring the implementation of action plans. |  |  |  |  | Suggestions and comments of civil society and professional associations related to defining the further steps in the reform process are regularly discussed at meetings of the body responsible for monitoring the implementation of action plan for Chapter 23. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |  |
| 1.1.6.1. | Preparation and publication of public call to civil society and professional associations to submit suggestions and comments for defining further steps in the reform processes and for performing supervision over the implementation of the reform steps |  |  |  | Ministry of Justice in cooperation with the Office for cooperation with civil society |  | Continuously, commencing from II quarter 2020 |  |  | Budget of the Republic of Serbia Preparation of public call 15.318 € In 2020. – 5.106 € In 2021. – 5.106 € In 2022. – 5.106 € Publication of public call – negligible cost activity |  | Number of published public calls to civil society and professional associations for submitting suggestions and comments Number of submitted suggestions and comments of civil society and professional associations |  |  |  |  | Activity is being successfully implemented. By the decision of the Minister of Justice on establishing the working groups for drafting the set of judicial laws in order to align them with the Constitutional amendments, the proffessional associations of judges and public prosecutors, that are also members of the National Convention of the EU, are included. Furthermore, the official minutes from the meetings of the working groups are continuesly being delivered to the CSOs and it is also planned that additional meetings with the CSOs will be held in order to further discuss the drafts laws. In addition, in the reporting period, the representatives of the Ministry of Justice participated at the meeting of the Working Group for Chapter 23 of the National Convention of the EU where the work on the set of judicial laws and future activities were discussed. |  |  |
| 1.1.6.2. | Publishing of and consideration of suggestions and comments submitted by civil society and professional associations on defining further steps in the reform processes |  |  |  | Ministry of Justice Council for monitoring of the AP23 implementation |  | Continuously, commencing from II quarter 2020 |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.1.6.1. |  | Number of published suggestions and comments of civil society and professional associations Number of adopted suggestions and comments of civil society and professional associations, out of those submitted |  |  |  |  | Activity is being successfully implemented In January 2022, the Ministry of Justice, with the support of the “EU for Justice” project, organized a round table with civil society organizations "Presentation of plans for a new set of judicial laws and Action Plan for the implementation of the Judicial Development Strategy for 2020-2025" which was held on March 21, 2022, at the Palace of Serbia, Belgrade. The following conclusions and recommendations were adopted: - The Ministry of Justice will establish continuity and sustainability in communication with civil society organizations. A "contact point" for quick communication with CSOs and professional associations will be appointed at the Ministry of Justice. Information on the "contact point" will be available on the website of the Ministry of Justice. The "contact point" will inform CSOs by e-mail about new proposals for strategic documents and laws, as well as planned public hearings, as soon as they are published on the website of the Ministry of Justice. The Contact Point will receive and process comments, suggestions and assessments from civil society organizations. The contact point will also be in charge of sending all information and documents received by civil society organizations to members of relevant working groups for drafting laws, as well as providing feedback on requests and initiatives of civil society organizations. - In the coming period, the Ministry of Justice will increase the number of meetings and consultations with all stakeholders (not only civil society organizations and professional associations, but also representatives of the judiciary, Faculty of Law, legal experts) in order to achieve tangible progress and create adequate conditions for implementation of constitutional amendments through legislative reform - The Ministry of Justice will establish constant and sustainable communication with civil society organizations and professional associations not only on this issue, but also on all activities related to the implementation of AP23 - Representatives of the Venice Commission will be directly involved in the law-making process and all stakeholders will rely on their opinions and expertise, with full application of EU standards - Communication and direct links between actors in the reform process will be established and strengthened, as well as a culture of democratic dialogue and mutual trust. Information will be shared on time, and different opinions and constructive criticisms will be accepted with respect In accordance with the Conclusions, the Ministry of Justice of the Republic of Serbia appointed a contact point (person) for cooperation with civil society organizations in April 2022 and informed the NCEU on April 21 about the appointment of a contact point. By the decision of the Minister of Justice on establishing the working groups for drafting the set of judicial laws in order to align them with the Constitutional amendments, the proffessional associations of judges and public prosecutors, that are also members of the National Convention of the EU, are included. Furthermore, the official minutes from the meetings of the working groups are continuesly being delivered to the CSOs and it is also planned that additional meetings with the CSOs will be held in order to further discuss the drafts laws. In addition, in the reporting period, the representatives of the Ministry of Justice participated at the meeting of the Working Group for Chapter 23 of the National Convention of the EU where the work on the set of judicial laws and future activities were discussed. The adopted Action Plan for Judicial Development Strategy and the IBM report of the Action Plan for Chapter 23 were also discussed. |  |  |
| 1.1.6.3. | Organizing roundtables to discuss achievements, shortcomings and options for improving cooperation in creating and implementing reform steps, following the good practice of providing the motivated feedback on CSOs’ suggestions |  |  |  | Ministry of Justice Negotiating Group for Chapter 23 Office for cooperation with Civil Society |  | Twice a year, commencing from II quarter 2020 |  |  | Budget of the Republic of Serbia 6.104 € |  | Number of round tables planned and held Number of civil society Organizations and professional associations participated |  |  |  |  | Activity is being successfully implemented By the decision of the Minister of Justice on establishing the working groups for drafting the set of judicial laws in order to align them with the Constitutional amendments, the proffessional associations of judges and public prosecutors, that are also members of the National Convention of the EU, are included. Furthermore, the official minutes from the meetings of the working groups are continuesly being delivered to the CSOs and it is also planned that additional meetings with the CSOs will be held in order to further discuss the drafts laws. In addition, in the reporting period, the representatives of the Ministry of Justice participated at the meeting of the Working Group for Chapter 23 of the National Convention of the EU where the work on the set of judicial laws and future activities were discussed. The adopted Action Plan for Judicial Development Strategy and the IBM report of the Action Plan for Chapter 23 were also discussed. |  |  |
| 1.1.6.4. | Improving other types of cooperation with civil society (jointly organized workshops, common publications, researches and raising awareness campaigns) in the process of defining reform steps, in accordance with: - Guidelines for cooperation between institutions which participate in Chapter 23 and civil society Organizations (prepared with the support of TAIEX expert) and - Guidelines for inclusion of civil society Organizations in implementation of the legislative process |  |  |  | Ministry of Justice Negotiating Group for Chapter 23 Office for cooperation with Civil Society |  | Continuously, commencing from II quarter 2020 Drafting Guidelines – IV quarter 2020 |  |  | Budget of the Republic of Serbia 7.659 €: In 2020. – 2.553 € In 2021. – 2.553 € In 2022. – 2.553 € |  | Guidelines for cooperation between institutions which participate in Chapter 23 and civil society Organizations with the support of TAIEX expert prepared Guidelines for inclusion of civil society Organizations in implementation of the legislative process prepared Number of jointly planned and held workshops Number of jointly prepared publications, researches and raising awareness campaigns Number of civil society Organizations participated in the above events, researches and campaigns |  |  |  |  | Аctivity is being successfully implemented The Ministry of Justice initiated discussions with the EU Delegation and civil society with the support of the project “EU for Justice” to develop a platform on cooperation with civil society in AP23. Moreover, following the meeting with NCEU in December, it has been agreed that the current draft laws will be provided to civil society for comments (e.g. Civil Procedure Code), including that additional time shall be provided for consideration by the CSOs. In January 2022, the Ministry of Justice, with the support of the “EU for Justice” project, organized a round table with civil society organizations "Presentation of plans for a new set of judicial laws and Action Plan for the implementation of the Judicial Development Strategy for 2020-2025" which was held on March 21, 2022, at the Palace of Serbia, Belgrade. The following conclusions and recommendations were adopted: - The Ministry of Justice will establish continuity and sustainability in communication with civil society organizations. A "contact point" for quick communication with CSOs and professional associations will be appointed at the Ministry of Justice. Information on the "contact point" will be available on the website of the Ministry of Justice. The "contact point" will inform CSOs by e-mail about new proposals for strategic documents and laws, as well as planned public hearings, as soon as they are published on the website of the Ministry of Justice. The Contact Point will receive and process comments, suggestions and assessments from civil society organizations. The contact point will also be in charge of sending all information and documents received by civil society organizations to members of relevant working groups for drafting laws, as well as providing feedback on requests and initiatives of civil society organizations. - In the coming period, the Ministry of Justice will increase the number of meetings and consultations with all stakeholders (not only civil society organizations and professional associations, but also representatives of the judiciary, Faculty of Law, legal experts) in order to achieve tangible progress and create adequate conditions for implementation of constitutional amendments through legislative reform - The Ministry of Justice will establish constant and sustainable communication with civil society organizations and professional associations not only on this issue, but also on all activities related to the implementation of AP23 - Representatives of the Venice Commission will be directly involved in the law-making process and all stakeholders will rely on their opinions and expertise, with full application of EU standards - Communication and direct links between actors in the reform process will be established and strengthened, as well as a culture of democratic dialogue and mutual trust. Information will be shared on time, and different opinions and constructive criticisms will be accepted with respect In accordance with the Conclusions, the Ministry of Justice of the Republic of Serbia appointed a contact point (person) for cooperation with civil society organizations in April 2022 and informed the NCEU on April 21 about the appointment of a contact point. The Ministry of Human and Minority Rights and Social Dialogue: During the reporting period, the Ministry of Human and Minority Rights and Social Dialogue conducted several activities that included civil society organizations in open debates of relevant actors on important social issues within the newly established institute of social dialogues. A total of 5 social dialogues were held on the following topics: "Young Roma Men and Women - Bearers of Change", "Protection and Promotion of Citizens' Rights in the Field of Mental Health", "Culture of Dialogue - the Civil Society and Media", "Sustainable Development Goals - Good Health, Quality Education and the World without Hunger" and "Economic Empowerment of Roma and Sustainable Development Goals in Serbia". Implementing the Guidelines for Involvement of Civil Society Organizations in Working Groups for Drafting Public Policy Documents and Draft Proposals, i.e. draft regulations adopted by the Government in January 2020, the Ministry launched 5 calls for the involvement of civil society organizations in various working groups for developing draft documents of public policies and regulations. The following public calls were implemented: Public Invitation to civil society organizations to participate in the process of monitoring, reporting and evaluating the implementation of the Strategy for Prevention and Suppression of Trafficking in Human Beings, Especially Women and Children and Protection of Victims, 2017-2022, when 4 civil society organizations were proposed to the Minister of the Interior; Public Invitation to civil society organizations for membership in the Special Working Group for developing a draft strategy for creating an enabling environment for civil society development in the Republic of Serbia for the period 2021-2030, when 21 civil society organizations were selected and proposed for membership in the Special Working Group, as well as the Public Invitation to civil society organizations for membership in the board of the project "Strengthening the Capacity of the Criminal Justice System to Combat Gender-based Violence in SEE"; "Public Invitation to civil society organizations for membership in the Working Group for Ex-ante Analysis of the Effects of the Law on Volunteering and developing Draft Law on Amendments to the Law on Volunteering Pursuant to that Analysis", when 5 civil society organizations were selected, Public Invitation to civil society organizations for membership in the Joint Monitoring Committee of the Interreg IPA Cross-border Cooperation Program Romania-Serbia 2021-2027, when one civil society organization was selected. With the establishment of the Ministry of Human and Minority Rights and Social Dialogue, a series of social dialogues on important topics of wider social interest, involving civil society organizations, has begun. A number of social dialogues were carried out at the initiative of civil society organizations. In this reporting period, 11 social dialogues were held, on the following topics: "Young Roma men and women bearers of change", "Protection and promotion of citizens' rights in the field of mental health", "Culture of dialogue - civil society and the media", "Sustainable development goals - a world without hunger, good health and quality education" and "Economic empowerment of Roma and goals of sustainable development in Serbia", "Improvement of the legislative framework for nature protection", "Concept of social entrepreneurship and examples of good practice in the Republic of Serbia", "How to achieve decent work in the media and responsible journalism”, "Intergenerational solidarity", "Human Rights Forum - Serbia in 2021", "Judiciary, state administration and local self-government and protection of human rights and gender equality - the results of the referendum". The participation of civil society organizations in debates on social dialogues gave a special contribution to the exchange of different views and opened the space for civil society to conduct a dialogue with public authorities and other interested social actors on important and current social issues. Based on the implementation of the Guidelines for Involvement of Civil Society Organizations in Working Groups for Drafting Proposals for Public Policy Documents and Draft Regulations, which have been in force since 2020, in this reporting period the Ministry published 7 calls for the involvement of civil society organizations in working groups for drafting public policy documents and drafts, i.e. draft regulations. The following public calls were executed: public call to civil society organizations to participate in the process of monitoring, reporting and evaluating the implementation of the Strategy for Prevention and Suppression of Trafficking in Human Beings, Especially Women and Children and Protection of Victims 2017-2022, within which 4 civil society organizations were proposed to the Minister of the Interior; public call to civil society organizations for membership in the Special Working Group for Drafting a Strategy for and Enabling Environment for Civil Society Development in the Republic of Serbia for the Period 2021-2030, within which as many as 21 civil society organizations were selected and proposed for membership in the Special Working Group; public call to civil society organizations for membership in the board of the project " Enhancing Criminal Justice Capacities for Combating Gender-based Violence in SEE"; "Public Call to Civil Society Organizations for Membership in the Working Group for Ex ante Analysis of the Effects of the Law on Volunteering and the Draft Law on Amendments to the Law on Volunteering in Accordance with That Analysis", in which 5 civil society organizations were selected; public call to civil society organizations for membership in the Joint Monitoring Committee of the Interreg IPA Cross-border Cooperation Program Romania-Serbia 2021-2027, within which one civil society organization was selected; public call to civil society organizations for membership in the Working Group for the development of the Operational Plan for the Fight against Corruption in the Health Sector, which was announced in cooperation with the Ministry of Health. Based on this call, 1 civil society organization was selected for membership in the said working group; public call to civil society organizations for membership in the Special Working Group for the preparation of the Proposal of the Action Plan for Exercising the Rights of National Minorities, in which 5 civil society organizations were selected. The Ministry of Human and Minority Rights and Social Dialogue started the process of drafting the first strategic document in the domain of human rights as to provide for a systematic, coordinated and continuous approach to monitoring and improving human rights situation, both at the national level on the whole and at the level of individual local self-government units. Online public consultations on the development of the Baseline for the development of the Strategy for Human Rights Monitoring and Promotion in the Republic of Serbia for the period 2023 - 2030 were conducted in the period from 9 December 2021 to 1 March 2022. Related comment form was available on the "eKonsultacije" portal at https://ekonsultacije.gov.rs, as well as on the website of the Ministry of Human and Minority Rights and Social Dialogue, at https://www.minljmpdd.gov.rs, and on the E- administration portal at https://euprava.gov.rs. Within the referred period, only one comment was submitted, by the Initiative for Economic and Social Rights - A11. Inclusiveness and transparency of the Strategy development process implies the involvement of the broadest possible range of entities, starting from individuals, through civil society organizations, including trade unions, employers' associations, journalists' associations, and religious communities, to representatives of independent state bodies and authorities at various levels of territorial organization. These entities will be involved in all stages of the drafting process and at all levels where public consultations and public debates are held - from the national to the local level. Civil society organizations working on the promotion of human rights, fully participate and cooperate with Serbian authorities in activities related to monitoring the implementation of international human rights treaties. The platform of organizations for cooperation with UN human rights mechanisms was clear in its commitment to participate in the process of drafting human rights strategy. For the first time, this Platform, together with a group of organizations, together with government representatives, discussed shadow reports submitted by civil society to the United Nations treaty body, the Committee on Economic, Social and Cultural Rights. The delegation of the Republic of Serbia had the opportunity, before consideration of the state report, to get acquainted with the content of shadow reports submitted to the Committee on Economic, Social and Cultural Rights, and to discuss priorities and ways for compliance with the recommendations that have been partially implemented or not implemented at all. The Ministry of Justice: By the decision of the Minister of Justice on establishing the working groups for drafting the set of judicial laws in order to align them with the Constitutional amendments, the proffessional associations of judges and public prosecutors, that are also members of the National Convention of the EU, are included. Furthermore, the official minutes from the meetings of the working groups are continuesly being delivered to the CSOs and it is also planned that additional meetings with the CSOs will be held in order to further discuss the drafts laws. In addition, in the reporting period, the representatives of the Ministry of Justice participated at the meeting of the Working Group for Chapter 23 of the National Convention of the EU where the work on the set of judicial laws and future activities were discussed. The adopted Action Plan for Judicial Development Strategy and the IBM report of the Action Plan for Chapter 23 were also discussed. The Ministry of Human and Minority Rights and Social Dialogue: Regarding the process of drafting the Strategy for Human Rights, the Ministry for Human and Minority Rights and Social Dialogue has organized consultative meetings with organizations that are part of the Platform for cooperation with UN mechanisms for Human Rights, with the support of the UN Team for Human Rights. The meeting was dedicated to the initial discussions related to the concept and structure of the future strategic document, along with issues of capacities and modalities for participation of the Platform in the process of monitoring the implementation of the Strategy. |  |  |

| 1.2. IMPARTIALITY AND ACCOUNTABILITY |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |
| 1.2.1. Serbia puts in place a coherent procedural framework and the necessary ICT tools ensuring random allocation of cases in all courts and prosecution offices. Serbia ensures that the Judicial and Prosecutorial Council have tools to monitor the random allocation of cases. |  |  |  | Rules for random allocation of cases are clarified and are implemented consistently; regular inspection on their implementation is carried out by competent bodies. |  | - Cases are randomly allocated in courts on an automatized principle of random allocation of cases; - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases in all courts based on the supervisory body report; - Cases are randomly allocated in prosecutors’ offices, on an automatized principle of allocation of cases, in line with the restrictions prescribed by laws and by-laws and considering the specific Organization of the prosecution; - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases in PPOs, based on the supervisory body report. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.2.1.1. | Amendments to the Law on Judges in part which deals with random allocation of cases, aiming at implementation of Program for case weighting |  | Ministry of Justice Government of the republic of Serbia National Assembly | II quarter of 2021 | Budget of the Republic of Serbia 55.697 € |  | Amended Law on judges in part which deals with allocation of cases by chance, aiming at implementation of Program for weighting of cases | Activity is fully implemented. The Law on Amendments to the Law on Judges was adopted in July 2021. |
| 1.2.1.2. | Adopt amendments to the Court Rules of Procedure in order to clarify rules concerning random allocation of cases (by chance) which takes into account complexity of cases |  | Ministry of Justice High Judicial Council | III quarter 2021 | Budget of the Republic of Serbia 30.878 € |  | Rules on random allocation of cases clarified upon adoption of amendments to the Court Rules of Procedure | Activity is not implemented. The amendments of the Court Rules of Procedure will follow the amendment of the set of judicial laws. |
| 1.2.1.3. | Application of the Program - methodologies for evaluation of cases in terms of their complexity in basic, higher and commercial courts |  | Ministry of Justice High Judicial Council Courts | IV quarter 2021 | Budget of the Republic of Serbia application of the Program € 22,977 Public procurement for maintenance and improvement of AVP application |  | Advanced formula for evaluating cases by their complexity in different types of cases implemented in the software system for random allocation of cases in all courts of general jurisdiction in order to achieve a uniform and equal workload of judges | Activity is fully implemented. The HSS Support Project, based on the analysis of the existing pilot system for weighting cases in 20 courts and on the basis of which it was concluded that the weighting formula works successfully in basic courts, started implementing the formula in the remaining 50 basic courts, with a deadline of December 2021. At the same time, the experts prepared concrete recommendations for improving the formula for higher courts, after which the Project will start implementing the improved formula in the remaining 23 higher courts, deadline December 2021. At the same time, the Project is undertaking activities to establish a working group for the analysis and development and implementation of a weighting formula for commercial courts, the deadline for the implementation of this activity is December 2021. The formula for the distribution of cases according to the criterion of "weight" has been implemented in all basic, higher and commercial courts in the Republic of Serbia. |
| 1.2.1.4. | Development of a Methodology for evaluating cases by their complexity in public prosecutor's offices in accordance with the specialization of deputy public prosecutor's offices and the need for a uniform and equal workload |  | Republic Public Prosecution in cooperation with State Prosecutorial Council | III quarter 2022 | Budget of the Republic of Serbia 17.285 € Donor support (unknown at this time) |  | Methodology for evaluating cases by their complexity in public prosecutor's offices in accordance with the specialization of deputy public prosecutor's offices and the need for a uniform and equal workload developed |  |
| 1.2.1.5. | Implementation of software-based automated case distribution in all prosecutors’ offices, with the provision of a tool for tracking random case assignment bearing in mind the specifics of the organization of the public prosecutor’s offices |  | Ministry of Justice Republic Public Prosecution | IV quarter 2022 | Budget of the Republic of Serbia Ongoing procurement to maintain and upgrade the SAPO application, in preparation for migration to the new system; IPA 2015 – Roll out SAPO 1.867.300 € |  | Developed a methodology for case weight in public prosecutors' offices, taking into account the specialization of deputy public prosecutors and the need for even and equal workload. Implementation of software-based automated case distribution in all prosecutors’ offices |  |
| 1.2.1.6. | Adopt amendments to the Rules on administration in public prosecutors’ offices in order to clarify rules on random allocation of cases, which will take into account complexity of cases as one of criteria for case assignment |  | Ministry of Justice Republic Public Prosecutors Office | III quarter 2021 | Budget of the Republic of Serbia 8.642 € |  | Rules concerning random allocation of cases have been clarified upon adoption of amendments to the Rules on administration in public prosecution | Activity is not implemented. Until the adoption of the Methodology for evaluating cases by their complexity in Public Prosecution's Offices by the State Prosecutorial Council (activity 1.2.1.4 envisaged for III quarter of 2022), Public Prosecution's Offices cannot draft the Rulebooks on Administration in Public Prosecution's Offices which will take into account complexity of cases as one of criteria for case assignment. The State Prosecutorial Council, at the invitation of the Ministry of Justice and in cooperation with the project "Strengthening the Independence and Accountability of the Judiciary" implemented within the joint program of the European Union and the Council of Europe "Horizontal Facility for the Western Balkans in Turkey II", participated in a round table 9/28/2021. The round table was organized to consider possible solutions for improving the efficiency and accountability of public prosecutors in the Republic of Serbia. On that occasion, the representatives of the State Prosecutors' Council pointed out the existence of the draft Rulebook that was drafted in 2015. The draft Rulebook was assessed as excellent during the presentation. It was concluded that a working group will be formed which will further analyse and possibly improve the Rulebook, after which it will submit it to the Council for adoption. |
| 1.2.1.7. | Establishing preparatory departments in all courts, which are in charge of, inter alia, application of case weighting methodology |  | High Judicial Council All court (court presidents) | IV quarter 2021 | Budget of the Republic of Serbia 3.064 € |  | Preparatory departments in courts established. Reports on the work of preparatory departments prepared and made public. | Activity is being sucesfully implemented. Based on the analysis of the collected data, the High Judicial Council concluded that about 60% of the basic courts in Serbia did not form a preparatory department, but that the majority carried out weighting through the AVP program. As for the higher courts, 45% have not formed a preparatory department, but the majority do weighting through the AVP program. About 70% of commercial courts in the Serbia have not formed a preparatory department, but the majority carry out weighting through the AVP program. The observed problems will be eliminated by adopting a set of judicial laws, the amendments of which are in progress, and the deadline for adoption is February 2023. |
| 1.2.1.8. | Establishing preparatory departments in public prosecutors’ offices, which are in charge of, inter alia, application of case weighting methodology and tracking of their work |  | Republic Public Prosecution All public prosecutors’ offices State Prosecutorial Council | IV quarter 2021 | Budget of the Republic of Serbia 3.064 € IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000€) |  | Preparatory departments in PPOs established. Reports on the work of preparatory departments prepared and made public. | Activity is not implemented. Establishing of preparatory departments in Public Prosecution's Offices in charge of evaluating cases by weight will be envisaged by the draft Rulebooks on Administration in Public Prosecution's Offices, which will specify the rules on automatic case distribution, where one of the distribution criteria will be case complexity. These activities cannot be carried out without the adoption of the Methodology for evaluating cases by their complexity in Public Prosecution's Offices by the State Council of Prosecutors (activity 1.2.1.4 envisaged for III quarter of 2022). |
| 1.2.1.9. | Preparing training program for staff working in the preparatory departments on the application of case weighting methodology and carrying out training of judicial and prosecutorial assistants |  | Judicial Academy High Judicial Council State Prosecutorial Council | Continuously, from III quarter 2021 | Budget of the Republic of Serbia Training program – 1.277 €; Implementation of trainings unknown at this time USAID Project “Rule of Law” 30.000 $ |  | Conducted training of judicial and prosecutorial assistants on the case weighting methodology. | Activity is being successfully implemented The program was adopted. |
| 1.2.1.10. | Follow-up the random allocation of cases in courts |  | Ministry of Justice | Continuously, from I quarter 2022 | Budget of the Republic of Serbia The total amount is unknown at this time, and the generation of one report from the monitoring system for each court is € 2,397 |  | Provide report from AVP case log allocation history to HJC regarding 100 random cases with high dispute value. Implement automatic alarm when case with same number is deleted and inputted more than twice in same day since it may be purpose action with intention to allocate case to specific judge. | Activity is being sucesfully implemented The formula for even distribution of cases has been implemented, after the feedback of the users, the procedure of monitoring the distribution will be developed. |
| 1.2.1.11. | Clear division of jurisdiction between the Ministry of Justice and the High Judicial Council / State Prosecutorial Council / Supreme Court of Cassation / Republic Public Prosecution in the performance of judicial administration in the field of supervision over the work and results of the work of the courts / public prosecutor's offices, including the field of collecting and analyzing statistical data |  | Ministry of Justice High Judicial Council State Prosecutorial Council Supreme Court of Cassation Republic Public Prosecutor Office | IV quarter 2020 | Budget of the Republic of Serbia budgeted within the activity 1.1.3.1. and 1.1.3.2. IPA 2016 Project “Support to High Judicial Council” 1.500.000 € |  | Passing the Law on Organization of Courts Passing the Law on Public Prosecutors Office The implementation of the provisions of the Law on the Organization of Courts that regulate the issue of jurisdiction for the performance of judicial administration in the field of supervision over the work and effect of courts, including the field of collecting and analyzing statistical data. | Activity is not implemented In April 2021, the President of the SPC, together with the President of the HJC and the Minister of Justice, signed a document relating to the delimitation of competencies of the judicial councils and the Ministry of Justice. They unanimously concluded that the issues of transfer of part of the competencies from the Ministry of Justice to the councils imply the inevitable redefining of the budget component, in which case they assess that it is not expedient to approach normative intervention at this moment. Amendments to the set of judicial and other related laws, which refer to the delimitation of competencies, will follow the amendment of the Constitution of the Republic of Serbia. |
| 1.2.1.12. | Coherent implementation of amended rules on random allocation of cases in courts with regular supervision /inspection of their implementation by the High Judicial Council |  | All courts High Judicial Council | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.2.1.9. и 2.553 € |  | Rules on random allocation of cases in courts are coherently implemented and regular supervision / inspection of their implementation is carried out by the High Judicial Council | Activity is not implemented |
| 1.2.1.13. | Coherent implementation of amended rules on random allocation of cases in public prosecutors’ offices with regular supervision / inspection of their implementation by the State Prosecutorial Council, having in mind the specific Organization of prosecution |  | All Public Prosecutor’s Office | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.2.1.9. и 2.553 € |  | Rules on random allocation of cases in public prosecutors’ offices are consistently implemented and regular supervision / inspection of their implementation is carried out by the State Prosecutorial Council, having in mind the specific Organization of prosecution | Activity is not implemented The situation is unchanged. |
| 1.2.1.14. | Establishment of a permanent working body of the High Judicial Council in order to monitor the proper distribution of cases in all courts and their reporting on visits and conducted controls, in accordance with the program made in advance |  | High Judicial Council Supreme Court of Cassation | III – IV quarter 2021 | Budget of the Republic of Serbia 8.642 € |  | Shortcomings remedied in the distribution of court cases Number of on-the-spot inspections carried out in courts Number of recommendations given to eliminate possible shortcomings The number of irregularities removed based on the report of the permanent working body of the High Judicial Council in charge of monitoring the correct implementation of the random allocation of cases | Activity is being successfully implemented During the fourth quarter, efforts continued related to introducing a formula for evaluating cases by complexity (“case weighting”) in commercial courts. The working group for the development of a formula for evaluating cases by weight in commercial courts at a meeting held on December 2, 2021, discussed the proposed formula developed by experts from the EU for Serbia Project - Support to the High Judicial Council. In cooperation with the Ministry of Justice, the agreed formula for evaluating cases by weight for commercial courts should be implemented by January 20, 2022 in civil cases (P.) and cases of economic offenses (Pk.). |
| 1.2.1.15. | Establishment of a permanent working body of the State Prosecutorial Council in order to monitor the proper distribution of cases in all public prosecutor's offices and their reporting on visits and conducted controls, in accordance with the program made in advance |  | Republic Public Prosecution | III – IV quarter 2021 | Budget of the Republic of Serbia 8.642 € |  | Shortcomings remedied in the distribution of cases in public prosecutors' offices Number of on-the-spot inspections carried out in public prosecutors' offices Number of recommendations given to eliminate possible shortcomings The number of irregularities removed based on the report of the permanent working body of the State Prosecutorial Council in charge of monitoring the correct implementation of the random allocation of cases | Activity is not implemented. A permanent working body for monitoring the proper distribution of cases in Public Prosecutions can be formed after the adoption of relevant bylaws that would regulate the distribution of cases. |
| RECOMMENDATION FROM THE SCREENING REPORT / INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |  |
| 1.2.2. Strengthen the accountability of judges and prosecutors through a strict application of all legal and disciplinary means, including through: - Review where necessary and effectively implement rules on disciplinary and dismissal procedures. IBM: Serbia ensures that magistrates are fully accountable providing an initial track record of using the system of asset declarations as an effective means to detect inexplicable wealth, raising awareness on and the strict application of conflict of interest rules, promoting and controlling the respect of codes of ethics, avoiding that the concept of functional immunity is abused, ensuring regular inspections by an independent inspection body of the work of judges and prosecutors. |  |  |  | The accountability of judges and public prosecutors strengthened through a strict application of all legal and disciplinary means, including through the effective implementation of "conflict of interest" rules; effective verification and cross-checking of asset declarations; effective monitoring of compliance with the code of ethics and carrying out trainings for judges and public prosecutors in the field of ethics; effective implementation of rules on disciplinary accountability, functional immunity, dismissal procedures and accountability of judges and public prosecutors. The respective Councils have both an inspection capacity based on clear rules and bestowed with powers allowing them to act ex officio or on signals from citizens, state bodies or other legal entities related to inter alia questions of integrity or professional failure. |  |  | - Regular opinion polls confirm that there has been a decrease in the perception of corruption among citizens regarding the manner in which judges and public prosecutors respect the rules of ethics and values, which is confirmed in the positive assessment positive evaluation by European Commission concerning the system of accountability of judges and public prosecutors stated in the Annual Progress Report on Serbia; - The system of asset declaration and verification is actively used as a tool for the prevention and detection of illicit enrichment of judges and public prosecutors; - Increased number of judges and prosecutors who are covered by training in the field of ethics, results in raising awareness of the need to respect ethical values; - Results of the evaluation of judges and public prosecutors included in ethics training; - Positive evaluation on the degree of compliance with the code of ethics from the reports of ethics committees of the High Judicial Council and State Prosecutorial Council; - Data on the number of disciplinary charges and disciplinary proceedings against judges and public prosecutors from the reports of the disciplinary bodies of the High Judicial Council and State Prosecutorial Council; - Data on criminal charges and criminal proceedings against judges and public prosecutors. |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.2.2.1. | Regular notification by courts and PPOs to the Anti-Corruption Agency concerning taking of and termination of the judicial / prosecutorial function, in order to efficiently check the existence of conflict of interests |  | Courts Public prosecutor`s office Anti-Corruption Agency | Continuously | Budget of the Republic of Serbia Negligible cost activity |  | Courts and Public prosecutor`s office regularly submit notifications concerning taking of and termination of the judicial / prosecutorial function that enables ACA regularly updating lists of holders of judicial and prosecutorial functions | Аctivity is being successfully implemented There are currently 2,935 active judges and 905 active prosecutors in the Register of Public Officials. In total, there are 5,138 registered judges and 1,438 registered prosecutors. In one case, proceedings for determining violation of the Law was initiated against Administrative Court Judge. In two proceedings, upon requests of Administrative Court judges and Higher Court judge the APC granted consent for delivering lectures at universities. In one case judge of the Commercial Appellate Court notified the APC on entry into respective office. |
| 1.2.2.2. | Raising awareness on the strict application of conflict of interests through an improved cooperation between the High Judicial Council / the State Prosecutorial Council and Anti-Corruption Agency, through holding regular meetings on a half-yearly basis and consideration of problems in order to coherently and timely implement duties of submitting reports on assets and incomes (assets declaration) of judicial office holders |  | High Judicial Council State Prosecutorial Council Anti-Corruption Agency | Continuously, twice a year for holding meetings | Budget of the Republic of Serbia Negligible cost activity |  | Improved cooperation between the High Judicial Council, State Prosecutorial Council and Anti-Corruption Agency Meetings scheduled and held regularly on a half-yearly basis Judicial office holders regularly submit assets declaration to the Anti-Corruption Agency Initial track record carried by the ACA of using the system of asset declarations as an effective means to detect inexplicable wealth in place | Аctivity is being successfully implemented On March 11th, a meeting was held between representatives of the High Judicial Council, the State Prosecutorial Council and the Agency for the Prevention of Corruption. Representatives of the Agency pointed out that it is necessary for judges and deputy public prosecutors to report to the Agency not only income and expenses of property, but also changes in the structure of property. Also, judges are obliged to submit property reports to the Agency even when their function is terminated. They informed those present that a list of officials - judges whose property will be inspected during 2022 - has been published on the Agency's website. Representatives of the High Judicial Council and the State Prosecutor's Council pointed out that they would inform all judges, ie deputy public prosecutors about the obligations arising from the Law on Prevention of Corruption, in order to avoid the application of sanctions for non-compliance with the law. So far, the total number of processed and published Asset and Income Declarations of judges is 9,253, and prosecutors 1,718. In the reporting period the APC conducted verification of the asset and income declarations of 125 judges and public prosecutors/deputy public prosecutors (100 judges, one public prosecutor and 24 deputy public prosecutors). There were no extraordinary checks of asset and income declarations of the judicial office holders in the same period. |
| 1.2.2.3. | Amendments to the legislative framework which regulates: - requirements for dismissal of judges with the aim of specifying the requirements; - body in charge of conducting disciplinary proceedings and making decisions; - statute of limitations for disciplinary misdemeanor; - sanctioning regime and practice; |  | Ministry of Justice Government of the Republic of Serbia National Assembly High Judicial Council | II quarter of 2022 | Budget of the Republic of Serbia 55.697 € |  | Analysis of the legislative framework performed by the working group of the Ministry of Justice Amendments to the Law on Judges and the Law on the High Judicial Council adopted High Judicial Council performs its duties concerning disciplinary proceedings in line with the amended legislation | Activity is being sucessfully implemented. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.2.2.4. | Amendments to the legislative framework which regulates: - requirements for dismissal of public prosecutor’s office holders with the aim of specifying the requirements; - body in charge of conducting disciplinary proceedings and making decisions; - statute of limitations for disciplinary misdemeanor; - sanctioning regime and practice. |  | Ministry of Justice Government of the Republic of Serbia National Assembly Republic Public Prosecutor Office State Prosecutorial Council | II quarter of 2022 | Budget of the Republic of Serbia 55.697 € |  | Analysis of the legislative framework performed by the working group of the Ministry of Justice Amendments to the Law on Public Prosecution and the Law on the State Prosecutorial Council adopted. State Prosecutorial Council performs its duties concerning disciplinary proceedings in line with the amended legislation. | Activity is being implemented sucessfully. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.2.2.5. | Amendments to the Law on Judges and the Law on the High Judicial Council in order to prescribe: - the Ethics Board as a permanent working body of the High Judicial Council; - the competencies of the High Judicial Council for the adoption of the Rules of Procedure of the Ethics Board - the obligation to draft a report on the work of the High Judicial Council Ethics Board on compliance with the provisions of the Code of Ethics |  | Ministry of Justice Government of the Republic of Serbia National Assembly High Judicial Council | II quarter of 2022 Continuously for reporting once a year (Reports on the work of the High Judicial Council Ethics Board) | Budget of the Republic of Serbia 55.697 € |  | Analysis of the legislative framework performed by the working group of the Ministry of Justice Amendments to the Law on Judges and the Law on the High Judicial Council adopted Rules of Procedure of the Ethics Board adopted Reports on the work of the High Judicial Council `s Ethics Board are prepared in regular periodicity | Activity is being successfully implemented. At the session held on June 9, 2022, the Council adopted the Rulebook on the work of the Ethics Committee of the High Council of the Judiciary ("Official Gazette of the Republic of Serbia", number 68/22 of June 26, 2022). The provisions of Article 4 of the Rules of Procedure of the Ethics Committee of the High Judicial Council stipulate that the Ethics Committee shall adopt Rules of Procedure for its work. Article 6 of the Rulebook on the work of the Ethics Committee of the High Judicial Council stipulates that the Ethics Committee submits an annual report on its work to the Council no later than March 1st of the current year for the previous year and whenever the Council requests it. |
| 1.2.2.6. | Analysis and in case the results of the analysis indicate the need, amending Code of Ethics for Judges |  | High Judicial Council | III quarter of 2021 | Budget of the Republic of Serbia 33.224 € |  | An analysis, with recommendations performed Amendments to the Code of Ethics for Judges in accordance with the recommendations. | Activity is fully implemented. See report for 1.2.2.9. |
| 1.2.2.7. | Amendments to the Law on Prosecution and the Law on the State Prosecutorial Council in order to prescribe: - the Ethics Board as a permanent working body of the State Prosecutorial Council - the competencies of the State Prosecutorial Council for the adoption of the Rules of Procedure of the Ethics Committee - the obligation to draft a report on the work of the State Prosecutorial Council Ethics Committee on compliance with the provisions of the Code of Ethics |  | Ministry of Justice Government of the Republic of Serbia National Assembly Republic Public Prosecutor Office State Prosecutorial Council | II quarter of 2022 Continuously for reporting once a year (Reports on the work of the SPC Ethics Board) | Budget of the Republic of Serbia 55.697 € |  | Analysis of the legislative framework performed by the working group of the Ministry of Justice Amendments to the Law on Public Prosecutors Office and the Law on State Prosecutorial Council adopted Rules of Procedure of the Ethics Board adopted Reports on the work of the SPC`s Ethics Board are prepared in regular periodicity | Activity is being implemented sucessfully. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.2.2.8. | Analysis and in case the results of the analysis indicate the need, amending Code of Ethics for public prosecutors and deputy public prosecutors |  | State Prosecutorial Council | III quarter of 2021 | Budget of the Republic of Serbia 33.224 € |  | An analysis, with recommendations performed Amendments to the Code of Ethics for Public Prosecutors in accordance with the recommendations | Аctivity is fully implemented. At its regular session held in April 2021, the Council adopted a new Code of Ethics for Public Prosecutors and Deputy Public Prosecutors of the Republic of Serbia, together with Guidelines for the Application of Ethical Principles. |
| 1.2.2.9. | Adoption of Rules of Procedure of Board of Ethics of the High Judicial Council and the State Prosecutorial Council which regulate monitoring of compliance with Code of Ethics for judges and (deputy) public prosecutors and conducting training of judges and (deputy) public prosecutors and on ethics |  | High Judicial Council State Prosecutorial Council | IV quarter of 2022 | Budget of the Republic of Serbia 11.362 € IPA 2017 EU for Serbia – “Support to the Prosecutorial System”, tender procedure in progress (the planned project amount is 1,500,000 €) |  | Rules of Procedure of Board of Ethics of High Judicial Council adopted Rules of Procedure of Board of Ethics of State Prosecutorial Council adopted Number of judges trained in ethics Number of (deputy) public prosecutors trained in ethics | Аctivity is being successfully implemented. At the session held on June 9th, 2022, the Council adopted the Rulebook on the work of the Ethics Committee of the High Judicial Council ("Official Gazette of the Republic of Serbia", number 68/22 of June 26, 2022). The provisions of Article 4 of the Rulebookof Procedure of the Ethics Committee of the High Judicial Council stipulate that the Ethics Committee shall adopt Rules of Procedure for its work. |
| 1.2.2.10. | Organizing seminars for judicial office holders on integrity rules and ethics |  | Judicial Academy High Judicial Council State Prosecutorial Council | Continuously | Budget of the Republic of Serbia 33.000 €: in 2020. – 14.400 € in 2021. – 14.400 € in 2022. – 4.200 € IPA 2017 Project “Support to the High Judicial Council” 1.500.000 € |  | Number of seminars held in relation to those planned on integrity rules and ethics Percentage of holders of judicial function trained on integrity rules and ethics in relation to those required/in needs of training | Аctivity is being successfully implemented. Due to the epidemiological situation, a series of debates on the ethics of judges - "Days of Judicial Ethics" in the period from January 21 to February 18th, were organized online, in a hybrid format that included participation and recording of panellists in the studio. Followed the debates via computer or telephone, via the link provided to them, this allowed participants to directly participate in the debate by direct inclusion in the program, with image and tone. The first online debate on the ethics of judges "Presentation of the Ethics Committee of the High Judicial Council" was held on January 21st, 2022. The second online debate on the ethics of judges, the "Code of Ethics for Judges and Standards of Judicial Ethics", was held on January 28th 2022. The third online debate on the ethics of judges "Judicial responsibility - the difference between disciplinary and ethical responsibility of judges" was reflected on February 4th 2022. The fourth online debate on the ethics of judges, "Confidential Adviser, Role and Comparative Legal Review", was held on February 11th 2022. The fifth online debate on the ethics of judges "The final debate on the ethics of judges" was held on February 18th 2022. The Council of Europe and the EU project "Strengthening the Independence and Accountability of the Judiciary", in cooperation with the Judicial Academy, organized advanced training programs for lecturers entitled "Recognition and protection from undue influence on judges": The first program was held from January 18th and 19th 2022 in Belgrade, and the second program from March 7th to 9th 2022 in Novi Sad. In addition to the members of the Ethics Committee of the High Judicial Council, judges of the republic rank also participated in the trainings, who expressed their desire to participate in these trainings by applying to the previously conducted public invitation of the Judicial Academy. During the reporting period, three online trainings, for a total of 222 participants (judges) were conducted, on the topic “Judicial ethics days- confidential advisor, role and comparative-legal representation.’’ Judicial Academy: During the second quarter 2022, six trainings were held for holders of judicial office for up to three years, on ethics and integrity rules. High Judicial Council: The Council of Europe and EU project "Strengthening the Independence and Accountability of the Judiciary" in cooperation with the Judicial Academy during June 2022 organized training for 60 newly elected judges in four appellate areas in Nis, Kragujevac, Belgrade and Novi Sad under the name "Recognition and protection against undue influence on judges". The lecturers at the trainings were the deputy presidents of the High Judicial Council, the president, the deputy president and a member of the Ethics Committee of the High Judicial Council, as well as judges of the Supreme Court of Cassation. |
| 1.2.2.11. | Drawing up of and publication of an updated brochure for judges for increasing awareness on ethics’ rules, containing examples of permissible / impermissible conduct, which encompasses examples from practice Publishing the brochure on the website of the High Judicial Council |  | High Judicial Council | IV quarter 2020 | Budget of the Republic of Serbia 22.935 € IPA 2017 Project “Support to the High Judicial Council” 1.500.000 € |  | Brochure encompassing ethics’ rules and containing examples of permissible / impermissible conduct is drawn up and available on the website of High Judicial Council Number of visits to the link with the electronic brochures Number of documents downloaded from the links | Аctivity is fully implemented. Within the IPA 2016 project - Support to the High Judicial Council, a comprehensive analysis of the legal framework for the ethics of judges of relevant comparative legal standards, as well as the existing Code of Ethics for Judges and the Code of Ethics for members of the High Judicial Council from the rank of Judges , was made and published on the website of the High Judicial Council www.vss.sud.rs , entitled: "Judicial Ethics in Serbia - Analysis of the Legal Framework and Recommendations for Improvement". See activity 1.2.2.13. - Realization data. |
| 1.2.2.12. | Drawing up of and publication of an updated brochure for public prosecutors for increasing awareness on rules of ethics containing examples of permissible / impermissible conduct from practice Publishing brochure on the website of the State Prosecutorial Council |  | State Prosecutorial Council | IV quarter 2020 | Budget of the Republic of Serbia 22.935 € |  | Brochure encompassing ethics’ rules containing examples of permissible/impermissible conduct is drawn up and available on the website of the State Prosecutorial Council. Number of visits to the link with the electronic brochures Number of documents downloaded from the links | Activity is being successfully implemented. In cooperation with the Council of Europe, a brochure on public prosecutorial ethics was prepared, which contains a Code of Ethics and Guidelines for its implementation. The brochure was printed, and in September it was delivered to all public prosecutor's offices. * see activity 1.2.2.9. |
| 1.2.2.13. | Proactive approach of judges and the High Judicial Council in creation and monitoring of compliance with the Code of Ethics for judges, through the promotion of ethical principles and professional behavior rules |  | High Judicial Council | Continuously | Budget of the Republic of Serbia 8.642 € |  | Judges and members of High Judicial Council take proactive approach in creating and monitoring of compliance with the Code of Ethics for judges, through a series of seminar, round tables, workshops etc. in order to present permissible/impermissible conduct from practice | Аctivity is being successfully implemented. The publication "Guide for Judges and Prosecutors Ethical Aspects of the Use of Social Networks" was published on the High Judicial Council's website, which was prepared within the joint project of the European Union and the Council of Europe "Strengthening the Independence and Accountability of the Judiciary". The guide was created on the basis of a comprehensive research in which elected members of the High Judicial Council participated. The authors of the guide are experts from the Council of Europe, and the author of the introductory speech is Omer Hadžiomerović, President of the Ethics Committee of the High Judicial Council. The guide is intended for holders of judicial functions as users, because they contain a mapping of potential risks they encounter when using social networks, and they also contain practical tips for dealing with the most common challenges. See activity 1.2.2.10. - Realization data. The President, Deputy President and member of the Ethics Committee of the High Judicial Council, during June 2022, as part of the Council of Europe and EU project "Strengthening the Independence and Accountability of the Judiciary"., gave lectures to newly elected judges in four appellate areas on the topic: "The concept of undue influence in the judiciary ", "Judicial independence and protection against undue influence - international standard and national legal framework" and "Types of undue influence, mechanisms for protection against undue influence and examples from comparative and domestic practice". See activity 1.2.2.10. - Realization data. |
| 1.2.2.14. | Amendments to the Law on Judges in the part concerning the disciplinary responsibility of judges, especially in parts of: - Differences between light, moderate and serious disciplinary offences; - respecting the principle of proportionality between disciplinary offences and disciplinary sanctions; - clear prescribing of the disciplinary procedure and jurisdiction for conducting the disciplinary procedure and the procedure for dismissal from function; - the role of the Disciplinary Commission in the proceedings; - establishing a database of disciplinary proceedings against judges and the outcome. |  | Ministry of Justice Government of the Republic of Serbia National Assembly High Judicial Council | II quarter 2022 | Budget of the Republic of Serbia 55.697 € |  | Analysis of the Law on Judges by the working group of the Ministry of Justice Amendments to the Law on Judges adopted | Activity is being implemented sucessfully. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.2.2.15. | Amendments to the Law on Public Prosecution in the part referring to the disciplinary responsibility of public prosecutors, especially in parts of: - Differences between light, moderate and serious disciplinary offences; - respecting the principle of proportionality between disciplinary offences and disciplinary sanctions; - clear prescribing of the disciplinary procedure and jurisdiction for conducting disciplinary procedure and the procedure for dismissal from function; - the role of the Disciplinary Commission in the proceedings; - establishing a database of disciplinary proceedings initiated against prosecutors and the outcome. |  | Ministry of Justice Government of the Republic of Serbia National Assembly Republic Public Prosecutor Office State Prosecutorial Council | II quarter 2022 | Budget of the Republic of Serbia 55.697 € |  | Analysis of the Law on Public Prosecution by the working group of the Ministry of Justice Amendments to the Law on Public Prosecution adopted | Activity is being implemented sucessfully. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.2.2.16. | Effective implementation of the Rules of Procedure on disciplinary proceedings and disciplinary liability of judges |  | High Judicial Council –disciplinary bodies | Continuously | Budget of the Republic of Serbia 21.901 € |  | Disciplinary bodies of High Judicial Council effectively implement the Rules of Procedure on disciplinary proceedings and disciplinary liability of judges Number of disciplinary proceedings initiated by type of disciplinary proceedings Number of cases completed by type of disciplinary proceedings Number of sanctions pronounced by type of sanctions | Activity is being successfully implemented. In the period from January1st 2022. To March 31st 2022., the Disciplinary Prosecutor of the High Judicial Council submitted to the Disciplinary Commission of the High Judicial Council 5 proposals for initiating disciplinary proceedings, due to the following disciplinary offenses: 1. Unjustified delay of the procedure from Article 90, paragraph 1, line 7 of the Law on Judges (proposal for conducting disciplinary proceedings was submitted on January 26th, 2022) 2. Serious disciplinary offense referred to in Article 90 paragraph 2 in conjunction with paragraph 3 of the Law on Judges, and in respect of a disciplinary offense unjustified delay of the procedure referred to in Article 90 paragraph 1 indent 7 of the Law on Judges; (proposal for conducting disciplinary proceedings submitted on January 26th , 2022) 3. Serious disciplinary offense under Article 90, paragraph 2 of the Law on Judges, in connection with the disciplinary offense unjustified delay of the procedure under Article 90, paragraph 1, line 7 of the Law on Judges (proposal for disciplinary proceedings was submitted on February 21, 2022) 4. Obviously incorrect treatment of participants in court proceedings and court staff From Article 90, paragraph 1, line 9 of the Law on Judges (proposal for conducting disciplinary proceedings was submitted on March 25th 2022) 5. Unjustified delay of the procedure from Article 90, paragraph 1, line 7 of the Law on Judges and Serious Violation of the provisions of the Code of Ethics from Article 90, paragraph 1, line 18 of the Law on Judges (proposal for disciplinary proceedings was submitted on March 30th, 2022) Number of cases completed "according to the type of disciplinary procedure" (cases resolved in the quarterly period, and lagging behind from the previous period in the work of the Disciplinary Commission: 1. The Disciplinary Commission of the High Judicial Council submitted on April 2nd .2022. submitted to the High Judicial Council a PROPOSAL to initiate proceedings to determine the reasons for dismissal of the president of the court, due to a serious disciplinary offense under Article 90 paragraph 2 of the Law on Judges regarding disciplinary offence under Article 90, paragraph 1, line 17 of the Law on Judges, and serious violations the provisions of the Code of Ethics from Article 90, paragraph 1, line 18 of the Law on Judges, in connection with items 4.1 and 7.1 of the Code of Ethics. (The Disciplinary Prosecutor of the HJC submitted a proposal to the Disciplinary Commission of the HJC for conducting disciplinary proceedings on November 17th 2021) 2. BY THE DECISION of the Disciplinary Commission of the High Judicial Council from January 21st 2022. , the proposal for conducting disciplinary proceedings was adopted, the judge was found responsible for committing a disciplinary offense unjustified delay in drafting decisions under Article 90 paragraph 1 indent 3 of the Law on Judges. Sanction: REDUCTION OF SALARY by 30% for a period of 1 (one) year. . (The Disciplinary Prosecutor of the HJC submitted a proposal to the Disciplinary Commission of the HJC on August 31st for conducting disciplinary proceedings unjustifiable delays in the drafting of decisions from Article 90 paragraph 1 indent 3 of the Law on Judges and serious violation of the Code of Ethics from Article 90 paragraph 1 indent 18 of the Law on Judges regarding item 3 paragraph 1 indent 3.3 of the Code of Ethics) 3. BY THE DECISION of the Disciplinary Commission of the High Judicial Council from March 18th 2022, the proposal for conducting disciplinary proceedings was adopted, the judge was found responsible for committing a disciplinary offense unjustifiable failure to notify the president of the court about cases with prolonged proceedings from Article 90 paragraph 1 indent 7 of the Law on Judges . Sanction: PUBLIC WARNING (On October 15th, 2021, the Disciplinary Prosecutor of the HJC submitted a proposal to the Disciplinary Commission of the HJC for conducting disciplinary proceedings) 4. BY THE DECISION of the Disciplinary Commission of the High Judicial Council of January 21st 2022. , the proposal for conducting disciplinary proceedings was adopted, the judge was declared responsible for committing a disciplinary offense Unjustified prolonging of proceedings;under Article 90, paragraph 1, line 7 of the Law on Judges. Sanction: PUBLIC WARNING (On November 22nd, 2021, the Disciplinary Prosecutor of the HJC submitted a proposal to the Disciplinary Commission of the HJC for conducting disciplinary proceedings).. During the period from 01.04.2022. Until 30.06.2022. The Disciplinary Prosecutor of the High Judicial Council submitted to the Disciplinary Commission of the High Judicial Council 7 proposals for the initiation of disciplinary proceedings, due to the commission of disciplinary violations: 1. Violation of the provisions of the Code of Ethics to a greater extent from Article 90 paragraph 1 paragraph 18 of the Law on Judges, (the proposal for conducting disciplinary proceedings was submitted on April 1, 2022) 2. Unjustified delay of the procedure referred to in Article 90, paragraph 1, indent 7 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on April 1st, 2022) 3. Serious disciplinary offense from Article 90 paragraph 2 of the Law on Judges, regarding the disciplinary offense violation of the provisions of the Code of Ethics to a greater extent from Article 90 paragraph 1 indent 18 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on April 4th, 2022) 4. Unjustified delay of the procedure referred to in Article 90, paragraph 1, indent 7 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on May 11th, 2022) 5. Frequent lateness to scheduled hearings or hearings referred to in Article 90 paragraph 1 subparagraph 6 of the Law on Judges and non-compliance with working hours referred to in Article 90 paragraph 1 subparagraph 10 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on 11.05.2022) 6. Obviously unfair treatment of participants in court proceedings and court employees from Article 90, paragraph 1, indent 9 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on May 27th, 2022) 5. Violation of the principle of impartiality from Article 90 paragraph 1 indent 1 of the Law on Judges and obvious unfair treatment of participants in court proceedings and court employees from Article 90 paragraph 1 indent 9 of the Law on Judges (the proposal for conducting disciplinary proceedings was submitted on June 21st .2022) The number of cases concluded "according to the type of disciplinary procedure" (cases that were resolved in the quarterly period, including cases that were overdue from an earlier period in the work of the Disciplinary Commission: 1. BY DECISION of the Disciplinary Commission of the Supreme Court of April 1st, 2022. The disciplinary proceedings against the judge were suspended, due to the resignation of the Disciplinary Prosecutor. (The HJC Disciplinary Prosecutor submitted a proposal to the HJC Disciplinary Commission for conducting disciplinary proceedings on January 26th, 2022) 2. BY DECISION of the Disciplinary Commission of the Supreme Court dated 06.05.2022, a proposal for conducting disciplinary proceedings was adopted, the judge was declared responsible for the commission of a disciplinary offense, unjustified delay of the proceedings from Article 90, paragraph 1, indent 7 of the Law on Judges. Sanction: REDUCTION OF SALARY 20% for a period of 6 (six) months and PROHIBITION FOR PROMOTION for 1 (one) year (On March 30,th 2022, the Disciplinary Prosecutor of the Supreme Court submitted a proposal to the Disciplinary Commission of the Supreme Court to conduct disciplinary proceedings due to the commission of an unjustified disciplinary offense delaying the procedure from Article 90 paragraph 1 subparagraph 7 of the Law on Judges and a disciplinary offense violation of the Code of Ethics to a greater extent from Article 90 paragraph 1 subparagraph 18 of the Law on Judges) 3. BY DECISION of the Disciplinary Commission of the Supreme Court of May 6th, 2022, a proposal for conducting disciplinary proceedings was adopted, the judge was declared responsible for committing a disciplinary offense Violation of the provisions of the Code of Ethics to a greater extent from Article 90 paragraph 1 paragraph 18 of the Law on Judges. Sanction: PROHIBITION FOR 1 (one) year. (On April 1, 2022, the HJS Disciplinary Prosecutor submitted a proposal for conducting disciplinary proceedings to the HJS Disciplinary Commission) 4. BY DECISION of the Disciplinary Commission of the Supreme Court of May 27th, 2022. The proposal for disciplinary proceedings was rejected. (On April 1, 2022, the HJC Disciplinary Prosecutor submitted a proposal to the HJC Disciplinary Commission for the conduct of disciplinary proceedings due to the disciplinary offense Unjustified delay of the proceedings from Article 90 paragraph 1 indent 7 of the Law on Judges). 5. BY DECISION of the Disciplinary Commission of the Supreme Court of May 13th, 2022., a proposal for conducting disciplinary proceedings was adopted, the judge was declared responsible for the commission of a disciplinary offense, a violation of the provisions of the Code of Ethics to a greater extent from Article 90, paragraph 1, indent 18 of the Law on Judges, in connection with points 4.4 and 7.3 of the Code of Ethics. Sanction: PUBLIC WARNING. (On April 4th, 2022, the HJC Disciplinary Prosecutor submitted a proposal for conducting disciplinary proceedings to the HJC Disciplinary Commission). |
| 1.2.2.17. | Effective implementation of Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors |  | State Prosecutorial Council –disciplinary bodies | Continuously | Budget of the Republic of Serbia 21.901 € |  | Disciplinary bodies of the State Prosecutorial Council effectively implement Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors Number of disciplinary proceedings initiated by type of disciplinary proceedings Number of cases completed by type of disciplinary proceedings Number of sanctions pronounced by type of sanctions | Аctivity is being successfully implemented. In the 1st quarter 2022, the Disciplinary Prosecutor had 27 disciplinary reports in progress, of which 9 decisions were made to reject the report, 1 was resolved in another way, other reports are pending. In the 2nd quarter 2022, the Disciplinary Prosecutor had 24 disciplinary reports, of which 19 were rejected and 5 were resolved in another way. |
| 1.2.2.18. | Conduct analysis of provisions that regulate functional immunity of judicial office holders |  | Minister of Justice High Judicial Council State Prosecutorial Council | III quarter of 2021 | Budget of the Republic of Serbia 8.642 € Council of Europe (ongoing discussion) |  | Conducted analysis of provisions that regulate functional immunity of judicial office holders | Activity is fully implemented Analysis of provisions that regulate functional immunity of judicial office holders is performed. |
| 1.2.2.19. | Implementation of measures in accordance with conducted analysis from the activity 1.2.2.18. |  | Ministry of Justice High Judicial Council State Prosecutorial Council | II quarter of 2022 | Budget of the Republic of Serbia Budgeted within the activity 1.2.2.18. Council of Europe (ongoing discussion) |  | Implemented measures in accordance with conducted analysis | Activity is not implemented. |
| 1.3. PROFESSIONALISM / COMPETENCE / EFFICIENCY |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT / INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |
| 1.3.1. Develop the Judicial Academy as a center for continuously and initial training of judges and prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the public prosecution and the Judicial Academy, including through: - introducing a yearly curriculum covering all areas of law, including EU law; - allocating sufficient resources and introduce a quality control system for initial and specialized training; - IBM: Serbia ensures that the Judicial Academy adopts a multi-annual work program, covering human and financial resources and a further development of its training program. - Serbia also provides a sustainable and long-term solution for financing the Judicial Academy applies a quality control mechanism and regularly and effectively assesses the impact of the training. |  |  |  | The Judicial Academy has been improved as a center for continuous and initial training of judges and public prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the Public prosecutor’s Office and the Judicial Academy. Trainings are held according to annual curriculum covering all areas of law, including EU law and are subject to regular control. |  |  | - Improved quality of continuous and initial training that is implemented on the basis of the annual training program; - Judicial Academy operates with adequate infrastructure, equipment and staff in relation to training needs; - Programs of continuous, specialized and initial trainings are subject to regular control of quality and are improved according to the results of control; - Needs for training and education for judicial office holders are determined as part of their annual evaluation, and in accordance with the real needs of the system. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME / DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.3.1.1. | Implementation of measures for improvement of initial training program of Judicial Academy: - Improvement of the entrance exam for initial training participants (two-year training) and development of multiple models of exams for participants in specific training programs, in accordance with the transitional solution of several entrance "gates" for candidates depending on work experience, practice and career path after passing the bar exam; - Improvement of initial training program through drawing up and adoption of annual curriculum of training that covers all areas of law (including EU law and human rights, ethics and integrity) and skills necessary for work in judiciary, which include the practical skills, along with all areas of law, depending on the category of the specific student and in particular usage of ICT system, legal analysis, methodology and method of decision drafting. - Improvement of transparency of elections of mentors; - Improvement of methods of teaching through workshops, simulations and the introduction of distance learning; - Improvement of the final exam for all categories of participants in the initial training programs; | Judicial Academy Ministry of Justice High Judicial Council State Prosecutorial Council |  | Continuously | Budget of the Republic of Serbia 3.083.301 € Judicial Academy – 319.125 €; Other responsible authorities – 8.642 € Training courses 700.000 € |  | Initial training program improved and implemented Impact assessment on the changes implemented | Аctivity is being successfully implemented. During the 1st quarter 2022, the working groups of the Judicial Academy worked on the review and selection of this year’s questions for the written and oral part of the entrance exam, which should be realized in May this year. In March 2022, Judicial Academy, in cooperation with the Portal ‘’Pištaljka’’, has organized a one-day training on the topic ‘’Judicial ethics and prevention of corruption’’, attended by 30 beneficiaries of the X generation of the Judicial Academy. During March, 16 beneficiaries of the initial training of the XI generation have attended a five-week online training on non-discrimination. Having in mind the professional obligations and duties of each trainee, the training was organized in an asynchronous form, with the support of mentors. The progress of the trainees is continuously monitored through the forms of testing knowledge at the end of each processed topic, but also by checking the changes in knowledge after the training. During the 1st quarter , the working groups of the Judicial Academy, having in mind the Initial training program worked on the development of criteria and guidelines for the selection of criminal and litigation cases that often occur in court and prosecutorial practice, and which are suitable as materials/case studies for verification of acquired knowledge i.e. preparing and taking the final exam. During the 2nd quarter 2022, the entrance exam was conducted, with a previously improved process of selecting questions for the written and oral part of the entrance exam. The criteria for evaluating and selecting candidates have not changed. During May, for a total of 50 beneficiaries of the initial training who passed the final exam and are awaiting election to the position, as an additional form of training was held a two-day training course “Administrative dispute and administrative procedure.” Seminars were held in Niš and Belgrade. Beneficiaries of the X and XI generation of the initial training attended an online course under the mentoring support “Justice for children” on the HELP platform of the Council of Europe. The course was designed in cooperation with the Judicial Academy, the Council of Europe and the Institute for Criminological and Sociological Research. In the following period, it is planned to organized a five-week training on non-discrimination for the beneficiaries of the initial training. During the 2nd quarter 2022, meetings were held with the members of the examining board and mentors for preparation for the final exam in order to improve the quality of the final exam. The task selection process, as well as the very way of preparation and evaluation through the work methodology even more focused on the assessment of critical thinking and competencies necessary for the performance of judicial functions. Preparation and realization of the final exam according to the improved methodology are planned for the third reporting period. |
| 1.3.1.2. | Implementation of measures for improvement of continuous training program of Judicial Academy such as: - Improving continuous training through a wider range of participants, potentially through prescribing the minimum number of training days per holder of judicial office annually, whereby the training must include not only judicial officials but also presidents, secretaries and managers, judicial and prosecutorial assistants, administrative staff and persons engaged in judicial professions; - Improvement of transparency of elections of trainers; - Improvement of methods of teaching through workshops, simulations and the introduction of distance learning; | Judicial Academy Ministry of Justice High Judicial Council State Prosecutorial Council |  | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | Continuous training program improved and implemented Impact assessment on the changes implemented | Аctivity is being successfully implemented. During March 2022, within the project ‘’Children’s Rights in Serbia- improving the position of children in the judicial system of the Republic of Serbia’’, a two-day pilot training ‘’Training for improvement of media reporting on child victims or witnesses of crime’’ was held. The target group of participants were judges of the criminal department of basic and higher courts, deputy public prosecutors of basic and higher public prosecutor’s offices, police representatives, social welfare centers representatives, as well as journalists of print and electronic media. A manual and curriculum for training professionals in contact with child victims of crimes ‘’Child victims and media’’ has been drafted. In the next period, the following activities are planned: realization of trainings for trainers on this topic, selection and formation of multidisciplinary pairs of lecturers (trainers) on this topic, realization of trainings for multidisciplinary composition of participants in the seats of the appellations. The final preparations of the Manual for the Training of Professionals in the field of child-based justice are ready. A circulation of 100 copies was printed. The digital edition of the Manual is in the final stages of preparation. In the following period, it is planned to examine the needs of judges and prosecutors on the topic of child-based justice, in order to adapt the curriculum to the practical needs of judicial office holders, as well as the organization of trainings for all four appellate territories. During the 2nd quarter 2022, a meeting of the project’s advisory board was held on ‘’Children’s Rights in Serbia- improving the position of children in the judicial system of the Republic of Serbia’’, where the results of the implemented activities within the project were presented. A meeting of the external evaluator of the project and the representative of the Judicial Academy was held on the occasion of the summative evaluation of the project activities. In June, the final conference of the project was held, where the representatives of the Judicial Academy presented the project activities and results. It is planned to continue the implementation of training in the following period, in accordance with educational needs and resource possibilities. The manual for the training of professionals in the field of Justice tailored to the child will be available on the website of the Judicial Academy in the digital content library section in the coming period. The printed edition in a circulation of 100 copies will be used by the Judicial Academy in the implementation of future trainings. Judicial Academy participated in the international program on human rights organized by the Judicial Academy of Turkey. It was agreed to sign a Memorandum of understanding of the Academies in the follwing period. |
| 1.3.1.3. | Development of monitoring system concerning quality of initial, continuous and specialized training that implies two-way evaluation system that would allow the assessment of the results of training or degree of advancement of knowledge of the participants as well as the assessment of the quality of the program and trainers in cooperation with the Institute for quality assurance of education and with Faculty of Philosophy – Department for pedagogy and andragogy. The system assumes that initial training candidates are evaluated by mentors and at the end of education they are passing the final exam, simulation of trial, evaluated by the commission. Continuous education is being evaluated through standard questionnaires, evaluating the following aspects, quality of lecturers and conditions of work. The further monitoring and evaluation enhancement shall be achieved through introduction of e-learning system, enabling more precise and complex measurement of different aspects of education process. | Judicial Academy High Judicial Council State Prosecutorial Council |  | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | Two-way evaluation system for monitoring of quality of initial, continuous and specialized training that allows the assessment of the results of training or degree of advancement of knowledge of the participants, as well as the assessment of the quality of the program and trainers developed and implemented | Аctivity is being successfully implemented. During the reporting period, the expert service of the Judicial Academy, performed continuous evaluation and monitoring of initial and continuous training, using previously developed instruments. For the purposes of evaluating and monitoring online trainings for non-discrimination for the beneficiaries of the initial training, special instruments have been developed to monitor the knowledge progress, assess the quality of training and participants satisfaction. Mentors of active generations of the beneficiaries of the initial training send reports on the work and progress of the beneficiary, which the expert service of the Judicial Academy collects and analyzes in order to improve the quality of initial training. During the 2nd quarter 2022, the expert service of the Judicial Academy, performed continuous evaluation and monitoring of initial and continuous training, using previously developed instruments. |
| 1.3.1.4. | The number of initial training participants is determined in accordance with the Human Resources Management Plan of the High Judicial Council and the State Prosecutorial Council and the objectives of the Human Resources Strategy for the Judiciary | High Judicial Council State Prosecutorial Council |  | II quarter of 2022 | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | Number of initial training participants determined in line with the Human Resources Strategy and Human resources management plan | Аctivity is being successfully implemented. At the session of the High Council of the Judiciary held on June 30, 2022, a decision was made to increase the number of participants of initial training who will enrol in the Judicial Academy by seven participants of initial training, so that the total number of participants of the 12th generation of initial training is 12. The number of participants is increased at the proposal of the Judicial Academy, taking into account the quality of candidates at the entrance exam and due to the number of judges retiring in the following period. |
| 1.3.1.5. | Implementation of measures for improvement of the Organization of the work of Judicial Academy such as: - Further development of the Center for Documentation and research - Adoption of a new act on systematization of jobs and strengthening of professional and administrative capacities, in accordance with planned program-Organizational changes | Judicial Academy |  | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | The Organization of work of the Judicial Academy as well as its administrative capacities improved | Аctivity is being successfully implemented. A new Act on job systematization of the Judicial Academy was adopted, which established new organizational units that should ensure the improvement of the quality of educational and organizational processes in the Academy. As a separate sector, the Sector for research and improvement of education was formed, which aims to, with the help of new tools that will be implemented within the new information system, the development of which was started in cooperation with UNDP, enable a proactive approach in defining annual training programs in the field of continuous as well as in the domain of the initial training of future judges and prosecutors and the Distance Learning Group, which completely takes over the management of databases related to the process of conducting ongoing training, the register of lecturers, the register of beneficiaries of trainings and the preparation of the Judicial Academy databases for connection to the personal sheets of the High Judicial Council and the State Prosecutorial Council (High Prosecutorial Council). Bearing in mind the necessity of strengthening other sectors and departments that deal with different types of training, as well as the need to establish an internal control mechanism through the position of internal control, the adopted systematization changes provide the necessary professional and administrative support for all business processes in the Academy and the scope that is necessary for the quality organization of the work process. Accordingly, the sector for the initial training was established, whose goal is to optimally organize tasks related to the organization of initial training with the use of new IT tools that are currently being developed in order to improve work in this area. In order to provide organizational and administrative support, an organizational unit for office affairs, office of the director and a special sector for coordinating the work of the Academy's regional centers were formed. At the same time, the sector for international cooperation and projects and the documentation and information center were redefined, by establishing separate organizational units. In accordance with that, the systematization of workplaces improved the organizational structure of the sector for the documentation and information center, so that separate workplaces were defined whose goal is to collect the ECtHR case-law and prosecutorial practice in the Republic of Serbia, their processing and linking and preparation of content for the Department's databases. As it is within the competence of the sector for documentation and information center and management of the electronic library of the Academy, by establishing positions whose job description includes tasks related to the management of this database, conditions are provided for starting the process of collecting, systematizing and processing additional work and educational materials. With these changes, the documentation center department is profiled as the foundation of the documentation center, with workplaces having a clearly defined role in the formation and maintenance of this center, as well as the role of the documentation center itself, which should support the work of the continuous and initial training sector through the collection of educational materials and multimedia contents. At the same time, the tasks of monitoring training programs through new specialized applications are entrusted to the Distance Learning Group, which includes the administration of all databases related to ongoing training (programs, beneficiaries, lecturers) as well as special applications for conducting online training (JARS LMS). However, most importantly, the sector for continuous education of judges and prosecutors was reorganized in accordance with the clear need to organize high-quality training for special areas of law, the planning and implementation of which is implemented in cooperation with the sector for research and improvement of education, with the use of new planning tools and analysis of conducted trainings. |
| 1.3.1.6. | Ensuring adequate infrastructural preconditions for the work of the Judicial Academy with increased capacities, through the adaptation and equipping of the adequate building in line with the decision of the Republic of Serbia Government, from the session held on April 9, 2015 on allocation of the building that is located in the center of Belgrade and has 2800 m2 | Judicial Academy Ministry of Justice |  | Reconstruction is in progress. | IPA 2015 (for improvement of Judicial Academy infrastructure) 3.000.000 € |  | Judicial Academy is properly structured and equipped, in material, human and infrastructure | Activity is being successfully implemented. The EU Delegation has ended the selection of the contractor. The signing of the contract between the EU Delegation and the Contractor is underway. |
| 1.3.1.7. | Continuous advancement of e-Academy | Ministry of Justice Judicial Academy |  | Continuously | Budget of the Republic of Serbia (Judicial Academy budget) 17.285 € Donor support is needed, which will be applied for in the coming period |  | Improving e-learning resources and number of users - mechanism for automatic generation of records on judges and prosecutors trained in certain areas (fight against corruption, ethics and integrity etc.) established; - mechanism for automatic data exchange and data synchronization between the databases of the Judicial Academy and the High Judicial Council and the State Prosecutorial Council established; - mechanism of automatic data exchange and data synchronization between the database of training users and the database of personal sheets of judges, prosecutors, court and prosecutorial staff established; - unique system of human resources, which includes a comprehensive record of initial training users with elements of statistical analysis established; - mechanism for transfer of personal sheets (personal files) of users of initial training into the database of personal sheets (personal file) of the High Judicial Council and the State Prosecutorial Council established; - register of mentors of the initial training users and training results of the initial training users established and automatically synchronized with the databases of judges and prosecutors; - register of engaged lecturers in continuous training programs that is automatically synchronized with the databases of judges and prosecutors established. | Аctivity is being successfully implemented. Work has started on the new website of the Judicial Academy, as well as on the application for the e-library, through the realization of a donation from the Council of Europe to the Judicial Academy. Since the e-library will also contain international agreements signed by the Republic of Serbia, with the aim of cross-linking them with domestic laws, the practice of domestic and international courts and other bodies, as well as the fact that a Protocol on cooperation with the Ministry of Foreign Affairs has been signed with the aim of developing this e-library segment, the administrative part of the application will be available to both JARS and the MFA. The implementation of the new technical solution of the website and the establishment of the e-library in accordance with the technical specification are in progress. With the development of a new information system that includes the establishment of databases of users, lecturers and training programs, which was started in cooperation with UNDP, the development of a system that will be connected to the databases of personal sheets of the HJC and SPC, so that through the web service, the information systems of these institutions take over data on training participants. At the same time, in order to establish a unique system for monitoring the activities of training users, the development of an application for monitoring the initial training was started, which will be connected to the databases of seminar users, whether they refer to initial or continuous training, and in this way it will be possible the creation of the so-called personal sheets of the beneficiaries of the initial training, which will contain data on all activities of the beneficiaries of the initial training and education that they have undergone at the Judicial Academy. The development of a new application for personnel affairs has also begun, which aims to consolidate a wide set of records on employees and beneficiaries of the initial training as employees of the JARS under a special type of contract. At the same time, this application should facilitate the work of the personnel department and enable the realization of the concept of a single source of data in accordance with the ICT Development Strategy in the Republic of Serbia. |
| 1.3.1.8. | Development of special training programs for judicial/ prosecutorial assistants in accordance with the new constitutional solutions and with the aim of enabling career advancement. | Judicial Academy |  | II - III quarter of 2022 | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | Special training programs for judicial/prosecutorial assistants developed | Activity is being successfully implemented. In the reporting period the Annual Trainings Program was adopted and the relevant program of trining is a part of this Annual Trainings Program and also special training programs for judicial and prosecutorial assistants have been developed. Now the adoption of the Law is awaited. |
| 1.3.1.9. | Further development of the cooperation of the Judicial Academy with its EU counterparts in the European Judicial Training Network (EJTN) and ensure participation of judges and prosecutors in EJTN's activities: - by inserting the financial support of these activities in the annual national IPA programme and - by preparing the adoption of a Memorandum of understanding with DG Justice to take part in the Justice programme (and enable the costs of participation in EJTN's activities to be covered by the operating grant that the EJTN receives from DG Justice) | Judicial Academy |  | Continuously | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  | Number of activities of the EJTN activities in which the Judicial Academy has taken part in Judges and prosecutors take part in training seminars and exchanges of the EJTN and its members. | Аctivity is being successfully implemented. During the I quarter of 2022, an online study visit to the Court of Justice of the European Union was held. Also, the beneficiaries of the initial training of the Judicial Academy, with their mentor, applied for participation in this year’s THEMIS 2022 competition. Also, within the cooperation with the EJTN and the implementation of the EJTN program, Judicial Academy signed an Agreement with the Academy of European Law (ERA). During the II quarter of 2022, one online study visit to the European Court of Human Rights was held, where there were five participants from Serbia. Also, the beneficiaries of the initial training of the Judicial Academy, with their mentor, participated in THEMIS 2022 competition. |
| INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |
| 1.3.2. Serbia ensures that training needs are evaluated as part of the performance assessments of judges and prosecutors. |  |  |  | The assessment of training needs is part of the performance appraisal of judges and public prosecutors. |  |  | 1. High Judicial Council and the State Prosecutorial Council refer judges and public prosecutors to continuous training based on the results of their performance appraisal, and based on the results of the evaluations from previous trainings; 2. Annual curriculums of trainings for judges and public prosecutors are proposed and adopted taking also into account performance appraisal results of judges and public prosecutors. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.3.2.1. | Defining criteria for referring judges to additional training based on the following: - performance appraisal results; - the results of the evaluations from previous trainings and - according to the results of performance appraisal. | High Judicial Council Judicial Academy |  | Defining criteria: II quarter 2022 Referring: Continuously | Budget of the Republic of Serbia 32.603 €: For defining criteria: 17.285 €; For referring judges to additional training: 5.106 € |  | An amended legislative framework concerning the criteria for additional training of judges The prescribed criteria for additional training High Judicial Council refers judges to additional trainings (which are implemented by Judicial Academy), according to criteria set in advance in accordance to the performance appraisal results and in accordance with the results from the evaluations from previous trainings. | Activity is not implemented. The Council has started activities aimed at improving the process of evaluating the work of judges, as well as at strengthening the capacities of the Judicial Academy to adequately respond to the training needs of judges, especially in terms of referring judges to training as a result of the evaluation of their work. In this regard, at the session of the High Council of the Judiciary, held on June 30, 2022, the Council considered the adoption of a decision to send one judge, after the evaluation process determined an "unsatisfactory" grade, to mandatory training at the Judicial Academy , in accordance with paragraph 1, article 26b of the Rulebook on criteria, standards, procedure and bodies for evaluating the work of judges and presidents of courts., which decision will subsequently be published on the Council's website. |
| 1.3.2.2. | Defining criteria for referring public prosecutor’s office holders to additional trainings based on: - performance appraisal results, - the results of evaluations from previous trainings and - according to the results of performance appraisal. | State Prosecutorial Council Judicial Academy |  | Defining criteria: II quarter 2022 Referring: Continuously | Budget of the Republic of Serbia 32.603 €: For defining criteria: 17.285 €; For referring judges to additional training: 5.106 € |  | An amended legal framework concerning the criteria and criteria for additional training of public prosecutors The prescribed criteria for additional training The State Prosecutorial Council refers public prosecutor’s office holders to additional trainings (which are implemented by Judicial Academy), according to criteria set in advance in accordance to the performance appraisal results and in accordance with the results from the evaluations from previous trainings. | Activity is being implemented sucessfully. On April 15th 2022, by the decision of the Minister of Justice, the Working Group for drafting the Law on Public Prosecution Office and the Law on High Prosecutorial Council as well as the Working Group for drafting the Law on Judges, the Law on High Judicial Council and the Law on Organisation of Courts. The working groups include representatives of the Ministry of Justice, judges, public prosecutors, proffessional associations, academic society and attorneys. In the reporting period, each of the working groups held 6 meetings. |
| 1.3.2.3. | Preparation of the annual program for training of judges, taking also into account the evaluation of the performance of judges and evaluation of trainings performed | High Judicial Council Judicial Academy |  | Continuously once a year | Budget of the Republic of Serbia 17.285 € |  | Annual program for training of judges proposed and adopted Percentage of the annual program for training of judges realized | Аctivity is being successfully implemented. The annual training program for judges was adopted in the first quarter at the session of the Program Council. The trainings are realized in accordance with the plan of realization dynamics. |
| 1.3.2.4. | Preparation of the annual program for training of public prosecutors, taking also into account the evaluation of the performance of public prosecutors and evaluation of trainings performed | State Prosecutorial Council Judicial Academy |  | Continuously, once a year | Budget of the Republic of Serbia 17.285 € |  | Annual program for training of public prosecutors proposed and adopted Percentage of the annual program for training of public prosecutors realized | Аctivity is being successfully implemented. The annual training program for public prosecutors was adopted in the first quarter at the session of the Program Council. The trainings are realized in accordance with the plan of realization dynamics. |
| INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |
| 1.3.3. Serbia conducts a comprehensive assessment of its court and prosecution network with a focus on costs and allocated resources, efficiency, workload and access to justice prior to taking any further steps in the development of the court and prosecution network. |  |  |  | Comprehensive analysis of the costs, efficiency and access to justice as the foundation for considering whether further steps are needed in the reform of the court network. |  |  | Regular monitoring of data using clear, previously defined methodology: - number of cases per 100 000 inhabitants; - number of courts and public prosecutors’ offices per 100 000 inhabitants; - number of judges and public prosecutors per 100 000 inhabitants; - average and maximum distances of courts and public prosecutors’ offices from settlements on the territory of that court or public prosecutor’s office; - the conditions and scope of the exercise of the right to free legal aid; - the conditions and scope of the exercise of the right to a legal remedy; - the amount of court fees; - the number of cases per court and public prosecutor’s office; - the number of cases per judge and per public prosecutor; - the number of cases in subject-matter per judge - the costs of operation of the judicial network, including the structure of the costs; - duration of court proceedings (according to the matter) on average; - number of backlogged cases; - number of old cases; - number of admitted applications before the European Court of Human Rights relating to the violation of the right to trial within a reasonable time. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.3.3.1. | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis, especially on the following: - judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; - needs and scope of workload analysis; workload of judges and public prosecutors especially taking into account human, financial and technical resources and possible further changes in structure of courts, recruitment and education of staff. (The same activity 1.3.4.1. and 1.3.5.1.) | Ministry of Justice, with the support of: High Judicial Council State Prosecutorial Council Judicial Academy, Supreme Court of Cassation and Republic Public Prosecutor’s Office. |  | IV quarter 2020 | Budget of the Republic of Serbia 30.878 € |  | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis produced | Activity is not implemented The new World Bank Functional Analysis is not finalized. The Ministry of Justice and the Supreme Court of Cassation commented on the Draft of the Functional Analysis that was provided by the World Bank to the Supreme Court of Cassation. |
| 1.3.3.2. | Establishing a new network of administrative courts (the two instance of the administrative justice) in line with prior analysis of concept, model and needs |  | Ministry of Justice High Judicial Council | I quarter 2023 | Budget of the Republic of Serbia 30.878 € |  | Two instances of the administrative justice network established Ensured access to justice and appeal procedure. |  |
| 1.3.3.3. | Strengthening the capacity of the administrative judiciary in terms of selecting a sufficient number of judges and court staff |  | Ministry of Justice High Judicial Council | Continuously | Budget of the Republic of Serbia Budgeted withing the activity 1.3.3.2., and the dynamics of strengthening the human resources of the administrative judiciary will be known after the implementation of activities 1.3.3.2. |  | Sufficient capacity at all levels Reduced number of cases Reduced processing time |  |
| 1.3.3.4. | Further improving of the infrastructure judicial network, improvement of infrastructure and internal procedures, according to results of mid-term assessment from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1. |  | Ministry of Justice High Judicial Council State Prosecutorial Council Supreme Court of Cassation Republic Public Prosecutor’s Office | Continuously | Budget of the Republic of Serbia It is necessary to wait for the results of the medium-term assessment from activities 1.3.3.1, 1.3.4.1. and 1.3.5.1. |  | Undertaken reform steps on correction of infrastructure of the judicial network, improvement of infrastructure and internal procedures, according to results of assessment of judicial network. | Аctivity is being successfully implemented. Over 300 locations were successfully transferred to the new Telekom provider with faster links, while the network of the Orion provider remained as a secondary link, thus fulfilling all standards and procedures for providing the network service. |
| INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |
| 1.3.4. Serbia adopts and implements a human resources strategy for the entire judiciary, leading to a measurable improvement in the workload spread, efficiency and effectiveness of the justice system. |  |  |  | Human resource strategy for the judiciary, based on an analysis of needs and workload, and bearing in mind possible further changes in the structure of courts, recruitment and training adopted and implemented. |  |  | Clear staffing situation in the reformed judiciary established, the needs are defined and adequately provided, and it is taken care to the greatest extent possible, that the workload is evenly distributed through the system. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.3.4.1. | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis, especially on the following: - judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; - needs and scope of workload analysis; workload of judges and public prosecutors especially considering human, financial and technical resources and possible further changes in structure of courts, recruitment and education of staff. (The same activity 1.3.3.1. and 1.3.5.1.) | Ministry of Justice, with the support of: High Judicial Council State Prosecutorial Council Judicial Academy, Supreme Court of Cassation and Republic Public Prosecutor’s Office. |  | IV quarter 2020 | Budget of the Republic of Serbia Budgeted withing the activity 1.3.3.1. |  | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis produced | Activity is not implemented The new World Bank Functional Analysis is not finalized. The Ministry of Justice and the Supreme Court of Cassation commented on the Draft of the Functional Analysis that was provided by the World Bank to the Supreme Court of Cassation. |
| 1.3.4.2. | Work on the drafting of the Human Resources Strategy for the judiciary, in accordance with the results of the impact analysis from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1., which will, inter alia, address the following questions: - adopting a rulebook on the criteria for determining the required number of holders of judicial functions, taking into account the working conditions, the number of cases, the structure and complexity of the cases in which the court is performing; - adoption of rules on criteria for determining the required number and structure of judicial and prosecutorial assistants; - adoption of rules on criteria for determining the required number and professional structure of administrative staff in the judiciary |  | Ministry of Justice High Judicial Council State Prosecutorial Council | Commencing from 2019 – working group of the Ministry of Justice | Budget of the Republic of Serbia 30.878 € |  | Human Resource Strategy in judiciary prepared and presented for public discussion addressing inter alia, the following questions: - The number and structure of judges and prosecutors; - Status, number and structure of judicial assistants and prosecutorial assistants; - Management, number and professional structure of administrative staff in the judiciary. | Activity is fully implemented. The Government of the Republic of Serbia adopted the Strategy of Human Resources in the Judiciary for the period 2022-2026 ("Official Gazette of RS", No. 133/21 of 31 December 2021) |
| 1.3.4.3. | Adoption of the Human Resource Strategy for the judiciary |  | Ministry of Justice | II quarter 2022 | Budget of the Republic of Serbia Negligible cost activity |  | Human Resource Strategy adopted | Activity is fully implemented. The Strategy was adopted by the Government of the RS on 29 December 2021. |
| 1.3.4.4. | Monitoring on the implementation of Human Resource Strategy in judiciary in order to achieve more effective / more optimal planning, recruitment, deployment, motivation and promotion within the judiciary |  | Ministry of Justice High Judicial Council State Prosecutorial Council Supreme Court of Cassation RPPO Judicial Academy | Annual Reporting on its implementation | Budget of the Republic of Serbia 59.514 € Per year 19.838 €- Preparation of reports – 2.553€ Supervision – 17.285 € |  | Efficient implementation of the Human Resource Strategy in judiciary. Effective / more optimal planning, recruitment, deployment, motivation and promotion within the judiciary in place | Activity is being successfully implemented. The EU Project „Support to reform of judiciary in Serbia“ which is implemented by the Council of Europe has initiated the procedure of engaging the experts in order to conduct the activities from the Strategy’s Action Plan which are related to drafting of analysis and which activities will be due during 2022. |
| 1.3.4.5. | Establishing human resources databases in all prosecutors’ offices |  | State Prosecutors Council Ministry of Justice | IV quarter 2023 | Budget of the Republic of Serbia 17.285 € |  | Human resources databases established in all PPOs | Activity is being successfully implemented. In the period from 1.3 to 18.3.2022. Workshops were held on the functioning of the information system for financial and human resources management. In the period from June 6 to September 2, 2022, a continuation of workshops related to the functioning of the information system for financial and human resources management will be held. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |
| 1.3.5. Ensure herewith a sustainable solution for workload imbalances. |  |  |  | Established efficient system for balancing the workload for judges and public prosecutors, taking into account Programs on case weighting methodology in all courts and PPO |  |  | - Number of cases per court; - Number of cases per public prosecutor’s office; - Number of cases per judge; - Number of cases per public prosecutor or deputy public prosecutor. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEADLINE | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |
| 1.3.5.1. | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis, especially on the following: - judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; - needs and scope of workload analysis; - workload of judges and public prosecutors especially taking into account human, financial and technical resources and - possible further changes in structure of courts, recruitment and education of staff. (The same activity 1.3.3.1. and 1.3.4.1.) | Ministry of Justice, with the support of: High Judicial Council State Prosecutorial Council Judicial Academy Supreme Court of Cassation and Republic Public Prosecutor’s Office. |  | IV quarter 2020 | Budget of the Republic of Serbia Budgeted within the activity 1.3.3.1. |  | Comprehensive impact analysis of the reforms implemented in the judiciary after the 2014 World Bank functional analysis produced | Activity is not implemented The new World Bank Functional Analysis is not finalized. The Ministry of Justice and the Supreme Court of Cassation commented on the Draft of the Functional Analysis that was provided by the World Bank to the Supreme Court of Cassation. |

| 1.3.5.2. |  | Based on the assessment and analysis from activity 1.3.5.1. defining measures to establish a sustainable solution to the problem of unequal workload of judges and public prosecutors with the number of cases: - periodic monitoring of the required number of judges and public prosecutors for each court / public prosecutor - transfer of judges / public prosecutors according to established criteria and criteria - delegation ("overflow") of cases in accordance with the statutory criteria | High Judicial Council State Prosecutorial Council Ministry of Justice |  |  |  | Annually |  |  | Budget of the Republic of Serbia Budgeted withing the activity 1.3.5.3. |  |  | Unequal burden per court and per PPOs removed |  |  |  | Activity is not implemented The new World Bank Functional Analysis is not finalized. The Ministry of Justice and the Supreme Court of Cassation commented on the Draft of the Functional Analysis that was provided by the World Bank to the Supreme Court of Cassation. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.5.3. |  | Monitoring of the implementation of the Human Resource Strategy in the judiciary which contribute to the functioning of an efficient system for equalizing the burden on judges and public prosecutors with the number of cases | High Judicial Council State Prosecutorial Council Ministry of Justice Judicial Academy Supreme Court of Cassation and Republic Public Prosecutor’s Office |  |  |  | Annual Reporting |  |  | Budget of the Republic of Serbia 38.295 € |  |  | Unequal burden per judges / public prosecutor / deputy public prosecutor removed |  |  |  | Activity is being successfully implemented. The EU Project „Support to reform of judiciary in Serbia“ which is implemented by the Council of Europe has initiated the procedure of engaging the experts in order to conduct the activities from the Strategy’s Action Plan which are related to drafting of analysis and which activities will be due during 2022. |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.3.6. Serbia implements its national backlog reduction programme - including through promoting the use of various alternative dispute resolution mechanisms - and establishes an initial track record of a sustainable decrease in the backlog of court cases. |  |  |  |  |  |  | Coherent implementation of the backlog reduction program and efficiently introduced alternative dispute resolution tools. |  |  |  |  |  | - Sustainable trend of reducing the average duration of court proceedings (per matter); - Sustainable trend of reducing the total number of backlogged (in particular old) cases; - Number of disputes resolved before mediator in one year; - Number of transactions concluded via public notaries. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 1.3.6.1. | Amending а Civil Procedure Code in order to improve efficiency particularly in part which deals with service of documents, hearing recording and discipline during the proceedings, particularly taking into account EU standards and practices of the ECtHR and the Constitutional Court |  |  |  |  | Ministry of Justice National Assembly | II quarter 2021 |  |  | Budget of the Republic of Serbia 71.136 € |  |  | Amending а Civil Procedure Code, whose provisions encourage efficiency, and particularly in the part relating to service of documents, recording of hearings and procedural discipline, aligned with EU standards and practices of the ECtHR and the Constitutional Court. |  |  |  | Activity is partially implemented. The draft law has been prepared. An extended working group with representatives of the Serbian Bar Association will further discuss the draft and prepare the final text. |  |  |
| 1.3.6.2. | Amending Criminal Procedure Code in order to improve efficiency of the proceedings in particular in part dealing with service of documents, trial recording and discipline during the proceedings taking into account EU standards, jurisprudence of the ECtHR and the Constitutional Court |  |  |  |  | Ministry of Justice National Assembly | II quarter 2021 |  |  | Budget of the Republic of Serbia 71.136 € USAID Project “Rule of Law” (50.000 $) |  |  | Adopted new Criminal Procedure Code, which provisions improve efficiency, particularly in part dealing with service of documents, trial recording and discipline during the proceedings aligned with EU standards, jurisprudence of the ECtHR and the Constitutional Court |  |  |  | Activity is not implemented. By the Decision of the Minister of Justice No. 119-01-126 / 2021-05 of 12 May 2021, a Working Group for the Analysis of Criminal Procedure was established in order to identify and eliminate the shortcomings of the CPC and prepare the Draft Law on Amendments to the Criminal Procedure Code based on the results of the analysis. The adoption is planed for IV quarter of 2022. |  |  |
| 1.3.6.3. | Adoption of the Uniform backlog reduction program for the period 2021-2025 in accordance with the implementation results achieved |  |  |  |  | Supreme Court of Cassation Ministry of Justice | IV quarter 2020 |  |  | Budget of the Republic of Serbia 17.285 € ''EU for Serbia – Support to the Supreme Court of Cassation'' (12.000 €) |  |  | Uniform backlog reduction program for the period 2021-2025 adopted |  |  |  | Аctivity is fully implemented In the first quarter of 2021, namely on February 5, 2021, the President of the Supreme Court of Cassation adopted a new Unified backlog reduction programme in the Republic of Serbia for the period 2021-2025. The new Unified programme for resolving old cases determines the measures to be taken to improve the efficiency of the courts: systemic measures (4) relating to the position of the judicial staff, filling up judge vacancies and court staff vacancies, trainings for implementation of the Law on Mediation and other laws necessary to apply the alternative dispute resolution and backlog reduction mechanisms, training for work in all existing case management applications in order to use their functionalities in a standardized manner, propose amendments to the Law on Civil Procedure etc. Further the general measures are envisaged (5). They include passing individual backlog reduction programmes in a standardised manner, in electronic form, passing individual backlog reduction plans for judges and active role of the courts’ presidents with that regard, establishing teams for monitoring the implementation of individual backlog reduction programmes etc. The special measures have been envisaged for pending enforcement cases (8.), measures to be taken by the Supreme Court of Cassation and courts, and in particular the courts in the territory of the City of Belgrade, as well as measures that should be taken by the Ministry of Justice ( 9 - 12). Regarding objectives (13) envisaged by the new Unified programme for the period 2021-2025, the total number of pending cases in courts in the Republic of Serbia remaining at the end of 2020 – 1,510,472 cases – should be reduced to 1,000,000 cases, thus reducing the share of backlog cases in the total number of pending cases, based on the current number of incoming cases, to 2,61%. |  |  |
| 1.3.6.4. | Monitoring the implementation of the Uniform backlog reduction program through holding regular meetings of the Working Group for the implementation of the Uniform Backlog Reduction Program |  |  |  |  | Supreme Court of Cassation Ministry of Justice | Quarterly, commencing from I quarter 2021 |  |  | Budget of the Republic of Serbia 10.212 € and budged withing the activity 1.3.6.3. |  |  | Number of meetings of the Working Group for the implementation of the Uniform Backlog Reduction Program held Number of interventions proposed and implemented |  |  |  | Аctivity is being successfully implemented. During the first quarter of 2022, the Annual Report on Work of Courts for 2021, was finalized. Within this Report the analysis and developments on backlog cases disposition has been given, and including the implementation of the Unified Backlog Reduction Programme 2021-2025. Through the implementation of measures from the strategic documents Supreme Court of Cassation has shown in this report the number of pending backlog cases from 2019, bearing in mind the Amendments to the Court Rules of Procedure regarding definition of backlog case (proceeding lasting more than three years since the date of filing the initial act). On July 1, 2022, Working Group for the implementation of the Unified Backlog Reduction Program session was held. According to the decision of the President of the Supreme Court of Cassation, appointed chair of the Working Group is Ms. Dragana Boljević, Justice of the Supreme Court of Cassation. Working group session involved discussion on measures to be implemented in order to reduce the backlog, especially in civil matter, in accordance with the Unified Backlog Reduction Program for the period 2021-2025. During the first quarter of 2022, the Annual Report on Work of Courts for 2021, was finalized. Within this Report the analysis and developments on backlog cases disposition has been given, and including the implementation of the Unified Backlog Reduction Programme 2021-2025. The adopted Conclusions from this session included the determination of new assignment of responsibilities for monitoring the disposal of old cases in Basic and Higher Courts in all four appellate areas (Belgrade, Novi Sad, Niš and Kragujevac), as well as Commercial Courts, Misdemeanor Courts, as well as state-level courts (Commercial Appellate Court, Misdemeanor Appellate Court and the Administrative Court). The dynamics of working group meetings on a quarterly basis have been established. The idea was put forward to propose to the President of the Supreme Court of Cassation to recommend to the presidents of the courts that the newly elected judges be assigned with such structure of cases that will correspond to the average structure, number and age in the specific department of the court to which the judge is assigned, or to assign those judges to the vacant panel of the former judge which is to be made average. Also, a proposal was submitted to the High Judicial Council to consider the possibility of forming a mini-court department for disposal of backlog cases (or else appointing several judges in the court to this purpose), with the previous consent of those judges who would be entrusted with such cases. If adopted, this is to be accompanied with drafting appropriate regulations regarding the influx of cases, standards per judge to be achieved and evaluation of the work of judges in those chambers. The idea was put forward to submit a proposal to the President of the Supreme Court of Cassation, the High Judicial Council and the Ministry of Justice to consider jointly the possibility of hiring retired judges in connection with possible measures for more accurate disposal of backlog cases. It has been concluded that the Draft Table with the necessary data for monitoring the disposal of backlog cases is to be submitted to the Ministry of Justice. |  |  |
| 1.3.6.5. | Follow-up of the implementation of functionality of automatic electronic scheduling of hearings |  |  |  |  | Ministry of Justice | Continuously |  |  | Budget of the Republic of Serbia 15.318 € |  |  | Regular report on number of hearings which have been automatically scheduled and report on number of reasons for delaying hearing selected from drop-down menu extracted from AVP. |  |  |  | Аctivity is being successfully implemented 1st quarter 2022: Report on the reasons for postponing hearings selected from the drop-down menu in the AVP application is available, so since the beginning of the application of this module, 6.049.570 hearings have been registered in all courts, while 343.042 hearings have been postponed for the following reasons: For the purpose of obtaining / presenting evidence: 207991 Prevention of the judge: 27709 The conditions for holding a hearing / hearing were not met: 135395 Concluded discussion: 10 Date changed: 913 Judgment rendered: 157 Lawsuit withdrawn: 159 2nd quarter 2022: In order to establish regular reporting on the number of hearings, the possibility of automatically proposing and scheduling the next date for the hearings was implemented, depending on the reason for the delay. It is also possible to report on the reasons for the postponement of hearings selected from the drop-down menu in the AVP application, so since the beginning of the application of this module in all courts, 6,966,592 held hearings have been recorded, while 514,559 hearings have been postponed for the following reasons: In order to obtain/provide evidence: 264741 Prevention of the judge: 48479 The conditions for holding a hearing/hearing have not been met: 199464 Concluded discussion: 10 Change of date: 1329 Judgment rendered: 248 Lawsuit withdrawn: 288 |  |  |
| 1.3.6.6. | Increase in the number of statistical parameters for efficiency of the judiciary which may be monitored via ICT and further development of the centralized systems of judicial bodies for the purpose of implementing central statistics. |  |  |  |  | Ministry of Justice | IV quarter 2021 |  |  | Budget of the Republic of Serbia 367.205 € Public procurement for the extension of the functionality of the system of unified reporting and data storage of judicial authorities in 2020 – 349.920 € (part of total budget) |  |  | System for central statistical reporting and unified reporting and data storage of judicial authorities extended so that statistics are automatically collected from both commercial and misdemeanor courts and integrated into Business Intelligence (BI) tools. Court Rules adapted to the compilation of mandatory reports from the central statistics tool. |  |  |  | Аctivity is being successfully implemented. On the system for central statistical reporting, reports related to the work of basic, higher, appellate, commercial and Administrative Courts and a part of the report on the work of misdemeanor courts have been established. Special reports on cases of domestic violence have been established in basic, higher and appellate courts and a report on the work of commercial courts where the basis of the dispute is land ownership, which will also be available on the Government Open Data Portal. In the reporting period, the so-called traffic lights reports which are showing the current status of the number of received, resolved, total pending cases, the number of currently unresolved cases by court and type of court, together with an overview of the coefficient of overcoming inflows, which aim to give a graphical presentation of work of the cours via the website of the Ministry of Justice and the Central Statistics System, were implemented also. The importance of this type of reporting is that it introduces daily reporting, in addition to the usual reporting done in relation to the Court Rules defined periods, which is the basis for automating reporting on the work of courts and the establishment of modern statistical-analytical reporting |  |  |
| 1.3.6.7. | Advance utilization of existing capacities through enhanced case management efficiency and enabling monitoring the duration of court proceedings in real time |  |  |  |  | Ministry of Justice | Continuously |  |  | Budget of the Republic of Serbia 533.405 € Public procurement for the improvement of the work of the courts through the identification and documentation of business processes – 76.271 € Ongoing public procurement Extending the functionality of the integrated reporting and storage system for judicial authorities – 457.134 € |  |  | Identified, linked and documented various business processes in work of judicial authorities for achieving optimization Upgraded CMS to accomplish tasks without explicit human-operator management with functionalities of automatization of simpler tasks and procedures. Increased number of digitized and automated procedures. Decrease in average speed of case resolution. |  |  |  | Activity is being successfully implemented. Two public procurements were conducted in the total value of 139 million dinars, which provided hardware equipment and appropriate licenses for strengthening the capacity of data centers. The importance of additional equipment related to new storage capacities for data migration to centralized systems is particularly important |  |  |
| 1.3.6.8. | Analyses and, if necessary, adopt amendments to Law on Notaries and the set of accompanying laws, in accordance with EU standards, based on the results of implementation. |  |  |  |  | Ministry of Justice Government of the Republic of Serbia National Assembly | IV quarter 2021 |  |  | Budget of the Republic of Serbia 71.136 € |  |  | Quality control system is improved. |  |  |  | Activity is not implemented. The analysis has been delayed. |  |  |
| 1.3.6.9. | Drawing up and adopting remaining by-laws and Chamber regulations envisaged in Law on Notaries such as: - The act of the Minister in charge of the judiciary referred to in Article 70 of the Law on Public Notary on the electronic format and conditions that the notary public document, which is made in electronic form, and which has not been printed on the paper, must fulfill it in order to be considered a public notary - Public Notary Rules and other acts that enable the digitization of notaries |  |  |  |  | Minister of Justice Chamber of Public Notaries | IV quarter 2021 |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.6.8. |  |  | By-laws and Chamber of Notaries regulations envisaged in Law on Notaries adopted. |  |  |  | Аctivity is being successfully implemented The Executive Board of the Serbian Notary Chamber (the SNC) prepared the Draft Rules of Procedure Amending and Supplementing the Notarial Rules of Procedure and submitted it to the members of the Chamber for familiarization with the same. An expert has been hired within the EU Project "EU for Justice - Support for Chapter 23" to conduct an analysis regarding the act of the Minister of Justice from Article 70 of the Law on Notary Public and to draft a bylaw. The Assembly of the Serbian Notary Chamber (the SNC), at the session, held on 10 April 2022, adopted the Rules of Procedure Amending and Supplementing the Notarial Rules of Procedure, which were published, after obtaining the approval from the Ministry of Justice, in the Official Gazette of the RS No. 59-2022. The final text with amendments/supplements is available on the Website of the SNC, link: https://www.beleznik.org/public/documents/upload/JAVNOBELE%C5%BDNI%C4%8CKI%20POSLOVNIK%20(Sl.%20glasnik%20RS,%20br.62-2016,%2066-2017,%2048-2018,%2054-2018,%20151-2020%20i%2059-2022).pdf On 20 June 2022, the representatives of the SNC held meetings with the persons engaged in the Project „EU for Justice – Support for Chapter 23“ for the purpose of preparing the drafts of amendments to the valid statutory requirements and regulations, as well as of adoption of the act of the minister in charge of the judiciary referred to in Article 70 of the Law on Notaries and the requirements that a notarial instrument/act made in electronic form must meet. |  |  |
| 1.3.6.10. | Conducting of notary state exam and appointment of additional number of notaries, in accordance with the Law on the Notaries and rulebook on the number of notaries’ positions and the official seats of notaries. |  |  |  |  | Ministry of Justice Chamber of Public Notaries | Continuously |  |  | Budget of the Republic of Serbia 7.149 € |  |  | Number of candidates for notaries increased; Increased number of notaries. Notaries for the territory of all basic courts appointed; |  |  |  | Аctivity is being successfully implemented As at 13 April 2022, 224 notaries were engaged in the activity in the territory of the Republic of Serbia. The list of notaries and their contact data, along with the interactive map, is available on the Website of the Notary Chamber: http://beleznik.org/index.php/sr/pronadi-svog-javnog-beleznika/spisak-javnih-beleznika-i-kontakti. The Ministry of Justice: In the reporting period, 1 decision was made on approving the announcement of a competition for public notaries; 1 decision was made on the appointment of public notaries (for the areas of the Basic Court in Belgrade); 4 decisions on approving the announcement of a competition for public notary assistants (for the areas of Basic Courts in Belgrade, Novi Sad, Kraljevo) were made; 3 decisions on the appointment of notary assistants (for the areas of basic courts in Belgrade) were made; One regular exam period for taking the notary public exam was organized and conducted. A total of 25 decisions were made on the approval of taking the notary public exam. A total of 9 candidates passed the notary public exam in the reporting period. Certificates of passing the notary public exam were prepared for 9 candidates. Statistical data on the number of candidates who took the exam in each exam period were updated. Chamber of public notaries:Further to the competition for appointment of notaries, published in the Official Gazette of the RS No. 48-2022 on 15 April 2022, which was administered by the Serbian Notary Chamber, the minister of justice issued the decision on appointment of a notary for the territory of the Third Basic Court in Belgrade, the City Municipality of New Belgrade. As at 6 July 2022, 226 notaries were engaged in the activity in the territory of the Republic of Serbia. The list of notaries and their contact data, along with the interactive map, is available on the Website of the Notary Chamber: https://www.beleznik.org/kancelarije |  |  |
| 1.3.6.11. | Promotion of public notary system |  |  |  |  | Ministry of Justice Chamber of Public Notaries | Continuously |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.6.10. |  |  | Benefits of notary system and results of work of notaries periodically presented |  |  |  | Аctivity is being successfully implemented In the first quarter of 2022, the SNC proceeded with the continuous work on the promotion of the notary activity. In this period, the central activity was related to the carrying on of the campaign „You are asking notaries“ in cooperation with the daily newspaper Blic and the accompanying portal. This campaign was initiated as a project by the Serbian Notary Chamber. In the course of its conducting, which was initiated on 15 November, and finished on 2 March, 24 texts were posted online, six texts for the printed edition, and 167 questions of citizens were answered to. Upon the finalization of the project, a detailed report was made which also presented the datum that, in the category specifically set up on the blic.rs portal, for the requirements of the project, there were 214,647 browsed Web pages. From the analytical data on this project, it follows that the campaign was successfully carried on and that it attracted a great attention of the public reading Blic. The online category „You are asking notaries“ was often on the list of the most browsed categories, particularly on the days when packages of answers were posted. In the first quarter of this year, the migration of data to the new Web portal was completed and its operation was tested in the course of March, relevant corrections were made, and all the data important for communication of notaries with the citizens were checked. Also, in the course of the first quarter of 2022, the SNC continued with the proactive cooperation with the media. All the 25 media queries from the sphere of competence of notaries were responded to, in which responses the affairs from the sphere of competence of notaries were also explained. In the second quarter of 2022, the SNC proceeded to work on the promotion of the notary activity. In the second quarter, at the session of the Executive Board, held on 8 June 2022, the Communication Strategy of the Serbian Notary Chamber was adopted for the period from 1 July 2022 to 1 July 2024. The Strategy included the plans-a for the promotion of the notary activity within the next two years, as well as the Communication Strategy for the purpose of strengthening of the reputation of the notary activity, which will be implemented within the next two years. In the second quarter of this year, after the period of testing and date migration, the new Website of the SNC has become fully functional. On a daily level, it is updated with new data and it provides full insight into contacts and the working hours of all the notary offices in Serbia, as well as into the activities of the SNC. Also, the SNC continued to proactively cooperate with the media. Answers were provided to 30 media queries, and we also proactively sent the communications containing service information from the sphere of competence of notaries to the media. The President of the Chamber participated in the work of the General Assembly of the Council of the Notaries of the EU, which was held in Italy, Como, on 24 June 2022. From 15 to 17 April 2022, the representatives of the Chamber participated in the Belgrade Conference of Jurists when the notary profession was presented to the students of the Faculty of Law. |  |  |
| 1.3.6.12. | Regular implementation of trainings for public notaries |  |  |  |  | Judicial Academy Chamber of Public Notaries | Continuously |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.1.1. |  |  | Trainings for notaries are organized regularly Number of trainings held increased Number of participants increased |  |  |  | Activity is being successfully implemented On 29 and 30 March 2022, the notaries and the employees in the notary offices participated in a two-day online training on the topic of more detailed familiarization with the functioning of the Register of issued and revoked powers of attorney, which had been developed by the Ministry of Justice with the support of the Project „EU for Justice – Support for Chapter 23“. In May and June, the notaries and employees in notary offices participated in a two-day online training on the topic of more detailed familiarization with the functioning of the Register of Testaments, which had been developed by the Ministry of Justice with the support of the Project „EU for Justice – Support for Chapter 23“. |  |  |
| 1.3.6.13. | Development and adoption of a strategic framework for improving the application of mediation |  |  |  |  | Ministry of Justice Supreme Court of Cassation | I – II quarter 2021 |  |  | Budget of the Republic of Serbia 17.285 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | Strategic framework for improving the application of mediation prepared and adopted |  |  |  | Аctivity is not implemented The Strategy has not been adopted. |  |  |
| 1.3.6.14. | Implementation of a strategic framework for improving the application of mediation and monitoring of its effective implementation |  |  |  |  | Ministry of Justice Supreme Court of Cassation | Continuously, starting from the adoption of the mediation strategic framework |  |  | Budget of the Republic of Serbia See the budget under the activity 1.3.6.13. IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | Periodical reports on the implementation of the strategic framework developed and published. |  |  |  | Activity is not implemented The Strategy has not been adopted. |  |  |
| 1.3.6.15. | Creation and adoption of laws regulating mediation, mediation conditions, rights and duties of mediators, and training program for mediators |  |  |  |  | Ministry of Justice Government National Assembly | II quarter of 2021 |  |  | Budget of the Republic of Serbia 71.136 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | The law was adopted in accordance with the standards of mediation contained in the acts of the United Nations, the European Union and the Council of Europe and in line with the objective of Directive 2008/52 / EC on certain aspects of mediation in civil and commercial matters ("establishing a balance between the number of court proceedings and the number of mediations ") |  |  |  | Activity is not implemented On June 26, 2020, the Government of the Republic of Serbia adopted the Action Plan for the Implementation of the Program for Simplification of Administrative Procedures and Regulations "e-PAPER" for the period 2020-2021, within which one of the points is the Simplification of Administrative Procedure for Issuance permits to state bodies, organizations and legal entities to conduct training for mediators. For the purpose of the above, an amendment to the Rulebook on detailed conditions and procedure for issuing a license for conducting basic and specialized training of mediators and supervision over the implementation of training followed, which was published with amendments in the Official Gazette No. 1/2021 on January 11, 2021 and enters into force on the eighth day from the date of publication in the same. |  |  |
| 1.3.6.16. | Adoption of program for basic mediators’ training and standards for continuous and specialized training of mediators and their implementation. |  |  |  |  | Ministry of Justice Judicial Academy Other accredited Organizations and institutions | Continuously, commencing from enacting of the Law on Mediation |  |  | Budget of the Republic of Serbia 8.642 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | Basic training program adopted by the Ministry of Justice Programs for specialized training of mediators adopted by relevant Organizations Initial, specialized and continuous training of mediators regularly conducted. Ministry of Justice keeps updated records of all conducted training and attendees. |  |  |  | Аctivity is being successfully implemented On June 30th 2022, 27 organizations received permission to conduct training for mediators, and in the period from April 1st 2022. until June 30th 2022. A total of 301 participants attended basic and specialized training for mediators. In the period from April 1st 2022. until June 30th 2022 basic training was held 7 times by 4 organizations, namely by: Faculty of Law for Economy and Justice of the University of Economics and Business Academy in Novi Sad, International Center for Education and Personal Development d.o.o., Institute for Mediation, Negotiation and public policy and JP Official Gazette, while a total of 200 people completed basic training in that period. As for specialized trainings, trainings were held 6 times by 4 organizations with a total of 101 participants by: - International Center for Education and Personal Development Ltd.: Mediation in commercial disputes; Specialized training Mediator in practice - from registering a business entity to finding a client, - JP "Službeni glasnik": Specialized training for mediators in the field of abuse at work - mobbing; Specialized training - Mediation in family disputes, - ADR Partners d.o.o.: Specialized training of mediators - advanced negotiation skills in the economy, - "Mreža Jug" - Educational network of Southern Serbia: Specialized training for mediators in consumer disputes. |  |  |
| 1.3.6.17. | Continuous updating of the Registry of Mediators and other relevant registers and improvement of access to information on licensed mediators and accredited training institutions, Organizations and legal entities |  |  |  |  | Ministry of Justice | Continuously |  |  | Budget of the Republic of Serbia 15.318 € |  |  | Registry of Mediators established and access to information on licensed mediators and accredited training institutions (state bodies, Organizations and legal entities) continuously improved. |  |  |  | Аctivity is being successfully implemented The Register of Mediators regarding mediation licenses is being reularly updated |  |  |
| 1.3.6.18. | Systematization and filling of an appropriate number of positions in the Ministry of Justice for conducting professional and administrative tasks related to mediation system, including: - keeping of the Register of Mediators and drafting of decisions related to mediation licenses; - keeping of the Register of training providers, drafting of decisions related to training accreditation; monitoring over the implementation of the training programs; - keeping of other relevant registers; - keeping and analyzing of statistics on mediation and other state of play supporting of the Commission for the revocation of mediation licenses - other relevant jobs supporting the development of the mediation system. |  |  |  |  | Ministry of Justice | Continuously, commencing from enacting of the Law on Mediation |  |  | Budget of the Republic of Serbia The amount will be known after the job systematization is made |  |  | Systematization of an adequate number and types of jobs in the Ministry of Justice performed. All systemized jobs filled. Number of attended training and mediation related events of Ministry of Justice employees |  |  |  | Аctivity is being successfully implemented Staff in the Department of the Judiciary perform professional and administrative tasks related to mediation system and attend trainings and mediation related events. |  |  |
| 1.3.6.19. | Further improvement and promotion of alternative dispute resolution through activities such as: - Publishing information on the website; - Publication of informative brochures and public service announcements; - Informing the media; - Designing infographics; - Organizing round tables, conferences and workshops |  |  |  |  | Ministry of Justice, Public Relations Service | Continuously |  |  | Budget of the Republic of Serbia 2.553 €: In 2020. – 851 € In 2021. – 851 € In 2022. – 851 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | Information on mediation system is easily and widely accessible to the public. |  |  |  | Аctivity is being successfully implemented Having in mind the situation surrounding the COVID-19 pandemic, all planned activities on mediation promotion have been cancelled or postponed. On the website of the Ministry of Justice, an overview information regarding the activities of the Ministry of Justice in order to promote mediation is regularly updated. In the reporting period, mediation system-related research activities were focused on finishing outstanding analyses and exploring online mediation and mediation training solutions. In addition, associations of mediators continue to be active in the promotion of mediation through newspaper articles and participating in news shows. |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.3.7. Serbia adopts and implements the new Law on Enforcement and Security and establishes an initial track record of an improved clearance and recovery rate of enforcement proceedings in civil and commercial cases. Serbia monitors the enforcement system and develops further measures where relevant. |  |  |  |  |  |  | Improved efficiency of the enforcement proceedings in civil law cases. Improved supervision of the work of the public enforcement officers through E-supervision. |  |  |  |  |  | - Trend of reduction of the number of backlogged cases in enforcement before the courts; - Reduced average duration of the enforcement proceedings where legal entities are parties by implementation of the E-bulletin board, E-auction and E-ZIO; - Further setting up the technological and legislative framework in order the new modern technologies to be implemented into the enforcement system. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 1.3.7.1. |  | Regular monitoring the amendments to the Law on Enforcement and Security and all relevant bylaws and control of the implementation of the system of enforcement officers by the Chamber of Enforcement Officers and Ministry of Justice, as prescribed by the Law on Enforcement and Security and relevant by-laws. |  | Ministry of Justice Chamber of the Public Enforcement Officers |  |  | Continuously |  |  | Budget of the Republic of Serbia 92.634 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | - Regular monitoring of the quality and efficiency of the system through: - Quarterly reports of the established Working Group for monitoring the implementation of the changed legal framework in the field of enforcement; - Reports on work of the public enforcement officers; - Regular reports by the Chamber of Enforcement Officers; - Number of performed inspections in enforcement officers’ offices; - Number of disciplinary proceedings initiated and completed, including number of imposed sanctions. - Necessary measures undertaken, when necessary. |  |  |  | Аctivity is being successfully implemented By the decision of the Minister of Justice No. 119-01-000163/2019-22 dated on November 4th 2019, a Working Group was established to monitor the implementation of the amended legal framework in the field of enforcement and security with the aim of defining possible problems and inconsistencies in the implementation of the Law on Enforcement and Security and all relevant by-laws. In the reporting period, the Working Group analyzed the situations pointed out by the courts, public bailiffs, and the parties themselves in the proceedings. Monitoring of the application of independent Article 166 of the Law on Enforcement and Security continued, as well as monitoring of the eAuction portal. As of June 30, 2021, 230 public enforcement officers and 31 deputy public enforcement officers are operating on the territory of the Republic of Serbia. In the reporting period, the Ministry of Justice continued with increased supervision over the work of public enforcement officers. In the period April - June 2022, the following activities were performed within the scope of the activities of the Department for Judicial Professions related to the supervision of the work of public enforcement officers: - in the reporting period of April - June 2022, 88 new complaints and petitions were received and acted upon, as well as upon repeated complaints by the parties; - in the Register of Public Enforcement Officers and Deputy Enforcement Officers, data on the change of address, phone or e-mail of public enforcement officers was regularly updated; - citizens are provided daily with information about the work of public enforcement officers by telephone; - in May, the public enforcement officers’ exam was organized, to which 8 candidates took part and out of 8, 6 candidates passed the exam; - 4 appointed public enforcement officers began to perform their activities after taking the oath, who were appointed by the decision of the Ministry of Justice in March 2022 (of which two persons were appointed as public enforcement officers who were appointed deputy public enforcement officers); - 1 complaint in an administrative dispute was dealt with; - 4 appointed deputy public enforcement officers took the oath; - one decision was made on the termination of the activity of the deputy public enforcement officers; - 7 requests for official opinions were processed Monitoring of the implementation of Article 166 of the Law on Amendments to the Law on Enforcement and Security ("Official Gazette of RS", number 54/2019-3) continued. According to the mentioned article, enforcement proceedings in which enforcement or security is carried out by the court, and for the implementation of which the public enforcement officer is exclusively competent according to the provisions of the Law on Enforcement and Security, will continue before the public enforcement officers. Monitoring the implementation of the mentioned article is important in order to obtain feedback on the achievement of the goal of introducing the mentioned provision, i.e., on the effect of the implementation of the mentioned article on the relief of the courts. In the reporting period, in accordance with the article 166, total number of 1493 cases were solved before the Commerical Courts and total number of 419.612 cases were solved before the basic courts. eAuction: Statistics from the beginning of work to the date of the report (September 1, 2020 to June 30, 2022) 31151 organized so far (from September 1, 2020 to June 30, 2022) 2369 completed with at least an accepted offer First sales of real estate 5425 organized public sales for real estate 898 with at least an accepted offer On average, the achieved price is 18% higher than the initial price. First sale of movable property 13914 for movable property 471 with at least an accepted offer On average, the achieved price is 25% higher than the initial price. The number of initiated and completed disciplinary procedures and the number of imposed sanctions: In the period April - June 2022, one new disciplinary procedure was initiated, three disciplinary procedures were completed and three disciplinary measures were imposed. One disciplinary procedure is ongoing. Chamber of public enforcement officers: In the second quarter of 2021, 178 complaints on the work of enforcement officers were submitted to the Chamber of the Public Enforcement Officers. In the same period, total 201 cases were solved and 1 extraordinary supervision was carried out. |  |  |
| 1.3.7.2. |  | Enacting of by-laws and Chamber regulations necessary for implementation of Law on Enforcement and Security, in particular for: - service of documents among public enforcement officers and state authorities, and - electronic file of the proposals for enforcement Conducting the initial and continuous trainings |  | Ministry of Justice Chamber of Enforcement Officers Judicial Academy |  |  | IV quarter of 2020 |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.7.1. and 770.889 € Contract for the provision of services for the maintenance and further development of the information system for the supervision of judicial authorities - 162,518 € Public procurement for the maintenance of the application "Judicial Information System" - € 162,306 Public procurement of services for expanding the functionality of the infrastructure platform for interoperability and eCourt system - 365,557 € Public procurement of services for Sustainable development of the Real Estate Traffic application – 80.508 € |  |  | Relevant by-laws and Chamber regulations enacted; Initial and continuous training programs and materials enacted. Implementation of upgrades of Electronic bulletin board. Extended eCourt system in litigation enforcement procedures in commercial litigation. |  |  |  | Аctivity is fully implemented Judicial Academy: During the reporting period, representative of the Judicial Academy, participated in the regional forum “HCCH 2019 Judgments Convention: Prospects for the Western Balkans’’ which was held in Skopje, North Macedonia. Chamber of Public Enforcement Officers: In the second quarter of 2022, the Chamber of Enforcement Officers organized several trainings as part of regular professional training for еnforcement оfficers and deputy of the enforcement officers, according to the adopted plan for 2022. The following were held: trainings from the module "Management of stressful situations" for 63 participants; training from the module "International Aspects of Enforcement" for 53 participants; training from the module "Public speaking skills and communication with the media" for 63 participants and training from the module "Other regulations governing issues related to the work of enforcement officers (Law on Civil Procedure, Law on Bankruptcy, etc.) for a total of 180 participants. According to the adopted initial training program, initial training of 26 candidates for public enforcement officers was conducted. The bylaws passed by the Chamber in the second quarter of 2021 were approved by the Ministry of Justice in September 2021, including the Rulebook on the Professional training of public enforcement officers, which provided the formal conditions for the preparation of a continuous training programs. According to the adopted initial training program, initial training of 31 candidates for public enforcement officers was conducted. In September 2021, the Chamber organized the Sixth Annual Conference of Public Enforcement officers. In November 2021, the Chamber of the Public Enforcement Officers organized a two-day seminar "Enforcement in Practice", which was attended by members of the Chamber and other participants from the judiciary. The eCourt application for eEnforcement has been developed in accordance with the functional specification adopted by the Commission for Monitoring, Standardization and Improvement of All Automated Processes and Electronic Systems in Enforcement and Security Procedures. The prepared decision was presented to the Commercial Court of Appeals and a plan was made to present the system to all commercial courts. During the reporting period, one initial training for candidates for public enforcement officers was conducted. In addition, a two-day, sixth annual conference of public enforcement officers was held in Novi Sad in September. On March 25, 2021, the Minister of Justice adopted the Rulebook on the model of submitting a proposal for enforcement based on an enforceable or authentic document in electronic form and the Rulebook on the electronically submission among the public enforcement officer and other authorities. |  |  |
| 1.3.7.3. |  | Monitoring the implementation of the E-auction and E bulletin board in the enforcement proceedings. |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 4.599 € IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € |  |  | Quarterly reports of the Working Group for monitoring the implementation of the changed legal framework in the field of enforcement. |  |  |  | Аctivity is being successfully implemented eAuction Statistics from the beginning of work to the date of the report (September 1, 2020 to June 30, 2022) 31151 organized so far (from September 1, 2020 to June 30, 2022) 2369 completed with at least an accepted offer First sales of real estate 5425 organized public sales for real estate 898 with at least an accepted offer On average, the achieved price is 18% higher than the initial price. First sale of movable property 13914 for movable property 471 with at least an accepted offer On average, the achieved price is 25% higher than the initial price. |  |  |
| 1.3.7.4. |  | Monitoring the implementation of the amendments to the Rulebook on Model of Keeping Record on Enforcement and Security Proceedings and Financial Conducting of Business of the Public Enforcement Officers, Reporting Model, Content of the Report on Work of the Public Enforcement Officers and the Model of Dealing with the Archive and all technical models that are part of the Rulebook in order to draft recommendations for the improvement of the system for e-supervision over the work of the public enforcement officers. |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.3.7.3. IPA 2015/2017 EU for Justice Support for Chapter 23 - pending project extension approval – 2.000.000 € USAID Project “Rule of Law” – 20.000 $ |  |  | Report of the Working Group on the implementation of the amendments to the Rulebook on Model of Keeping Record on Enforcement and Security Proceedings and Financial Conducting of Business of the Public Enforcement Officers, Reporting Model, Content of the Report on Work of the Public Enforcement Officers and the Model of Dealing with the Archive and all technical models that are part of the Rulebook. Number of trainings held. Number of people trained. Evaluation of the trainings performed with respect to the performance assessment of the employees in the Ministry of Justice. |  |  |  | Аctivity is being successfully implemented Monitoring of the submission of data to the e-surveillance system in accordance with the Rulebook is carried out continuously. Expert support has been engaged through the "EU For Justice" Project, whose task will be to prepare a proposal for the improvement of the alarm system for illegal and timely work of public enforcers after the analysis. |  |  |
| 1.3.7.5. |  | Improvement of electronic data exchange between notaries and bailiffs and cadaster |  | Ministry of Justice |  |  | I quarter 2020 |  |  | Budget of the Republic of Serbia 160.500 € Public procurement of services for Sustainable development of the Real Estate Traffic application |  |  | Number of documents submitted to the cadaster electronically. Number of digitalized procedures between notaries and bailiffs and cadaster according to needs of business processes Training for system users. |  |  |  | Аctivity is fully implemented Through the improvement of the process of data exchange between notaries, Public Enforcement Officers and cadastre, the number of documents submitted to the cadastre electronically has increased. The number of digitized procedures between notaries, public enforcement officers and the cadastre has increased, so in October 2020 a new service was introduced within the Judicial Information System for obtaining data for which certificates from the real estate cadastre are issued and which do not exist in electronic cadastre records (such as copies of the lot plan, etc.). |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.3.8. Serbia develops and rolls out a coherent e-Justice system allowing systematic automated information exchange across the court system and prosecution offices, the electronic assignment of cases and the development and use of a sound statistical capacity (in line with CEPEJ guidelines on judicial statistics) to allow inter alia the measurement of the average duration of court proceedings. Serbia ensures sufficient training for the users of the system. |  |  |  |  |  |  | Developed an e-Justice system as a means to improve the efficiency, transparency and consistency of the judicial process, building on the existing automated case management system. Ensured the visibility of reliable and consistent judicial statistics and introduced a system to monitor the length of trials. |  |  |  |  |  | - Increased number of statistical parameters of efficiency of judiciary that can be monitored by means of Information and Communication Technology; - Possibility of actual monitoring of length of court proceedings by introducing the uniform case number; - Perception of transparency of the court proceedings through availability of data via Information and Communication Technology (judicial office holders, attorneys, citizens); - Perception of data transparency, in relation to the efficiency of the judiciary, through availability of data via Information and Communication Technology (judicial office holders, attorneys, citizens). |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 1.3.8.1. |  | Analysis Roll out applications for the automatic case management system in courts, prosecutors' offices and Institute for the Execution of Criminal Sanctions (SAPS, SAPA and SAPO) and development of strategic guidelines based on the analysis made |  | Ministry of Justice |  |  | I quarter of 2021 |  |  | IPA 2015 € 1,867,300 for public prosecution € 1,747,592 for penitentiaries |  |  | Analysis with strategic guidelines performed |  |  | Аctivity is fully implemented The strategic guidelines for all three centralized systems are part of the adopted ICT system development strategy in the judiciary (link of activity 1.3.8.2 which was implemented). |  |  |  |
| 1.3.8.2. |  | Drafting and adopting Strategy for ICT in judiciary and Action Plan for implementation |  | Ministry of Justice |  |  | IV quarter of 2022 |  |  | Budget of the Republic of Serbia 30.878 € |  |  | Strategy for ICT in judiciary adopted by Sectorial Council with IT Guidelines as ,umbrella``act and in accordance with Law on planning. Strategy and action plan elaborate measures and activities that establish sustainable maintenance and development of the ICT systems and education of personnel and users of the system. |  |  | Аctivity is fully implemented The ICT Council resumed its work in January 2022. The ICT Strategy was adopted on 4 February 2022. An Action Plan was also adopted and implementation has begun. |  |  |  |
| 1.3.8.3. |  | Implementation of the Strategy for ICT in judiciary and the Action Plan for its implementation |  | Ministry of Justice |  |  | Continuously from III quarter of 2021 |  |  | Budget of the Republic of Serbia 7.659 € |  |  | Strategic guidelines implemented Uniformed and centralized case management system is established |  |  | Аctivity is being successfully implemented The ICT Council resumed its work in January 2022. The ICT Strategy was adopted on 4 February 2022. An Action Plan was also adopted and implementation has begun. |  |  |  |
| 1.3.8.4. |  | Ensuring further development of standardized and centralized ICT systems in courts (“Super SAPS”) |  | Ministry of Justice |  |  | IV quarter of 2021 |  |  | Budget of the Republic of Serbia 17.285 € and for public procurement unknown at this time |  |  | Prepared legislative framework setting for proper usage of new centralized court CMS („Super SAPS“) by preparing draft on Law on registers, records and data processing in the judiciary and Draft on Additions and amendments on Court rulebook and procedural court laws. Infrastructural framework setting provided by new equipment in courts and proper preparing of Data center of Courts. Mapping data in AVP for future migration into centralized ICT systems in courts Budgetary sustainability of the Court Case Management System (super SAPS) by providing 30% of sum of software development cost as yearly maintenance budget. Human resources for the sustainability of system provided by proper engagement of ICT staff in Ministry of Justice |  |  | Аctivity is being successfully implemented The Ministry of Justice provided the DEU comments on the Inception report. The implementation of comments and intervention on the document is awaited as a precondition for adoption. Operational working groups for the verification of documentation as well as the Steering Committee are being formed. A focus group for the delivery of equipment was formed and the first all-day workshop was held on July 5, 2022, and the next one is scheduled for July 21st 2022. A survey and analysis of the age of computers in the courts was carried out and the DEU proposed to change the distribution list for the delivery of invoices in such a way that 95% of the old computers in the courts would be replaced from the equipment donated by the DEU through this project. An initiative to procure licenses for the Windows operating system for 5700 computers was sent to KITEU. |  |  |  |
| 1.3.8.5. |  | Ensuring further development of standardized and centralized ICT systems in institutions for the execution of criminal sanctions |  | Ministry of Justice The Administration for the Enforcement of Penal Sanctions (Institute for the Execution of Criminal Sanctions) |  |  | IV quarter of 2021 |  |  | Budget of the Republic of Serbia 17.285 € |  |  | Prepared legislative framework setting for proper usage of new centralized CMS by preparing draft on Law on registers, records and data processing in the judiciary and Draft on Additions and amendments on Court rulebook and procedural court laws. Infrastructural framework setting provided by new equipment in courts and proper preparing of DC Budgetary sustainability for CMS by providing 30% of sum of software development cost as yearly maintenance budget. Human resources for the sustainability of system provided by proper engagement of ICT staff in Institute for the Execution of Criminal Sanctions |  |  | Аctivity is being successfully implemented All participants agreed with Provisional acceptance. |  |  |  |
| 1.3.8.6. |  | Organization of focused trainings of end-users of existing platforms for the use of methodological instructions for "cleaning" data, the implementation of "cleaning" and addition to the information in the ICT system |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the annual training program, for each year |  |  | Clean data in the ICT system Defined training programs for end-users in the judiciary Focused trainings planned and held for end-users |  |  | Аctivity is being successfully implemented Obtaining donor and expert support for the application of the methodology of data cleansing in court systems for 1.6 million active cases is underway as a prerequisite for the successful implementation of the data migration phase in "superSAPS" (phase in the implementation of activities 1.3.8.4). |  |  |  |
| 1.3.8.7. |  | Further improvement of ICT systems through considerable investments in infrastructure, software and improvement of human resources, with the aim of establishing unique ICT system throughout the entire judicial system, and in accordance with the Guidelines that define the directions of development (conceptual model) of ICT system in the justice system of the Republic of Serbia |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the annual training program, for each year |  |  | Measures aimed at establishing a unified ICT system in the entire judicial system of the Republic of Serbia are constantly being implemented through considerable investment in infrastructure, improvement of software and human resources development Uniformed and centralized case management system established.in justice system |  |  | Аctivity is being successfully implemented During March and April, trainings were held for 66 basic courts and 231 notary offices for the use of the Register of issued and revoked powers of attorney. During the month of June, trainings were held for 66 basic courts and 231 notary public offices for using the Register of Wills. |  |  |  |
| 1.3.8.8. |  | More efficient utilization of hardware resources, availability of these resources, as well as integrating different IT technologies into a single logical and functional whole which would provide for availability of different services at any given moment |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the annual training program, for each year |  |  | Optimized use of data center resources. Prepared data centers for the operation of advanced and modern applications and ICT services in the judiciary. Completed preparations for the introduction of the Judicial Cloud storage New hardware equipment for users. New equipment in central locations. Increased link speed (network capacity). |  |  | Аctivity is being successfully implemented. More efficient use of hardware resources, availability of these resources, as well as integration of different IT technologies into a single logical and functional whole that would enable the availability of different services at any time. After the realization of public procurement in 2021 related to infrastructure, eJustice has predominantly switched to HCI technology and VMware is used as a platform for virtualization. Data backup is dominantly used on the veb. In the reporting period, technical intervention was performed due to the storage space for written and pdf document viewers on the e-bulletin board (1.3.7.3). |  |  |  |
| 1.3.8.9. |  | Drawing up documents on input and exchange of data in ICT system (and scanning of documents) with the purpose of unification of conduct in entire judicial system and training programs for staff in the judiciary with the aim of improving the quality of the existing ICT platforms |  | Ministry of Justice |  |  | III quarter 2021 |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the annual training program, for each year |  |  | Documented Instructions on data entry for ICT systems. Implemented software changes regarding closed fields and drop-down menus. Trainings for users in courts. |  |  | Аctivity is being successfully implemented A draft act containing instructions for data entry and exchange in ICT systems has been prepared. After the additional normative processing of the act and the adoption of amendments to the Rules of Procedure of the Court, as a condition of earlier activities, the adoption of this act is expected. Based on this act, as a logical later activity, the existing software will be changed and a new one will be developed for the courts, and employees will be trained. |  |  |  |
| 1.3.8.10. |  | Further implementation of the central system for case management (CMS) in all prosecutors’ offices, enabling connectivity between prosecutor’s offices and providing adequate user training; |  | Ministry of Justice Republic Public Prosecutor's Office |  |  | IV quarter 2022 |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the annual training program, for each year |  |  | New informational system for public prosecutor's offices developed. Data migration from the old information system into new completed. Instruction manual for case data input adopted. Providing 30% of sum of software development cost as yearly maintenance budget. Completed training of users from public prosecutor's offices. Establishment and upkeep of Secure Network connection for public prosecutor's offices. Providing new ICT equipment for users in public prosecutor's offices. Establishing an Active Directory for the structure for public prosecutor's offices. Providing upkeeping the Data Centre of public prosecutor's offices. |  |  |  |  |  |  |
| 1.3.8.11. |  | Establishing a centralized electronic application for dealing with citizens' complaints about the work of courts and judges, which would provide a centralized, efficient and transparent mechanism for monitoring complaints. |  | Ministry of Justice |  |  | IV quarter 2023 |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined after the investment project and documentation |  |  | Established centralized electronic application for complaints about the work of courts and judge |  |  |  |  |  |  |
| 1.3.8.12. |  | Continuous advancement of data exchange between the bodies within the judicial system and other state organs. |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 850.881 € |  |  | New data sets for electronic access added on Judicial Informational System. New services for sending data sets and documents from courts to the competent state authorities developed. Court Rules adapted for the procedure of delivery courts decisions and other documents in electronic form. Increase in the number of electronic inquiries through the Judicial Information System and the delivery of documents electronically |  |  | Аctivity is being successfully implemented A new service has been established on the Judicial Information System (JIS) to verify data from the records of motor vehicles and trailers of the Ministry of the Interior (MOI). The service from the Register of Motor and Trailer Vehicles is available to all users of justice (courts, public prosecutor's offices, notaries and public executors) from March 28, 2022, and in the first three weeks of use more than 24,000 inquiries were made, eliminating more than 48,000 correspondence between the judiciary and the Ministry of the Interior. The service for mass inquiries used by public enforcement officers has been expanded with the service for inquiries to the vehicle register. |  |  |  |
| 1.3.8.13. |  | Creating normative framework and taking other measures to advance ICT security |  | Ministry of Justice |  |  | IV quarter 2021 |  |  | Budget of the Republic of Serbia 17.285 € |  |  | Appropriate antivirus protection established and regularly updated with periodic training for system administrators in the courts Development of Information Security Act for the largest courts. Information security trainings by ISO standards for court IT staff. Implementation of risk management procedures. Optimized control and security procedures in data exchange. |  |  | Activity is being successfully implemented Public procurement has been published for the service of two-year maintenance of licenses for anti-virus software for workstations in judicial bodies. |  |  |  |
| 1.3.8.14. |  | Further advancement of transparency of the work of judicial bodies and judicial professions through utilization of ICT tools |  | Ministry of Justice |  |  | IV quarter 2021 |  |  | Budget of the Republic of Serbia 171.023 €- а) public procurement 169.491€ b) administration 1532 € Public procurement for maintenance and further development of information system for supervision of judicial professions - 169,491 € |  |  | Increased number of more various courts reports and real time and historical courts statistical data available online in machine-readable format (open data) via the Ministry of Justice website and The State Open Data Portal. |  |  | Activity is being successfully implemented An analysis to further expand the number of statistical reports is underway. |  |  |  |
| 1.3.8.15. |  | Further expansion of options to initiate and conduct court proceedings electronically for the benefit of lawyers and citizens using the e-Court application or other commercial software bundles available on the market relying on Application Programming Interface (API) technology, in compliance with the prescribed standards |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 421.741 €- а) public procurement -406.456 € б) working group 17.285 € Public procurement for services of expanding the functionality of the infrastructure platform for interoperability and the eCourt system in 2020 for the procedure of enforcement and security before the commercial court amounts to - 406,456 € |  |  | Extension of number of procedures which sre conducted before judiciary by using ICT means. Extended e-Court System (eSud) to Misdemeanor Courts. Extended e-Court System (eSud) to Commercial Courts. Continuous extension of courts procedures in which court acts can be communicated to parties via Electronic bulletin board services. |  |  | Activity is being successfully implemented The software solution of the eCourt for eEnforcement has been completed (improvements to the registration of legal entities and lawyers have been made and tested). The development of the system implementation plan is underway through the planning of software piloting activities in commercial courts, offices of public enforcement agents and lawyers, as well as the activity of conducting trainings and informing the public about the beginning of the implementation of the new electronic service. |  |  |  |
| 1.3.8.16. |  | Further opening of judicial data which are eligible for publication on the state’s open data portal in compliance with the applicable regulations on personal data protection and through the process of public consultations, carried out by the Ministry of Justice at least once a year. |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 1.533 € |  |  | Increased number of courts statistical data sets available online in machine-readable format (open data) via The State Open Data Portal. |  |  | Activity is being successfully implemented In order to improve the model of publishing data on the open data system, a project was developed to establish a separate section related to reporting on the work of misdemeanour courts. Having in mind the specifics of reporting by misdemeanour courts, a meeting was held with the Department of Statistics of the Supreme Court of Cassation, at which a new report (PKSS) was defined and its content to be available on the central statistics system. The report is being developed. |  |  |  |
| 1.3.8.17. |  | Improving the collection of court fees with ICT tools |  | Ministry of Justice |  |  | IV quarter 2020 |  |  | Budget of the Republic of Serbia Unknown at this time |  |  | Centralized software solution for the recording of tax actions in court and for exchanging the relevant data set with the State Treasury and central monitoring of collection and revenue planning on this basis. |  |  | Activity is being successfully implemented. The Ministry of Justice, in integration with the system of the Office for IT and eGovernment "+ ePayment" has developed a portal for online payment of court fees https://etakse.sud.rs/ which enables insight to all parties i.e. individuals and legal entities with regard to the determined court fees in a particular case, including the possibility of electronic payment via the Internet. The system is functional in all basic, higher and commercial courts. |  |  |  |
| 1.3.8.18. |  | Improving the misdemeanor charge collection with ICT tools |  | Ministry of Justice |  |  | IV quarter 2020 |  |  | Budget of the Republic of Serbia Unknown at this time |  |  | Integration of court information systems with the State payment portal (ePlacanje+) for online payment. |  |  | Activity is fully implemented. The integration of the judicial information system with the state portal for electronic payment (ePayment +) has been completed. |  |  |  |
| 1.3.8.19. |  | Continuous advancement of е-service and expansion of options related to the monitoring of case proceedings and availability of other information on the work of judiciary |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 210.664 € Public procurement for maintenance of „SIPRES maintenance and improvement“ planned in 2020 |  |  | Number of e-services available for citizens. |  |  | Activity is being successfully implemented The register of given and revoked powers of attorney was put into production in June 2022 and 5,254 powers of attorney were filed. Migration of data to the Register of Wills is underway. The development of a system for submitting e-Complaints about the work of courts and public prosecutor's offices is underway, which should be in production during the third quarter of 2022. |  |  |  |
| 1.3.8.20. |  | Improvement of courts web pages |  | Ministry of Justice |  |  | Continuously |  |  | Budget of the Republic of Serbia 50.936 € Public procurement for the sustainable development of portals, websites and e-mails under the jurisdiction of the Ministry of Justice planned for 2020 |  |  | Number of courts using centralized platform for court websites. Creation of appropriate templates on the platform for court sites for publication of the necessary information and documents Amendments to court rules to specify the obligation of courts to make certain information and documents publicly available |  |  | Activity is being successfully implemented In the reporting period, an internet domain was provided for a new platform for reporting and combating domestic violence, "Off Violence", which is currently being developed and is being filled with content. In the reporting period, a public procurement procedure was conducted for the services "Sustainable development of portals, internet presentations and e-mails under the authority of the Ministry of Justice", which ensured the maintenance and further development of a centralized system for internet presentations of all courts. The number of courts using the central platform for their websites increased in the reporting period and is now used by over 70 bodies using the platform. |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.3.9. Serbia ensures a qualitative improvement of the consistency of jurisprudence, including by ensuring easy access to jurisprudence for all courts through an electronic database and their publication within a reasonable amount of time. |  |  |  |  |  |  | Improved consistency of jurisprudence in all areas of law; judicial decisions and judicial motivations are timely published in all available electronic data bases. |  |  |  |  |  | - Established uniform and comprehensive electronic database of jurisprudence available to everyone, which is in compliance with regulations governing data confidentiality and protection of personal data resulting in a greater uniformity of jurisprudence; - Number of accepted applications against Republic of Serbia because violation of Article 6 paragraph 1 European Convention for Human Rights before ECHR; - Number of accepted Constitutional complaint because violation of Article 32 of Constitution of the Republic of Serbia before Constitutional Court of Republic of Serbia based on inconsistent jurisprudence; - Positive opinion from European Commission, stated in Annual Progress Report on Serbia, concerning progress achieved in the field of uniformity and availability of jurisprudence. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.3.9.1. |  | Conduct analysis of the normative framework which regulates: the issue of taking into account of jurisprudence, right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning |  | Ministry of Justice Supreme Court of Cassation |  |  | I quarter of 2021 |  |  | Budget of the Republic of Serbia 30.878 € |  |  | Conducted analysis of normative framework which regulates: the issue of taking into account of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning |  |  | Activity is not implemented. An informal analysis of the normative framework regulating the issue of the right to a legal remedy and competencies for deciding on legal remedies, publishing court decisions and explanations was performed. Based on the results of that analysis, the Draft Law on Amendments to the Law on Civil Procedure was drafted. An analysis of the normative framework governing the issue of taking into account case law will be carried out after the adoption of the Constitutional Amendments |  |  |  |
| 1.3.9.2. |  | Amending normative framework, in line with the analysis performed under activity 1.3.9.1., which regulates: - the issue of taking into account of jurisprudence; - right to legal remedy and jurisdiction for deciding on legal remedy; - publishing judicial decisions and judicial reasoning. |  | Ministry of Justice Supreme Court of Cassation National Assembly |  |  | II quarter 2021 |  |  | Budget of the Republic of Serbia 71.136 € |  |  | Normative framework which regulates: the issue of taking into account of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning is in line with EU standards and the best practice. |  |  | Activity is not implemented An analysis of the normative framework governing the issue of taking into account case law will be carried out after the adoption of the Constitutional Amendments. |  |  |  |
| 1.3.9.3. |  | Improving access to regulations and case law, through establishment and promotion of comprehensive and widely available electronic databases of legislation and case law, with respect to the provisions governing data confidentiality and personal data protection, and bearing in mind the provisions of Law on publishing laws and other regulations, Law on Judicial Academy, Law on Courts and Law on Public Prosecution |  | Public Enterprise “Official Gazette” Supreme Court of Cassation Republic Public Prosecution Judicial academy |  |  | Continuously |  |  | Budget of the Republic of Serbia 305.490 € (101.830 € per year) |  |  | Comprehensive electronic databases and widely available electronic databases of legislation and case law, with respect to the provisions governing data confidentiality and personal data protection, and bearing in mind the provisions of the Law on publishing laws and other regulations, Law on Judicial Academy, Law on Courts and Law on Public Prosecution established and regularly updated and improved. |  |  | Аctivity is being successfully implemented In compliance with the Law on Publishing Laws and Other Regulations and Acts (Official Gazette of the RS, No. 45/13), the electronic database Register and Texts of Regulations in Force and Other Acts in the Legal and Information System of the Republic of Serbia - http://www.pravno-informacioni-sistem.rs/reg-search, which is available free of charge to all citizens, is being continuously updated by publishing the basic and consolidated texts of regulations accompanied by links to PDF files of the official gazettes in which the basic text of the regulations, amendments and additions, corrigenda and decisions of the Constitutional Court impacting the regulations’ texts are published. This database is updated daily and contains all regulations in force of the Republic of Serbia. In the period 1 January 2022 – 31 March 2022, a total of 296 new regulations was published in the said database and drafted 168 unofficially (editorially) consolidated texts of regulations, with the accompanying basic data on the act, as well as references, and in particular: the enacting authority, type of document, adoption date, publication date, application commencement date, legal predecessor, i.e. successor, grounds for adoption, related regulations, as well as a version of consolidated text, if any. During this reporting period, the continuous updating of the COVID 19 page continued (https://www.pravno-informacioni-sistem.rs/fp/covid19) within which were, for easier accessibility to all citizens, singled out all regulations in force published in connection with, i.e. regarding the spread of the COVID-19 disease caused by SARS-Cov-2 virus. Continuous Improvement of the Contents of the Database of Case Law In compliance with the Law on Publishing Laws and Other Regulations and Acts and since the moment of its establishing, the contents of the electronic database of case law within the Legal and Information System - http://www.propisi.pravno-informacioni-sistem.rs has been continuously improved through publishing of the decisions of the Republic of Serbia courts of general and special jurisdiction, of the Constitutional Court and of the judgments of the European Court of Human Rights pertaining to the Republic of Serbia. In I quarter of 2022, a total of 610 court decisions was published in this database, so that at the time of reporting this database contains a total of 32,278 decisions, including judicial reasonings, legal opinions and court responses. In accordance with the provisions of the Law on Personal Data Protection, all the decisions in this database are published in anonymised form. Improvement of the Contents of Other Databases within the Legal and Information System of the Republic of Serbia The Legal Acts in English database within the Legal and Information System of the Republic of Serbia - http://www.propisi.pravno-informacioni-sistem.rs is being continuously updated with unofficial signed translations in English of the recently adopted laws, as well as of the system laws of the Republic of Serbia, which are of significance for the EU accession process, as well as for economic activities. In the first quarter of 2022, the Legal Acts in English database was updated with the translations in English of a total of 24 laws (basic texts, i.e., amendments adopted by the National Assembly during 2021, as well as in early 2022), i.e. 829 pages of text were translated. Moreover, translation into English of the text of the Act Amending the Constitution of the Republic of Serbia and the Constitutional Law for the Implementation of the Act Amending the Constitution of the Republic of Serbia was prepared. At the moment of reporting, this database contains more than 200 translations of the laws of the Republic of Serbia into English. Within the database Opinions, Models, Literature - https://www.pravno-informacioni-sistem.rs/mml-standard-search in which are systemized: opinions and other acts produced in the course of operations of the public authorities and state and other organizations, legal literature, model acts and other information of significance for interpretation and implementation of legal norms, in the first quarter of 2022, a total of 256 documents (including legal literature as well) was published, so that at the moment of reporting this database contains more than 13,309 results. Special attention was paid to publication of the opinions, instructions and other acts of the competent state authorities and organisations given regarding the new legal solutions, the implementation of which began in 2022. The case-law database of the European Court of Human Rights, whose connecting case-law database and prosecutorial practice, has established a unique system of related case-law database and prosecutorial practice database, establishes individual links with public databases of case-law database and prosecutorial practice database, i.e. with anonymized versions of court decisions and prosecutorial documents. This preserves the confidentiality of data guaranteed by anonymization. Given that the e-Juris system is such, that it has only a public instance, and that the data contained in the judgments of the European Court of Human Rights are not anonymized, except at the direct request of the applicant, there was no need to stablish an internal database. With that in mind, in order to make it easier to establish connections, the connecting was made with the public case-law database and prosecutorial practice database. In relation to the case-law database of the European Court of Human Rights, which is managed by the Judicial Academy, additions were made to the database of judgments from additional sources (guides, publications and thematic collections). At the same time, in addition to the existing links to judgments and decisions of domestic courts, new links have been established that should facilitate the process of citing ECtHR judgments and reviewing practice in a legal situation for users. In order to collect the largest possible volume of relevant materials related to the practice of international bodies for the protection of human rights, a new content module has been established within the e-case application, which refers specifically to the practice of the ECtHR presented through the guide for the application of the Convention, by the thematic unit of application and per article. In accordance with this, a content library of about 80 publications was created, that were created either with the support or realization of the project activities of the Council of Europe, which are available to all users of the application, without restrictions. A significant amount of additional material has been collected, which will be available through the e-library to the beneficiaries of the Judicial Academy's training, and in the creation of which the Council of Europe did not directly participate, and which refers to collections and guides for the application of the Convention. |  |  |  |
| 1.3.9.4. |  | Capacity strengthening and improvement of efficiency of operation of departments for jurisprudence in Supreme Court of Cassation, courts on Republic level and appellate courts. |  | Supreme Court of Cassation Administrative Court Commercial Appellate Court Misdemeanor Appellate Court Appellate courts of general jurisdiction |  |  | Continuously |  |  | Budget of the Republic of Serbia 88.701 € а) employment 85.101 €, In 2021 31.913 € In 2022 53.188 € and б) Training, total 3.600 €, 1200 € per year |  |  | Capacities and efficiency of operation of department for jurisprudence in the Supreme Court of Cassation, courts on Republic level and appellate courts. are continuously improved. |  |  | Аctivity is being successfully implemented In criminal matter, the Appellate Courts nominate and harmonize disputed legal issues, further submitting them to the Supreme Court of Cassation, where those are being discussed at the session of the its Criminal Department, resulting with legal standings in form of response being distributed back to the Appellate Courts. The Supreme Court of Cassation continuously decides on disputed legal issues in civil matter arising from queries posed by lower-instance courts in pending cases, as in accordance with the provisions of the Law on Civil Procedure (Articles 180-185), through legal views and standpoints contributes to the court jurisprudence harmonization. In the reporting period of the year, the weekly-based studying of the ECtHR practice continued, through participation within the Supreme Courts’ Network. Also, the first Bulletin of Court Jurisprudence of the Supreme Court of Cassation (No. 1/2022) was prepared. In the reporting period of the year, the monitoring of the ECHR jurisprudence continued, also through participation within the Superior Courts' Network (SCN) with the ECHR. During the reporting period, the focal point on behalf of the SCC in SCN took part in the Fifth Focal Points Forum on June 10, 2022. The topic of the Forum was domestic violence. On June 29, 2022, training was held in cooperation with the SCN and the Office of the Council of Europe in Serbia with regard to the use of the resources for the research of the ECHR jurisprudence (including, HUDOC official data base and the newly developed Knowledge sharing platform of the European Court of Human Rights, that enables even more simplified search of the jurisprudence of the European Court of Human Rights, per articles of the Convention. The training has been attended by ten (10) judicial advisers of Case Law Department of the Supreme Court of Cassation and one (1) Justice of the Supreme Court of Cassation. Futhermore, during the reporting period, four Justices of the Supreme Court of Cassation took part in a study visit to the Council of Europe (including the European Court of Human Rights) as part of a mixed delegation of representatives of both courts and prosecutor's offices of the Republic of Serbia, supported by the Council of Europe Project "Strengthening effective legal remedies to human rights violations in Serbia" (Horizontal Facility for the Western Balkans and Turkey 2019-2022). Delegation of Serbian judiciary had meetings with ECtHR judges, as well as lawyers working in ECHR Registry and the Jurisconsult, with a focus on Judicial Dialogue (in the light of Protocol No.16 of the ECHR), and the Knowledge Sharing Platform of the ECHR, and used the opportunity to exchange views on importance of the systematization of court jurisprudence and the methodology of classifying issues concerning human rights, the digital transformation of the judiciary, as well as other current issues related to the interpretation and application of the European Convention for the Protection of Human Rights. |  |  |  |
| 1.3.9.5. |  | Improving the Case law portal |  | Ministry of Justice Supreme Court of Cassation |  |  | Continuously |  |  | Budget of the Republic of Serbia 50.338 € Ongoing and planned public procurement to maintain and enhance the case law application in the courts |  |  | Functionalities of advanced and more accurate search methods implemented. Increase in the number of decisions and the number of courts whose decisions are in the decision database |  |  | Аctivity is being successfully implemented The meetings, according to the Agreement of the Presidents of the Аppellate Courts, were partly held live in the previous quarter, due to the relaxation of the situation caused by the pandemic: - in civil matters, in Kragujevac, June 3, 2022. (with the participation of 4 appellate courts and the Commercial Appellate Court). - In criminal matters, the appellate courts nominate and agree disputed legal issues and submit them to the Supreme Court of Cassation, which discusses the submitted legal issues at a session of the Criminal Division and reports the adopted conclusions to the appellate courts. - In the matter of competence of special judicial institutions for combating corruption, a joint session of Special Departments for combating corruption was held in Novi Sad, June 27-28, with a focus on the topic of high corruption, with the contribution of a Spanish judge, in the capacity of an expert of the European Union. The entry of court decisions of appellate courts and state-level courts in the Case Law Database continued. Until 30 June 2022, the total number of court decisions uploaded amounts, as follows: - Supreme Court of Cassation: 12,085 anonymized decisions, 112 legal understandings, 33 bulletins of case law and 17 sentences (unchanged); while in relation to appellate courts and certain state-level courts the total number of court decisions uploaded has increased and amounts to: - Appellate Courts: 83,786 integral decisions and 4,582 anonymized decisions; - Misdemeanour Appellate Court: 5,874 integral decisions (unchanged); - Commercial Appellate Court: 22,780 integral decisions and 2,111 anonymized decisions; - Administrative Court: 189,880 integral decisions and 19,297 anonymized decisions. The Supreme Court of Cassation continues to publish its decisions, legal standings, sentences and bulletins on its website (www.vk.sud.rs) in accordance with Article 33, paragraph 2 of the Law on the Organization of Courts "Official Gazette of RS", no. 116/2008, .... 88/2018). |  |  |  |
| 1.3.9.6. |  | Development of internal database of prosecutorial practice, accessibility of the database for all prosecutors’ offices and connecting it to the Judicial Academy’s database (e-Academy) and the case law database |  | Ministry of Justice Republic Public Prosecutors Office |  |  | IV quarter 2021 |  |  | Budget of the Republic of Serbia Project “Roll out SAPO” (IPA 2015) 1.867.300 € for PPOs |  |  | Internal prosecutorial practice database created and interconnected with Court practice portal and Judicial Academy’s database (e-Academy) Steady increase in the number of prosecutors' offices with users of prosecutorial practice database. |  |  | Activity is fully implemented In the past period, the connection of the database of prosecutorial practice (both public and internal) with the database of judgments of the European Court of Human Rights has been established, by using the assigned descriptor from the open book of descriptors of the Supreme Court of Cassation. This allows all judgements from the e-Juris system of the Judicial Academy, to which these groups of descriptors have been assigned, to be displayed within the prosecutorial practice database, along with a document assigned to one of the descriptors related to the fundamental rights system from the European Convention on Human Rights, and which relate to the Republic of Serbia. In addition to linking the content made using descriptors from the open list of descriptors of the Supreme Court of Cassation, which enabled the establishment of a unique linked system of case-law of the ECtHR, domestic courts and domestic prosecutor’s offices, individual links were established (decision to decision). These links, established in this way, are mutual and reciprocal (from the e-case database to prosecutorial practice and vice versa) for individual documents, while linking by group and by descriptor is applicative and involves the display of related documents by content in relation to the assigned descriptor. The case-law database of the European Court of Human Rights, whose connection with case-law and prosecutorial practice has established a unique system of related case-law and prosecutorial practice, establishes individual links with public databases of case-law and prosecutorial practice, i.e. with anonymized versions of court decisions and prosecutorial documents. This preserves the confidentiality of data guaranteed by anonymization. Given that the e-Juris system is such, that it has only a public instance, and that the data contained in the judgements of the European Court of Human Rights are not anonymized, except at the direct request of the applicant, there was no need to establish an internal database. With that in mind, in order to make it easier to establish connections, the connecting was made with public case-law database and prosecutorial practice database. The database also includes connections (individually and through descriptors) with the database of domestic case-law, as well as with numerous external contents (publications and bulletins). Bearing in mind that the work on connection has only just begun, in the coming period it is expected to establish new models of connection and a large number of related decisions. Workshops were held for using the database of prosecutorial practice and workshops for citing judgments and decisions of the ECtHR, where users from the public prosecutor’s offices for all four appellate territories were trained in using the database of prosecutorial practice. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT / INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.3.10. Recommendation: Conduct a mid-term review at the end of 2015 as well as an impact assessment in 2018 of the results generated by the 2013 Strategy and its revised action plan. Define on that basis and where needed measures to cover the remaining period up until accession. IBM: Serbia implements its national Judicial Reform Strategy (2013 – 2018) and Action Plan ensuring full alignment with its Action Plan for Chapter 23. It assesses its impact at the end of 2018 and takes remedial action where needed. Serbia ensures that recommendations from the functional review are followed up on and conducts a new functional review in early 2018. |  |  |  |  |  |  | A mid-term review assessed the impact of the reform of judiciary for period up until 2018 and an impact assessment on that basis served to define measures for period after 2018 up until accession. |  |  |  |  |  | 1. Data from analysis of mid-term results of implementation of reform in 2015; - Data from impact assessment for the period up until 2018; - Measures planned for period from 2018 up until accession, based on an analysis of the mid-term results and projection for period until 2018. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.3.10.1 |  | Adoption of a new strategy for the judiciary sector for the period of 2020-2025, with the proposed measures, until accession |  | Ministry of Justice Government National Assembly |  |  | III quarter 2020 |  |  | Budget of the Republic of Serbia 71.136 € |  |  | New Strategy for justice sector adopted for the period of 2020-2025 with measures until accession. |  |  | Activity is fully implemented On July 10, the Government of the Republic of Serbia, adopted Judicial Development Strategy for the time period between 2020 and 2025. On March 31st 2022, the Government of the Republic of Serbia adopted the Action Plan for implementation of the Judicial Development Strategy. |  |  |  |
| 1.3.10.2. |  | Conduct a mid-term impact assessment on the implementation of the strategy from activity 1.3.10.1. with corrective measures proposed |  | Ministry of Justice in cooperation with Coordination Body for implementation of the Action Plan for Chapter 23 |  |  | IV quarter of 2022 |  |  | Budget of the Republic of Serbia 17.285 € Donor support (непознато у овом тренутку) |  |  | Developed methodology for drafting the mid-term impact assessment on the implementation of the Strategy Mid-term impact assessment conducted and presented Number of the corrective measures undertaken |  |  |  |  |  |  |
| 1.4. WAR CRIMES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.4.1. Serbia effectively demonstrates adequate investigations of allegations and equal treatment of suspects avoiding giving the impression that anyone is above the law, regardless of their nationality or ethnicity or that of the victims. |  |  |  |  |  |  | All priority and serious allegations in accordance with prosecutorial strategy have been properly investigated and all trials for war crimes have been completed, with full and accurate implementation of international standards concerning the support of victims and witnesses and their protection. |  |  |  |  |  | - New prioritized and serious allegations prosecuted in line with prosecutorial strategy; - Number of proceedings completed with final judgment; - Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; - Positive reports from other relevant governmental and non-governmental Organizations; - Public Opinion Survey on citizens’ perceptions whether the suspects for war crimes are properly investigated and punished; - Duration of the proceedings (efficient investigative and pre-investigative actions); - Quality of proceedings and judgments for war crimes in comparison to international standards |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.4.1.1. |  | Monitoring the effective implementation of the National Strategy for prosecution of war crimes (2016-2020). |  | Working group of the Government of Serbia, including participation of experts and civil society |  |  | Quarterly reporting |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.1.2. |  |  | National Strategy for prosecution of war crimes 2016-2020 being effectively implemented. Number of quarterly made reports on the implementation of the National Strategy for prosecution of war crimes 2016-2020 Number of recommendations for improving the procedure on war crimes Positively assessed findings from the Report by the EU and CSOs that prepare alternative reports |  |  | Activity is fully implemented The Strategy expired. The Ex ante analysis of the Strategy is available at MOJ website at: https://www.mpravde.gov.rs/sr/sekcija/53/radne-verzije-propisa.php The Working body for monitoring of the Strategy consisted of the representatives of all relevant stakeholders in charge of the Strategy implementation as well as academic community has been meeting regularly. All reports are available in Serbian and English on the web page of the MoJ https://www.mpravde.gov.rs/tekst/17978/izvestaj-o-sprovodjenju-nacionalne-strategije-za-procesuiranje-ratnih-zlocina.php |  |  |  |
| 1.4.1.2. |  | Establishment of the working group and elaboration of the analysis of the results achieved with defining further steps in the processing of war crimes |  | Working group of the Ministry of Justice |  |  | I quarter of 2021 |  |  | Budget of the Republic of Serbia 30.878 € |  |  | In line with the National Strategy for prosecution of war crimes (2016-2020), working group for the preparation of the analysis of the achieved results in the implementation of the National Strategy for the Prosecution of War Crimes established The analysis of the achieved results in the implementation of the National Strategy for the Prosecution of War Crimes prepared and further steps presented Necessary steps performed according to analysis conclusions |  |  | Activity is fully implemented The Working group finalized its work Еx ante analysis has been developed and is available at the website of the Ministry of Justice |  |  |  |
| 1.4.1.3. |  | Drafting and adoption of the new strategic document for prosecution of war crimes for the period 2020-2024 as continuation of the National Strategy for prosecution of war crimes (2016-2020) |  | Working group of the Ministry of Justice the Government of Serbia |  |  | II quarter of 2021 |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.1.2. |  |  | New strategic document drafted for the period of 2020-2024 in line with the conclusions of the analysis |  |  | Activity is fully implemented National Strategy for the prosecution of war crimes for the period from 2021 to 2026 was adopted on October 14, 2021. |  |  |  |
| 1.4.1.4. |  | Monitoring the effective implementation of the new strategic document for prosecution of war crimes 2020-2024 |  | to be determined by the document |  |  | Quarterly since the adoption of the new strategic document |  |  | Budget of the Republic of Serbia Unknown at this time, will be known after the new strategic document is adopted |  |  | The new strategic document is being effectively implemented. Number of quarterly made reports on the implementation of the strategic document Number of recommendations for improving the procedure on war crimes Positively assessed findings from the Report by the EU and CSOs that prepare alternative reports |  |  | Activity is being successfully implemented. On June 30th 2022, a meeting of the Working Body for monitoring the implementation of the Strategy was held, at which the report on the implementation of the Strategy from the moment of its adoption, ending with the first quarter of 2022, was adopted. The report is published on the website of the Ministry of Justice. |  |  |  |
| 1.4.1.5. |  | Complete insight and research of International Criminal Tribunal for former Yugoslavia (ICTY) and Residual Mechanism (IRMCT) archives (about war crimes on the territory of former Yugoslavia including documents not only from Serbia but also from BiH and RH, as well as general and specific allegations already investigated by independent prosecutors of ICTY), analysis of the discovered documents through the established liaison officers based on EU project that will ensure that all priority and serious allegations or war crimes are properly investigated and subsequently prosecuted and tried in line with prosecutorial strategy. -Identifying ICTY/IRMCT materials and evidence which are relevant to the cases identified as a priority under activity 1.4.1.3 above and transfer of identified documents and evidence from the ICTY and IRMCT to the War Crime Prosecutor Office (support obtained and memorandum of understanding signed). -Transferring the ICTY know-how through: - Cooperation of the WCP with the ICTY/IRMCT on concrete cases in which the evidence was transferred in order to also obtain general and case specific knowledge, expertise and strategies from the ICTY and IRMCT investigators/prosecutors (transparency is ensured as information and expertise are obtained from independent experts) Cooperation of the WCP with the ICTY/IRMCT on concrete cases in which the evidence was transferred in order to share the strategy and transfer knowledge and practice on jurisprudence relating to crimes and types of responsibility that will be used as allegation in concrete cases (transparency is ensured as information and expertise are obtained from independent experts) - Ad hoc presence of the WCP advisor in the ICTY and IRMCT prosecutor’s office on ad hoc basis related to concrete national cases, analyzing ICTY prosecutor’s case files and developing a strategy for concrete cases that will be prosecuted by the WCP before the High Court in Belgrade. |  | War Crime Prosecutor Office |  |  | Continuously |  |  | Budget of the Republic of Serbia 51.855 €: In 2020. – 17.285 € In 2021. – 17.285 € In 2022. – 17.285 € |  |  | Fully available/accessible ICTY and IRMCT archives Adequate use of the ICTY and IRMCT archives Evidence transfer completed Knowledge and expertise of the ICTY is applied in investigation and prosecution of war crimes in Serbia |  |  | Activity is being successfully implemented OWCP case handlers continuously search the Mechanism archives and access the database through the Electronic Disclosure System, which provides direct access to a significant portion of the ICTY/Mechanism’s evidence fund. In the previous quarter, OWCP has initiated continued training with Mechanism representatives in order to transfer the practical knowledge and expertise of the ICTY and the Mechanism and to apply them in conducting investigations and war crimes proceedings. In the previous quarter, a meeting was held at the level of Chief Prosecutors and their associates via videoconference to discuss current issues relevant to the six-month report of the Chief Prosecutor to the United Nations Security Council. The next meeting has been initiated and is expected to be held in the middle of the second quarter. During the 1st quarter, 8 requests for assistance to the Mechanism for specific cases were sent through the liaison officer. Cooperation with the Mechanism regarding the submission of evidence and information in complex cases at the end of 2022, resulted in the indictment of one high-ranking accused person. Cooperation between the Office of the War Crimes Prosecutor (OWCP) and the International Residual Mechanism for Criminal Tribunals (IRMCT) has continued. On 29 April 2022, a meeting was held between OWCP representatives, the IRMCT Office of the Prosecutor and the Prosecutor’s Office of Bosnia and Herzegovina with the aim of resolving important issues related to regional cooperation in specific legal cases. Also, on 4 May 2022, another meeting was held at the level of the chief prosecutors of the OWCP and the IRMCT Office of the Prosecutor and their associates, for the purpose of preparing the six-monthly report submitted by the Chief Prosecutor of the Mechanism to the UN Security Council. Proceedings in three category 2 cases that were transferred from the Prosecutor’s Office of Bosnia and Herzegovina as part of legal aid are ongoing before the competent court, and proceedings have also begun in a case that is the result of intensive cooperation between the OWCP and the IRMCT. Active cooperation with the IRMCT included joint work on cases in which high-ranking persons were accused and in connection with those proceedings, the Office of the Prosecutor had previously provided extensive investigative material. In one of those cases, cooperation resulted in the indictment being filed in December 2021, which was then confirmed by the competent court and whose proceedings are ongoing. In regard to the other case, the investigation is still ongoing. During the last visit of the Chief Prosecutor of the Mechanism to the OWCP, the participants of the meeting agreed on the formation of a working group for specific cases, with the aim of transferring knowledge and expertise, and in whose work representatives of the IRMCT and the OWCP will be involved. During the 2nd quarter, the liaison officer continued to send requests for assistance to the IRMCT for the needs of specific cases, and a response is expected in the following period. The archive and evidence fund of the IRMCT is continuously searched via the Electronic Disclosure System, which is accessed by the case handlers. |  |  |  |
| 1.4.1.6. |  | Strengthening capacities of War Crimes Prosecutor’s Office through electing prosecutor’s deputies and employment/transfer of prosecutor’s assistants. |  | War Crimes Prosecutor`s Office State Prosecutorial Council |  |  | Continuously |  |  | Budget of the Republic of Serbia Unknown at this time, will be known after the new strategic document is adopted |  |  | Strengthened capacities of War Crimes Prosecutor’s Office through electing prosecutor’s deputies and employment/transfer of prosecutor’s assistants. |  |  | Аctivity is being successfully implemented The number of deputy prosecutors who perform public prosecutor functions in the OWCP is in accordance with the decision of the State Council of Prosecutors A. no. 69/21 dated 4 February 2021. During 2021, 2 deputy public prosecutors were sent to the OWCP based on the decision of the Republic Prosecutor. There is a plan to start activities of hiring an additional number of assistant prosecutors in the next quarter. |  |  |  |
| 1.4.1.7. |  | - Continuous/further implementation of the system of training and education in the area of international criminal law for the related judges and prosecutors - Initial training for the newly appointed members of state bodies dealing with war crimes - Continuous education training for judges and prosecutors in line with National strategy and prosecutorial strategy (ensuring that the latest IHL developments are included). |  | Judicial Academy War Crime Prosecutor’s Office Supreme Court of Cassation Higher Court in Belgrade Appellate Court in Belgrade High Judicial Council State Prosecutorial Council |  |  | Continuously |  |  | Budget of the Republic of Serbia 9.842 € |  |  | Trainings in the field of international criminal law are held continuously according to previously adopted program for other judges and prosecutors on as needed basis. The established curriculum (curriculum) for initial training in the above areas for newly elected and new employees in war crimes cases |  |  | Activity is being successfully implemented. Judicial Academy: During the reporting period, 13 two-day seminars of the international certification program in the field of fraud research and money laundering prevention (CFE and CAMS programs) were held. The seminars were attended by 188 participants from the ranks of basic and senior public prosecutors and their deputies, judicial and prosecutorial assistants and associates, police officers. Also, 1 one-day seminar was held on the topic: “Presentation of the Manual for filling out reports for conditional release”, in Belgrade, for a total of 18 participants, with the support of the OSCE Mission in Serbia. Also, in the reporting period, Judicial Academy, with the support of the OSCE Mission in Serbia, organized four one-day interactive workshops on the topic: ”New approaches in the exclusion of micro-traces during forensic processing of crime scenes; recognition of foreign judicial decisions and evidence collected abroad”, in Belgrade, Niš, Kragujevac and Novi Sad, for a total of 75 participants. |  |  |  |
| 1.4.1.8. |  | Continuous enhancement and regular updating of the WCP website to enable the public to monitor what activities and when have been performed by the WCP in relation to specific criminal charges. |  | War Crime Prosecutor Office |  |  | Continuously, as activities occur |  |  | Budget of the Republic of Serbia 3.063 € |  |  | Enhanced WCP website which provides an opportunity for the public to monitor which activities have been performed by the WCP in relation to specific criminal charges. |  |  | Аctivity is being successfully implemented The website is updated with the regular publication of information regarding new activities carried out by OWCP. The public is immediately informed about the decisions of the competent courts in the proceedings on OWCP indictments, as well as about other important activities. The site is also available in English. Since the regulations applied by OWCP contain provisions regarding limited access to investigation data, the Office publishes indictments in accordance with the Rulebook on Anonymization - indictments at the stage when they are confirmed by the competent court, as well as indictments taken over for criminal prosecution and after the end of the preparatory hearing. With the main goal of permitting the public to gain access to the work of the OWCP, all relevant information and the most important news regarding the activities carried out in the reporting period are posted on the OWCP website as soon as it is possible. The public is informed in a timely manner about the OWCP meetings held at the regional and wider international level, which are important for solving specific issues related to regional cooperation in war crimes cases. Given that new indictments were filed in the previous period, in accordance with current practice, they will be available in anonymised form immediately after the conclusion of the preliminary hearings. |  |  |  |
| 1.4.1.9. |  | Publication of a report by the War Crimes Prosecutor’s Office, in line with the established methodology of reporting, which will be available to the public indicating what has been done in respect of all criminal charges since 2005, to determine and to represent whether all allegations of war crimes are investigated appropriately. (the same activity 1.4.3.5.) |  | War Crimes Prosecutor’s Office |  |  | Once a year, and always when needed |  |  | Budget of the Republic of Serbia 25.926 € Per year 8.642 € |  |  | Reporting methodology determined Report of War Crimes Prosecutor’s Office published on the website, including activities related to all criminal charges since 2005, focusing on cases of highly ranked officers. Annual reporting of War Crimes Prosecutor’s Office with regard to all criminal charges in the reporting period, in accordance with the established methodology of reporting Presentation of the Annual WCP report at the press conference |  |  | Аctivity is being successfully implemented In accordance with the previously established reporting methodology, the updated report on the activities of the OWCP regarding criminal charges in war crimes cases was prepared in December 2021 and is publicly available on the OWCP website. The preparation of the next report is planned for the 4th quarter of 2022. |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| Serbia ensures proportionality of sentences and a sentencing policy in line with international criminal law standards |  |  |  |  |  |  | Imposed sentences are proportional to criminal offence in accordance with the international standards. |  |  |  |  |  | - Level of sentences imposed in comparison to the jurisprudence of international tribunals; - Positive evaluation from analysis and reports of international and non-governmental Organizations concerning proportionality of sentences; - Implementation of international criteria (including aggravating and mitigating circumstances) in imposition of sentences in war crimes cases. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.4.2.1. |  | Publishing and follow up the conclusions from conferences organized in the region with reference to proportionality of sentences and a sentencing policy in line with international criminal law standards |  |  |  | Higher Court in Belgrade, War Crime Chamber Appellate Court in Belgrade Supreme Court of Cassation Wаr Crime Prosecutors Office Ministry of Justice | Continuously |  |  | Budget of the Republic of Serbia Negligible cost activity |  |  | Published and implemented conclusions from the conferences. |  |  | Аctivity is not implemented The OWCP has started organizing a regional conference. It is planned that representatives of all relevant institutions from the Republic of Serbia and from the region involved in the field of investigation and proceedings for war crimes, as well as IRMCT representatives, will be participating. The conference is planned for the beginning of September 2022, and one of the key topics will be the proportionality of sentencing and the sentencing policy in the context of the application of international standards. After the conference, the relevant subjects will draw up the main conclusions. |  |  |  |
| 1.4.2.2. |  | Publication and dissemination of reports on the Higher, Appellate Court and Supreme Court of Cassation case law on sentencing policies in war crime proceedings for judges’ prosecutors and lawyers. |  |  |  | Higher Court in Belgrade, War Crime Chamber Appellate Court in Belgrade Supreme Court of Cassation Ministry of Justice | Continuously, yearly and when needed |  |  | Budget of the Republic of Serbia 1.500 € Per year 500 € |  |  | Printed and disseminated reports of the Higher, Appellate Court and Supreme Court of Cassation jurisprudence on sentencing in war crime proceedings for judges’ prosecutors and lawyers. |  |  | Activity is being successfully implemented. Through Case law database (https://www.sudskapraksa.sud.rs/sudska-praksa), the case law of Appellate court in Belgrade has been available (search of the register: Кж2-По2 – appeals in cases of war crimes) including anonymized decisions of the Appellate court in Belgrade. Also, the decisions of the Supreme Court of Cassation regarding extraordinary legal remedies have been available (register Кзз РЗ – request for the protection of legality in cases of war crimes). Moreover, on the website of the Higher Court in Belgrade, the list of decisions of that Court, in criminal matter - which were the subject of request for information of public importance, are available, including the decisions regarding war crimes (https://www.bg.vi.sud.rs/tekst/3191/baza-odluka-vs-u-beogradu.php). |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 1.4.3. Serbia provides an initial track record of investigation, prosecution and adjudication of a higher number of cases including against high level suspects as well as of cases transferred from ICTY to Serbia. |  |  |  |  |  |  | Suspects – irrespective of their (former) rank or grade or current occupancy - are treated equally before the court both in terms of sentencing as well as in terms of the speed of bringing their cases forward. |  |  |  |  |  | - The number of new cases against high level officials; - The number of resolved cases against high level officials; - Positive evaluation in the report of the ICTY Chief Prosecutor and President to the Security Council; - Positive evaluation in the reports from relevant international and non-governmental Organizations. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME / DEADLINE |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 1.4.3.1. |  | Monitoring the effective implementation of the National Strategy prosecution of war crimes (2016-2020). |  |  |  | Working group established by the Government of Serbia, comprised of representatives of the institutions with jurisdiction in war crimes and academic community Experts and civil society | Quarterly reporting |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.3.2. |  |  | National Strategy for prosecution of war crimes 2016-2020 being effectively implemented. Number of quarterly made reports on the implementation of the National Strategy for prosecution of war crimes 2016-2020 Number of recommendations for improving the procedure on war crimes Positively assessed findings from the Report by the EU and CSOs that prepare alternative reports |  |  | Activity is fully implemented The Strategy expired. The Ex ante analysis of the Strategy is available at MOJ website at: https://www.mpravde.gov.rs/sr/sekcija/53/radne-verzije-propisa.php The Working body for monitoring of the Strategy consisted of the representatives of all relevant stakeholders in charge of the Strategy implementation as well as academic community has been meeting regularly. All reports are available in Serbian and English on the web page of the MoJ https://www.mpravde.gov.rs/tekst/17978/izvestaj-o-sprovodjenju-nacionalne-strategije-za-procesuiranje-ratnih-zlocina.php |  |  |  |
| 1.4.3.2. |  | Establishment of the working group and elaboration of the analysis of the results achieved with defining further steps in the processing of war crimes |  |  |  | Working group of the Ministry of Justice | I quarter of 2021 |  |  | Budget of the Republic of Serbia 15.439 € |  |  | Working group established In line with the National Strategy for prosecution of war crimes (2016-2020), working group for the preparation of the analysis of the achieved results in the implementation of the National Strategy for the Prosecution of War Crimes established The analysis of the achieved results in the implementation of the National Strategy for the Prosecution of War Crimes prepared and further steps presented |  |  | Activity is fully implemented The Working group finalized its work Еx ante analysis has been developed and is available at the website of the Ministry of Justice |  |  |  |
| 1.4.3.3. |  | Drafting and adoption of the new strategic document for prosecution of war crimes 2020-2024 as continuation of the National Strategy for prosecution of war crimes (2016-2020) |  |  |  | Working group of the Ministry of Justice the Government of Serbia | II quarter of 2021 |  |  | Budget of the Republic of Serbia 17.285 € |  |  | New strategic document drafted in line with the conclusions of the analysis |  |  | Activity is fully implemented. The Strategy for War Crimes Prosecution was adopted with the accompanying Action Plan in October 2021 in October 2021. Data on ex ante analysis and drafting process are available at https://www.mpravde.gov.rs/sr/sekcija/53/radne-verzije -propisa.php |  |  |  |
| 1.4.3.4. |  | Monitoring the effective implementation of the new strategic document for prosecution of war crimes |  |  |  | to be determined by the document | Quarterly since the adoption of the new strategic document |  |  | Budget of the Republic of Serbia Unknown at this time, will be determined in the new document |  |  | The new strategic document is being effectively implemented. Number of quarterly made reports on the implementation of the strategic document Number of recommendations for improving the procedure on war crimes Positively assessed findings from the Report by the EU and CSOs that prepare alternative reports |  |  | Activity is being successfully implemented. On June 30, 2022, a meeting of the Working Body for monitoring the implementation of the Strategy was held, at which the report on the implementation of the Strategy from the moment of its adoption, ending with the first quarter of 2022, was adopted. The report is published on the website of the Ministry of Justice. |  |  |  |
| 1.4.3.5. |  | Monitoring the Implementation of the Prosecutorial Strategy for the Investigation and Prosecution of War Crimes in the Republic of Serbia 2018 - 2023 |  |  |  | Prosecutor for war crimes Collegium War Crimes Prosecutors Office | Quarterly |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.3.2. |  |  | Analysis made for quarterly evaluations of the Prosecutorial Strategy published on the web site of the War Crimes Prosecutors Office Republic Public Prosecutor Office Annual Reports on the Application of the Prosecutorial Strategy |  |  | Аctivity is being successfully implemented The report on the implementation of the Prosecutorial Strategy for the 3rd and 4th quarters of 2021 was prepared and submitted in a timely manner to the Republic Public Prosecutor’s Office, and then published on the OWCP website. The revised Prosecutorial Strategy is in the final stage of development, together with the accompanying Action Plan. Until then, the current Prosecutorial Strategy (2018-2023) will be applied and its implementation will be monitored. A compilation of a consolidated report for the 1st and 2nd quarters of 2022 is underway, posted on the OWCP website and delivered to the Republic Prosecutor’s Office in a timely manner. |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT / INTERIM BENCHMARK |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 1.4.4. Recommendation: Step up security of witnesses and informants and improve witness and informant support services; IBM: Serbia strengthens its investigative, prosecutorial and judicial bodies including ensuring a more proactive approach and the confidentiality of investigations, providing for training for new and current staff members, improving its witness protection and victim support system and ensuring victims' rights and access to justice without discrimination |  |  |  |  |  |  |  | Security of witnesses and informants has been stepped up and support services for witnesses and informants have been improved. |  |  |  |  |  |  | - The number of witnesses in witness protection program and increased number of witnesses willing to appear in the war crime cases without protection; - Positive Annual progress report on the Republic of Serbia issued by the European Commission concerning the level of security of witnesses and informants and concerning functioning of support services for witnesses and informants; - Decreasing number of instances were witnesses status and information about them is put in jeopardy or publicly revealed; - Positive evaluation in the reports from relevant international and nongovernmental Organizations. |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |
| 1.4.4.1. |  | Activities aimed at establishing and improvement of the service for the support and assistance to witnesses and victims national wide network, based on results of the previous analyses, and taking into account already established services for the support and assistance to victims in courts and public prosecutor’s offices. |  |  | Ministry of Justice High Judicial Council State Prosecutorial Council Courts PPO |  |  | Continuously |  |  |  | Budget of the Republic of Serbia 282.932 € |  |  | The service for the support and assistance to witnesses and victims national wide network, established and being improved, based on results of the previous analyses, and taking into account already established services for the support and assistance to witnesses and victims in courts and public prosecutor’s offices |  |  |  | Activity is partially implemented. On April 22, 2021, the Government of the Republic of Serbia established a Coordination Body for Support to Victims of Crime and Witnesses in Criminal Proceedings, whose task is to continuously monitor and improve support to victims of crime and witnesses in criminal proceedings, including monitoring the implementation of the National strategies for exercising the rights of victims and witnesses with an accompanying Action Plan. The coordination body has held one meeting so far. In co-operation with the OSCE Mission to Serbia within the EU project entitled "Support to Victims and Witnesses of Crime in Serbia", the High Courts in Belgrade, Novi Sad, Kragujevac, Nis and Novi Pazar received specially equipped rooms where audio testimony will be provided -video link. Also, in cooperation with the OSCE Mission to the Republic of Serbia, reporting forms have been developed, which will enable monitoring of the implementation of the National Strategy. |  |
| 1.4.4.2. 6.2.11.4 (AP24) |  | Adopt adequate implementing laws to effectively implement the change of identity as protective measure for witnesses, in line with the article 45 of the Law on the Protection Program for Participants in Criminal Proceedings |  | Ministry of Justice and all relevant state organs that have any jurisdiction over the issue War Crimes Prosecutor’s Office In cooperation with the Service for the support to victims and witnesses |  |  |  |  | II quarter of 2021 |  | Budget of the Republic of Serbia 71.136 € |  |  | Relevant laws needed to implement the change of identity as a witness protection measure amended. |  |  |  | Activity is not implemented The War Crimes Prosecution Strategy was adopted in October 2021. This issue will be resolved in accordance with the defined measures of the strategy. At the beginning of March 2021, Protection Unit re-initiated the procedure of forming a working group that would be engaged in drafting the regulations from Article 45 of the Law on the Program for the Protection of Participants in Criminal Proceedings. The representatives of several ministries of the Government of the Republic of Serbia, whose competence includes keeping records on citizens, would work in the working group. Pursuant to the initiative of the Protection Unit, the Ministry of Justice, which is responsible for passing regulations related to the Program for the Protection of Participants in Criminal Proceedings, entrusted the Judicial Academy with coordination with representatives of competent state administration bodies. The participation of the representatives of the relevant ministries in the work of the joint body is necessary because the measure to protect the change of identity is materialized by issuing appropriate documents or documents, in a procedure that does not differ from the procedure for issuing an original personal document or document before the competent authority. Apart from the preliminary meeting between the representatives of the Unit and the director of the Judicial Academy - where the normative and methodological framework for the consistent application of the protection measure Change of Identity was clarified - organized by the Judicial Academy, a working meeting of representatives of the Protection Unit and the Ministry of State Administration and Local Self-Government was held on December 20, 2021. At the meeting, it was stated that in the shortest possible period, a working body should be formed from representatives of all competent ministries, which would work on drafting the proposal of the mentioned regulation. At the same time, it was agreed that the director of the Judicial Academy should establish contacts with representatives of other competent ministries. At the beginning of February 2022, the Protection Unit made a working version of the Rulebook on the manner of issuing an identity document - entering data in official records in the process of changing identity. It is expected that a working group will be formed and deal with regulations from Article 45 of the Law on the Program for the Protection of Participants in Criminal Proceedings. |  |
| 1.4.4.3. |  | Further capacity development and filling in the positions of psychologists in the War Crime Prosecutor`s Office to deal with victims and witnesses when there is a need, in accordance with the implementation of the Prosecutorial Strategy for the Investigation and Prosecution of War Crimes in the RS |  |  | War Crime Prosecutor`s Office |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia 20.424 € For 2021 and 2022, each 10.212 € |  |  | Working positions of psychologists filled in |  |  |  | Аctivity is fully implemented. The activity was completed. In January 2021, the OWCP recruited a full-time psychologist, who provides professional support to victims and witnesses as needed. |  |
| 1.4.4.4. |  | Improving administrative capacities of the Ministry of Interior’s Protection Unit through training |  |  | Ministry of Interior War Crimes Prosecutor’s Office Ministry of Justice Higher Court in Belgrade |  |  | Continuously |  |  |  | Budget of Republic of Serbia Unknown at this time |  |  | Improved administrative capacities of the Ministry of Interior’s Protection Unit through training. |  |  |  | Аctivity is being successfully implemented In accordance with the plan and program of professional training of police officers of the Protection Unit for 2022, the Protection Unit conducted regular trainings for members of the Units, which consisted of theoretical classes regarding the normative framework and practical classes in shooting and tactical actions. In accordance with that, from May 23 - June 03, 2022, testing of the police officers of the WP Unit was conducted, which included areas from testing knowledge of police officers from theoretical classes, acquired skills in the application of police powers and testing physical skills. |  |
| 1.4.4.5. 6.2.11.2 (AP24) |  | Strengthening the administrative capacity of the Ministry of Interior’s Protection Unit by increasing the number of staff and involving experts in psychology and social sciences from other police departments |  |  | Ministry of Interior |  |  | I quarter of 2021 |  |  |  | Budget of the Republic of Serbia Unknown at this time |  |  | Employees assigned to the Protection Unit |  |  |  | Аctivity is partially implemented The election procedure for filling six positions in the Protection Unit has been completed, through an internal competition, as follows: junior officer of the Protection Unit for operational affairs with protected persons (2 executors), operative worker of the Protection Unit for security protection affairs (2 executors), operative worker of the Protection Unit for operational support affairs (2 executors), an officer of the Protection Unit for operational affairs (1 executor), an officer of the Protection Unit for operational affairs with protected persons (1 executor) and officer of the Protection Unit for temporary program financing affairs protection (1 executor) and a decision on the selection of candidates is pending. In the reporting period, there were no realized admissions for a definite and indefinite period in the Protection Unit. The number of systematized jobs compared to the previous reporting period is unchanged and amounts to 62, as well as the number of employees which is 52. |  |
| 1.4.4.6. |  | Adoption of the National Strategy on the rights of victims and witnesses of crime with the accompanying Action Plan |  |  | Ministry of Justice Ministry of Interior High Judicial Council State Prosecutorial Council Supreme Court of Cassation RPPO |  |  | III quarter 2020 |  |  |  | Budget of the Republic of Serbia Negligible cost activity |  |  | National Strategy and the related Action Plan adopted |  |  |  | Аctivity is fully implemented National Strategy for Exercising the Rights of Victims and Witnesses of Criminal Offenses in the Republic of Serbia for the Period 2020-2025.was adopted at the Government session on July 30, 2020, and the accompanying action plan was adopted |  |
| 1.4.4.7. |  | Regular monitoring of the implementation of the National Strategy on the rights of victims and witnesses of crime with the accompanying Action Plan, especially strong procedural guarantees for victims of war crimes |  |  | Ministry of Justice Ministry of Interior High Judicial Council Supreme Court of Cassation RPPO |  |  | Quarterly reporting |  |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.4.1. |  |  | The Coordinating Body for Victims and Witnesses support has been established and regularly meets. Reports on the implementation of the Strategy and the Action Plan are periodically drafted. |  |  |  | Activity is being successfully implemented. The meeting of the Coordination Body was held on March 22, 2022. A report on the implementation of the Strategy is being prepared. The report will cover the period from the adoption of the Strategy, concluding with the 1st quarter of 2022. The report is expected to be adopted during the 2nd quarter of 2022. On June 30, 2022, a meeting of the Coordination Body for monitoring the implementation of the Strategy was held, at which the report on the implementation of the Strategy from the moment of its adoption, ending with the first quarter of 2022, was adopted. The report is published on the website of the Ministry of Justice. |  |
| 1.4.4.8. |  | Establishing a network of services nationwide to support victims, witnesses and injured parties in the investigation and all stages of the criminal proceedings. |  |  | Ministry of Justice Ministry of Interior Supreme Court of Cassation RPPO High Judicial Council State Prosecutorial Council |  |  | Need to consult the deadline within the National Strategy on the rights of victims and witnesses of crime with the accompanying Action Plan |  |  |  | Budget of the Republic of Serbia Budgeted within the activity 1.4.4.1. |  |  | A network of support and assistance services for witnesses and victims established at the national level. |  |  |  | Activity is partially implemented. The action plan envisages detailed dynamics of establishing the network. According to the available data gathered from higher courts in Belgrade, Novi Sad, Niš, Kragujevac and Novi Pazar, there are services for witnesses and victims in accordance with the Action Plan for the implementation of the National Strategy on the rights of victims and witnesses of crime (2020-2025.). In the Higher Court in Vranje there is no special service, but there is special office for victims and winesses of crime with the adequate equipment, donated earlier by the OSCE Mission in Serbia and by the Government of Norway. |  |
| 1.4.4.9. |  | Conduct training of judges, public prosecutors and police officers on the application of minimum standards on the rights, support and protection of victims in accordance with Article 25 of Directive 2012/29 / EU |  |  | Judicial Academy |  |  | Continuously |  |  |  | Budget of the Republic of Serbia Unknown at this time – will be determined in the Action plan within the activity 1.4.4.6. |  |  | Number of trainings held in relation to the training planned Number of judges, prosecutors and police officers trained in relation to those required/in needs of training |  |  |  | Аctivity is being successfully implemented During the reporting period, 4 one-day trainings on domestic violence (Phase 1) were conducted, in which a significant part of the training was dedicated to the protection and support of victims. The trainings were attended by the following participants: 37 judges, 6 assistant judges, 9 basic public prosecutors and deputy public prosecutors, 16 prosecutorial associates, 1 court secretary and 1 beneficiary of the JA. |  |
| INTERIM BENCHMARK |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 1.4.5. Serbia strengthens its investigative, prosecutorial and judicial bodies including ensuring a more proactive approach and the confidentiality of investigations, providing for training for new and current staff members, improving its witness protection and victim support system and ensuring victims' rights and access to justice without discrimination |  |  |  |  |  |  |  | Investigations are confidential including witness and informant testimony. |  |  |  |  |  |  | 1. Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; 2. Positive evaluation issued in Annual progress report on the Republic of Serbia by European Commission concerning improvement of Constitution’s provisions |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/ DEADLINE |  |  |  | FINANCIAL RESOURCES |  |  | RESULT |  |  |  | IMPLEMENTATION STATUS |  |
| 1.4.5.1. |  | Organizing round tables and lectures for the members of Ministry of Interior (War Crime investigative Service and Protection Unit) on the subject of „Basic communication with media“ |  |  | War Crimes Prosecutor’s Office Ministry of Interior |  |  | Continuously |  |  |  | Budget of the Republic of Serbia 7.200 € 2.400 € per year |  |  | Round tables organized and lectures delivered. |  |  |  | Аctivity is being successfully implemented During the reporting period, the Protection Unit held a meeting on April 20, 2022, with the representatives from OCSE Mission from the project: "Support to Strengthening the Rule of Law in the Republic of Serbia", of the OSCE Mission, and it was agreed to submit a training proposal for members the Protection Unit. |  |
| 1.4.5.2. |  | In line with the provisions of the National Strategy (activity 1.4.1.1.) assess confidentiality rules and their respect within relevant institutions, amend them where needed and strengthen control over implementation |  |  | War Crimes Prosecutor’s Office |  |  | Continuously |  |  |  | Budget of the Republic of Serbia See the budget under the activity 1.4.1.2. |  |  | Confidentiality rules and control over their implementation improved in line with the provisions of the National Strategy from activity 1.4.1.1. |  |  |  | Аctivity is being successfully implemented In accordance with the current National Strategy for the Prosecution of War Crimes (Art. 1.1.5), activities were implemented through the monitoring of positive regulations and their implementation through the application of measures to protect data from unauthorized access, disclosure and any other misuse, in accordance with the Law on Personal Data Protection. Persons who have been made aware in the last period of the work of the Office of the War Crimes Prosecutor are informed of the obligation to protect and preserve the confidentiality of data and information in accordance with the Data Secrecy Law and other laws and bylaws, part of which is the Order on the obligation to keep secrecy of confidential information. In the coming period, staff will continue to be informed about any changes in regulations relevant for access to confidential information, with regular monitoring of the strict compliance of all employees with the General Data Protection Regulation, and by monitoring the implementation of laws and bylaws in this area on the part of the War Crimes Prosecutor and the authorized Deputy Prosecutor. Since the new Law on Free Access to Information of Public Importance and Personal Data Protection has been adopted and is applied by the Office of the War Crime Prosecutor, all information and data that the Prosecutor’s Office makes public or provides to interested parties will be harmonized with this Law. The activity is carried out through the regular application of all valid regulations in the field of data protection against unauthorized access, publication and any other misuse. |  |

| - FIGHT AGAINST CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1. IMPLEMENTATION OF ANTI-CORRUPTION MEASURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| CURRENT STATE OF PLAY: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The legislative framework regulating anti-corruption in Serbia encompasses: National Anti-Corruption Strategy for the period 2013-2018 (“Official Gazette of RS“, No. 57/13); Revised Action plan for the implementation of the National Anti-Corruption Strategy for the period 2013-2018 (“Official Gazette of RS“, No. 61/2016); Law on Financing Political Activities (“Official Gazette of RS“, No. 43/11, 123/14 and 88/19); Law on Anti-Corruption Agency (“Official Gazette of RS“, No. 97/08, 53/10, 66/11-CC, 67/13-CC, 8/15- CC and 88/19); Law on the Prevention of Corruption – in effect from 1st September 2020 (“Official Gazette of RS“, No. 35/2019 and 88/19), Law on Lobbying (“Official Gazette of RS“, No. 87/2018), Criminal Code of Serbia (“Official Gazette of RS“, No. 85/05 88/05, 107/05, 72/09, 111/09,121/12, 104/13, 108/14, 94/16 and 35/2019); Law on Free Access to Information of Public Importance (“Official Gazette of RS“, No. 120/2004, 54/2007, 104/2009 and 36/2010); Law on Public Procurement (“Official Gazette of RS“, No. 124/12, 14/15 , 68/15); the new Law on Public Procurement – in effect from 1st July 2020 (“Official Gazette of RS“, No. 91/19), Law on Privatization (“Official Gazette of RS“, No. 83/14, 46/15, 112/15, 20/16 - authentic interpretation); Criminal Procedure Code (“Official Gazette of RS“, No. 72/11, 101/11, 121/12, 32/13, 45/13, 55/14 and 35/19); Law on State Audit Institution (“Official Gazette of RS“, No. 101/2005, 54/2007, 36/2010 i 44/2018 – other law), Law on Seizure and Confiscation of the Proceeds from Crime (“Official Gazette of RS“, No 32/13, 94/16 and 35/19); Law on Liability of Legal Persons for Criminal Offenses (“Official Gazette of RS“, No. 97/2008); Law on International Legal Assistance in Criminal Matters (“Official Gazette of RS“, No. 20/2009); Law on the Program of Protection of Participants in Criminal Proceedings (“Official Gazette of RS“, No. 85/2005); Law on organisation and competence of state authorities in suppression of organised crime, terrorism and corruption (“Official Gazette of RS“, No. 94/2016 and 87/18 - other law); Law on Public Prosecutor's Office (“Official Gazette of RS“, No. 116/2008, 104/2009, 101/2010, 78/2011 - other Law, 101/2011, 38/2012 - Decision of the Constitutional Court, 121/2012 and 101/2013, 111/2014 - Decision of the Constitutional Court, 117/2014, 106/2015 and 63/16); Law on the State Prosecutorial Council ("Official Gazette of the Republic of Serbia", no.116 / 2008, 101/2010 and 88/2011 and 106/2015); Law on Police ("Official Gazette of the Republic of Serbia", No. 6/2016, 24/2018 i 87/2018), Law on Property Origin and Special Tax – in effect commencing from March 11, 2021 ("Official Gazette of the Republic of Serbia", No.18/2020), Law on Tax Procedure and Tax Administration ("Official Gazette of RS", No. 80/02, 84/02, 23/03, 70/03, 55/04, 61/05, 85/05 - other law, 62/06 - other law, 63/06, 61/07, 20/09, 72 / 09 - other law, 53/10, 101/11, 2/12, 93/12, 47/13, 108/13, 68/14, 105/14, 91/15 - authentic interpretation, 112 / 15, 15/16, 108/16, 30/18, 95/18 and 86/19); Law on Protection of Whistleblowers ("Official Gazette of RS" No. 128/2014); Law on ratification the UN Convention against Corruption (“Official Gazette of Serbia and Montenegro - international contracts“, No. 12/2005); Law on the Confirmation of the Criminal Law Convention on Corruption ("Official Gazette of the FRY - International Treaties", No. 2/2002 and "Official Gazette of SCG - International Agreements", No. 18/2005); Law on the Confirmation of the Additional Protocol to the Criminal Law Convention on Corruption ("Official Gazette of the Republic of Serbia - International Agreements", No. 102/2007); Law on the Confirmation of the Civil Law Convention on Corruption ("Official Gazette of the Republic of Serbia - International Agreements", No. 102/2007); Law on the Confirmation of the United Nations Convention against Transnational Organized Crime and Supplementary Protocols ("Official Gazette of the FRY - International Treaties", No. 6/2001). In the Republic of Serbia there is developed consciousness and political will to eliminate corruption to the fullest extent, in order to achieve economic, social and democratic development of the country. The consequences of corruption are mostly linked to the impoverishment of society and the state, the drastic decline in trust in democratic institutions, as well as uncertainty and instability of the economic system. The Republic of Serbia is committed to achieving significant progress in the fight against corruption, with respect for democratic values, the rule of law and protection of fundamental human rights and freedoms. The Republic of Serbia has ratified all major international instruments in the fight against corruption. Generally, laws and regulations are mostly compatible with accepted international standards. In order to overcome deficiencies in the legislative solutions, the representatives of the Republic of Serbia are actively involved in the compatibility assessment conducted by European and international organisations, such as the evaluation by the Group of States against Corruption (GRECO) and the UN Office on Drugs and Crime. Plan to harmonise the internal legal system with the EU acquis for the period 2018-2021, has been determined in the National Program for the Adoption of the Acquis. Basic guidelines for planning the necessary legislative changes used to represent the measures previously identified in the Action Plan for the National Anti-Corruption Strategy for the period 2013-2018 and in Action Plan for Chapter 23, subchapter Fight against Corruption. National Anti-Corruption Strategy for period 2013-2018 and the accompanying Action Plan envisaged extensive field for the fight against corruption, such as political activities, public finance, privatization and public-private partnerships, the judiciary, the police, planning and construction, the media, prevention of corruption as well as range of concrete measures against corruption in the vulnerable areas such as: health care, taxes, education, customs and local self-government. Implementation of these measures is harmonised with the European Commission's recommendations and measures of priority reforms following the adoption of the Action Plan for Chapter 23, through Revised Action Plan for implementation of the National Strategy, adopted in 2017. On June 30th 2016, the Government of Republic of Serbia adopted Revised Action Plan for the implementation of National Strategy for the Fight against Corruption for the period from 2013 to 2018. All activities that are envisaged by the Action Plan for Chapter 23, which have also been prescribed in the Action Plan for the implementation of National Strategy, are monitored through appropriate activities in Action Plan for Chapter 23. As per percentage of implementation of Revised Action Plan for the implementation of National Strategy, 37% activities were implemented, 60% activities were not implemented whereas 3% activities were not assessed (activities were doubled or implementing entity was not properly defined or indicator was not properly defined so it was not possible to assess the implementation of the activity). ACA did not measure the effect given than many activities were deleted from the AP for implementation of the Strategy and incorporated into the AP for Ch 23. IMPLEMENTATION OF ANTI-CORRUPTION MEASURES The institutional design in implementation of anti-corruption measures encompasses: Coordination body for the implementation of the Action plan for the Implementation of the National Anti-Corruption Strategy in the period 2013-2018 (Coordination Body), Anti-Corruption Agency (ACA), Anti-Corruption Council (Council). The system for coordination and monitoring the implementation of National Strategy for the Fight against Corruption was established in 2013 for effective implementation of strategic documents in the field of anti-corruption. Coordination of measures from anti-corruption strategies was performed by the Coordination body. The Ministry of Justice (MOJ) provided administrative support to the Coordination body through the Group for Coordination (the Group). The Council and MOJ participated in the process of coordination. Coordination mechanism 2013 – 2018: As the fight against corruption represents one of the key priorities, the Government of the Republic of Serbia adopted the Decision on the establishment of the Coordination Body on August 7th 2014. The head of the Coordination Body was the Prime Minister. Members of this body were: ministers in charge of judiciary and finance and one member of the Anti-Corruption Council. The system of coordination was designed in a way that the Prime Minister resolves all the problems that arise in the implementation of the strategic documents, directs the implementation of anti-corruption measures and strategic documents and holds meetings at least once in six months. Competencies of the Coordination body were planned to be extended by amending the Decision on the establishment of the Coordination Body to also include the implementation of the Action Plan for Chapter 23, Subchapter fight against corruption. On the political-technical level, the State Secretary in charge of anti-corruption (at the MOJ) participated in the work of the Coordination body through coordination of the state bodies. Each state body responsible for the implementation of the Action plan determined one contact person for the communication with the State Secretary in charge of Anti-corruption at the MOJ. Also, Office for Cooperation with civil society determined one contact person for the communication with the State Secretary in charge of Anti-corruption at the MOJ. State Secretary in charge of anti-corruption, with the support of the Group, maintained regular bilateral and multilateral meetings with other state authorities, stakeholders of the Strategy and Action Plan. The State Secretary in charge of anti-corruption at the MOJ and the Group represented a link between all state authorities - stakeholders of the Strategy and Coordination body. Unfortunately, despite all invested efforts, the system of coordination did not manage to achieve its goals, due to the reasons listed bellow. New state of play: Gap analysis on the implementation of the National Anti-corruption Strategy its Action Plan for implementation and the Action Plan for Chapter 23(hereinafter: Gap analysis) was conducted in 2018 within IPA Project „Prevention and Fight against Corruption“, with aim to identify obstacles to more successful implementation of anti-corruption measures, deficiencies in the implementation of these measures, as well as measures to overcome deficiencies. Gap analysis, among other things, found that the coordination system which was set up on three levels - political, administrative and technical, was insufficiently balanced at the stated levels, which burdens the first level (political) with affairs of the administrative and technical level. Gap analysis recommends that the political level should be made more operational, in such a way that an official in the Cabinet of the Prime Minister should be appointed to coordinate the implementation of the measures. Furthermore, the Ministry of Justice should play a leading role at the level of political - technical coordination, as the Secretariat for coordination at the political level. The Ministry of Justice must have clear powers for issuing instructions for coordination of the implementation of measures. The Ministry of Justice, participates in the political and technical coordination of the implementation of measures. The work of the Coordination Body should be based on clear procedures. Therefore, a new Decision on the Coordination Body (activity 2.1.1.2.) needs to be drafted, which will take into account the experiences from the previous coordination process as well as Gap analysis recommendations. This co-ordination mechanism will primarily be used to coordinate measures of the Operational Plan for the Prevention of Corruption in areas of particular risk (activity 2.1.1.1.) Operational plan will represent overview of all anticorruption policies since 2005, when the first National Anti-corruption Strategy was adopted, over second National Strategy 2013-2018, while taking into consideration experiences gained from implementation of AP 23, Subchapter Fight Against Corruption. Operational Plan will include the overview of the actions of the mentioned strategies and action plans, their level of implementation as well as impact assessment of implemented measures. This Operational plan will represent the main basis for drafting the new ambitious national strategy. Operational plan will by-pass period between two major national strategies and AP 23 on one hand, and the third national strategy on the other. Operational Plan will reiterate firm commitment of the Republic of Serbia towards major reforms already conducted in the field of prevention and repression of corruption and their consolidation in the legal system of the Republic of Serbia, setting a clear path in creating and developing anti-corruption policies. Monitoring the implementation of anti-corruption measures is performed by the independent state body Anti-corruption Agency (ACA). ACA monitors the implementation of anti-corruption strategic documents, pursuant to the law governing the establishment and jurisdiction of ACA. The competencies of ACA were further extended by adoption of the new Law on the Prevention of Corruption (new Law on Anti-Corruption Agency). New state of play: Gap analysis recommends strengthening of monitoring mechanisms in the work of Anti-Corruption Agency, with the aim of better reporting and implementation of anti-corruption measures arising from the Action Plan. The Anti-Corruption Agency should proactively seek the necessary information for monitoring, and at the same time should be available for assistance and support. Within its proactivity, Anti-Corruption Agency should develop reporting guidelines in line with the newly established online monitoring form. Authorities responsible for implementation of AP 23 activities should eliminate all obstacles in their internal procedures that prevent quality reporting. The new Law on the Prevention of Corruption extends the competence of the Agency for monitoring the implementation of Revised AP for CH 23, subchapter Fight against Corruption as well as all other future strategies and action plans in the field of prevention and fight against corruption. Analysis of compatibility of Anti-corruption legislation in the Republic of Serbia with EU acquis and international standards was conducted. The mentioned analysis shows that the Serbian legislation is broadly aligned with the EU acquis and relevant international standards in the field of fight against corruption. Taking into consideration lessons learned and insights derived from the previous coordination process it is necessary to set up a more efficient coordination mechanism. In order to ensure effective strategic management and top down planning, as well as implementation and monitoring of the activities within the prescribed deadlines a new mechanism should be put in place. After the adoption of the Revised AP for CH 23 the picture of coordination and monitoring will be substantially changed. Coordination body for implementation of NACS 2013-2018 will be abolished, since it had exhausted its purpose, given that the National Strategy expired in 2018. Namely, it shall be replaced by Coordination body for the implementation of the Operational plan (2.1.1.2.), The Coordination mechanism will consist of the new Coordination body and three Implementation Groups. The new Coordination body shall be presided by the Prime Minister and the Minister of Justice. It shall also include Minister of Interior, Minister of Finance, Minister of Education, Minister of Public Administration and Local Self-Government and Minister of Health. In order to achieve a sufficient level of political accountability while withholding prompt operability of the Coordination body, the respective ministers, expect the Minster of Justice, may be represented by their state secretaries at the meetings of the Coordination body. The Coordination body shall ensure political level coordination for implementation of the activities, deliver guidelines in that respect, monitor the work of implementation groups and promptly solve problems that occur in the process of implementation. Meeting of the Coordination body shall be held semi-annualy or in case when a problem needs to be immediately resolved and urgent actions taken in that regard. Each Implementation Group shall consist of representatives of the lead institutions responsible for implementation of activities in particular area falling within the scope of work of the Group. These Groups are responsible for operational and technical management needed for the implementation of the activities within the envisaged timeframes. Implementation Groups will report to the Coordination body quarterly. They will also report on any obstacles and risks encountered or predicted for implementation of the activities. Reporting serves to facilitate track progress towards implementation of the activities, to help institutions identify risks and problems in achieving the results in a timely manner and to design measures to manage risks effectively or to eliminate problems that have already arisen. Ministry of Justice will provide administrative support to the Coordination body by organizing the meetings of the Coordination body, preparing materials for its sessions, collecting and distributing the reports submitted by the Implementation Groups. Monitoring will be carried out by ACA. Regarding the activities from AP 23, subchapter Fight Against Corruption, coordination will be conducted by Coordination Body for CH 23 (for more details, please see Introductory part – Judiciary) Monitoring of AP 23, subchapter Fight Against Corruption, will be carried out by ACA, in line with the new Law on the prevention of corruption. President of Negotiating Group for CH 23/Deputy President shall attend all the meetings of the Coordination body for implementation of Operational plan, ensuring link between Coordination body for implementation of AP 23 and Coordination body for implementation of Operational plan. The President of Negotiating Group for CH 23/Deputy President will brief Coordination body on implementation of activities from AP 23, subchapter Fight against Corruption, and report on all outstanding issues which require high-level political coordination in order to foster AP 23 towards full and timely implementation and to maintain consistency in anti-corruption policies in the country. PREVENTION OF CORRUPTION The legislative framework regulating prevention of anti-corruption in Serbia encompasses: Law on Financing Political Activities (“Official Gazette of RS“, No. 43/11, 23/14 and 88/19); Law on Anti-Corruption Agency (“Official Gazette of RS“, No. 97/08, 53/10, 66/11 –CC, 67/13-CC, 8/15-CC and 88/19); Law on the Prevention of Corruption (“Official Gazette of RS“, No. 35/2019 and 88/19); Law on Free Access to Information of Public Importance (“Official Gazette of RS“, No. 120/2004, 54/2007, 104/2009 and 36/2010); Law on Public Procurement (“Official Gazette of RS“, No. 124/1214/2015 and 68/2015); the new Law on Public Procurement – in effect from 1st July 2020 (“Official Gazette of RS“, No. 91/19), Law on Privatization (“Official Gazette of RS“, No. 83/14, 46/15 and 112/15), Law on Protection of Whistleblowers ("Official Gazette of RS" No. 128/2014), Law on Lobbying ("Official Gazette of RS" No. 87/18“), Law on State Audit Institution ("Official Gazette of RS" No.101/2005, 54/2007, 36/2010 and 44/2018 – other law). The most important bodies representing institutional framework in this matter are: Anti-Corruption Council (Council), Anti-Corruption Agency (ACA), Commissioner for Information of Public Importance and Personal Data Protection (the Commissioner), State Audit Institution (SAI). The key issues in the field of prevention of corruption involve: conflicts of interest, financing political activities, access to information of public importance, public procurement, protection of whistleblowers, professionalization and integrity of public administration. The key measure for prevention of corruption in the Action Plan for chapter 23 was the adoption of new Law on Anti-Corruption Agency (new Law on Prevention of Corruption). This Law regulates the field of prevention of corruption in a comprehensive manner. The Anti-Corruption Agency (ACA) is an independent state authority, which reports to the National Assembly for its operation. Law on the ACA provides a wide range of responsibilities of the Agency relating to resolving the incompatibility of public offices and conflict of interest, controlling the assets of public officials and keeping a register of public officials, property and gifts; controlling the financing of political subjects, addressing the complaints of citizens, education, supervision over the implementation of the strategic framework, the analysis of regulations, and so on. New state of play: Within recommendations of the analysis „Recommendations for normative amendments for full transposition of the GRECO recommendation no. 13 in the Draft law on the Prevention of Corruption of the Republic of Serbia”, conducted within MDTF-JSS Project, the necessity for internal pre-composition of Anti-Corruption Agency competences, as a complex independent authority, was especially emphasized. It was recommended that the Board of the Agency should retain only the second instance jurisdiction in relation to the decisions of the director, while the role of the Director of the Agency should be strengthened with competences which now belong to the Board. Election of Director of the Agency and members of the Board should be subordinated to the principle of meritocracy. It was recommended that the Agency should have the right on direct electronic access to databases of relevant state authorities. Furthermore, there is the obligation of other legal entities to develop and maintain enhanced cooperation with the Agency as well as to submit required relevant data to the Agency. On 21th May 2019, National Assembly adopted new Law on the Prevention of Corruption. The Law on the Prevention of Corruption is completely aligned with Analysis „Recommendations for normative amendments for full transposition of the GRECO recommendation no. 13 in the Draft law on the Prevention of Corruption of the Republic of Serbia”. New law further strengthens the independence of the Anti-Corruption Agency, enables sufficient financial and human resources for its work as well as connection with other relevant authorities (including access to their databases). The new Law on Prevention of Corruption redefines and improves regulations concerning conflicts of interest and incompatibility of public functions and empowers the Agency with new tools for controlling the assets of public officials and keeping the registers of public officials, property and gifts. Agency is explicitly empowered to initiate misdemeanor and criminal proceedings. Administrative investigations of the Agency are further strengthened through the right to direct access to relevant state authorities’ databases. The Agency also received new competences in connection with the Law on lobbying, in terms of keeping the registry of lobbyists, and monitoring of lobbyists and lobbying entities. Training courses for more than 4,000 participants were held in the fields of ethics and integrity, integrity plans, reporting on the National Strategy for Fight against Corruption and accompanying Action Plan, control of assets, conflicts of interest, control of financing of political activities, including training courses that were held within Twinning project "Prevention and Fight Corruption " Within Twinning project "Prevention and Fight Corruption", the test software application for monitoring the implementation of activities prescribed in Subchapter Fight against corruption of Action Plan for Chapter 23 was developed. Under the same project, the enhanced software application related to the integrity plans was developed. The task of the Anti-corruption Council is to: review the activities in the field of fight against corruption, to propose to the Government measures to be taken in order to effectively fight against corruption, monitor their implementation, and take initiatives for the adoption of regulations, programs, and other acts and measures in this field. As an advisory body of executive power, Anti-Corruption Council used to regularly prepare and submit reports and initiatives to the Government on the phenomena of corruption, systemic corruption, but there was lack of interactive relation between the two bodies. The envisaged measures are presented below and their implementation will ensure that the Government and competent state authorities systematically review reports and initiatives of Anti-Corruption Council in implementing measures in the field of fight against corruption. New state of play: The Anti-Corruption Council is advisory body of the Government of the Republic of Serbia, established by the Government Decision on 11 October 2001 (“Official Gazette” no. 59 01) in line with respective Law on Government. The Government's Decision has been changed several times, the last time in 2006. In the meantime, a new Law on Government was adopted in 2005 ("Official Gazette” no. 55/2005, 71/2005 - correction, 101/2007, 65/2008, 16/2011, 68/2012 - Decision of the Constitutional Court, 72/2012 7/2014- Decision of the Constitutional Court, 44/2014 and 30/2018 – other Law), but Decision on the establishment of the Anti-Corruption Council still remains nonaligned with the new Law on the Government. This situation has contributed to the difficulties in the Council's work. Analysis” Anti-Corruption Council of the Government of the Republic of Serbia in the light of best practices in the European Union” was conducted within IPA Project “Prevention and Fight against Corruption”. The analysis contains recommendations for improvement of the Council's work, of which we highlight following key recommendation: to introduce the possibility that Council is composed of key public administration holders dealing with relevant information in the anti-corruption area, and prominent representatives from various areas of social life proposed by the Council, whereby non-governmental members have to be in majority. There is a necessity to harmonise Decision governing the work of the Council with the new Law on the Government, which is also a recommendation from the abovementioned IPA project analysis that states the need to harmonise the Decision on establishing the Council and the Rules of Procedure of the Council (activity 2.1.2.2.). The adoption of the Law on Financing Political Activities the Republic of Serbia has significantly improved the legal framework in this area and fully implemented the second evaluation round GRECO recommendations. The Anti-Corruption Agency, on May 31st 2013, presented the First report on the control of financing of political entities - the election campaign after the elections in 2012. Implementation of the Law indicated that the changes of certain legal provisions would lead to better implementation in practice, and in particular the provisions concerning the mechanisms for control of financial reports, obligation to deliver financial reports and sanctioning. Political entities are not compulsory subjects of the audit of the State Audit Institution (SAI). An additional problem in this area is the lack of the necessary capacity of authorities responsible for the control of funding. Law on amendments and supplements of the Law on Financing Political Activities (“Official Gazette of RS“, No. 123/14) introduced certain novelties in this area: political parties now have the opportunity to buy real estate from the budget sources with condition that real estate is used only for purposes of performing political activities; annual financial reports are submitted to the Anti-Corruption Agency and published on ACA official web-site, instead of submitting to the Official Gazzette for publishing; sources for financing of regular activities of political subjects are also used for financing costs of election campaign. New state of play: Analysis on the effects of implementation of the Law on Financing of Political Activities was conducted, with recommendations for improvement of legislative framework in this area. The Law on Financing of Political Activities was amended in December 2019 ( "Official Gazette of RS" No. 88/2019). Amendments to the Law were made with the aim of enhancing accountability of political parties that are participants in the elections, both in terms of use and dispose of public resources, and obligations of the Agency for Fight against Corruption in terms of sanctioning political entities that do not comply with the provisions of the law in the election campaign. Mechanisms for the prevention and elimination of conflicts of interest in Serbia have been improved by adopting the Law on the ACA ("Official Gazette of RS" No. 97/2008, 53/2010, 66/2011 - Decision of the Constitutional Court, 67/2013 - Decision of the Constitutional Court, 112/2013 - authentic interpretation and 8/2015 - Decision of the Constitutional Court) which governs the issue of conflicts of interest that applies to officials performing public functions. Legal provisions preventing conflicts of interest did not exist or existed only partially for other employees in state bodies and organisations. Inconsistency of legislation in this area was described as the main obstacle in the annual report of the Anti-Corruption Agency in 2013. The lack of a coherent legal framework that would create the same mechanisms for the prevention and elimination of conflicts of interest for all employees in the public sector hampered the fight against this phenomenon. Consequently, awareness of the concept of conflict of interest and methods for its prevention were not sufficiently developed at all levels. As the Republic of Serbia ratified international instruments which, inter alia, regulate the issue of conflict of interest, appropriate measures were undertaken in order to harmonise legislation and implement international standards. New state of play: Law on Civil Servants ("Official Gazette of RS" No. 79/05, 81/05 - correction, 83/05 - correction, 64/07, 67/07 - correction, 116/08, 104/09, 99 / 14, 94/17 and 95/18) improved and significantly tightened the rules on conflict of interest for civil servants (Article 25 of the Law, amended in 2018). The Law on Employees of Autonomous Provinces and Local self-government Units ("Official Gazette of RS" No. 21/16, 113/17, 113/17 - other law, 95/18) regulates conflict of interest of employees in the bodies of local self-government units and autonomous provinces (Article 9 and articles 39-46). Law on Employees in the Public Service ("Official Gazette of the Republic of Serbia", No. 113/17, 95/18 and 86/19), in effect commencing from 1st January 2021 regarding employees in public services (education, science, culture, health, social protection) regulates prevention of conflict of interest in the work of employees in these areas (articles 27 and 28). Law on Public Agencies ("Official Gazette" No. 18/05, 81/05 - correction, 47/18) prescribes application of the regulations applying on prevention of conflict of interest in the work of public servants. Along with the changes to the concept of conflict of interest of officials that perform public functions, prescribed in the new Law on the Prevention of Corruption, a system for prevention of conflict of interest in the public administration is completed. The UN Convention against Corruption recommends Member States to consider introducing a crime "Illicit enrichment" if it was in accordance with the Constitution and the fundamental principles of the national legal system. The criminal legislation of the Republic of Serbia still does not provide the alleged offense, given that it may be contrary to the fundamental principles of criminal law and the principles of individual responsibility of the offender. On the other hand, the Anti-corruption agency has the authority to monitor and control the reporting of assets and revenue of officials, and in the case of possible irregularities identified, there are no clear mechanisms for sanctioning. Control of assets and income is particularly important from the aspect of implementation of financial investigations and tracing criminal proceeds. National Anti-Corruption strategy for period 2013- 2018 and Action Plan for Chapter 23, subchapter Fight against Corruption identified the need for a comprehensive analysis of the institutional and legal framework for finding effective solutions for cases of illicit enrichment. The chapter on criminal offenses against the economy of the Criminal Code of Serbia) is harmonised to a great extent with the Council of Europe Criminal Law Convention on Corruption, the UN Convention against corruption, the OECD Convention on Combating Bribery of Foreign Public Officials in International Business Transactions and other international instruments. The GRECO report on Serbia’s compliance with the recommendations analysed the criminal offenses of corruption in the third round of evaluation and offered five recommendations for improvement. Additional report on implementation has been sent to GRECO Secretariat. GRECO concluded that Serbia has implemented satisfactorily fourteen of the fifteen recommendations contained in the Third Round Evaluation Report. By that, the third-round compliance procedure in respect of Serbia was finished. The need to fully align the chapter on criminal offenses against the economy of the Criminal Code with international instruments has been recognised in the National Anti-Corruption Strategy for the period from 2013 to 2018, the accompanying Action Plan, and in Action Plan for Chapter 23, subchapter Fight against Corruption, providing the improvement of economic and corruption offenses in the Criminal Code. New state of play: In November 2016, extensive amendments to the Criminal Code ("Off. Gazette no. 94/16") were adopted. These amendments include revision of Criminal Code heads related to crimes against the economy and crimes against official duty. With these changes, Criminal Code is modernised thus providing a good framework for the work of the police and public prosecutors offices. Also, in November 2016 new Law on organisation and competence of state authorities in suppression of organized crime, terrorism and corruption (“Official Gazette of RS“, No. 94/2016 and 87/18 - other law) was adopted, introducing a complete specialization in police, public prosecutor's offices and the courts for this type of crime, as well as modern tools for prosecution of these crimes. IPA project "Prevention of and Fight against Corruption" carried out an analysis "Illicit enrichment - Analysis of the Serbian model," whose conclusion is that Serbian model of criminal legislation provides a comprehensive solution in this area, and that is not necessary to make further changes. Analysis urges Serbia to monitor the application of its legislation in relation to the corruptive offenses where the perpetrators are officials performing public functions, and to, in accordance with results of the analysis, estimate the need of establishing” illicit enrichment” criminal offense, in accordance with the UN Convention against Corruption. Application of Criminal Code will be closely monitored in accordance with the recommendation of the above-mentioned analysis (activity 2.2.4.1.). Monitoring the implementation of the Criminal Code as well as the Law on Organisation and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption will be conducted by the Ministry of Justice. Partner institutions are courts and public prosecutors’ offices of general and special jurisdiction, with obligation to deliver reports on number of initiated and completed proceedings. Ministry of Justice draws up uniform report. Furthermore, in March 2020, the National Assembly adopted the Law on origin property of and special tax, which establishes system of determination and taxation of illicit property. The right of citizens to access information of public importance was established by the Law on Free Access to Information of Public Importance. Despite the fact that the current law is based on high international standards of exercising the rights from the perspective of methods for the protection of the rights, authorities coverage, the number and nature of exceptions to the principle of free access to information and similar criteria, practice of application of this law showed that improvements are necessary. From the standpoint of the legal framework for the exercise of the right of access to information, it is important that the Government, on the initiative of the Commissioner, determined the liability of public authorities to obtain the opinion of competent institutions in the process of adopting regulations through the amendments of the Government’s Rules of Procedure, and enabled the availability of materials and information to the public through the amendments of the Rules of Procedure - obligation of public debate in drafting laws. New state of play: In the field of ​​access to information of public importance, the "Analysis of the Law on Free Access to Information of Public Importance, with recommendations for its amendments" was carried out. During the process of drafting amendments of the Law on Free Access to Information of Public Importance, the comments of SIGMA experts have been incorporated into the Draft Law to the extent possible.Capacities of Commissioner for Information of Public Importance and Personal Data Protection are strenghtened - Rulebook on internal organisation and classification of jobs in Commissioner's Office was amended on 10 May 2017, by which the Commissioner's Office has systematized jobs for 94 employees. Current number of full-time employees in Commissioner's Office is 74. Implementation of the Law on Free Access to Information of Public Importance is regularly monitored, on a monthly, quarterly and annual basis. Training courses for officials authorised to decide on requests for free access to information are continuously performed, and continuous approach to training will continue in the framework of the Revised Action Plan for CH 23. The Republic of Serbia has a legal framework that guarantees a wide range of public access to information of public importance, which is a fundamental right in a democratic society. The implementation of regulations in this area, in connection with the respect of the right to personal data protection and the presumption of innocence, still represents a challenge. Exposure of the details of investigations based on anonymous sources of information that was "leaked" from police action or criminal prosecution, may jeopardize the investigation, undermine the presumption of innocence and violate the right to privacy. In such cases, the absence of adequate response against persons who have exposed sensitive and confidential information from the investigation is notable. The aim of the regulations on personal data protection is the protection of fundamental human rights, which requires that the information can only be obtained in accordance with the law - under strict conditions and for the purposes defined by law. Therefore, it is necessary to strengthen internal control mechanisms and sanctioning to prevent the disclosure of confidential information to the media. One of the main goals of the previous Public Administration Reform Strategy (PAR Strategy) for the period 2004 - 2013 was the professionalization and de-politicization of public administration. Little progress was made in this field a, which is the reason why Public Administration Reform Strategy in Serbia, adopted in February 2014, provides a continuation of the ongoing reform activities and extends them with the system of state administration in the public administration system. The two key objectives of the new strategy relating to the de-politicization of public administration were the establishment of a harmonised public service system based on merit and promotion of human resource management, and the strengthening of transparency, ethics and accountability in the performance of public administration. Government of the Republic of Serbia adopted accompanying Action plan for the implementation of PAR Strategy on March 19, 2015, which further regulates numerous activities for realisation of stipulated goals. It is planned to achieve the results in this area by introducing civil service system based on the principles of de-politicization, professionalization, as well as a model of progress and reward according to merit (merit system). Special attention is given to clearly and precisely define the requirements and criteria for candidate selection and promotion, especially in the case of managerial jobs, i.e. position. In the area of control mechanisms, regulations on internal audit and financial management and control are aligned with international standards, Central Harmonization Unit continued to direct the technical activities, in particular training and certification of internal audit. New state of play: In the Republic of Serbia, in accordance with the strategic directions set forth in the Public Administration Reform Strategy ( "Off. Gazette" No. 9/14, 42 / 14, and 54/18 - correction) there is ongoing comprehensive reform process of the legislation dealing with the system of labor relations and wages of employees in public administration, with the aim to improve the legal framework on unique basis, regulating the status of employees in public administration, in accordance with the principles of de-politicization, professionalism and merit. The Law on Employees of Autonomous Provinces and Local self-government Units ( "Official Gazette of RS" No. 21/16, 113/17, 113/17 - other law, 95/18), in effect since 1 December 2016 in the bodies of local self-government and autonomous provinces, prescribes for the first time the system of labor relations in autonomous provinces and local self-governments in a comprehensive manner, in order to establish the basic principles of the civil service system, based on the standards adopted in modern comparative legal systems. Law on Employees in the Public Service ("Official Gazette of the Republic of Serbia", No. 113/17, 95/18) was adopted, and it is in effect commencing from 1st January 2020. Law regulates labor status and salaries of employees in public services (education, science, culture, health and social protection), establishes system of labor relations in public services based on merit and introduces the functions of human resources management through mandatory institutes (staff planning, the competition process, evaluation of work results, etc.). Amendments to the Law on Public Agencies ( "Official Gazette" No. 18/05, 81/05 - correction, 47/18), introduce principle of merit in the system of employment in public agencies, through mandatory checks of professional training, knowledge and skills of the candidates in the selection procedure. Law on Amendments to the Law on Civil Servants (‘’Official Gazette’’, No. 79/05, 81/05 - correction, 83/05 - correction, 64/07, 67/07 - correction, 116/08, 104/09, 99/14, 94/17, 95/18), provides a legal basis for introducing the system of competencies in all human resource management functions for the purpose of improving and enhancing the employment process and strengthening the competition process that allows greater impartiality and transparency, improving the evaluation system and strengthening professional training. Within Action Plan for implementation of Public Administration Reform Strategy for period 2018-2020 (‘’Official Gazette’’, No. 54/18), there are new measures developed, which will contribute in establishment of harmonised system of labor relations and salaries in the public administration based on the principles of transparency and fairness, as well as establishment and improvement of functions of human resources management services in public administration and local self-government units, through the introduction of new instruments and capacity building for human resources management services. Positive legal framework of the Republic of Serbia now does provide adequate protection for persons reporting suspicions of corruption or any other illegal actions (whistleblowers) as they may suffer some consequences and often the ones that affect their employment status. In accordance with previous reports on the progress of the Republic of Serbia in the process of European integration, while keeping in mind the United Nations Convention against Corruption, in response to perceived shortcomings of the existing system of protection, the National Anti-Corruption Strategy for the period 2013 - 2018, and the related Action Plan stipulated the obligatory enactment of a comprehensive law to regulate the issue of the protection of whistleblowers. The Law on protection of whistleblowers was adopted by the National Assembly in November 2014 and entered into force in June 2015.The main aim of the law is to establish an efficient and effective protection of whistleblowers. In addition to establishing an adequate legal framework, a series of measures for the effective implementation of regulations in practice and awareness raising about the importance and methods to protect whistleblowers were envisaged. For that purpose, within preparatory activities for effective implementation of the law, official trainers hired by Judicial Academy, conducted nearly 50 professional trainings for judges of all higher courts, for the territory of four Appellate courts in Serbia. New state of play: Implementation of the Law on Protection of Whistleblowers is regularly monitored through the preparation of the Ministry of Justice annual reports. Annual reports for 2015-2016, 2016-2017 and 2017-2018 were prepared and published on the Ministry of Justice official website. Since the beginning of the implementation of the Law on Whistleblowers (5th June 2015) to 31st December 2019, in all courts in the Republic of Serbia there are 774 cases received, of which 714 are resolved and 60 are unresolved. Monitoring of the implementation of the law will be continued, within the framework of the Revised AP 23, subchapter Fight against Corruption. In the global professional community, Law on Protection of Whistleblowers is characterized as a "gold standard" in whistleblowers protection. Training courses in this area have been conducted regularly, and the civil sector that deals with the protection of whistleblowers is growing stronger. In 2018 only, 16 training courses in the field of protection of whistleblowers were held for 293 representatives of judicial authorities (judges, judicial assistants, prosecutors, prosecutorial assistants, users of initial training of the Judicial Academy) as well as representatives of civil society organisations and trade unions. Within the IPA project "Prevention of and Fight against Corruption" the “Analysis of best practices in whistleblowers protection” was carried out. Republic of Serbia will continue to monitor the effects of the Law on Protection of Whistleblowers in terms of state authorities’ proceedings regarding whistleblowers disclosures (activity 2.2.7.3.). On 13 November 2018, Serbia adopted the Law on Lobbying (‘’Official Gazette’’, No. 87/18). The law has been in effect since September 2019. Lobbying is defined as an activity that influences the authorities of the Republic of Serbia, autonomous provinces and local self-government bodies, bodies of public authority holders, founded by the Republic of Serbia, autonomous province or local self-government unit in the process of adopting laws, other regulations and general acts within the jurisdiction of those authorities, in order to achieve the interests of users of lobbying, in accordance with the law. This law regulates the conditions and manner of lobbying, lobbying rules, registry and records related to lobbying and other issues of importance for lobbying. The Anti-Corruption Agency plays a significant role in the process of registration and supervision of lobbyists and lobbying entities. The Law on Public Procurement (as follows: PPL) provided a series of measures to strengthen control and supervision over its implementation. There are special provisions on the prevention of corruption and conflict of interest, as well as greater transparency in public procurement procedures. The Public Procurement Office (PPO) and the Republic Commission for the Protection of Rights in Public Procurement Procedures (RC), were given new powers and greater authority. PPO supervises the implementation of the Law on Public Procurement. In order to prevent un-reasoned implementation of the negotiation procedure without a prior public call, an obligation to obtain the prior opinion of the PPO was introduced. It is introduced that the PPO and the State Audit institution (DRI) monitor procurement plans and the merits of changes to public procurement contracts. A longer statute of limitations for violations of Public Procurement (3 years) is prescribed. PPO has received authorisation for initiating misdemeanor proceedings, while the RC is responsible for prosecution in the first degree. Both institutions are responsible for initiating the procedure for the determination of void public procurement contract. RC in cases prescribed by law terminates public procurement contract, impose fines and decides on prohibition of misusage of right to petition for protection of the right. A key problem during the past year of implementing the new system of supervision and control of the implementation of the Law on Public Procurement is the limited administrative capacity of PPO, above all in terms of personnel. It is also necessary to analyse the effects of all mechanisms of supervision and control, and in accordance with the findings of the analysis make changes through amendments to the Public Procurement Law, as well as make recommendations in respect of other legislation. Cooperation between the institutions in the system of supervision and control is significantly improved from the beginning of implementation of the Law on Public Procurement on April 1st 2013, but it is necessary to work on its further improvement. New state of play: Law on Public Procurement was amended in 2015 (‘’Official Gazette’’, No. 124/12, 14/15 and 68/15). Amendments to the law determined series of measures with aim of further strengthening control and supervision of its implementation, specific provisions on the prevention of corruption and conflict of interest, as well as the provisions related to greater transparency in public procurement procedures. Public Procurement Office competencies have also been expanded in terms of monitoring the implementation of the Law and initiation of misdemeanor procedures. The new Law on Public Procurement was adopted in December 2019 (‘’Official Gazette’’, No. 91/19), in terms of better implementation of public procurement principles, as well as further harmonization with the EU acquis. Analysis of the effects of the application of mechanisms for monitoring, oversight and control of public procurement was conducted, as well as Needs analysis of the Public Procurement Office concerning staff and technical capacity. The Rulebook on internal organisation and job classification in the Public Procurement Office was adopted on 11 January 2018, by which number of employees in PPO is increased. Further strenghtening of staff capacities in PPO is expected. Public Procurement Portal (http://portal.ujn.gov.rs/) has been upgraded by means of introducing new contents and by upgrading the search system (publishing contracting authorities' procurement plans, publishing procurements to be conducted by international procedures, development of Portal's page in English, upgrading the searching, establishing the register of public contracts, improving the reporting system). New Public Procurement Portal will be developed, in line with the new functionalities arising from the new Public Procurement Law. In 2019, a new Public Procurement Law is adopted in order to increase transparency and efficiency in public procurement and to strengthen control procedures in public procurement, with aim to further harmonise PPL with the EU acquis. Republic of Serbia will continue to monitor implementation of the law. Training courses for police, public prosecutors and courts in this area will continue to be organized in the future. Privatization process in Serbia has proved to be one of the most critical areas of corruption. The report of the Anti-Corruption Council and many other indicators point to a number of irregularities that have occurred due to a series of inaccuracies and non-transparency of the privatization legislation. Such vagueness of regulations has created numerous opportunities for abuse. In addition, many of the privatization contracts contain violations of the equivalence of benefits, which was enabled by inadequate control, both in terms of performance of the contract, and in the exercise of powers of the Director of the Privatization Agency. The National Anti-Corruption Strategy in the period from 2013 to 2018 provides a number of measures to prevent corruption in the privatization process. They can be grouped into two categories: changes of the corruptive provisions of the rules and improvement of the conduct of the competent authorities in the detection and prosecution of criminal offenses in the privatization process. New Law on Privatization ("Official Gazette of RS" No. 83/2014) was adopted in order to improve the legal provisions of the privatization process and eliminate the deficiencies that have led to numerous abuses. The adoption of the new law represents the beginning of implementation of the Action Plan for implementation of the Strategy, which provides a number of other measures to improve these areas. New state of play: The Law on Public Enterprises (“Official Gazette of RS”, no. 15/16 and 88/19) was adopted in 2015. During the drafting of the Law on Public Enterprises, special attention was paid to issues concerning the appointment procedure of directors (terms and conditions, criteria, actions of the Commission for the appointment of directors, the possibility of dismissal of the director of a public enterprise, the period of appointment of acting director). The law defines and tightens conditions for the election of members of the supervisory board, both in terms of work experience and responsibilities, and expands criteria for termination of the mandate of the President and members of the Supervisory Board before the expiration of the period for which they are appointed. Executive Board is no longer exists, and it is envisaged that Director elects executive directors, in order to personalize responsibility both of directors and executive directors. The criteria and elements for determining the criteria for the appointment of directors of public enterprises are determined by the Regulation on the Criteria for the Appointment of Directors of Public Enterprises (“Official Gazette of RS", no. 65/16). The Law on Public Enterprises was amended in December 2019 (“Official Gazette of RS”, no. 88/19), in terms of greater liability of director of public enterprise. Namely, the director of public enterprise will be removed if he/she uses public enterprise resources for promotion of political parties/subjects, carry out activities related to the promotion of political parties or political entities and election campaign during working hours, put pressure on employees and persons engaged on other grounds in the public enterprise in connection with the support of political party or candidate in the elections, and if he was aware that persons employed or engaged on other grounds in the public enterprise uses the resources of a public enterprise for the promotion of political parties or political entities or puts pressure on other employees and engaged on other grounds in the public enterprise in relation with the support of political party or candidate in the elections, but failed to take actions for which is responsible to prevent it. The amendments to the Law on Public Private Partnership and Concessions (“Official Gazette of RS”, no. 88/11, 15/16 and 104/16) were adopted in 2016. During the drafting of the Law on Public Private Partnership and Concessions special attention was paid to issues concerning: establishment of a register of public contracts in order to make available information on public-private partnership to the public (register was established in December 2015); the introduction of better control of the financial impact of public-private partnerships; defining additional elements of public contracts that protect the public interest in projects of public-private-partnership and concessions; criteria for establishing balanced relations in risk sharing between public and private partners; compliance with international standards and international best practices. The Law on Amendments to the Law on Bankruptcy was adopted on December 14th, 2017 (“Official Gazette of RS”, no. 113/17). Following these changes, the Law on Bankruptcy was amended twice, in order to comply with the Law on financial security and to improve the position of the Republic of Serbia in Doing Business list. The latest amendments to the Law on Bankruptcy in 2018 were adopted in order to improve the efficiency and transparency of the existing legal framework and to remedy identified deficiencies. These changes give more rights to creditors in the selection of bankruptcy administrators, submission of reorganisation plan, as well as more rights to creditors’ assembly in bankruptcy proceedings. Law on Privatization (“Official Gazette of RS", no. 83/14), which entered into force in August 2014 as well as amendments to this law adopted in 2015 ("RS Official Gazette", no. 46/15 and 112/15), regulates the privatization procedure and control of the privatization procedure, with aim to eliminate the risk of corruption. In terms of the risk of corruption, the law stipulates who can be a buyer in the privatization process. It also stipulates that the Ministry of Economy shall obtain, from the competent anti-money laundering authority, an opinion on the absence of obstacles the buyer or strategic investor may encounter when concluding the agreement. The application of this article significantly reduces the possibility of corruption in the privatization process. The Directorate for Prevention of Money Laundering issued positive opinions on all requests submitted in 2016, 2017 and 2018. Bearing in mind that the latest amendments to the Law on Privatization regulate and control the privatization process in order to eliminate the risk of corruption, and the fact that the privatization process in Serbia is nearing its end, further changes to legislation in this area are not expected. New state of play: Law on Customs Service was adopted on 7th December 2018 and entered into force on 17th December 2018. Law regulates the operations of the customs service, its internal organisation and the management, competences, rights, duties and responsibilities of customs officers, which are the basis for determining the competences of customs officials in accordance with the fundamental values ​​of the EU framework of customs competences. The novelties of the law are, among other things, related to the competences in terms of customs-misdemeanor procedure, subsequent customs control as well as operations of internal control, which was not regulated in previous legislation. Article 55 of the Constitution guarantees freedom of political, union or any other association and the right to stay out of any associations, and associations are established without prior approval, by registration in the register kept by the state authority in accordance with the law. In this regard, in January 2011, the Government established the Office for Cooperation with Civil Society Organisations (Office) to support the development of civil dialogue between government institutions and civil society organisations in the process of the reform of the institutions and society in general. The importance and the role of the Office are reflected, inter alia, in the establishment of clear standards and procedures for the involvement of civil society at all levels of decision-making. In recent years, civil society has been very active in monitoring and evaluating the work of public authorities in this field, through public hearings, conferences, round tables and debates organized by various civil society organisations and government institutions. In terms of the development of the National Anti-Corruption Strategy from 2013 to 2018, and the accompanying Action Plan, as well as Action Plan for Chapter 23 and Draft of Revised Action Plan for Chapter 23, representatives of civil society organisations were involved in all phases of the aforementioned acts, which have been contributed by their comments, suggestions and proposals. This has resulted in the adoption of the strategic objectives relating to the creation of conditions for active participation of civil society in the fight against corruption. New state of play: The Office for Cooperation with Civil Society of the Government of the Republic of Serbia continued with the series of regular activities in order to encourage and increase more efficient participation of citizens in the fight against corruption. On March 5, 2018 a new Regulation on Funds for Programme Promotion or the Lacking Funds for Programmes in Public Interest Implemented by Associations was adopted, introducing, among other changes, the obligation for all public administration units to submit the annual plan of public calls to the Office for Cooperation with Civil Society. It also introduces the issue of conflict of interest and the definition of situations in which the conflict of interests may appear either for the members of the Commission or the funds beneficiaries, as well as the possible measures for its removal. The National Assembly of the Republic of Serbia adopted the Law Amending the Law on State Administration at its session held on 20 June 2018 ("Official Gazette of RS" no. 47/2018 and30/2018 – other law). The amendments to the Law provide for a more effective participation of the interested public in the process of adoption of regulations, which ensures transparency and improves the quality of the legislative process. The Methodology for planning, monitoring the implementation and evaluation of civil society programs/projects financed from the budget, as well as the Manual for implementing the Methodology were carried out and published on the web page of the Office. Public calls for allocation of funds for civil society organisations with purpose to carry out projects in the fight against corruption have been implemented, and the projects were carried out by civil society organisations. Implementation of the competition for alternative reporting on the implementation of the National Strategy and Action Plan for Fight against Corruption was conducted successfully. Alternative reports were submitted. REPRESSION OF CORRUPTION The legislative framework regulating repression of corruption in Serbia encompasses: Criminal Procedure Code (“Official Gazette of RS“, No. 72/11, 101/11, 121/12, 32/13, 45/13, 55/14 and 35/19); Law on Seizure and Confiscation of the Proceeds from Crime (“Official Gazette of RS“, No 32/13, 94/16 and 35/19);Criminal Code of Serbia (“Official Gazette of RS“, No. 85/05 88/05, 107/05, 72/09, 111/09,121/12, 104/13, 108/14, 94/16 and 35/19), Law on organisation and competence of state authorities in suppression of organised crime, terrorism and corruption (“Official Gazette of RS“, No. 94/2016 and 87/18 - other law). Institutional repressive apparatus consists of: police (detection of corruption offenses), public prosecutors (prosecution of corruption), and courts (sanctioning corruption). The key measure in the field of repression of corruption was the adoption and implementation of the Financial Investigations Strategy for period 2015-2016. This Strategy is an integrative document for the largest number of anti-corruption repressive measures. Responsible authorities for the implementation of this Strategy were Ministry of Justice and Public Prosecutor's Office. The Financial Investigations Strategy from 2015 through 2016, along with the new Law on ACA (in the prevention field) represents the pillars of the Action Plan for Chapter 23, subchapter fight against corruption. Established efficient and proactive action in detecting and prosecuting corruption and organized crime represents the basis of the repressive action against these phenomena. The key prerequisites for effective acting involve independent competent institutions, adequate staffing, effective horizontal and vertical cooperation established and exchange of information between the police, public prosecutors, courts and other state bodies and institutions. The Financial Investigations Strategy from 2015 through 2016 prescribes specialization in economic crime matters in police, prosecution offices and four appellate courts, advanced trainings in cooperation with the Judicial Academy of judicial officers (in four Appellate courts) who handle financial investigations, establishment of task forces comprised of police officers and officers of other relevant government authorities, appointment of liaison officers for contact with the prosecutor’s office and the police in every authority which comes across facts connected to financial crimes. Regarding introduction of forensic accounting offices within Public Prosecutor’s offices, the Prosecutor’s Office for Organized Crime should have at least two forensic accountants, while departments in the four higher prosecutor’s offices should have minimum of one forensic accountant. A forensic accountant should be able to identify criminal activity from the financial standpoint, but he should also be familiar with investigation and evidentiary techniques. Forensic accountants need to assist public prosecutors in finding answers that they cannot provide because of the complexity of the case. In a domain of repression of corruption, proper implementation of the Financial Investigations Strategy activities represented key contribution for reformation of repression system, prioritisation of the work on 24 controversial privatization cases from current phases to satisfactory resolution in line with Anti-Corruption Council recommendations. Also, implementation of the Financial Investigations Strategy represented adequate tool for resolving financial criminal cases in future. When it comes to 24 controversial privatization cases, Republic of Serbia is demonstrating strong will to resolve all cases. The need for cooperation with national and European institutions and organisations, as well as other international organisations (Eurojust, OLAF, GRECO, OECD, etc.) is particularly emphasized. With the entry into force of the new Criminal Procedure Code, in all public prosecutors’ offices, of general and special jurisdiction, the prosecution has obtained a leading role in obtaining evidence and their presentation in court. Certain results have been achieved in practice; however, further progress is necessary particularly in cases of high-level corruption. Improving financial investigations is one of the prerequisites for achieving significant results in practice, in addition to strengthening the independence and mutual information exchange between relevant authorities. (See further Chapter 24, subchapter fight against organized crime.) In the Republic of Serbia, the police, prosecution and courts use different systems for monitoring criminal cases. In practice, such an approach creates several problems. The police keeps statistical records according to the number of reported crimes; the prosecution according to the number of reported persons; whereas the court statistics is kept according to the number of cases. Such record keeping is not suitable for measuring the progress and the level of efficiency of the criminal justice system, neither for setting up criminal policy. The goal of establishing a unique records keeping system or an electronic record for criminal offenses with elements of corruption is, inter alia, the precise systematization and classification of data as well as regular control and information exchange. One of the tasks this information system has to correspond to is to establish a uniform system of reporting on corruption and organized crime. By achieving this goal, the Ministry of Justice shall have the ability to produce reliable annual report on cases with elements of corruption, which contain all the relevant information about the course of the investigation, the progress of the criminal proceedings and their outcome. Mutually compatible forms in the police, courts and prosecutors’ offices should also include the possibility of monitoring cases of proactive conduct, acting upon the reports of the Agency, State Audit Institution, Tax Administration, and Administration for public procurement, etc. The legal framework for conducting financial investigations and tracing criminal proceeds is regulated by the Law on Seizure and Confiscation of the Proceeds from Crime ("Official Gazette of RS", no. 32/2013, 94/16 and 35/2019). Also, the Criminal Procedure Code ("Official Gazette of RS", no. 72/11, 101/11, 121/12, 32/13, 45/13, 55/14 and 35/19) provides for special investigative techniques that are used to facilitate tracking of the proceeds from crime. Competent authority for the implementation of financial investigation is the Financial Investigation Unit, responsible for financial investigation at the Ministry of Interior, while the Directorate for Administration of Seized Assets is responsible for the management of seized assets within the Ministry of Justice.The Action Plan for Chapter 23 provides for measures to improve the implementation of financial investigations and management of seized assets. It is necessary, inter alia, to improve the efficiency of relevant institutions, records keeping and information exchange at the national and international level. New state of play: The goals set by the Financial Investigations Strategy were fully implemented by adoption and implementation of the Law on organisation and competence of state authorities in suppression of organised crime, terrorism and corruption (“Official Gazette of RS“, No. 94/2016 and 87/18 - other law). The first goal - the establishment of effective repressive authorities was fulfilled by the establishment of a new organisation in the public prosecutor's offices, courts and police. Special departments for suppressing corruption were established in four higher public prosecutors offices, as well as equivalent departments in higher courts. In the police, within the Criminal Police Directorate, the Anti-Corruption Department was formed, which consists of nine sections: the Department of Coordination and Planning and the Anti- Corruption sections in Belgrade, Novi Sad, Nis, Kraljevo, Subotica, Zajecar , Jagodina and Uzice. The above mentioned Special departments for suppressing corruption represent four regional judicial center in which full specialization for corruption criminal offenses was made. Each of these departments is territorially competent for its appellate areas. The second goal - improved cooperation was fulfilled by establishing a network of liaison officers. Within 13 competent state authorities, at least two liaison officers were appointed. All liaison officers have passed specialised training for work in multidisciplinary teams. For fulfillment of this goal it is important to emphasize that the law provides possibility of establishing task forces that work on the most complex cases of corruption. The third goal - the establishment of financial forensics was fulfilled by the introduction of financial forensic experts in the work of four Special departments for supressing corruption and in the Prosecutor's Office for Organized Crime. The fourth goal – training courses, represents horizontal goal that permeates all of the above-mentioned goals of Financial Investigations Strategy. In this regard, numerous training courses have been conducted. Training courses are organized by the Judicial Academy, with the crucial support of the IPA project "Prevention of and Fight against Corruption": in 2018, there were eight three-day training seminars on "financial investigations techniques" for judges, prosecutors, police investigators and members of the institutions within the jurisdiction of the appellate courts (Belgrade, Novi Sad, Nis, Kraljevo) with 232 participants (64 judges, 72 public prosecutors, 71 policeman and 25 representatives of the liaison institutions); two three-day training seminars on financial investigations for higher operational heads of specialised "task force" units, where 59 supervisors were trained; eight one-day roundtables in four regional centers for judges and public prosecutors selected for work in Special departments for supressing corruption on "Effective management of the procedure and the use of circumstantial evidence in cases of economic crime and corruption" with total of 86 participants (28 judges, 20 judicial associates, 21 public prosecutors, 15 prosecutor associates); eight 1-day training sessions on Practical aspects of ethical dilemmas and their resolution for the judges and prosecutors were organised; five practical communication trainings were organised for heads and their deputies of the specialised AC department; 20 trainings were organised where more than 340 representatives of the public administration, local-self-government, prosecutors, judges, police officers and representatives of the CSO were trained in the field of prevention and combating of the corruption; six 5-day Train the Trainers training were conducted. More than 120 new trainers (representatives of the public administration, local-self-government and CSOs) are trained in the field of prevention and combating of the corruption; Partner in the implementation of training courses was the USA Ministry of Justice - OPDAT. In 2019, 3 roundtables on current issues in enforcement of Law on Organisation and Jurisdiction of State Authorities in Combating Organized Crime, Terrorism and Corruption were organized for the judges, deputy prosecutors and financial forensics (16 high courts judges (special departments), 20 appellate courts judges, 2 deputy prosecutors and 2 financial forensics); 6 full day events were organized on cooperation mechanisms (liaison agencies) between Republic public prosecutors’ office, Ministry of Interior – AC department and 12 out of 13 liaison agencies’ representatives; (partner in the implementation – OPDAT) ; Five seminars on capacity building of Tax Administration (Misdemeanor or Criminal Offence – identifying criminal intent) - 121 chiefs in tax control tax police attended; 4 AC operational teams’ workshops for deputy prosecutors and 21 AC police officers – total of 43 deputy prosecutors and 78 AC police officers. Within extensive organisational and technical preparations for the implementation of new legal solutions, a reconstruction of a 1500 square meter building in Novi Sad was completed, and will be used for the needs of Special department of the Prosecutor's Office for supressing corruption and Special Department of the Higher Court. A complete reconstruction of the Palace of Justice in Belgrade with an area of ​​26,350 square meters was finished. Reconstruction is financed by European Investment Bank credit in the amount of 16.6 million euros. Special Department of the Prosecutor's Office for the suppression of corruption and equivalent Special Department of the Higher Court are located there. Also, an adequate building for judicial authorities was provided in Kraljevo. As of 31 December 2019, five task forces were formed, one in each Special Department, except in Nis, where three task forces were formed. By adoption of the Law on Personal Data Protection ("Official Gazette of RS" no. 87/18), conditions for membership of the Republic of Serbia in Eurojust have been met. Republic of Serbia and Eurojust signed Agreement on cooperation in December 2019. With regard to cooperation with OLAF, AFCOS network was established and fully operational. In order to establish a system of uniform statistical monitoring and reporting for corruption criminal offences by all competent authorities, Feasibility study on development and implementation of the methodology for the collection of statistical data was conducted, within the IPA project "Prevention and fight against corruption“. The concept of Feasibility study was developed by gathering information on the current state of information and communication technology within all competent authorities. The aim of the Feasibility study was to evaluate the current state of ICT equipment in the competent bodies, as well as the legislative framework that enables the exchange of information, and to propose the most efficient methodology for developing a system for uniformed statistical reporting. On 23. 11. 2016, National Assembly adopted the Law on Amendments and Supplements to the Law on Seizure and Confiscation of the Proceeds from Crime ("Official Gazette of RS" no. 94/16), aligned with the EU Directive 2014/42, as well as necessary by-laws: Instruction on the content and drafting requirements of seized assets reports, Instruction on the sales method of temporarily seized movable assets and Rules of Procedure for the assessment of the value of seized assets("Official Gazette of RS" no. 25/2018). Material and technical capacities of the Directorate for Administration of Seized Assets were strengthened through the purchase of software for recording of seized property. Representatives of the Directorate attend training courses in the field of commercial and criminal law, regularly organized by the Judicial Academy. The development of a platform for negotiations to sign contracts with directorates from the countries of the region and the EU countries is in progress. Pursuant to the Constitution of the Republic of Serbia, the following categories of persons shall enjoy immunity: MPs, the President of the Republic, the President and members of the Government, the judges of the Constitutional Court, judges, public prosecutors and deputy public prosecutors, the Ombudsman, members of the High Judicial Council and State Prosecutorial Council. Parliamentary immunity includes substantive immunity (immunity from liability) and the procedural immunity. A judge may not be detained in proceedings instituted for a criminal offence committed in the performance of judicial functions without the approval of the High Judicial Council. Member of High Judicial Council shall enjoy immunity as a judge. A public prosecutor and deputy public prosecutor cannot be held responsible for the opinions expressed in the exercise of prosecutorial functions unless it is a criminal offence of violating the law by the public prosecutor or deputy public prosecutor. A public prosecutor and deputy public prosecutor may not be deprived of liberty in proceedings instituted for a criminal offence committed in the exercise of prosecutorial function or service, without the approval of the competent committee of the National Assembly. Member of the State Prosecutorial Council shall enjoy immunity as a prosecutor. A judge of the Constitutional Court shall enjoy immunity as a deputy. The Constitutional Court decides on his/her immunity. New state of play: National Assembly and General Secretariat of the Government conducted „Analysis of the provisions regulating immunity of the officials whose immunity is subject to decisions of the National Assembly and Government (scope and procedure for lifting immunity)”. Analysis conclusion is that the current regulations already provide effective and efficient implementation of the procedure for lifting immunities, and that there were no cases of obstruction of criminal investigations and criminal proceedings in connection with corruption and other crimes. Regarding measures to prevent leaks to the media of confidential information to the media in connection with criminal investigations, the Analysis of normative, organisational and functional framework, with particular emphasis on measures to prevent information leaks and repressive measures to suppress unauthorised communication of data relating to criminal proceedings was carried out. The „Ideal model for the detection of offenders and proving criminal offence of disclosing official secrets ("leaking information to the media")“ was developed. As an integral part of the „Ideal model“, Instruction on the obligation to protect and preserve the secret and confidential data and Declaration on keeping secret and confidential data, applicable on all employees in the Public Prosecutor's Office and the Ministry of Interior, were created. An Analysis of the current level of IT security system was conducted, based on which proposals for future steps were made, regarding the increasement of IT protection level and the introduction of an early warning system and alarm system. The Republic Public Prosecutor's Office and the Ministry of the Interior continuously monitor the sanctioning of violations of regulations preventing disclosure of confidential information. Results achieved by implementing the Action Plan for the Implementation of the National Strategy for the Fight against Corruption for the period from 2013 to 2018 had been analized in 2016. On that basis, Government adopted Revised Action Plan for the implementation of National Strategy for the Fight against Corruption. Revision was made based on Anti-Corruption Agency Annual Reports, contributions submitted by the authorities responsible for the implementation of the Action Plan, perceived difficulties in the implementation and monitoring of the implementation of the Action Plan, and the fact that the Action Plan for Chapter 23 envisages the same or essentially the same obligations as the Action plan for the implementation of the National Strategy for the Fight against Corruption. Having said that, all activities envisaged by the Action Plan for Chapter 23, which have also been prescribed in the Action Plan for the implementation of National Strategy, continue to be monitored through appropriate activities in Action Plan for Chapter 23. Results achieved by implementing the Action Plan for the Implementation of the National Strategy for the Fight against Corruption for the period from 2013 to 2018 and Action Plan for Chapter 23, were analized again in 2018, through document „Gap analysis on the implementation of the National Anti-corruption Strategy its Action Plan for implementation and the Action Plan for Chapter 23“ done within IPA Project „Prevention and Fight against Corruption“. Findings and recommendations of the „Gap analysis“ serve as the basis for defining the measures that need to be implemented for the remaining period up to accession of the Republic of Serbia to the European Union. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1.IMPLEMENTATION OF ANTI-CORRUPTION MEASURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.1.1. Broaden the political and institutional ownership, including high level coordination, of the fight against corruption and identify clear high level institutional leadership in the implementation of the anti-corruption strategy in particular; |  |  |  |  |  |  | Coordination of implementation of anti-corruption measures established at the highest political level, along with political and institutional accountability of high level institutional leadership for the implementation of strategic measures in the fight against corruption. |  |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia - Extent of implementation of measures and activities from the Operational plan, based on the reports of the Anti-Corruption Agency and Coordination Body for the implementation of the Operational Plan - at least 2/3 of activities/measures in the Operational Plan for the Prevention of Corruption in areas of particular risk implemented at the end of validity period. |  |  |  |  |  |  |
| Interim benchmark: Serbia implements the Action Plan accompanying the National Anti-Corruption Strategy for the period 2013-2018. It strictly monitors the implementation and takes remedial action where needed. Serbia conducts an impact assessment in 2018 of its results. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.1.1.1. | Preparing and adopting the Operational Plan for the Prevention of Corruption in areas of particular risk. |  |  |  | -Ministry of Justice (State secretary in charge of anti- corruption) -Anti-Corruption Agency -all relevant institutions -with participation of CSOs |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 34.569 € and IPA 2013 „Prevention and Fight Against Corruption“project – 3.600.000 € | Operational Plan for the Prevention of Corruption in areas of particular risk adopted. |  |  |  |  |  | Activity is fully implemented. After the end of the public debate, on its 83rd session held on September 30, 2021, the Government, at the proposal of the Ministry of Justice, adopted a conclusion adopting the Operational Plan for Prevention of Corruption in Areas of Special Risk. |
| 2.1.1.2. | Adopting Decision on establishing the Coordination Body for the implementation of the Operational Plan for the Prevention of Corruption in areas of particular risk. |  |  |  | -Government of the Republic of Serbia -Ministry of Justice (State secretary in charge of anti-corruption) |  | II quarter of 2021. |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs. | Decision on establishing the Coordination Body for the implementation of the Operational Plan for the Prevention of Corruption in areas of particular risk adopted. The Coordination Body holds meetings and solves identified problems and takes measures for fulfillment of the Operational Plan. |  |  |  |  |  | Activity is fully implemented. The Government adopted the Decision on the Establishment of the Coordination Body for the Implementation of the Operational Plan for the Prevention of Corruption in Areas of particular risk on November 25, 2021. |
| 2.1.1.3. | Organizing regular meetings of the Coordination Body in line with new Decision (activity 2.1.1.2.) Meetings of the coordination bodies are open to the public and participation of civil society organisations. |  |  |  | -Ministry of Justice (State secretary in charge of anti- corruption) -Anti-Corruption Agency -all relevant institutions |  | Continuously, commencing from adoption of Decision from 2.1.1.2. |  |  |  | Budget of the Republic of Serbia 2.553 € in 2020 - 851 € in 2021 - 851 € in 2022 - 851 € | Publishing of reports from meetings of the Coordination Body on the website of Ministry of Justice. Reports of Anti-Corruption Agency on the monitoring of the implementation of the Operational Plan for the Prevention of Corruption in areas of particular risk reviewed. The Coordination body considers CSO concrete propositions on Coordination body reports on implementation of the Operational Plan. The Coordination Body solves problems arising in fulfillment of the Operational Plan. |  |  |  |  |  | Activity is not implemented. The first meeting of Coordination Body shall take place in third quarter of 2022. |
| INTERIM BENCHMARK: |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.1.2. The Serbian government engages in a constructive relationship with the Anti-Corruption Council, seriously considers the latter's recommendation and takes them as much as possible into account. |  |  |  |  |  |  | Systematic consideration of the recommendations of the Anti-Corruption Council ensured. |  |  |  |  | - Number of reviewed recommendations which have been taken into consideration by the Government and other competent state authorities during implementation of measures in the field of fight against corruption stated in Annual report on work of Anti-Corruption Council. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  |  | IMPLEMENTATION STATUS |
| 2.1.2.1. | The Government considers the reports of the Anti-Corruption Council at its meetings and takes them as much as possible into account. The Council is invited on the Government session to present the main findings. |  |  |  | -Government of the Republic of Serbia |  | Continuously |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs. | The Government considered reports of the Council and adopted the conclusions on further act in accordance with the findings and recommendations of the Council. |  |  |  |  |  | Activity is not implemented. In the first quarter of 2022, the Anti-Corruption Council submitted to the Government the Report on the privatization of the Jaroslav Cerni Institute. The Council has no feedback on whether the Government has considered the recommendations and conclusions of this Report. In the second quarter of 2022, the Council submitted the Report on the news agency "Tanjug" to the Government of the RS. The Council has no feedback on whether the Government of the RS considered the recommendations and conclusions from this Report. |
| 2.1.2.2. | Adopt a new Decision of the Government that regulates the work of the Anti-Corruption Council, in line with analysis “Anti-Corruption Council of the Government of the Republic of Serbia in the light of best practices in the European Union” conducted within IPA 2013 “Prevention and Fight against Corruption” project. |  |  |  | -Government of the Republic of Serbia -Ministry of Justice (State secretary in charge of anti- corruption) -Anti-Corruption Council |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs. | New Decision of the Government that regulates the work of the Anti-Corruption Council is adopted in line with Analysis. |  |  |  |  |  | Activity is not implemented. The Ministry of Justice is conducting activities, in accordance with the IPA 2013 analysis "Council for the Fight against Corruption of the Government of the RS in the light of EU best practices", in order to draft a Decision amending the Decision regulating the work of the Council. After drafting the draft Decision, it will be sent for further procedure. The official standpoint of the Government in relation with the work of the Council is expected. |
| 2.1.2.3. | Inclusion of Anti-Corruption Council in legislative procedure concerning regulations which, according to Council’s assessment, bear a risk of corruption, through active participation in working groups for law drafting, on the initiative of the Council or the authorities competent to propose laws. Members of the Council are required to take active participation in the operation of working groups. |  |  |  | -Anti-Corruption Council |  | Continuously. |  |  |  | Budget of the Republic of Serbia-25.926 € | The Council timely receives information about legislative activities; acts proactively in its work and members of the Council take active participation in legislative procedure. |  |  |  |  |  | Activity is being partially implemented. On June 15, 2022, the Anti-Corruption Council participated in the meeting of the Special Working Group in charge of formulating proposals for optimizing and improving the content of planning documents for the prevention of corruption in local self-government units within the Operational Plan for the Prevention of Corruption in the Areas of special risk. |
| 2.1.2.4. | The Republic Public Prosecutor's Office considers the report of Anti-Corruption Council from the point of possible criminal liability and forwards them to the competent public prosecutor's offices, monitors implementation and draws up reports. |  |  |  | -The Republic Public Prosecutor’s Office -Government of the Republic of Serbia |  | Continuously. |  |  |  | Budget of the Republic of Serbia- 2.553 € in 2020 - 851 € in 2021 - 851 € in 2022 - 851 € | The Republic Public Prosecutor's Office drawn up annual reports on implementation of activities in compliance with reports of Anti-Corruption Council and submitted reports to the Government. |  |  |  |  |  | Аctivity is being successfully implemented. The Republic Public Prosecution Office analyzes reports submitted by the Anti-Corruption Council, forwards them to the competent prosecution offices, monitors criminal cases initiated upon Council’s reports and inform the Council. A draft report on the work of public prosecutor's offices in cases formed on the basis of the report of the Anti-Corruption Council for 2021 has been prepared. |
| 2.1.2.5. | Additional strengthening of budgetary and staff capacities of Anti-Corruption Council. |  |  |  | -Government of the Republic of Serbia -Anti-Corruption Council |  | II quarter of 2021. |  |  |  | Budget of the Republic of Serbia- 181.125 € | Government issued decree on appointment of members of Anti-Corruption Council. Higher degree of administrative support of General Secretariat of the Government. |  |  |  |  |  | Activity is not implemented. There were no activities in the reporting period. |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.1.3. Serbia conducts a comprehensive assessment of its legislation comparing it against the EU acquis and the United Nation's Convention against Corruption and amends its legislation where needed. Serbia follows up on all GRECO recommendations. |  |  |  |  |  |  | Ensured legal alignment with the EU Acquis and UNCAC in field of fight against corruption including as regards the definitions of active and passive corruption. |  |  |  |  | - Positive opinion of European Commission stated in annual progress report on Serbia; - GRECO reports on evaluation; - Reports of UN Office on Drugs and Crime on compatibility with UNCAC; |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.1.3.1. | Adopt amendments and supplements to legal framework of fight against corruption taking into account reccomendations of the “Analysis of compatibility of anti-corruption legislation with EU Acquis and international standards” conducted within IPA 2013 “Prevention and fight against Corruption” project. |  |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) - other ministries in accordance with their responsibilities -Government of the Republic of Serbia -National Assembly |  | IV quarter of 2021 |  |  |  | Budget of the Republic of Serbia-30.878 € and IPA 2019 (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility- 5.000.000 €) In 2021. | Amendments and supplements to the regulations adopted. |  |  |  | Activity is fully implemented. The National Assembly adopted on September 23, 2021 Law on Amendments to the Law on Prevention of Corruption in order to comply it with GRECO recommendations. |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.1.4. Clarify the co-ordination and co-operation between the different actors in charge of implementing and monitoring the action plan |  |  |  |  |  |  | Coordination of implemenation and monitoring of implementation of the strategic documents is clearly defined and divided. All institutions involved in the coordination of implementation are committed to the proper coordination. ACA has a clear role in the monitoring of the implementation of the strategic documents. There is a solid and operational mechanism of indicating “under-performers” (based on ACA annual report on implementation of strategic documents) to the Coordination Body which would follow up on it. |  |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia - Degree of implementation of measures and activities from Action plans (AP 23, Subchapter Fight against Corruption and Operational plan), based on the reports of the Anti-Corruption Agency and Coordination Body for the implementation of the Operational Plan for the Prevention of Corruption in areas of particular risk - At least 2/3 of activities/measures in the Operational Plan for the Prevention of Corruption in areas of particular risk and AP 23, Subchapter Fight against Corruption implemented at the end of validity period. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.1.4.1. | Adopting Decision on establishing the Coordination Body for the implementation of the Operational Plan for the Prevention of Corruption in areas of particular risk (activity 2.1.1.2.). |  |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) -Government of the Republic of Serbia |  | II quarter of 2021. |  |  |  | Budget of the Republic of Serbia – in 2021 Activity requiring insignificant costs. | Decision on establishing the Coordination Body for the implementation of the Operational Plan adopted. |  |  |  | Activity is fully implemented. The Government adopted the Decision on the Establishment of the Coordination Body for the Implementation of the Operational Plan for the Prevention of Corruption in Areas of particular risk on November 25, 2021. |  |  |
| 2.2. PREVENTION OF CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.1. Interim benchmark: Serbia adopts the new Law on the Anti-Corruption Agency (ACA) providing it with a clear and strong mandate. Serbia ensures that ACA continues to enjoy the necessary independence, receives sufficient financial and human resources as well as training and is well connected to other relevant authorities (including to their databases). Serbia ensures that bodies that fail to report and cooperate with ACA are held accountable. Interim benchmark: Serbia provides an initial track record of effective implementation of the asset declaration and verification system, including dissuasive sanctions for non-compliance and appropriate follow up measures (including through criminal investigations where relevant) in cases where the reported assets do not correspond to the reality. |  |  |  |  |  |  | Improved efficiency of Anti-corruption Agency in exercising its competencies through an amended legal basis, strengthen its administrative capacity and ensured better connectivity to various agencies and state authorities. |  |  |  |  | - Positive opinion of European Commission stated in Annual Progress Report on Serbia - Annual report on work of Anti-Corruption Agency reflects improved efficiency within the ACA mandate. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  | IMPLEMENTATION STATUS |  |  |
| 2.2.1.1. | Monitoring the implementation of new Law on the Prevention of Corruption and acting of all state authorities, in line with the new Law on the Prevention of Corruption. |  |  |  | -Anti-Corruption Agency -in cooperation with other relevant institutions |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia- 275.724 € | Annual report on the activities of the Anti-Corruption Agency contains following elements: 1) number of obligations fulfilled by public officials in line with the Law on Corruption Prevention; 2) number of measures issued by the ACA which is complied with by public officials; 3) percentage of institutions which complied with obligation to adopt integrity plan and local anti-corruption plan; 4) percentage of measures in integrity plan and local anti-corruption plan implemented by relevant institutions; 5) number of institutions complying with obligation to conduct ethics and integrity trainings as per ACA’s plan and programme. 6) qualitative analyses, comparisons with previous years, comparison of results with the number of reported cases and subjects of control. National Assembly adopted conclusions on the implementation of the new Law on the Prevention of Corruption. Government and other state authorities act in accordance with conclusions of National Assembly. Report on progress of the Republic of Serbia issued by European Commission. |  |  |  |  |  | Аctivity is being successfully implemented. By applying the Law on Prevention of Corruption a total of 263 requests were resolved in first quarter of 2022. Total of 11 decisions were issued, thus rejecting the request of a public official to perform another public office, i.e. to perform another job or activity (out of which in one proceedings the incompatibility of concurrent discharging public office and performing another job was determined). Upon final decision (seven), in five proceedings the public official ceased with concurrent discharging of public offices, i.e. performing other job or activity, while in two proceedings the deadline for submitting evidence that the decision was complied with is in progress. In four proceedings deadline for appeal has not elapsed, decision is not final. By applying the Law on Corruption Prevention, a total of 97 decisions on violation of the Law on Corruption Prevention were imposed to public officials and 91 measures and six decisions determining termination of other public office by force of law (Article 56, par. 8 of the Law on Corruption Prevention). Out of 91 measures, the following were imposed: - 80 measures of reprimand, - 10 measures of public announcement of decision on violation of the Law and - one measure of public announcement of recommendation for dismissal from public office. From the imposed reprimand measures, five measures included an order to a public official. In two proceedings deadline for acting has not elapsed yet. In three proceedings decision has not been final yet (delivery to public official is underway). One decision, by which the measure of public announcement of recommendation for dismissal from public office has not been final, i.e. deadline for lodging an appeal has not elapsed yet. Upon three final decisions imposing the measure of public announcement of recommendation for dismissal from public office (all issued in 2021, when the proceedings have also started), initiatives to the competent bodies were filed. In terms of decisions imposing termination of other public office, in one case acting upon appeal is underway. Five decisions determining termination of other public office by force of law have not been final. During the reporting period, the number of submitted Asset and Income Declarations of public officials was 1,616; the number of public authorities that notified the APC on the entry and termination of public office was 574, and five legal entities notified the APC of participation in the public procurement, privatization or other procedure, outcome of which is the conclusion of a contract with a public authority. In terms of asset and income declarations, 66 measures of reprimand were issued due to failure to submit declaration within the legally prescribed deadline upon the entry or termination of public office. During the reporting period, in the course of verification of asset and income declarations of public officials, the APC initiated 23 proceedings for determining violation of the Law on Corruption Prevention, issued 29 measures of reprimand, filed 10 requests for initiating misdemeanor proceedings and submitted one report to the competent prosecutor's office due to suspicion that a criminal offense from Article 101 of the Law on Corruption Prevention had been committed, i.e. another criminal offense being prosecutable ex officio. In terms of integrity plans, implementing entities are currently assessing institutional corruption risks, and the APC provides support to them through bilateral meetings and instructions, as well as responding to their questions on a daily basis. In the first quarter of 2022 distance training on ethics and integrity was attended by 7,978 participants out of which 3,740 successfully completed the training. The number of public authority bodies in which employees and heads attended ethics and integrity training in the said period is 246. By applying the Law on Prevention of Corruption a total of 194 requests were resolved in second quarter of 2022. Total of eight decisions were issued, thus rejecting the request of a public official to perform another public office, i.e. to perform another job or activity (out of which in one proceedings the incompatibility of concurrent discharging public office and performing another job was determined). All respective proceedings are currently underway. By applying the Law on Corruption Prevention, a total of 83 decisions on violation of the Law on Corruption Prevention were imposed to public officials and 69 measures and 14 decisions determining termination of other public office by force of law (Article 56, par. 8 of the Law on Corruption Prevention). Out of 69 measures, the following were imposed: - 50 measures of reprimand, - 14 measures of public announcement of decision on violation of the Law and - five measures of public announcement of recommendation for dismissal from public office. From the imposed reprimand measures, four measures included an order to a public official. In one proceedings deadline for acting has not elapsed yet. In three proceedings decision has been final (public officials complied with the APC decision). Decisions, by which the measure of public announcement of recommendation for dismissal from public office have not been final, i.e. deadline for lodging an appeal has not elapsed yet. Upon three final decisions imposing the measure of public announcement of recommendation for dismissal from public office (all issued in 2021, when the proceedings have also started), initiatives to the competent bodies were filed. In terms of decisions imposing termination of other public office, in one case acting upon appeal is underway. Four decisions determining termination of other public office by force of law have been final, whereas for nine decisions the proceedings is underway, i.e., they have not been final yet. During the reporting period, the number of submitted Asset and Income Declarations of public officials was 1,594; the number of public authorities that notified the APC on the entry and termination of public office was 383, and five legal entities notified the APC of participation in the public procurement, privatization or other procedure, outcome of which is the conclusion of a contract with a public authority. In terms of asset and income declarations, 45 measures of reprimand were issued due to failure to submit declaration within the legally prescribed deadline upon the entry or termination of public office. During the reporting period, in the course of verification of asset and income declarations of public officials, the APC initiated 42 proceedings for determining violation of the Law on Corruption Prevention, issued 25 measures of reprimand, one measure of public announcement of decision on violation of the Law and filed 10 requests for initiating misdemeanor proceedings. In terms of integrity plans, implementing entities are currently assessing institutional corruption risks, and the APC provides support to them through bilateral meetings and instructions, as well as responding to their questions on a daily basis. In the second quarter of 2022 distance training on ethics and integrity was attended by 25,145 participants and 20,704 successfully completed the training in this period. The number of public authority bodies in which employees and heads attended ethics and integrity training in the said period is 586. |
| 2.2.1.2. | Conduct analysis of the effects of implementation of the new Law on the Prevention of Corruption, which will cover the period from the beginning of its implementation and the next three years, particularly in the following areas: -assets declaration and incomes of public office holders, including dissuasive sanctions for non-compliance and appropriate follow up measures (including through criminal investigations where relevant); -prevention of conflict of interest; -control of financing the political activities; -supervision over implementation of integrity plans; -supervision over implementation of Revised Action Plan for Chapter 23, subchapter fight against corruption. |  |  |  | -Anti-Corruption Agency -Misdemeanor courts -Republic Public Prosecutors Office -in cooperation with other relevant institutions |  | IV quarter of 2023 |  |  |  | Budget of the Republic of Serbia- budgeted in 2.2.1.1. - Donor support is needed, for which will be applied in the upcoming period | Аnalysis has identified the effects of implementation of the new Law Law on the Prevention of Corruption in the following areas: -assets declaration and incomes of public office holders; -prevention of conflict of interest; -control of financing the political activities; -supervision over implementation of integrity plans; -supervision over implementation of Revised Action Plan for Chapter 23, subchapter fight against corruption. Analysis includes both quantitative and qualitative indicators. Analysis is publicly available on ACAS official web-site. |  |  |  |  |  | The activity is partially implemented. The activity is not due yet. In cooperation with the OSCE Mission, the APC drafted the Methodology for the assessment of effects of the implementation of the Law on Corruption Prevention. |
| 2.2.1.3. | Continuous specialised trainings for employees of the Anti-Corruption Agency in order to implement the new Law on the Prevention of Corruption and the Law on Lobbying. |  |  |  | -Anti-Corruption Agency |  | Continuously, commencing from adoption of the Law on the Prevention of Corruption and the Law on Lobbying |  |  |  | Budget of the Republic of Serbia 4.023 € in 2020 - 1.341 € in 2021 - 1.341 € in 2022 - 1.341 € and USAID GAI Project/OSCE Within international organizations broader program of support, funds have been provided for the implementation of trainings until the end of 2020. Donor support will be needed for the period after 2020, for which will be applied in the upcoming period. | Conducted trainings. Out of total number of ACA staff at least 2/3 of ACA staff attended trainings for implementation of the new Law on Corruption Prevention, i.e. Law on Lobbying in the first year of implementation. |  |  |  |  |  | Аctivity is being successfully implemented. First quarter 2022: With the support of the International Foundation for Electoral Systems one training on cyber hygiene for 25 APC employees was held. In addition to 82 APC employees who successfully finalized distance training on ethics in integrity in 2021, in the first quarter of 2022 additional two did so. 2nd quarter/2022: Six APC employees attended the second regional workshop within the UNODC Project “Fostering sustainable development by supporting the implementation of the UN Convention against Corruption in countries along the Silk Road Economic Belt“, organized by UNODC with the support of the Serbian Ministry of Justice. One APC employee attended the training on running successful public awareness campaign in the area of combating corruption within the Project “Enhancing Whistleblowing Policies and Culture in the Western Balkans and Moldova“, implemented by the Regional Anti-Corruption Initiative Secretariat and funded by EU. Four APC employees attended preparatory training cycle for the fraud examiners and anti-money laundering certification, organized by the US Bureau of International Narcotics and Law Enforcement Affairs, US Department of Justice and Judicial Academy. |
| 2.2.1.4. | Customise software for reporting on National Anti-Corruption Strategy and Action plan for its implementation to respond to the needs of monitoring the relevant measures in the Revised Action Plan for Chapter 23. Test and regularly maintain the software. |  |  |  | -Anti-Corruption Agency |  | For software update: IV quarter of 2020 For maintenance: continuously |  |  |  | b) for software maintainance The total amount of funds for software customization is not known yet. | Updated software to respond to the needs of monitoring the relevant measures in the Action Plan for Chapter 23. Software is tested and regularly maintained |  |  |  |  |  | Activity is fully implemented. Software is operational (although still being tested with identified deficiencies being eliminated) and is regularly maintained. Implementing entities use the application and the APC concurrently collects data via email and in writing. |
| 2.2.1.5. | Customise software for reporting on the Revised Action Plan for Chapter 23, subchapter Fight Against Corruption, to respond to the needs of monitoring the Operational Plan for the Prevention of Corruption in areas of particular risk. |  |  |  | -Anti-Corruption Agency |  | I quarter of 2021 |  |  |  | Budget of the Republic of Serbia 9.950 € If the necessary funds are not provided in the RS budget, donor support will be needed, for which will be applied in the upcoming period. | Updated software to respond to the needs of monitoring the Operational Plan for the Prevention of Corruption in areas of particular risk. |  |  |  |  |  | Activity is not implemented. The software is not fully customized. The Agency for the Prevention of Corruption monitors the implementation of the Operational Plan, and the first six-month report has already been published on the Agency's website. The Agency planned funds for adjusting the software for reporting on the implementation of the Revised AP for the Chapter 23 to be suitable for the implementation of the Operational Plan, after which these funds were approved in the Agency's budget for 2022. However, the adjustment of the software implies the third upgrade of the basic software that was used for reporting on the implementation of strategic documents that were valid in the period from 2013 to 2018, and then on RAP 23-subchapter Fight against corruption, which would significantly affect the stability of the application. Having in mind that the validity of the Operational Plan is limited to the end of 2022, and that this type of software primarily benefits the Agency for Statistical Data Processing, as well as that those obliged to report can also submit this data via e-mail, this type of reporting does not significantly facilitate reporting process. |
| 2.2.1.6. | Upgrade software application that refers to the integrity plans. Regular maintenance of the software application that refers to the integrity plans. |  |  |  | -Anti-Corruption Agency |  | For software upgrade: IV quarter of 2021 For software maintenance: continuously |  |  |  | Budget of the Republic of Serbia and donor support If the necessary funds are not provided in the RS budget, donor support will be needed, for which will be applied in the following period. | Software upgraded and regularly maintained. |  |  |  |  |  | Activity is fully implemented. The activity was fully implemented and software is being maintained. |
| 2.2.1.7. | Development of video tutorials for the third cycle of development, implementation and reporting on implementation of integrity plans. |  |  |  | -Anti-Corruption Agency |  | IV quarter of 2021 |  |  |  | Budget of the Republic of Serbia – 9.950 € and donor support. If the necessary funds are not provided in the RS budget, donor support will be needed, for which will be applied in the following period. | Video tutorials developed, operational and publicly available. |  |  |  |  |  | Activity is fully implemented. Video tutorials for the third cycle of development, implementation and reporting on implementation of integrity plans were finalized and available at the following link: https://youtu.be/NE2ZNFd-mgM. |
| 2.2.1.8. | Organizing multidisciplinary training sessions and workshops with institutions that intensively cooperate with the Anti-Corruption Agency, including training courses for journalists. |  |  |  | -Anti-Corruption Agency |  | Continuously |  |  |  | Donor support (including USAID GAI Project) Donor support is needed for which will be applied in the upcoming period. Within international organizations broader program of support, funds have been provided for the implementation of trainings until the end of 2020. Donor support will be needed for the period after 2020, for which will be applied in the upcoming period. | Organized training sessions and workshops that contribute to the higher level of knowledge necessary for the implementation of the new Law on the Prevention of Corruption. At least two training sessions per year organized with institutions with which the ACA intensively cooperates. At least one training session for journalists organized per year. |  |  |  |  |  | Аctivity is being successfully implemented. After the second (final) workshop on comparative practices on access to financial and non-financial sector information and related inter-agency cooperation for effective verification of asset declarations, at which Council of Europe experts from Slovenia and Romania presented their recommendations in 2021, in 2022 experts drafted the final document with recommendations for improvement of data exchange in the area of asset verification. The activity was implemented within the Project on Prevention of Money Laundering and Terrorist Financing in Serbia, supported by Swedish International Development and Cooperation Agency and implemented by the Council of Europe. Upon adoption of the new Law on Financing of Political Activities, on February 22 the APC organized training for political subjects, media and civil society organizations on the novelties stemming from the Law and the corresponding role of the APC. On May 20, 2022 the APC organized online training for media and civil society organizations on monitoring the implementation of strategic documents in the area of combating corruption, with a focus on the Second Report on implementation of the Revised Action Plan for Chapter 23-Subchapter Fight against Corruption for 2021, which was submitted by the APC to the National Assembly on March 29, 2022. The APC organized two trainings for directors of institutions in the public sector titled “Director as an initiator of institutional integrity development“, with a primary aim to familiarize participants with the purpose and significance of development and implementation of integrity plan as a tool for corruption prevention at the institutional level. The first training was held on May 26, 2022 for directors of primary and high schools in the City of Belgrade. It was attended by 18 participants. The second training was held on June 9, 2022 for directors of public companies in the City of Novi Sad. It was attended by 22 participants. Two APC employees attended the workshop within the Swedish and Serbian Police Cooperation Programme “Support Programme of Swedish Police III (SPAP III) 2019-2022“, pertaining to providing support to implementation of the National Criminal-Intelligence System in the Republic of Serbia. In addition to the APC representatives, the workshop was attended by the representatives of the Ministry of Interior, Republic Public Prosecutor’s Office, Prosecutor’s Office for Organized Crime, Tax Administration, Customs Administration, Administration for Prevention of Money Laundering, Office of the National Security Council and Classified Information Protection, Ministry of Justice and University of Criminal Investigation and Police Studies. |
| 2.2.1.9. | Organizing workshops with the relevant parliamentary committees in order to implement the recommendations of the Agency, including training for MPs on ethics and integrity. |  |  |  | -Anti-Corruption Agency - relevant parliamentary committee |  | Continuously |  |  |  | Budget of the Republic of Serbia- 21.450 € total; 8.050 € per year | Organized workshops that contribute to the higher level of knowledge necessary for the implementation of the new Law on the Prevention of Corruption. At least two workshops per year organized with MPs, i. e. members of the relevant committees of the National Assembly |  |  |  |  |  | Аctivity is being successfully implemented. Due to elections for MPs there were no activities related to workshops with the relevant parliamentary committees. In line with the Law on Corruption Prevention, on March 29, 2022 the APC submitted to the National Assembly its 2021 Annual Report, which is publicly available at the APC’s website. In 2022 there were no new trainings on ethics and integrity for MPs, but the APC had the meeting with the members of the Ethics Commission related to 2022 work plan upon the constitution of the new National Assembly convocation. |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.2. Serbia amends its Law on Financing of Political Activities and reinforces the independence and administrative capacity of relevant supervisory authorities, in particular the State Audit Institution and the Republic Electoral Commission. Serbia provides an initial track record on the proper implementation of the law, including deterrent sanctions where required. |  |  |  |  |  |  | Law on control of financing of political activities is implemented efficiently in particular in terms of adequate sanctioning of noncompliance with the provisions of the law. |  |  |  |  | 1. Positive opinion of European Commission on progress of Serbia. 2.Report on control of political activities issued by Anti-Corruption Agency reflects improved efficiency in control of political activities; 3.Reports of the State Audit Institution and electoral committee; 4. Number of initiated and finalized misdemeanor procedures and other proceedings, including the number and level of sanctions applied. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |  |
| 2.2.2.1. | Amend the Law on Financing of Political Activities in order to clarify and separate duties of Agency, State Audit Institution and other relevant state authorities in the process of control of political activities and precisely determine duties and mechanisms for transparency of financing of political subjects in accordance with quality analysis on implementation of Law on Financing of Political Activities. Ensure that amendments encompass strengthening ACA capacity to receive the necessary information on financial flows. |  |  |  | -Ministry of Finance -Anti-Corruption Agency -Government of the Republic of Serbia -National Assembly -With participation of Civil Society Organisations |  | IV quarter of 2020. |  |  |  | Budget of the Republic of Serbia-48.900 € | Adopted amendments and supplements to Law on Financing of Political Activities. |  | Activity is fully implemented. The Ministry of Finance, as the responsible entity for fulfilling this measure, undertook all activities that led to the adoption of the Law on Financing Political Activities in the National Assembly of the Republic of Serbia on February 4, 2022. The law was published in the "Official Gazette of the Republic of Serbia" on February 7, 2022, and entered into force on February 8, 2022. The adoption of this law is an indicator of the results of the implemented activities. |  |  |  |  |
| 2.2.2.2. | Prescribe that the program of revision entails compulsory revision of parliamentary political parties on the republic level and introduction of duty of director of Tax administration to include in the annual or extraordinary plan of tax control, donors of financial resources and other services to political subjects, in compliance with report of Agency on financing political activities and subjects. |  |  |  | -Ministry of Finance -Government of the Republic of Serbia -National Assembly |  | IV quarter of 2020. |  |  |  | Budget of the Republic of Serbia-budgeted in 2.2.2.1. | Adopted amendments and supplements to Law on Financing of Political Activities. |  | Activity is fully implemented. The activity was fully implemented with the adoption of the Law on the Financing of Political Activities ("Official Gazette of RS", No. 14/22) and its entry into force on February 8, 2022. |  |  |  |  |
| 2.2.2.3. | Monitoring the implementation of Law on Financing Political Activities, including application of detterent sancions. |  |  |  | -Anti-Corruption Agency -Misdemeanour Courts -Republic Public Prosecutors Office |  | Continuously |  |  |  | Budget of the Republic of Serbia- 15.318 € in 2020 - 5.106 € in 2021 - 5.106 € in 2022 - 5.106 € | Report of Anti-Corruption Agency on financing of political activities and election campaign: 1) at least 50% of political subjects submitted annual financial reports; 2) at least 70% of political subjects submitted election campaign costs. 3) number of initialized misdemeanor proceedings, number and level of sanctions imposed by Misdemeanour Courts Annual Reports of Republic Public Prosecutors Office on criminal proceedings derived from application of article 38. of the Law on Financing Political Activities, including the number and level of sanctions applied |  | Аctivity is being successfully implemented. In the reporting period elections were held for the MPs in the National Assembly, for the President of the Republic of Serbia and for deputies in city assemblies of Belgrade and Bor as well as municipality assemblies of Aranđelovac, Smederevska Palanka, Lučani, Medveđa, Knjaževac, Bajina Bašta, Doljevac, Kula, Kladovo, Majdanpek and Sečanj. Total of 126 political subjects were obliged to submit preliminary reports on election campaign costs. In the reporting period 95 of them complied with this obligation. Total of 255 political subjects are obliged to submit annual financial reports. As per the new Law on Financing of Political Activities deadline for submission of annual financial reports is until April 30 of the current for the preceding year. In the reporting period 26 annual financial reports were submitted. In the reporting period in proceedings conducted upon reports and ex officio due to violation of the Law on Financing of Political Activities nine warning measures were issued, three decisions determining violation of the Law were issued and requests for initiation of misdemeanour proceedings will be filed (total of 21 decisions were issued-in nine decisions no violation of the Law was determined). Ex officio proceedings were conducted on the basis of reports of observers engaged by the APC for monitoring activites of political subjects on the field during the election campaign. For that purpose the APC engaged approx. 130 field observers. 2nd quarter/2022: In the reporting period the following reports were submitted: 10 preliminary reports on election campaign costs; 85 final reports on election campaign costs and 140 annual financial reports of political subjects. The APC filed 52 requests for initiation of misdemeanour proceedings; issued five measures of warning due to violation of the Law on Financing of Political Activities (out of which two measures related to the election campaign); two decisions on suspension of proceedings initiated ex officio in terms of violation of the law during the election campaign as well as one decision based on report determining no violation of the law. The Republic Public Prosecutor's Office monitors the actions of public prosecutor's offices in cases formed on the basis of criminal charges related to the violation of the provisions of the Law on Financing Political Activities. The report on the work of public prosecutor's offices in these cases was sent to the Agency for the Prevention of Corruption in January 2022. |  |  |  |  |
| 2.2.2.4. | Adoption of by-laws which regulate criteria and deadlines for controlling reports of political subjects by introducing the plan of priority control of reports in order to enable prioritisation of control of reports. |  |  |  | -Anti-Corruption Agency |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia and donor support Donor support is needed for which will be applied in the upcoming period. Budgeted in 2.2.2.1. | Adopted by-laws. |  | Аctivity is fully implemented. Upon the adoption of the new Law on Financing of Political Activities on February 4, 2022 the APC issued the following acts: 1) Rulebook on records and reports of political subjects (adopted on February 11 and published in the Official Gazette of the Republic of Serbia on February 17); 2) Plan of the control of reports on election campaign costs related to elections for MPs and local elections (adopted on February 18 and published at the APC’s website); 3) Plan of control of reports on election campaign costs for presidential elections (adopted on March 4 and published at the APC’s website) and 4) Plan of control of annual financial reports of political subjects for 2021 (adopted on March 10 and published at the APC’s website). |  |  |  |  |
| 2.2.2.5. | Strengthening capacities of all entities responsible for implementation of the Law on financing political activities, the Republic Electoral Commission, the training of judges of misdemeanor courts. |  |  |  | -Anti-Corruption Agency -Judicial Academy -Republic Electoral Commission |  | Continuously, commencing from I quarter of 2021 |  |  |  | Budget of the Republic of Serbia- 1.310 € per year If the necessary funds are not provided in the RS budget, donor support will be needed, for which will be applied in the upcoming period. | Capacities of all entities responsible for implementation of the Law on financing political activities, the Republic Electoral Commission, trained judges of misdemeanor courts strengthened. Number of trainings held in relation to planned trainings on Law on financing political activities implementation. |  | Аctivity is being successfully implemented. Upon adoption of the new Law on Financing of Political Activities, on February 22 the APC organized training for political subjects, media and civil society organizations on the novelties stemming from the Law and the corresponding role of the APC. During the reporting period, in the first quarter, three trainings were organized on the implementation of the Law on Financing Political Activities, by the Judicial Academy. |  |  |  |  |
| 2.2.2.6. | Strengthening technical capacities of the Anti-Corruption Agency for the monitoring the financing of political activities, software for on line notification, better availability of published data. |  |  |  | -Anti-Corruption Agency |  | Continuously, commencing from IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia - 20.044 € | Technical capacities that enable effective control of monitoring the financing of political activities strengthened. |  | Аctivity is being successfully implemented. Upon adoption of the Law on Referendum and People’s Initiative as well as Law on Financing Political Activities the APC adjusted the existing software applications to the new requirements and created new forms for political subjects, including forms for preliminary reports of political subjects. In addition, after the support provided by the OSCE Mission and Council of Europe for i2 IBM analytical tool and corresponding trainings in 2021, the APC provided new annual license for this tool through budgetary funds for 2022, which is being used for control of financing of political activities. |  |  |  |  |
| 2.2.2.7. | Developing online training modules related to the implementation of the Law on Financing of Political Activities. |  |  |  | -Anti-Corruption Agency |  | Continuously, commencing from II quarter of 2021 |  |  |  | Donor support Donor support is needed for which will be applied in the upcoming period. Costs currently unknown. | Online training modules developed. |  | Аctivity is partially implemented. For implementation of this activity the APC will be supported by the International Foundation for Electoral Systems (IFES) and immediately after the adoption of the new Law on Financing of Political Activities the APC started with development of training module. Implementation of the activity is underway. |  |  |  |  |
| 2.2.2.8. | Designing a handbook for the implementation of the Law on financing political activities. |  |  |  | -Anti-Corruption Agency |  | II quarter of 2021 |  |  |  | Donor support Donor support is needed for which will be applied in the upcoming period. Costs currently unknown. | Handbook designed. |  | Аctivity is partially implemented. For implementation of this activity the APC will be supported by the International Foundation for Electoral Systems (IFES) and immediately after the adoption of the new Law on Financing of Political Activities the APC started with development of training module. Implementation of the activity is underway. |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.3. Serbia provides an initial track record showing an increase in the number of detected and resolved conflict of interest cases, including deterrent sanctions. Serbia provides trainings and raises awareness so as to ensure that the concept is well understood at all levels. |  |  |  |  |  |  | The legal and administrative framework to prevent and deal with conflicts of interest improved. Ensured that the concept is well understood at all levels. |  |  |  |  | - More conflicts of interest are prevented; - There is a good understanding of the concept at all levels of the administration; - Conflict of interest cases, especially as a part of criminal offence of corruption are adequately sanctioned; - Positive opinion of European Commission on progress of Serbia; - Annual report on operation of Anti-Corruption Agency; - Annual report of High Civil Service Council - Number of initiated and finalized misdemeanor and other proceedings increased when compared to the previous relation between initiated and finalized misdemeanour and other proceedings |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT | IMPLEMENTATION STATUS |  |  |  |  |  |
| 2.2.3.1. | Drafting the Guidebook on prevention of conflicts of interest after the adoption of the Law on the Prevention of Corruption. Presentation of the Guidebook. |  |  |  | -Anti-Corruption Agency |  | III quarter of 2020 |  |  |  | USAID GAI Project Within USAID GAI support the necessary funds were provided for 2020. | Drafted and published guidebook, which should enable understanding of the concept of conflict of interest, informs all risk categories that may come into conflict of interes and guide them in avoiding conflict of interest. Guidebook presented at round table. |  |  |  |  | Activity is fully implemented. The activity was previously fully implemented. In cooperation with the USAID/GAI, after the Law on Prevention of Corruption started to apply, the APC developed and published on its website the Manual for the Recognition and Management of Conflicts of Interest, which enables the understanding of the concept of conflict of interest and informing of all risk categories that may enter a conflict of interest. The Manual is available on the APC website at the following link: http://www.acas.rs/wp-content/uploads/2020/11/Conflict-of-Interest-MANUAL-for-Website-30Oct20FINAL.pdf. |  |
| 2.2.3.2. | Develop video materials-potential conflicts of interest situations, including dissemination and awareness raising component. |  |  |  | -Anti-Corruption Agency |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia-20.000€ and donor support. If additional funds are needed, it will be applied for donor support. | Video materials developed, operational, disseminated and extensively used during the trainings for public officials conducted by the ACA. |  |  |  |  | Activity is fully implemented. The activity was implemented in line with the deadline. Video material - a conflict-of-interest film that points to potential conflict-of-interest situations, including dissemination and awareness raising component is available on the APC website, i.e. the official YouTube channel of MyIntegrity at the following link: https:/www.youtube.com/watch?v=KCoV0KRJb1g&t=12s The video material was also made available through the APC official social media accounts.. |  |
| 2.2.3.3. | Conduct professional education of employees in public administration in connection to issues of prevention of conflict of interests. |  |  |  | -National Academy of Public Administration |  | Continuously |  |  |  | Budget of the Republic of Serbia Costs currently unknown – will be known will after development of the training plan of the National Academy of Public Administration. | Conducted professional education of employees in public administration in connection to issues of prevention of conflict of interests. Number of seminars held in relation to planned trainings on prevention of conflict of interests. |  |  |  |  | Аctivity is being successfully implemented. In total 20 participants have finished the online course “Inspection” and 29 participants have finished the online course “Constitutional organisation” since the beginning of 2022 (in total 125 participants in “Inspection” and 153 participants in “Constitutional organisation” since the uploading of the courses to the platform). The training “Constitutional organisation” have been finished by 41 participants since the beginning of 2022. The webinar “Prevention of conflict of interest, control of property of high officials, registers and lobbying in the Republic of Serbia” was conducted and 16 participants attended it. The National Academy for Public Administration has conducted the General Training Programme for civil servants, General Training Programme for employees in local self-government units, Training Programme for managers in government bodies and Training Programme for managers in local self-government units, adopted by the Government of the Republic of Serbia. The Introductory Training Programme for 2022 for both civil servants and employees in local self-government, including those with secondary and with tertiary education, within the programme field covering the preparation for taking the state professional examination, envisaged the training “Constitutional organisation” and “Constitutional organisation and fundamentals of state administration system” aimed at preparing for state professional exam pursuant to the Regulation on the programme and method of passing the state professional exam. The topics concerning the prevention of conflict of interest make a part of this training. The training “Prevention of conflict of interest, control of property of high officials, registers and lobbying in the Republic of Serbia” was developed in the General Training Programme for civil servants for 2022 within the thematic area “Prevention of corruption”. In addition, the online training “Inspection” was developed within the thematic area “Inspection” and it contains the thematic unit “integrity of inspectors: conflict of interest”. The training “Solving ethical dilemmas” covering also the topic of the conflict of interest was developed within the Training Programme for managers in government bodies for 2022. The training “Ethics and integrity of public officials in the local self-government units”, within the thematic field Key aspects of management in local self-government for public officials and and officials at positions in LSGU, and the training “Improvement of ethical action and management of conflict of interest” for managers in internal organisational units of city/municipal administration were developed within the Training Programme for managers in local self-government units for 2022. |  |
| 2.2.3.4. | Regular monitoring of public officials’ conflict of interest cases, including the number and level of sanctions applied. |  |  |  | -Anti-Corruption Agency -Republic Public Prosecutors Office -Misdemeanor courts |  | Continuously |  |  |  | Budget of the Republic of Serbia 2.553 € in 2020 - 851 € in 2021 - 851 € in 2022 - 851 € | Public officials’ conflict of interest cases are regularly monitored through Anti-Corruption Agency reports. |  |  |  |  | Аctivity is being successfully implemented. 1st quarter/2022: By applying the Law on Prevention of Corruption a total of 263 requests were resolved. Total of 11 decisions were issued, thus rejecting the request of a public official to perform another public office, i.e. to perform another job or activity (out of which in one proceedings the incompatibility of concurrent discharging public office and performing another job was determined). Upon final decision (seven), in five proceedings the public official ceased with concurrent discharging of public offices, i.e. performing other job or activity, while in two proceedings the deadline for submitting evidence that the decision was complied with is in progress. In four proceedings deadline for appeal has not elapsed, decision is not final. By applying the Law on Corruption Prevention, a total of 97 decisions on violation of the Law on Corruption Prevention were imposed to public officials and 91 measures and six decisions determining termination of other public office by force of law (Article 56, par. 8 of the Law on Corruption Prevention). Out of 91 measures, the following were imposed: - 80 measures of reprimand, - 10 measures of public announcement of decision on violation of the Law and - one measure of public announcement of recommendation for dismissal from public office. From the imposed reprimand measures, five measures included an order to a public official. In two proceedings deadline for acting has not elapsed yet. In three proceedings decision has not been final yet (delivery to public official is underway). One decision, by which the measure of public announcement of recommendation for dismissal from public office has not been final, i.e. deadline for lodging an appeal has not elapsed yet. Upon three final decisions imposing the measure of public announcement of recommendation for dismissal from public office (all issued in 2021, when the proceedings have also started), initiatives to the competent bodies were filed. In terms of decisions imposing termination of other public office, in one case acting upon appeal is underway. Five decisions determining termination of other public office by force of law have not been final. 2nd quarter/2022: By applying the Law on Prevention of Corruption a total of 194 requests were resolved. Total of eight decisions were issued, thus rejecting the request of a public official to perform another public office, i.e. to perform another job or activity (out of which in one proceedings the incompatibility of concurrent discharging public office and performing another job was determined). All respective proceedings are currently underway. By applying the Law on Corruption Prevention, a total of 83 decisions on violation of the Law on Corruption Prevention were imposed to public officials and 69 measures and 14 decisions determining termination of other public office by force of law (Article 56, par. 8 of the Law on Corruption Prevention). Out of 69 measures, the following were imposed: - 50 measures of reprimand, - 14 measures of public announcement of decision on violation of the Law and - five measures of public announcement of recommendation for dismissal from public office. From the imposed reprimand measures, four measures included an order to a public official. In one proceedings deadline for acting has not elapsed yet. In three proceedings decision has been final (public officials complied with the APC decision). Decisions, by which the measure of public announcement of recommendation for dismissal from public office have not been final, i.e. deadline for lodging an appeal has not elapsed yet. Upon three final decisions imposing the measure of public announcement of recommendation for dismissal from public office (all issued in 2021, when the proceedings have also started), initiatives to the competent bodies were filed. In terms of decisions imposing termination of other public office, in one case acting upon appeal is underway. Four decisions determining termination of other public office by force of law have been final, whereas for nine decisions the proceedings is underway, i.e., they have not been final yet. |  |
| 2.2.3.5. | Monitoring of conflict of interest cases through implementation of Code of Conduct for civil servants, in terms of number of detected and resolved conflict of interest cases, including disciplinary measures. |  |  |  | -High Civil Service Council |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia 15.318 € in 2020 - 5.106 € in 2021 - 5.106 € in 2022 - 5.106 € | High Civil Service Council annual report contains data on number of detected and resolved conflict of interest cases, including disciplinary measures. |  |  |  |  | Аctivity is being successfully implemented. The report on compliance with the Code of Conduct for Civil Servants for 2021 was submitted to the Ministry of State Administration and Local Self-Government and published on the website of the Personnel Management Service www.suk.gov.rs. |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.4.Look into and adequate and institutional solution to effectively address cases of illicit enrichment; |  |  |  |  |  |  | Cases of illicit enrichment are efficiently resolved according to adequate legal and institutional framework. |  |  |  |  | - Positive opinion by European Commission on Serbia’s progress - Number of initiated and finalized misdemeanor and other procedures. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.4.1. | Monitoring the implementation of the Criminal Code and the Law on Organisation and Competence of State Authorities in Suppression of Organized Crime, Terrorism and Corruption along with obligation of courts and public prosecutors’ offices of general and special jurisdiction, to deliver reports on number of initiated and completed proceedings. Ministry of Justice draws up uniform report (composed of reports of all mentioned authorities) and publishes it on the website. (Connected activity 2.3.1.3.) |  |  |  | -Ministry of Justice (State secretary in charge of anti-corruption) |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia- 63.060 € in 2020 - 21.020 € in 2021 - 21.020 € in 2022 - 21.020 € | Prepared and published report on the website of the Ministry of Justice. Annual report of Anti-Corruption Agency. |  |  |  |  | Аctivity is being successfully implemented. The report for 2021 was prepared in June 2022 and published on the official website of the Ministry of Justice: https://www.mpravde.gov.rs/tekst/33769/statistika-koruptivnih-krivicnih-dela-.php |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.5. Serbia amends its law on Free Access to Information of Public Importance, it strengthens the administrative capacity of the Office of the Commissioner for Information of Public Importance and Personal Data Protection, provides training on handling access to information requests and an initial track record of improved access to information, including with regard to privatisation deals, the activities of state owned enterprises, public procurement processes, public expenditures and donations from abroad to political parties. |  |  |  |  |  |  | Regulation in the field of free access to information are improved, their implementation is improved, inter alia, in regards to privatization, public procurement, public expenditures and donations from abroad to political subjects. |  |  |  |  | - Requests for access for information are adequately handled; - Positive opinion on progress of Serbia issued by European Commission; - Number of initiated and finalized procedures before Commissioner; - Number of rejected requests, court proceedings launched (on the basis of rejections) and number and content of court decisions - Annual report on work of Commissioner |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.5.1. | Conduct analysis of implementation of Law on free access to information of public importance, in particular emphasizing the following areas: -privatization - public procurement -public expenditures -foreign donations to political subjects. |  |  |  | -Commissioner for Information of Public Importance and Personal data Protection -with participation of Civil Society Organisations |  | Analysis: III quarter of 2020. |  |  |  | Budget of the Republic of Serbia- 8.642 € in 2020. | Conducted analysis of implementation of Law on free access to information of public importance, in particular emphasizing areas of privatization, public procurement, public expenditures and foreign donations to political subjects. |  |  |  |  | Activity is fully implemented. The Commissioner published the Report on the work of the Commissioner for Information of Public Importance and Personal Data Protection for 2020, which contains relevant analyzes by thematic areas. Political parties are not bound by the Law, so the Commissioner cannot comment on this area. All questions and analyses related to the application of this law can be found in the annual reports of the Commissioner (pages 22-32). Specific statistical indicators of the Commissioner's activities in the implementation of the Law in 2020 are also available on pages 68 – 95. The report was submitted to the National Assembly for consideration and published on the Commissioner's website at the following link: https://bit.ly/2QduXEz |  |
| 2.2.5.2. | Adopt amendments to Law on free access to information of public importance based on analysis of implementation of Law on free access to information of public importance. |  |  |  | -Ministry of Public Administration and Local-Self-government Partner institution: -Commissioner for Information of Public Importance and Personal data Protection -Government of the Republic of Serbia -National Assembly |  | IV quarter of 2020. |  |  |  | -Budget of the Republic of Serbia- 48.909 € in 2020. | Adopted amendments to Law on free access to information of public importance. |  |  |  |  | Activity is fully implemented. The Law on Amendments to the Law on Free Access to Information of Public Importance ("Official Gazette of the RS", No. 120/04, 54/07, 104/09, 36/10 and 105/21) has begun to apply on the February 17th. 2022. The Instruction for the preparation and publication of the Information Booklet on the work of public authorities has been adopted ("Official Gazette of the RS", No. 10/22). |  |
| 2.2.5.3 | Capacity building of the Commissioner based on previously conducted analysis of current staff capacities in particular: - organisational structure - number of employees - degree of competencies, in line with amended Rulebook on internal organisation and classification of jobs. |  |  |  | - Commissioner for Information of Public Importance and Personal Data Protection -National Assembly – Board for Administrative matters |  | Continuously, commencing from six months after adoption of amendments to the Law |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after the completion of the analysis. | Amended Rulebook on internal organisation and classification of jobs. Vacancies filled in accordance with amended Rulebook. |  |  |  |  | Activity is partially implemented. The Rulebook on Internal Organization and Systematization of Workplaces has been amended due to amendments to the Law on Free Access to Information of Public Importance. The number of employees in the Commissioner's Office is 107. |  |
| 2.2.5.4. | Monitoring of implementation of Law of free access to information of public importance. |  |  |  | -Commissioner for Information of Public Importance and Personal data Protection |  | Continuously, commencing from entry the Law into force |  |  |  | Budget of the Republic of Serbia-- 639 € in 2020 - 213 € in 2021 - 213 € in 2022 - 213 € | Overview of current state in annual report issued by Commissioner for Information of Public Importance and Personal data Protection. |  |  |  |  | Activity is being succesufully implemented. The table with January- June 2022 data is available in the quarter reports. |  |
| 2.2.5.5. | Conduct trainings for officials authorised to decide on requests for free access to information, in accordance with case law and international standards. |  |  |  | - National Academy of Public Administration -Commissioner for Information of Public Importance and Personal data Protection |  | Continuously |  |  |  | Budget of the Republic of Serbia Costs currently unknown – will be known will after development of the training plan of the National Academy of Public Administration. and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Trainings conducted. Percentage of trained officials authorised to decide on requests for free access to information in relation to those required/in needs of training. |  |  |  |  | Activity is being succesufully implemented. The Commissioner for Information of Public Importance and Personal Data Protection organized: - 3.2.2022. - training for employees on the news from the Law on Free Access to Information of Public Importance. - 10.2.2022. - training for employees on the news from the Law on Free Access to Information of Public Importance. - 22.2.2022.- training on novelties from the Law on Free Access to Information of Public Importance was held for 49 interested persons, organized by the National Academy of Public Administration. - On May 5, 2022, a training on novelties from the Law on Free Access to Information of Public Importance, held in Kragujevac for 28 local self-government employees within the Standing Conference of Towns and Municipalities (SKGO) framework. - On May 16, 2022, a training for employees on novelties from the Law on Free Access to Information of Public Importance, held in Novi Sad for 21 local self-government employees (SKGO). - On May 30, 2022, a training on novelties from the Law on Free Access to Information of Public Importance, held in Novi Gradište for 11 local self-government employees (SKGO). - On June 2, 2022, a training on novelties from the Law on Free Access to Information of Public Importance, held for 30 employees of the Civil Aviation Directorate. - On June 13, 2022 a training on novelties from the Law on Free Access to Information of Public Importance, held in Šabac for 13 local self-government employees (SKGO). - On June 20, 2022, a training on novelties from the Law on Free Access to Information of Public Importance, held in Vrnjačka Banja for 15 local self-government employees (SKGO). - On June 27, 2022, a training on novelties from the Law on Free Access to Information of Public Importance, held in Niš for 18 local self-government employees (SKGO). In the reporting period, one training (in the form of webinar) “Right to access to public information” with 49 participants was conducted. The National Academy for Public Administration has conducted the General Training Programme for civil servants, General Training Programme for employees in local self-government units, Training Programme for managers in government bodies and Training Programme for managers in local self-government units, adopted by the Government of the Republic of Serbia. The training “Right to access to public information” was developed in the General Training Programme for civil servants for 2022 within the thematic area “Prevention of corruption”. The Sectorial continuous professional development programme for employees in local self-government units, being the part of the General Training Programme for employees in LSGU for 2022, envisaged the training “Exercising rights to obtain public information” within the thematic area “Good governance”. |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.6. Serbia recruits and manages the career of civil servants on the basis of clear and transparent criteria, focusing on merits and proven skills. Serbia develops and applies a mechanism for the effective implementation of the Code of Conduct for civil servants. Serbia provides an initial track record of effective sanctions in cases of breaches of this Code. Serbia ensures prevention of corruption through systematic introduction of effective internal control systems and strengthening managerial accountability in the public sector. |  |  |  |  |  |  | Public administration has been depoliticized and transparent, with strengthened integrity of public administration and internal control and audit bodies. |  |  |  |  | - Positive opinion of European Commission on Serbia’s progress; - Number of officials in public administration who are employed or promoted in accordance with merits system; - Percentage of state authorities which have internal control and/or audit body - Harmonised finance management to INTOSAI standards of internal control. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.6.1. | Ensure implementation of the new legal framework based on competencies in the processes of recruitment, evaluation, promotion and career development of civil servants. |  |  |  | -Human Resources Management Service -High Civil Service Council -Ministry of Public Administration and Local Self-government |  | Continuously |  |  |  | Budget of the Republic of Serbia-8.642 € | Processes of recruitment, evaluation, promotion and career development of civil servants are based on the full implementation of the system of competences (evidented in the Human Resources Management Service relevant reports). |  |  |  |  | During the period since 01.01.2022 until 31.03.2022 the Human Resources Management Service announced 285 vacancies for filling executive positions by hiring a total of 346 executors. Out of 285 announced competitions, 21 are internal, and 264 are public. By the end of the reporting period, 52 procedures were completed, as follows: 5 internal, 47 public; while the remaining 233 competitive procedures are in progress. For the purpose of assessing behavioral competencies in competition procedures in other public bodies, psychologists performed an assessment for 57 candidates, for the Tax administration, 9 candidates for Second Court in Belgrade, 1 candidate for the Anti-Corruption Agency as well as for First Court in Belgrade, 7 candidates for Administrative Court and 3 candidates for Constitutional Court. At the end of the first quarter of 2022, the employees of the HRMS gathered data for a Questionnaire for assessing candidates` satisfaction related to the competition procedure from 183 fulfilled forms. Gathering information and data from the administration bodies for completing Report on quality of filling vacancies (HRMS proposed steps and mesurments for improving based on statistics and collected data) is in progress. In terms of performance appraisal, the HRMS is working on collecting annual reports from state administration bodies for 2021, with the aim of preparing a summary annual report to be submitted to the RS Government and to the line ministry during the second half of 2022. Also, due to the amendments to the Regulation on performance appraisal that came into force in early 2022, activities have been intensified to provide instruction to human resources management units on setting annual goals of organizational units, which now include determining performance indicators, starting and estimated value and sources of verification. Regarding career development and promotion of civil servants in the reporting period, the 1st quarter of 2022, the following activities were carried out: an analysis of individual development potentials for the needs of promotion to a managerial position for 40 civil servants; 3 officials from the local self-government passed the procedure of assessment of general functional and behavioral competencies for the need of taking over through the Internal labor market; 8 people applied for online competence assessment for development purposes; career counseling was conducted with 51 civil servants; 4 coaching sessions were held with 2 civil servants; 4 civil servants at the appointed positions passed the 360 ​​degree Feedback assessment for development purposes. The Service also drafted two new decrees that came into force at the beginning of 2022, namely: the Decree on Determining Competences for the Work of Civil Servants and the Decree on Determining Competences for the Work of Servants in the bodies of AP and LSGU. During the period from 01.04.2022 to 30.06.2022 the Human Resources Management Service announced 319 vacancies for filling executоrial positions and 378 executors were hired. Out of 319 announced competitions 21 are internal and 298 are public. By the end of the reporting period 60 procedures were completed, as follows: 12 internal, 48 public; while the remaining 259 competitive procedures are in progress. In addition to this, the Human Resources Management for the purpose of assessing behavioral competencies in selection procedures in other public bodies, psychologists of the HRMS performed an assessment for 38 candidates for the Commercial Court in Belgrade, 1 candidate for the Anti-Corruption Agency and 13 candidates for Administrative Court and 13 candidates for Tax Administration. During May HRMS employees completed “Report on quality of filling vacancies in the state administration bodies”. In terms of performance appraisal, the HRMS is working on collecting annual reports from state administration bodies for 2021, aiming to prepare a summary annual report to be submitted to the RS Government and to the line ministry during the second half of 2022. During April an online survey of the satisfaction of civil servants with the performance evaluation procedure was carried out, on a sample of 1455 respondents. The results of this research will be an integral part of the summary report on the performance appraisal in the state administration bodies for 2021. Regarding career development and promotion of civil servants in the reporting period, the 2nd quarter of 2022, the following activities were carried out: an analysis of individual development potentials for the needs of promotion to a managerial position for 62 civil servants; 1 official from the local self-government passed the procedure of assessment of general functional and behavioral competencies for the need of taking over through the Internal labor market; 6 people applied for online competence assessment for development purposes; career counseling was conducted with 81 civil servants; 4 coaching sessions were held with 2 civil servants; 35 civil servants at the appointed positions passed the 360 ​​degree Feedback assessment for development purposes. The HRMS developed a Guide to Career Counseling and Career Planning for Civil Servants, which is available on the HRMS website for all stakeholders (civil servants, managers and employees in human resources management units) for this area of development. |  |
| 2.2.6.2. | Completion of all initiated vacancy procedures for filling appointed positions in the state administration and the commencement of competition procedures for all vacant positions (including appointed positions that are currently in acting status). |  |  |  | -Human Resources Management Service -High Civil Service Council -authorised proposers -Government of the Republic of Serbia |  | Continuously |  |  |  | Budget of the Republic of Serbia 630.000 € in 2020 - 210.000 € у 2021 - 210.000 € у 2022 - 210.000 € | Vacancy procedures implemented. All initiated vacancy procedures for filling appointed positions in the state administration completed by Competition Commissions. |  |  |  |  | Аctivity is being successfully implemented. Total number of advertised competition procedures for filling appointed positions in the period January-March 2022 is 19 competitions, out of which 6 are internal and 13 are public. Out of the total number of announced competitions 10 competitions are competed: 3 internal and 7 public. In the reporting period 29 competition procedures, that were announced in the earlier period, are conducted and finalized in the reporting period, namely 2 internal and 27 public competitions. Total number of vacancies for appointed positions in the State administration – 407. Total number of employees who are currently in appointed positions, appointed by the Government after public or internal competition procedure conducted – 180. Total number of advertised competition procedures for filling appointed positions in the period April- June 2022 was 11 competition procedures, out of which 8 were internal and 3 were public. Out of the total number of announced competitions neither was completed. In the reporting period 14 competition procedures were completed that had been announced in the previous period, namely 3 internal and 11 public competitions. Total number of vacancies for appointed positions in the State administration – 407. Total number of employees who are currently in appointed positions, appointed by the Government after public or internal competition procedure conducted – 178. |  |
| 2.2.6.3. | Monitoring the Code of Conduct for civil servants violations, through the applied sanctions in cases of violation of the Code. |  |  |  | -High Civil Service Council |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia budgeted in 2.2.3.5. | Sanctions in cases of violation of the Code of Conduct for civil servants are applied. Annual reports of the High Civil Service Council. |  |  |  |  | Аctivity is being successfully implemented. At the 112th session of the High Civil Service Council on March 10, 2022, a Working Group with the task of drafting a report on compliance with the Code of Conduct for Civil Servants based on reports from state administration bodies, was formed. At the 113th session of March 30, 2022, the High Civil Service Council adopted the Report on Compliance with the Code of Conduct for Civil Servants for 2021, with a proposal for measures to improve compliance with the Code. The report on compliance with the Code of Conduct for Civil Servants for 2021 was submitted to the Ministry of State Administration and Local Self-Government and published on the website of the Personnel Management Service www.suk.gov.rs. |  |
| 2.2.6.4. | Improve program budgeting implementation process (operational and methodological improvement of the process of planning and preparing of multiannual budget on all levels of government). |  |  |  | -Ministry of Finance |  | Continuously |  |  |  | Budget of the Republic of Serbia - 30.878 € and Donor support. Donor support will be needed, for which will be applied in the following period. Costs currently unknown – will be known until the end of 2020. | Program budgeting implementation process improved on all levels of government. |  |  |  |  | Аctivity is being successfully implemented. No activities in the reporting period. |  |
| 2.2.6.5. | Conduct periodical analyses of program budgeting process and identify recommendations for improvement. |  |  |  | -Ministry of Finance |  | Continuously, once a year |  |  |  | Budgeted in 2.2.6.4. and in Chapter32 | Percentage of budget users switched to the program budgeting. Recommendations for improvement identified. |  |  |  |  | Аctivity is being successfully implemented. No activities in the reporting period. |  |
| 2.2.6.6. | Improve methodology of program budgeting and preparing new instructions in line with analyses recommendations (activity 2.2.6.5.). |  |  |  | -Ministry of Finance -Republic Secretariat for public policies |  | Continuously, once a year |  |  |  | Budgeted in 2.2.6.4. and in Chapter32 | Percentage of harmonization of budget users program structures with Instruction for preparation of program budgeting. |  |  |  |  | Аctivity is being successfully implemented. In the reporting period, there were no activities or changes in relation to the previously submitted reports. |  |
| 2.2.6.7. | Strengthen staff capacities of the Central Harmonization Unit (which performs central directing and coordinating of the activities of the public internal control) in accordance with amended Rulebook on job classification. |  |  |  | -Ministry of Finance |  | IV quarter of 2022 |  |  |  | Budgeted in 2.2.6.4. and in Chapter32 | Positions filled. |  |  |  |  | Activity is partially implemented. As of March 2022, 11 people were permanently employed at the CHU (one person has a statutory status at rest) without an assistant minister, while 2 people were hired on a contract basis. The plan is to fill the vacancies in 2022. In the first quarter of 2022, one person was hired on a contract for temporary and occasional jobs to support the collection of annual reports on the state of internal controls and internal audit activities with users of public funds. The internal competition filled two executive positions in the CHU in June 2021 (r.m. coordinator for financial management and control and internal audit, as well as r.m. coordinator for the methodology of internal audit). As of Jun 2022, 12 people were permanently employed at the CHU with an assistant minister, while 2 people were hired on a contract basis. The plan is to fill the vacancies in in forthcoming period. |  |
| 2.2.6.8. | Increase the number of trained managers and employees in the public administration on the basis and importance of financial management and control, and increase the number of qualified internal auditors. |  |  |  | -Ministry of Finance |  | Continuously |  |  |  | Budgeted in Chapter32 | Consolidated Annual Report on state of internal financial control in public sector. Number of newly trained managers and employees in the public administration and certified internal auditors in relation to 2013. |  |  |  |  | Аctivity is being successfully implemented. Theoretical trainings for FMC (five-day) and IR (seven-day) are held regularly (usually twice a year), and by the end of March 2022, the CHU had trained 2,880 managers and employees of public funds beneficiaries (PFB) through basic training for FMC. Theoretical training for IA as of March 2022, 1.138 candidates. In addition to these trainings, the CHU conducts one-day trainings for top managers at the PFBs. Two online trainings for FMC were organized through the NAPA platform in 2021 and 137 + 159 participants were attended. Practical training for internal auditors conducted by mentors from the CHU is continuously conducted. By the end of March 2022, 506 candidates had passed the exam for internal auditors and acquired the title of certified internal auditor in the public sector. - The first quarter of 2022 - a theoretical training for internal auditors was held - 47 participants were attended, and a one-day training for top managers was held at the Institute of Nuclear Sciences – Vinca - 26 people were attended. Theoretical trainings for FMC (five-day) and IR (seven-day) are held regularly (usually twice a year), and by the end of March 2022, the CHU had trained 2,880 managers and employees of public funds beneficiaries (PFB) through basic training for FMC. Theoretical training for IA as of March 2022, 1.138 candidates. In addition to these trainings, the CHU conducts one-day trainings for top managers at the PFBs. Two online trainings for FMC were organized through the NAPA platform in 2021 and 137 + 159 participants were attended. Practical training for internal auditors conducted by mentors from the CHU is continuously conducted. By the end of Jun 2022, 532 candidates had passed the exam for internal auditors and acquired the title of certified internal auditor in the public sector. During second quarter of 2022 - workshops for financial management and control were held in the cities of Čačak, Novi Pazar and Prokuplje, 102 participants attended (23+54+25). In the same quarter (April 12) the exam for internal auditors was held and 26 candidates passed. |  |
| INTERIM BENCHMARK |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.7. Serbia effectively implements the new Law on Whistle-Blowers and monitors its implementation. |  |  |  |  | Implementation of the Law on Whistle-Blowers is effective and regularly monitored. |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings for the protection of whistle-blowers. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.7.1. | Conduct training on the implementation of the Law on protection of whistleblowers for the police, public prosecutors, judges, as well as special departments for suppression of corruption in Higher public prosecutors' offices and Higher courts. |  |  |  | -Judicial Academy |  | Continuously |  |  |  | IPA 2013 – 3.600.000 € “Prevention and Fight against Corruption” Project and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Training courses for the police, public prosecutors, judges, and special departments for suppression of corruption in Higher public prosecutors' offices and Higher courts conducted. Percentage of police officers, public prosecutors and judges trained on the implementation of the Law on protection of whistleblowers in relation to those required/in needs of training. |  |  |  |  | Аctivity is being successfully implemented. During the firs quarter of 2022, Judicial Academy has conducted one training on the topic ‘’Law on protection of whistleblowers’’, for a total of 16 participants. Also, during the reporting period, in cooperation with the Association ‘’Pištaljka’’, a one-day training was held on the topic ‘’Professional ethics in prevention and fight against corruption’’, for a total of 23 participants (judges). On the topic ‘’Identification and protection from inappropriate influence on judges- advanced training of trainers’’, 1 one-day and 1 two-day trainings were conducted, for a total of 44 participants.. During the second quarter of 2022, Judicial Academy has conducted two one-day trainings on the topic ‘’Law on protection of whistleblowers’’, for a total of 38 participants. Also, during the reporting period, in cooperation with the Association ‘’Pištaljka’’, 3 one-day trainings were held in Kragujevac, Niš and Novi Sad on the topic ‘’Professional ethics in prevention and fight against corruption’’, for a total of 88 participants. Also, on the topic ‘’Identification and protection from inappropriate influence on judges- advanced training of trainers’’, 4 one-day trainings were conducted, for a total of 63 participants. |  |
| 2.2.7.2. | Monitor the implementation of the Law on whistle blowers through the preparation of the annual report of the Ministry of Justice made ​​on the basis of periodic reports of the competent authorities on cases of acting in relation to the whistle blowers. |  |  |  | -Ministry of Justice (state secretary) |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia - 1914 € in 2020 - 638 € in 2021 - 638 € in 2022 - 638 € and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Annual Report of the Ministry of Justice developed and published with detailed statistics. |  |  |  |  | Аctivity is being successfully implemented. Report on the application of the Law on Protection of Whistleblowers for 2021 was prepared and published on the official website of the Ministry of Justice. https://www.mpravde.gov.rs/obavestenje/36949/izvestaj-o-primeni-zakona-o-zastiti-uzbunjivaca-za-2021godinu.php |  |
| 2.2.7.3. | Monitor the effects of the Law on protection of Whistle-blowers in terms of acting of state authorities upon whistleblowers disclosures. |  |  |  | -Ministry of Justice (state secretary) |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia – budgeted in 2.2.7.2. and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Ministry of Justice report on the state authorities’ actions upon whistleblowers disclosures is developed and published. |  |  |  |  | Activity is being successfully implemented. The report on the actions of state authorities according to the reports of whistleblowers for 2021 is prepared and published on the official website of the Ministry of Justice. https://www.mpravde.gov.rs/obavestenje/36949/izvestaj-o-primeni-zakona-o-zastiti-uzbunjivaca-za-2021godinu.php |  |
| 2.2.7.4. | Raising awareness of citizens about the Law on protection of Whistleblowers and raising their readiness to report wrongdoings as whisleblowers. |  |  |  | -Ministry of Justice (state secretary) |  | IV quarter of 2021 |  |  |  | IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) and USAID GAI | Raising awareness campaign conducted. |  |  |  |  | Activity is not implemented. The Ministry of European Integration has hired an expert to analyze the Law on the Protection of Whistleblowers. Based on this analysis, the need for a possible change in the law will be considered, and a brochure will be prepared in order to raise the level of awareness among citizens about the Law on the Protection of Whistleblowers and raise their readiness to act as whistleblowers |  |
| INTERIM BENCHMARK |  |  |  |  | OVERALL RESULT |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.8. Serbia implements and assesses the impact of measures taken to reduce corruption in vulnerable areas (health sector, taxation and customs, education, local authorities, the privatisation process, public procurement and the police), takes remedial action where needed and establishes an initial track record of a measurable reduction of corruption in these areas. |  |  |  |  | Measures taken to reduce corruption in public procurement are implemented and assessed. Track record of a measurable reduction of corruption in public procurement is established. |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Annual supervision report of the Public Procurement Office, Annual report of the Republic Commission for the Protection of Rights in Public Procurement and Annual report of the State Audit Institution; - Number of initiated and finalized misdemeanor and other proceedings for breaches of the Law on Public Procurement. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.8.1. | Strengthen staff capacity of the Public Procurement Office especially in terms of the number and position of employees. |  |  |  | -Public Procurement Office |  | IV quarter of 2020. |  |  |  | Budget of the Republic of Serbia In 2020. Staff capacity strengthening costs currently unknown. | Positions filled. |  |  |  |  | Activity is partially implemented. The Public Procurement Office has adopted a new Rulebook on the internal organization and systematization of jobs in the Public Procurement Office No: 110-00-2/2020 November 2nd 2020, which provides total of 36 systematized jobs, of which 4 are civil servants on position, so that the maximum number of civil servants who can be hired in PPO now are 55 in relation to the maximum number of 38 civil servants according to the previous Rulebook on internal organization and systematization of jobs. As of December 2021, a total of 33 civil servants were employed in the Public Procurement Office and 11 persons on the basis of contracts for temporary and occasional work, while as of March 31st, 2022, there were a total of 33 civil servants in PPO and 12 persons on the basis of contracts for temporary and occasional work. |  |
| 2.2.8.2. | Establish a new public procurement portal in line with new functionalities arising from the new Public Procurement Law. |  |  |  | -Public Procurement Office |  | IV quarter of 2020. |  |  |  | Budget of the Republic of Serbia - 80.000 € and IPA 2013 “Prevention and Fight against Corruption” Project – Public Administration Reform Sector - 800.000 € | New public procurement portal established and operational. |  |  |  |  | Activity is fully implemented. Situation has not chaged, the activity was previously implemented. |  |
| 2.2.8.3. | Monitoring the implementation of the measures of supervision and control in public procurement. |  |  |  | -Public Procurement Office -Republic Commission for the Protection of Rights in Public Procurement -Ministry of Finance |  | Continuously, once a year |  |  |  | Budget of the Republic of Serbia -1.914 € In 2020 - 638 € In 2021 - 638 € In 2022 - 638 € | Report of the Administration for Public Procurement on supervision over the implementation of the Law on Public Procurement. Report of the Republic Commission for the Protection of Rights in Public Procurement. Report of the Ministry of Finance on monitoring the execution of public procurement contracts. |  |  |  |  | Аctivity is being successfully implemented. During the 1st quarter, the PPO continued to monitor the implementation of public procurement regulations. Data on the conducted monitoring for 2021 in accordance with the legal deadline were submitted to the Government and the National Assembly in the form of the Annual Report on the conducted monitoring for 2021, based on Article 180, paragraph. 6 of the Law on Public Procurement ("Official Gazette of RS", No. 91/19). |  |
| 2.2.8.4. | Conduct training courses for police officers, prosecutors, judges and Public Procurement Office staff to efficiently prosecute cases of corruption in public procurement (pursuant to Financial Investigations Strategy). |  |  |  | -Public Procurement Office -Republic Commission for the Protection of Rights in Public Procurement -Judicial Academy |  | Continuously |  |  |  | Budget of the Republic of Serbia- 3.083.301€ (budgeted in 2.2.8.6.) and donor support IPA 2019 – 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Training courses conducted. Percentage of police officers, public prosecutors, judges and Public Procurement Office staff trained in relation to those required/in needs of training. |  |  |  |  | Activity is being succsesfully implemented. During the 1st quarter, the Public Procurement Office did not conduct any training for members of the police, prosecutors and judges in order to process cases of corruption in public procurement more efficiently. The plan is to organize trainings for members of the police, prosecutors and judges in 2022. In the reporting period, 1 one-day seminar was held on the topic ‘’Public procurement- responsibility of the procuring entity’’, with the support of NALED, for a total of 15 participants from special departments for the suppression of corruption. Also, eight one-day seminars were held on the topic: “Financial forensics module 1: Corruption, fraud and public procurement” for a total of 62 participants. |  |
| 2.2.8.5. | Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in public procurement area. |  |  |  | -Anti-Corruption Agency -Public Procurement Office -Republic Commission for the Protection of Rights in Public Procurement |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.8.6.) and donor support. Within IPA 2013 – Prevention and Fight against Corruption Project, the necessary funds were provided. | Methodology for Impact assessment of measures undertaken to reduce corruption in public procurement area is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.8.6. | Establish the Working Group for drafting Impact assessment in Public Procurement field and collect all relevant data. |  |  |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia - 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in Public Procurement field collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.8.7. | Conduct and present Impact assessment in Public Procurement field. |  |  |  | -Anti-Corruption Agency |  | I quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.8.6.) and donor support. Donor support is needed, for which will be applied in the upcoming period. | Impact assessment in Public Procurement field is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.8.8. | Undertake corrective measures based on impact assessment findings |  |  |  | -all relevant institutions, based on impact assessment findings |  | I quarter 2023 |  |  |  | Budget of the Republic of Serbia and donor support Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.8.7. | Corrective measures based on impact assessment findings undertaken. |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.9. Serbia implements and assesses the impact of measures taken to reduce corruption in vulnerable areas (health sector, taxation and customs, education, local authorities, the privatisation process, public procurement and the police), takes remedial action where needed and establishes an initial track record of a measurable reduction of corruption in these areas. |  |  |  |  |  |  | Prevention and sanctioning of corruption in the private sector, particularly in the privatization process is performed through concrete measures establishing transparency and accountability, particularly in commercial entities owned or controlled by the state. |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Reports of the Anti-Corruption Council; - Number of initiated and finalized criminal proceedings for corruption in the private sector. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME /DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.9.1. | Establish internal control in all public companies. |  |  |  | -Ministry of Finance, Central Harmonization Unit -All public companies |  | IV quarter of 2022 |  |  |  | Budgeted in Chapter 32 | Internal control established in all public companies, which is confirmed in Annual report of the Central Harmonization Unit. |  |  |  |  | Activity is partially implemented. Implementation of activities is underway and PFBs independently establish internal control in their organizations on the principle of decentralized system of internal controls, while the Ministry of Finance Sector - Central Harmonization Unit provides legal and methodological framework and continuously conducts training and promotional activities importance and obligations of establishing a system of internal controls. In order to raise awareness and train managers and employees on internal controls, in the second and fourth quarters of 2021, the CHU organized basic training for financial management and control for 120 + 145 participants, as well as for internal auditors for 60 participants at the beginning of the third quarter and at the end of the first quarter of 2022 for 55 candidates. According to the Law on Budget System, PFBs are obliged to establish a system of financial management and control. On the authority of this law, the Head of the PFBs is responsible for the establishment of the system of financial management and control. Having in mind the above, this activity (2.2.9.1.) from the revised AP is not defined in accordance with Article 81, paragraph 4 of the Law on Budget System because besides to public companies, the Ministry of Finance - CHU Sector has been appointed as the holder of activities for the establishment of internal controls in public companies (PFBs). According to the law, PFBs should inform the Minister of Finance on the implementation of internal controls in their organization, State of play of the PFBs is monitored by the Sector - Central Harmonization Unit and based on individual reports of the PFBs prepares Consolidated Annual Report on internal financial control in RS and reports to the Government. Based on the data from the on the State of Internal Financial Control in the Public Sector in the RS for 2020 adopted by the Government of the RS by the conclusion 05 Number: 400-7619 / 2021-2 of August 26, 2021, from public enterprises and companies capital from the central republic level monitored by the Central Harmonization Unit, 36 submitted a report on the state of the financial management and control system, or 87.80% of the group of public found beneficiaries. |  |
| 2.2.9.2. | Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in privatisation process. |  |  |  | -Anti-Corruption Agency -in cooperation with Ministry of Commerce |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.9.3.) and donor support If the donor support is needed, for which will be applied in the upcoming period. | Methodology for Impact assessment of measures undertaken to reduce corruption in privatisation process is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.9.3. | Establish the Working Group for drafting Impact assessment in privatisation process and collect all relevant data. |  |  |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in privatisation process collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.9.4. | Conduct and present Impact assessment in privatisation process. |  |  |  | -Anti-Corruption Agency |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.9.3.) and donor support 21.000,00 € Donor support is needed for which will be applied in the upcoming period. | Impact assessment in privatisation process is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.9.5. | Undertake corrective measures based on Impact assessment findings. |  |  |  | -all relevant institutions, based on impact assessment findings |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.9.4. | Corrective measures based on Impact assessment findings undertaken. |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.10. Serbia implements and assesses the impact of measures taken to reduce corruption in vulnerable areas (health sector, taxation and customs, education, local authorities, the privatisation process, public procurement and the police), takes remedial action where needed and establishes an initial track record of a measurable reduction of corruption in these areas. |  |  |  | Assessment of the measures against corruption in the field of health, tax, education, police, customs and local government indicates that they are improved and fully implemented. |  |  |  |  |  |  |  | 1. Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; 2. The extent of fulfillment of the measures and activities in the areas identified in the Operational Plan and sectoral strategies and action plans, based on the reports of the Anti-Corruption Agency; |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME /DEADLINE |  |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.10.1. |  | HEALTH. Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in health sector. | -Anti-Corruption Agency -in cooperation with Ministry of Health |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.2.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in in health sector is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.2. |  | Establish the Working Group for drafting Impact assessment in health sector and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in health sector collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.3. |  | Conduct and present Impact assessment in health sector. |  | -Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.2.) and donor support 21.000,00 € Donor support is needed for which will be applied in the upcoming period. | Impact assessment in health sector is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.10.4. |  | Undertake corrective measures based on Impact assessment findings. |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.10.3. | Corrective measures based on Impact assessment findings undertaken |  |  |  |  |  |  |
| 2.2.10.5. |  | Prepare and adopt Operational Plan for fight against corruption in the health area. |  | -Ministry of Health -with participation of CSOs |  |  | IV quarter of 2021 |  |  |  | Budget of the Republic of Serbia 17.285 € | Operational Plan for fight against corruption in the health area adopted. |  |  |  |  | Activity is fully implemented. The Operational plan for the fight against corruption in health area was adopted on December 28, 2021. In addition to the representatives of the Ministry of Health and the competent chambers, representatives of civil society also participated in the development of the Operational plan. |  |
| 2.2.10.6. |  | TAXATION. Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in taxation area. | -Anti-Corruption Agency -in cooperation with Ministry of Finance, Tax Administration |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.7.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in taxation area is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.7. |  | Establish the Working Group for drafting Impact assessment in taxation area and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in taxation area collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.8. |  | Conduct and present Impact assessment in taxation area. |  | -Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.7.) and donor support 21.000,00 € Donor support is needed for which will be applied in the upcoming period. | I Impact assessment in taxation area is drafted and presented to the National Assembly |  |  |  |  | Activity is fully implemented The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.10.9. |  | Undertake corrective measures based on Impact assessment findings. |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.10.8. | Corrective measures based on Impact assessment findings undertaken |  |  |  |  | . |  |
| 2.2.10.10. |  | Prepare and adopt Operational plan for fight against corruption in the taxation area. |  | -Ministry of Finance, Tax Administration -with participation of CSOs |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia 17.285 € | Operational plan for fight against corruption in the taxation area adopted. |  |  |  |  | Activity is fully implemented. The Operational Plan for the Prevention of Corruption in the Field of Taxation was adopted on December 31, 2021 for the year 2022. In accordance with that, and in order to fulfill the activities from the Operational Plan for Prevention of Corruption in the Field of Taxation, a meeting was held in the premises of the Tax Administration on the implementation of measures, namely training programs for tax officers employed in the Department of Internal Control on the topic of detecting crimes related to corruption, obtaining evidence and further actions. Implementation of measures and activities envisaged by the Operational Plan of the Tax Administration for the Prevention of Corruption: • 2.1.1.3 Development of a training program for employees of the Internal Control Department; • 2.1.1.4 Implementation of a training program for tax officials employed in the Department of Internal Control on the topic of detecting crimes related to corruption, obtaining evidence and further action. Considering that the mentioned activities are carried out in cooperation and with the help of the University of Criminal Investigation and Police Studies, it was agreed to provide information on the educational profile, number of employees in the Department of Internal Control, proposal of possible training time, number who need accommodation, proposed amendment to LTPTA and the draft Rulebook on Internal Control. In the premises of the Tax Administration Headquarters, a meeting was held with the representatives of the University of Criminal Investigation and Police Studies, who, in order to develop the Draft of the training program for internal control inspectors, submitted a request for information on the number of employees in the Internal Control Department of the Tax Administration, as well as a proposal for the possible time of the training and the number of employees who will need to have provided accommodation. Also, it was requested to submit the proposal to amend the LTPTA and the text of the Draft Rulebook on Internal Control. The requested information was provided at the next meeting held in the premises of the University of Criminal Investigation and Police Studies, and it was agreed that the Training Program Proposal would be presented at the next meeting. In the premises of the University of Criminal Investigation and Police Studies, a meeting was held at which the Proposal for a training program for internal control inspectors on the topic of detection of criminal acts of corruption was presented, which was agreed to by the Head of the Internal Control Department of the Tax Administration. Related to the activity from the Operational Plan of the Tax Administration for the prevention of corruption in the area of taxation for the year 2022, the activity related to the submission to the Ministry of Finance of the Proposal for amendments and supplements to the LTPTA and the text of the Draft Rulebook on Internal Control, the preparation of proposals for amendments and supplements to the aforementioned acts are in procedure. |  |
| 2.2.10.11. |  | EDUCATION. Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in education area. | -Anti-Corruption Agency -in cooperation with Ministry of Education |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.12.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in education area is developed and based on clear criteria |  |  |  |  | Activity is fully implemented. The Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.12. |  | Establish the Working Group for drafting Impact assessment in education area and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in education area collected |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.13. |  | Conduct and present Impact assessment in education area. |  | -Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.12.) and donor support 21.000,00 € Donor support is needed for which will be applied in the upcoming period. | Impact assessment in education area is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.10.14. |  | Undertake corrective measures based on Impact assessment findings |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.10.13. | Corrective measures based on Impact assessment findings undertaken. |  |  |  |  |  |  |
| 2.2.10.15. |  | Prepare and adopt Operational plan for fight against corruption in education area. |  | -Ministry of Education -with participation of CSOs |  |  | III quarter of 2021 |  |  |  | Budget of the Republic of Serbia 17.285 € | Operational plan for fight against corruption in education area adopted. |  |  |  |  | Activity is fully implemented. The activity was previously successfully implemented.The Operational Plan for fight against corruption in education area was adopted by the Minister’s Decision number 021-02-126/2021-09 on October 15, 2021. In the second quarter of 2022, the following activities were undertaken in the realization of the goals envisaged by the Operational Plan for Fight Against Corruption in the field of Education. In respect of implementation of part II of the Operational Plan related to the goal – ENROLLMENT OF STUDENTS IN ACCORDANCE WITH THE LAW, in the course of regular inspections carried out by the Department for Inspection Supervision in higher education institutions and institutions of pupil and student standard, checks in respect of enrolment of students were carried out, inter alia, through checklists. Unlike the previous school year of 2020/2021, when 2 requests were submitted for the initiation of misdemeanor proceedings due to the enrolment of students exceeding the number approved by the Operating License, in this academic year of 2021/2022 until 08 June 2022, in regular inspection supervisions, there were no illegalities in the behaviour of the institutions when enrolling students. Regarding the implementation of Part III of the Operational Plan related to the objective – Issuing diplomas in accordance with the Law and verification of authenticity of public documents, we note that the republic educational inspectors continuously check the authenticity of public documents at the request of the Ministry of Interior, the Police Directorate, the Ministry of Foreign Affairs, public administration authorities, public enterprises and other bodies. Since the beginning of 2022, a total of 490 such requests have been received, which are continuously resolved. During the verification of authenticity of public documents, omissions in the work of institutions or the placing of falsified public documents in legal circulation have been found, in which case criminal charges have been filed by the supervised subject, the requester of the authenticity verification or the acting inspector. In regards to the implementation of Part IV – Standardizing the work of inspections and reducing the susceptibility of inspectors to influence, on the proposal of the Sector for Inspection Affairs, the Sectoral special training programme for educational inspectors for 2022 of the Ministry of Education, Science and Technological Development was adopted, which is intended for the implementation of trainings for city/municipal educational inspectors, as well as for republic educational inspectors until the end of 2022. The sectoral programme includes the following topics: Laws in the field of education – amendments to the law from December 2021; Laws in the field of education – labour relations and delimitation of competences; Laws in the field of education – child/student rights. |  |
| 2.2.10.16. |  | POLICE. Develop mechanisms to strengthen the integrity of the police officers: a) Develop corruption risk analysis for each job position in police; b) Create the conditions for the normative regulation, strengthening the integrity of the police officers (amendments to the procedures and work methodologies); | -Ministry of Interior |  |  | For item а): IV quarter of 2021. For item b): III quarter of 2020. |  |  |  | a) Budget of the Republic of Serbia - 8.642 € b) Budgeted in Chapter 24 | Corruption risk analysis in police conducted. Risk registry developed. Procedures for methodology of work and acting in the Department developed. |  |  |  |  | Activity is partially implemented. Item a) In the reporting period, working groups for the implementation of corruption risk analyses in the organizational units of the MoI continued their activities. Internal Affairs Sector has formed working groups for the implementation of corruption risk analyses in all organizational units of the General Police Directorate, activities of the most working groups are close to an end. Results of the corruption risk analyses will be used as a base for Integrity Plan of the MoI. In the period from April 12 to 14, 2022, in cooperation with OSCE Mission in Serbia and Geneva Centre for Security Sector Governance (DCAF), online training was organised for Internal Affairs Sector’s police officers and members of the working groups for corruption risks analysis in the Ministry of the Interior of the Republic of Serbia, i.e. in 27 Regional Police Directorates, which aim was to continuously follow activities of the working groups as well as to gain additional experience in the area of corruption risk analysis. The experts/lecturers were from the Agency for corruption prevention and the Anti-Corruption General Directorate, Ministry of the Interior, Romania, with whom Internal Affairs Sector and OSCE Mission in Serbia have a long-term, successful cooperation. Item b) All bylaws that were prescribed by the Law on Police were passed in 2018. Also, the Ministry of the Interior adopted the Code of Police Ethics, and on August 24, 2021, the Instruction on Gifts in the Ministry of the Interior. |  |
| 2.2.10.17. |  | Strengthen the capacity of the internal control for the purpose of prevention and suppression of corruption in the police in accordance with the performed analysis and amended normative framework. |  | -Ministry of Interior |  |  | Continuously, until IV quarter of 2021. |  |  |  | Capacity building - Budget of the Republic of Serbia Costs currently unknown. Will be known after the completion of the analysis. | Capacities strengthened – number of employees in Internal control sector increased. |  |  |  |  | Аctivity is being successfully implemented. The number of systematized working positions in the Internal Control Sector was increased by 8 in the reporting period, and now there are 187 working positions. The number of employees in the Sector is 162. |  |
| 2.2.10.18. |  | Continuous training of staff in the Department of internal control and all employees of the Ministry of Interior in relation to the integrity. |  | -Ministry of Interior -Criminalistics Police Academy |  |  | Continuously |  |  |  | IPA 2016 -"European Union support for effective border management” Project | Training courses conducted. Percentage of MoI employees trained on integrity rules in relation to those required/in needs of training. |  |  |  |  | Аctivity is being successfully implemented. In the period from 19 to 21 April 2022, in the organization of the OSCE Mission in Serbia and Geneva Centre for Security Sector Governance (DCAF), the security vetting training for the police officers of the Internal Affairs Sector was held. |  |
| 2.2.10.19. |  | Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in police. |  | -Anti-Corruption Agency -in cooperation with Ministry of Interior and relevant CSOs |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.20.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in police is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.20. |  | Establish the Working Group for drafting Impact assessment in police and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions and CSOs |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in police collected. Working Group collects all relevant data in line with indicators set out in Methodology (2.2.10.19.) and insures assistance to the Agency in the process of conduction of Impact Assessment. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.21. |  | Conduct and present Impact assessment in police. |  | -Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.20.) and donor support. Donor support is needed, for which will be applied in the upcoming period. | Impact assessment in police is drafted and presented to the National Assembly and to the general public. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.10.22. |  | Undertake corrective measures based on Impact assessment findings |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.10.21. | Corrective measures based on Impact assessment findings undertaken. |  |  |  |  |  |  |
| 2.2.10.23. |  | CUSTOMS. Establish the Working group in Ministry of Justice for consideration of Customs Administration initiative (based on Corruption Risk Analysis of the customs system legal framework) for amendments to Criminal Procedure Code, and act in accordance with its conclusions. (link with activity 2.3.7.2.) | -Ministry of Justice -Customs Administration, Ministry of Finance -Government of the Republic of Serbia -National Assembly |  |  | For establishing Working group: I quarter of 2021 For amendments and supplements: by IV quarter of 2022 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working group is established. Amendments and supplements to the law adopted, in line with Working group conclusions. |  |  |  |  | Аctivity is being successfully implemented. By the Decision of the Minister of Justice No. 119-01-126 / 2021-05 of 12 May 2021, a Working Group for the Analysis of Criminal Procedure Code was established in order to identify and eliminate its weaknesses and shortcomings and draft a working text of the Law on Amendments of the Criminal Procedure Code based on the results of the analysis. The Working group meets on regular basis. |  |
| 2.2.10.24. |  | Conduct training of the staff at customs in line with new regulations. |  | -Customs Administration, Ministry of Finance |  |  | Continuously |  |  |  | Budget of the Republic of Serbia 24.000 € in 2020 - 8.000 € in 2021 - 8.000 € in 2022 - 8.000 € | Training conducted. Percentage of Customs staff trained in relation to those required/in needs of training. |  |  |  |  | Activity is not implemented. The activity is closely related to the amendment of the Criminal Procedure Code (activity 2.2.10.23). The amendment of the Code falls within the competence of the Ministry of Justice and since it has not been amended yet, it was not possible to implement activity 2.2.10.24. |  |
| 2.2.10.25. |  | Strengthen capacities of the Department of Internal Control through purchasing adequate accompanying equipment, IT equipment, uniforms and staff recruitment of 15 people. |  | -Customs Administration, Ministry of Finance |  |  | Continuously |  |  |  | Budgeted in Chapter 29 | Capacities strengthened (adequate accompanying equipment, IT equipment, uniforms and other). Increased number by 13 systematized jobs in 2021. |  |  |  |  | Activity is partially implemented. There were no recruitments of new employees within the Department of Internal Control in the first quarter of 2022. The Customs Administration has amended the Regulation number: 110-00-307/3/2021-08 of 21 June 2021 through which it has classified one more position within the Department of Internal Control, so now the total number of classified positions is 18. |  |
| 2.2.10.26. |  | Install video surveillance in customs offices and border crossings with centralised recorder of Signal in the Customs Administration and the ability of the Customs Administration to access video surveillance in each object in the real time. |  | -Customs Administration, Ministry of Finance |  |  | IV quarter of 2021. |  |  |  | Budgeted in Chapter 24 | Video surveillance installed. |  |  |  |  | Activity is not implemented. There were no activities in reporting period. The Customs Administration makes efforts to obtain funds for implementing this activity through the new strategy of Integrated Border Management for the period 2022 - 2027, with the supporting Action Plan for the period 2022 - 2024. The section Interagency Cooperation of the Action Plan stipulates the measure of installing video surveillance in all border crossings points, with the supporting activities for its realization. |  |
| 2.2.10.27. |  | Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in customs. |  | -Anti-Corruption Agency -in cooperation with -Customs Administration, Ministry of Finance |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.28.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in customs is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.28. |  | Establish the Working Group for drafting Impact assessment in customs and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in customs collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.29. |  | Conduct and present Impact assessment in customs. |  | Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.28.) and donor support 21.000,00 € Donor support is needed, for which will be applied in the upcoming period. | Impact assessment in customs is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. |  |
| 2.2.10.30. |  | Undertake corrective measures based on Impact assessment findings |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Impact assessment – activity 2.2.10.29. | Corrective measures based on Impact assessment findings undertaken. |  |  |  |  |  |  |
| 2.2.10.31. |  | LOCAL ADMINISTRATION. Assemblies of the autonomous provinces and local self-governments adopt local action plans and form a permanent working body for monitoring of implementation of local action plans. | For adoption: -Assemblies of autonomous provinces and local self-governments For reporting: -Anti-Corruption Agency, based on data collected from autonomous provinces and local self-governments |  |  | For adoption: IV quarter of 2020 For reporting: continuously, until the implementation of the obligations of local self- governments and autonomous provinces |  |  |  | Budget of the Republic of Serbia Activity requires insignificant costs. Donor support (including USAID GAI Project) If additional funds are needed, it will be applied for donor support. | Local action plans developed. Formed working body for monitoring of implementation of local action plans. Assemblies of local self-governments and territorial autonomy units have adopted their local anti-corruption plans and established bodies to monitor their implementation in accordance with the Anti-Corruption Agency model of local action plan. |  |  |  |  | Activity is being succssesfully implemented. Since the beginning of April 2017, when the APC published the Local Anti-Corruption Plan Model (LAP Model), until March 15, 2022, in total 109 local self-government units (LSU) adopted the local anti-corruption plans (LAP), i.e. 75% of 145 LSU that are subject to this obligation (without the territory of the Kosovo and Metohija). The APC was informed by 30 LSU that they had not developed the LAP, and six of them did not submit data on development of the LAP and the establishment of a body for its monitoring. Out of 109 plans submitted to the APC by LSU, 92 were drafted in line with the LAP Model, 12 were partly drafted in line with the Model, four adopted LAP do not correspond to the Model in both form and substance, whereas one LSU did not submit sufficient data as to assess whether LAP was drafted in line with the Model. The reasons for the partial compliance of individual LAP are reflected in the fact that during the process of plan drafting in some working groups for LAP drafting there were no civil society representatives, in some reports on LAP adoption, LSU did not properly explain why the certain measures had not been taken from the Model, activities were not properly defined, etc. Total of 37 LSU established the body in charge of monitoring of LAP implementation, out of which 24 were mainly established in line with the Model, one was partly in line with the Model, seven bodies were established with significant deviations in terms of the Model, whereas there are no sufficient data for five bodies as to assess the respective compliance. During the process of establishing bodies in charge of monitoring LAP implementation, i.e. selection of members of bodies, in certain commissions there were no civil society representatives, some LSU had to repeat a public competition for selection of members of bodies, due to insufficient number of applications submitted and certain municipalities established a temporary body, in line with the supplemented LAP Model after two public competitions at which there were no submitted candidatures. In the first quarter of 2022 two municipalities-Gadzin Han and Zabari submitted draft LAP to the APC as to obtain APC’s opinion, comments, suggestions, and corrections of the proposed solutions in LAP prior to organizing public debate. The APC drafted the opinions and submitted them to these municipalities out of which the Municipality Gadzin Han adopted LAP in the meantime and the Municipality Zabari plans to do so in the upcoming period, i.e., during the next session of the Assembly. During the first reporting period in 2022, 27 LSU submitted information on the adoption of the LAP and the establishment of a body in charge of its implementation monitoring. Out of this number, two municipalities-Gadzin Han and Pecinci reported that they adopted LAP (first at the beginning of 2022, the second in mid-2021) whereas the remaining 25 LSU notified the APC that there had been no changes in relation to the previous reporting period. At the end of the second quarter of 2022, 23 LSU adopted the LAP and established a body to monitor its implementation mainly in accordance with the APC Model. |  |
| 2.2.10.32. |  | Develop Methodology for drafting the Impact assessment of measures undertaken to reduce corruption in local self-governments. |  | -Anti-Corruption Agency |  |  | IV quarter of 2020 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.33.) and donor support. If additional funds are needed, it will be applied for donor support. | Methodology for Impact assessment of measures undertaken to reduce corruption in in local self-governments is developed and based on clear criteria. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.33. |  | Establish the Working Group for drafting Impact assessment in local self-governments and collect all relevant data. |  | -Anti-Corruption Agency -in cooperation with all relevant institutions |  |  | II quarter of 2021 |  |  |  | Budget of the Republic of Serbia 30.878 € | Working Group is established and operational. All relevant data for drafting Impact assessment in local self-governments collected. |  |  |  |  | Activity is fully implemented. Situation has not been changed since the last reporting period, the activity was previously implemented. |  |
| 2.2.10.34. |  | Conduct and present Impact assessment in local self-governments. |  | -Anti-Corruption Agency |  |  | II quarter of 2022 |  |  |  | Budget of the Republic of Serbia (budgeted in 2.2.10.33.) and donor support 21.000,00 € Donor support is needed, for which will be applied in the upcoming period. | Impact assessment in local self-governments is drafted and presented to the National Assembly. |  |  |  |  | Activity is fully implemented. The APC finalized the Report on impact assessment for eight vulnerable areas which was sent to the National Assembly. |  |
| 2.2.10.35. |  | Undertake corrective measures based on Impact assessment findings. |  | -all relevant institutions, based on impact assessment findings |  |  | II quarter of 2023 |  |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of the Impact assessment – activity 2.2.10.34. | Corrective measures based on Impact assessment findings undertaken. |  |  |  |  |  |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  | OVERALL RESULT |  |  |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.2.11. Ensure that civil society is involved in the anticorruption agenda |  |  |  | Civil society is involved in the anticorruption agenda. |  |  |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Annual report of the Office for Cooperation with Civil Society; - Number of measures against corruption which are carried out in partnership between CSOs and state authorities; - Number of joint programs/activities implemented; - Decrease of perceived level of corruption within the society. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/DEADLINE |  |  | FINANCIAL RESOURCES |  | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.2.11.1. | Conduct joint activities to encourage and increase the participation of citizens in the fight against corruption. |  |  | -Office for Cooperation with Civil Society |  |  | Continuously. |  |  |  | Budget of the Republic of Serbia and donor support Donor support is needed, for which will be applied in the upcoming period. | Joint activities periodically organized. |  |  |  |  | Activity is being succssesfully implemented. During Q1 2022, the Ministry of Human and Minority Rights and Social Dialogue, in cooperation with the Ministry of Justice, published a public call to civil society organizations to nominate members to the Working Group tasked with the drafting of the National Anti-Corruption Strategy for 2023-2028 and the Action Plan for the implementation of the National Anti-Corruption Strategy for the period 2023-2028. Two organizations were selected under this public call. However, bearing in mind that the organizations whose applications were rejected are organizations with long-time experience which have participated in numerous reform processes and processes of drafting regulations and public policy documents, as well as taking into account that the Action Plan for Chapter 23 promotes inclusion of civil society organizations in all phases of planning documents drafting, the Commission made a motion to examine the possibility of including all 5 organizations that submitted applications for nominating members to the Working Group tasked with the drafting of the National Anti-Corruption Strategy for the period 2023-2028 and the Action Plan for the implementation of the National Anti-Corruption Strategy for the period 2023-2028. |  |
| 2.2.11.2. | Further improvement of civil society organisations transparent funding system through: -monitoring of the implementation of the Regulation on Funds for Programme Promotion or the Lacking Funds for Programmes in Public Interest Implemented by Associations -capacity building for public administration employees. |  |  | -Office for Cooperation with Civil Society |  |  | Continuously |  |  |  | Budget of the Republic of Serbia and donor support Costs currently unknown. Will be known will after development of the training plan of the National Academy of Public Administration. Donor support is needed, for which will be applied in the upcoming period. | Annual summary report on spending of funds planned and disbursed to associations and other civil society organisations from the budget of the Republic of Serbia consists relevant information on the implementation of the Regulation. Number of seminars for public administration employees held in relation to planned trainings on CSOs transparent funding system. |  |  |  |  | Activity is being successfully implemented. In the reporting period, the monitoring of the implementation of 20 programs of citizens' associations supported within the Public Competition "Implementation of Anti-Discrimination Policies in the Republic of Serbia for 2021" continued. The exhibition of photographs "Beauty of Aging", delivered by the citizens' association Strength of Friendship "Amity" within its project in Belgrade, Aleksinac and Arandjelovac, attracted a lot of public attention. Due to the great interest of the public, the project was revised to encompass a larger number of cities and municipalities that were given the opportunity to see the exhibition. As part of its project, the IDEAS Center for Research and Social Development organized a conference on the future of social and economic rights with a focus on the role of the business sector in the inclusion process. The three-day conference was attended by more than 40 panelists and 120 different stakeholders, and the intensive dialogue set the tone for work priorities. Priorities include continued activities on the development of the national human rights strategy and accompanying action plan, more direct involvement of the private sector in the development of human rights policy. The results of companies’ contributions at the conference will be harmonized and systematized in a document providing a platform for businesses consolidation, i.e. coalition association, for organized action aimed at supporting exercise of human rights by social groups at increased risk of discrimination. During the reporting period the activities related to the upgrade of the Calendar of Open Calls for projects took place, aiming to provide easy accessibility of data on the upcoming Open Calls, targeted areas for project implementation, potential applicants and the implementation period. The Database would also contain data on all Open calls for projects that have been completed, projects approved for implementation as part of the Open Call procedure and the amounts granted to recipients. |  |
| 2.2.11.3. | Implement public calls for allocation of funds to the CSOs for projects in the field of anti-corruption for the initiatives at national and local level, as well as for media initiatives in the field of fight against corruption. |  |  | -Anti-Corruption Agency |  |  | Continuously. |  |  |  | Budget of the Republic of Serbia 209.352 € in 2020 - 69.784 € in 2021 - 69.784 € in 2022 - 69.784 € | The civil sector is involved in the fight against corruption on the basis of conducted competitions for grants to civil society organisations for projects in this area. |  |  |  |  | Аctivity is being successfully implemented. The APC organized public competition for allocation of funds to civil society organizations for projects focused on corruption prevention on February 25, 2022. The APC successfully finalized another public competition for allocation of funds to civil society organizations for projects focused on corruption prevention. Contracts were concluded for four projects with the following civil society organizations: Transparency Serbia, Center for Integrity Niš, Užice Center for Human Rights and Democracy and Bečej Youth Association. The implementation of the projects started on June 1. |  |
| 2.3. REPRESSION OF CORRUPTION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.3.1. Serbia revises its Criminal Code and provides an effective solution for dealing with economic crime cases and in particular the criminal offense of "abuse of position of a responsible person". |  |  |  |  |  |  |  | Section of the Criminal Code regulating the chapter on criminal offenses against the economy is aligned with the EU standards, especially with regard to the criminal offense of abuse of office. |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Positive GRECO assessment; - Number of prosecuted persons for criminal offences against the economy. |  |  |  |  |  |  |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  |  |  |  | TIMEFRAME/DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.1.1. | Monitor the implementation of the amended Criminal Code - corruption and economic criminal offenses, with the obligation of the police, public prosecutors and courts to submit annual statistical reports on initiated and concluded proceedings to the Ministry of Justice. Ministry of Justice prepares a single annual report and publishes it on the website. |  | -Ministry of Interior -Republic Public Prosecutors’ Office -Supreme Court of Cassation -Ministry of Justice (state secretary in charge of anti- corruption) |  |  |  |  | Continuously |  |  | Budget of the Republic of Serbia - 3.192 € in 2020 - 1.064 € in 2021 - 1.064 € in 2022 - 1.064 € | Annual report published. |  |  |  |  | Аctivity is being successfully implemented. The report for 2021 was prepared in June 2022 and published on the official website of the Ministry of Justice: https://www.mpravde.gov.rs/tekst/33769/statistika-koruptivnih-krivicnih-dela-.php . Special Departments for the Suppression of Corruption and the Prosecution Office for Organized Crime submitted to the Republic Public Prosecution Office annual reports on the initiated and completed proceedings in connection with corruption and economic criminal acts. Based on aforementioned reports, the Republic Public Prosecution Office developed Annual report on work of Public Prosecutions on crime prevention and the protection of constitutionality and legality for 2021. The Annual report includes an analysis of corruption and economic crime, report on the work of the Anti-Corruption Department of the Republic Public Prosecutor's Office, as well as a statistical report - a table overview of the work of the Special Departments for the Suppression of Corruption and the Prosecution Office for Organized Crime in corruption cases and criminal cases against economy and official duty. Data collected by the Sector for Analytics, Telecommunication and Information Technologies of the Ministry of the Interior, regarding the number of criminal offenses under certain articles of the law in the period January - June 2022 is are available in the quarter reports. |  |
| 2.3.1.2. | Conduct training of judges and prosecutors to implement Criminal Code. |  | -Judicial Academy |  |  |  |  | Continuously |  |  | Budget of the Republic of Serbia and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) Budgeted in 1.3.1.1. | Training conducted. Number of seminars held in relation to planned trainings on CC implementation. |  |  |  |  | Аctivity is being successfully implemented. No new information in the reporting period. |  |
| 2.3.1.3. | Monitor the implementation of the amended criminal offense "abuse of position of a responsible person“that contains the mechanism of "legal subsidiarity“, valid from 1 March 2018. Monitoring is related to criminal events occured after March 1, 2018. |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Republic Public Prosecutors’ Office |  |  |  |  | Continuously |  |  | Budget of the Republic of Serbia - 639 € in 2020 - 213 € in 2021 - 213 € in 2022 - 213 € | Annual reports published. |  |  |  |  | Аctivity is being successfully implemented. The report for 2021 was prepared in June 2022 and published on the official website of the Ministry of Justice: https://www.mpravde.gov.rs/tekst/33769/statistika-koruptivnih-krivicnih-dela-.php Special Departments for the Suppression of Corruption and the Prosecution Office for Organized Crime submit to the Republic Public Prosecution Office quarterly reports on proceedings in cases for criminal act Abuse of position of responsible person under Article 227 of CC. Based on aforementioned reports, the Republic Public Prosecution Office monitors the activities in cases related to criminal events occured after March 1, 2018. |  |
| INTERIM BENCHMARK |  |  |  |  |  |  |  | OVERALL RESULT |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.3.2. Serbia makes an analysis of its organisational structures and bodies prior to amending the Law on Organisation and Jurisdiction of State Authorities in the fight against organised crime, corruption and other particularly serious criminal offences. Serbia pays particular attention to capacity building in the prosecution service and the police and ensures the necessary financial and human resources and training. It substantially improves inter-agency co-operation and intelligence exchange in a safe and secure manner. |  |  |  |  |  |  |  | Independent, effective and specialised investigation/prosecution is fully insured, and in particular through: - Proposing and implementing measures to strengthen the independence of the investigative and judicial authorities working on the investigation of corruption in order to effectively protect them from undue political pressure, -Providing adequate resources (including budget, staff, specialised training) to all investigative and judicial authorities involved in the fight against corruption, -Improvement of cooperation and exchange of information between the authorities involved in the fight against corruption, including the tax authorities and other indirectly linked bodies, through a better interconnection of databases and the establishment of a secure platform for communication, -Fully implementing recommendations of the FATF and strengthening capacity to conduct complex financial investigations in parallel with criminal investigations, as well as the strengthening of the special units of the Ministry of Interior and the provision of adequate training. |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings for criminal offences of corruption; - Following the systematic use of financial investigations, there is a gradual increase in the number and value of seized criminal assets. - Positive expert opinion following the analysis of reasons for concluding corruption cases at the stage of investigation, prosecution and adjudication. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.2.1. | Conduct analysis of compatibility of Republic of Serbia normative framework with FATF recommendations for conducting financial investigations parallel with criminal investigations. Develop planning document in the field of fight against financial crime, based on analysis findings. (link with AP for Chapter 24, activity 6.2.5.4.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Republic Public Prosecutors’ Office -Prosecutors’ Office for Organized Crime -Ministry of Interior -Administration for the Prevention of Money Laundering |  |  | For analysis:IV quarter of 2020 For planning document: IV quarter of 2021 |  | Budget of the Republic of Serbia 30.878 €, and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Analysis of compatibility of Republic of Serbia normative framework with relevant FATF recommendations conducted. Planning document in the field of fight against financial crime developed. |  |  |  |  | Activity is partially implemented. The formation of a multi-departmental working group that will analyze the legal framework in the field of property restitution and harmonization with the acquis communautaire in this area has been postponed to the third quarter of 2022. We note that the analysis of the harmonization of Serbian legislation with the acquis communautaire in the field of confiscation of property has been finalized, by experts hired by the Council of Europe through the project of the Embassy of the Kingdom of Sweden. The analysis will serve as a starting point for the work of the aforementioned multi-departmental working group. The legislation of the Republic of Serbia has been harmonized with 40 FATF recommendations to the extent possible. |  |
| 2.3.2.2. | Strengthening the capacity of the Unit for financial investigation of the Ministry of Interior RS, based on the results of the analysis performed. Conduct trainings for Ministry of Interior Unit for financial investigation employees. (link with Chapter 24, activity 6.2.5.3.) |  |  |  |  | -Ministry of Interior |  |  | Commencing from II quarter of 2016, onwards. |  | Budgeted in Chapter 24 | The number of employees in the Financial Investigation Unit increased - from 57 to 63 police officers. Trainings conducted. Percentage of Unit for financial investigation employees trained in relation to those required/in needs of training. |  |  |  |  | Activity is being successfully implemented. There are no realized receptions for a definite and indefinite period of time in the Unit for Financial Investigations of the Ministry of the Interior, and there are no announced internal and public vacancies in the Financial Investigation Unit.The number of systematized jobs in relation to the previous reporting period is unchanged and amounts to 64 and the number of employees is 63. Police officers of the Financial Investigation Unit attended the following seminars in the reporting period: - Webinar on "Seizure of Digital Assets" - Seminar on "Value Added Tax Evasion" organized by the OSCE Mission to Serbia - UNDOC organized training on "Financial Investigations and Restitution of Property for Trafficking in Human Beings, including Compensation to Victims in Southeast Europe" - OSCE Mission to Serbia organized three seminars on "Cryptocurrencies" |  |
| 2.3.2.3. | Conduct professional training of employees focusing on a mechanism of information exchange at the international level in accordance with the Framework Decision 2006/960/PUP for the purpose of effective seizure, confiscation and asset management. |  |  |  |  | -Judicial Academy -Ministry of Interior |  |  | IV quarter of 2021, onwards. |  | Budget of the Republic of Serbia - 4.800 € in 2021 - 2.400 € in 2022 - 2.400 € | Training conducted Percentage of employees trained on a mechanism of information exchange at the international level in relation to those required/in needs of training.. |  |  |  |  | Activity is being successfully implemented. Police officers of the Financial Investigation Unit attended the workshop on "Confiscation of Digital Assets", organized by the OSCE. During the reporting period, in February, a one-day Presentation of the Manual for Confiscation of proceeds of crime was realized, with the support of the US Embassy and the OSCE Mission to Serbia, for 20 participants. Also, in the reporting period, one online seminar was held on the topic ‘’Standards and practice of confiscation of proceeds of crime’’ in cooperation with the AIRE Center and the RAI Secretariat, with the support of the UK Government, for 56 participants, beneficiaries of the initial training of the Judicial Academy. In the second quarter of 2022, one online seminar was held on the topic ‘’Confiscation of proceeds of crime’’ in cooperation with the AIRE Center and the RAI Secretariat, for 40 participants, from the ranks of judges, prosecutors and beneficiaries of Judicial Academies from the region. |  |
| 2.3.2.4. | Continuous training of police, prosecutors and judges for conducting financial investigations, monitoring cash flows, proactive approach and special investigative techniques (link with Chapter 24 activity 6.2.5.2.) |  |  |  |  | -Judicial Academy -Ministry of the Interior - Criminal Police Directorate |  |  | Continuously |  | IPA 2013-Project of prevention and fight against corruption, Service contract-3.600.000 € IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Training conducted. Percentage of police officers, public prosecutors and judges trained on financial investigations, monitoring cash flows, proactive approach and special investigative techniques, in relation to those required/in needs of training. |  |  |  |  | Аctivity is being successfully implemented. The situation has not been changed since the last reporting period. |  |
| 2.3.2.5. | Provide mutual database connectivity for criminal investigation and a safe system of electronic information exchange between public prosecutor's offices, the police, the Customs Department, Tax Administration, AntiCorruption Agency and other relevant bodies that have databases of importance to combating corruption. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Ministry of Interior - State Prosecutorial Council -Republic Public Prosecutors’ Office -Anti-Corruption Agency |  |  | I quarter of 2022. |  | IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Database connectivity established. |  |  |  |  | Аctivity is partially implemented. Representative of the Republic Public Prosecution Office, member of the Intergovernmental and state authorities Working Group for Legal and Organizational Issues related to the implementation of the NCIS participated in the workshop on implementation of NCIS in November 2021. Furthermore, the Republic Public Prosecution Office defined the type and scope of data that will be shared with other state authorities that will have access to the NCIS. Also, Graphic User Interface of the Intelligence System was defined in line with the users` needs. During May 2022 a threeday workshop was held in Šabac where members of the group dealing with IT/technical issues and the group dealing with legal issues jointly worked on the Draft Law on NCIS. |  |
| 2.3.2.6. | Adopt the by-law from the Article 16, Paragraph 4, of the the Law on Organisation and Competence of State Authorities in Suppression of Organised Crime, Terrorism and Corruption, which will regulate the deadlines, the manner of conduct and the manner of official communication between the police and the public prosecutor's office, in organized crime cases and corruption. (link with AP for CH 24 activity 6.2.2.1.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Ministry of Interior -Republic Public Prosecutors’ Office -Prosecutors’ Office for Organized Crime |  |  | IVquarter of 2021 |  | Budget of the Republic of Serbia - 2.553 € in 2020 - 851 € in 2021 - 851 € in 2022 - 851 € | The by-law adopted. |  |  |  |  | Аctivity is partially implemented. Representatives of the Ministry of Justice and the Republic Public Prosecutor's Office are working on the finalization of the by-law and its adoption is expected in the third quarter of 2022. |  |
| 2.3.2.7. | Strengthtening the capacity of the Prosecutors’ Office for Organized Crime and the Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption, through training courses on implementation of the new mechanism prescribed by the Law on Organisation and Competence of State Authorities in Suppression of Organised Crime, Terrorism and Corruption (liaison officers, task forces, financial forensic service). (link with AP for CH 24 activity 6.2.2.3.) |  |  |  |  | Judicial Academy --Prosecutors’ Office for Organized Crime - Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption |  |  | Continuously |  | IPA 2013 „Prevention and Fight Against Corruption“ project “- 3.600.000 € | Training courses delivered. Percentage of employees trained in relation to those required/in needs of training. |  |  |  |  | Аctivity is being successfully implemented. Representatives of the Prosecutor's Office for Organized Crime (POOC) participated in a number of educational activities such as: - CEPOL webinar “Raising awareness on EMPACT“; - Seminar on ballistic evidence; - Webinar: Presentation of reports on illegal financial flows in the region; - On-line seminar on investigations of misuse of virtual property for the purpose of money laundering; - Online case studies of terrorism prosecution from the USA; - Regional Workshop on Exchange of Best Practices and Experiences in Preventing, Detecting and Prosecuting Crime, Smuggling of Migrants and Trafficking in Human Beings in the Western Balkans; - Training for reporting on AP for PG 23; - Human Resources Software Development Workshop; - As a trainer in the training on proactive investigation of fraud related to value added tax (VAT); - As a lecturer at the training for judges and judicial assistants of the special departments for the suppression of corruption of the Higher Courts in the field of public procurement "Effective public procurement in the service of economic growth"; - Preparatory Training for Certified Fraud Examiners (CFE) -Presenter at the round table on the topic: "Misuse of European Union funds"; - Regional Kick-Off Conference and Coordination Meeting of Regional Actors - Task Force on Combating Smuggling of Migrants and Trafficking Coordinators -Training in the use of antivirus protection; - Webinar: "Offshore Investment Mapping and Analysis"; -Symposium on organized crime, drug trafficking and money laundering; - Online workshops on combating smuggling and trafficking in human beings; - Forum of Law Enforcement Bodies in the Fight against Terrorism; -Workshops "Implementation of the National Criminal Intelligence System (NCIS)"; - As a lecturer at the training for deputy public prosecutors and assistant prosecutors on the topic: "Writing indicting acts" -Counseling in the field of criminal law -Seminar: "Evidence from social media - how to collect, analyze and present it in court" -Presenter at the round table on the topic: "Misuse of European Union funds"; - Presenters on the topic: "Assessment of the risk of money laundering and terrorist financing and the financing of the proliferation of weapons of mass destruction, Risk assessment in the digital property sector - harmonization of internal acts, state risk assessment and the actions of taxpayers"; -Presenters in the panel "Seizure of assets derived from criminal acts - examples of good practice and the importance of regional cooperation"; -Participant in preparatory training for certified fraud investigators (CFE); -Participant in the seminar: "Evidence from social media - how to collect, analyze and present it in court"; -Webinar participant: "Analysis of the drug market in the EU: cocaine"; -Participants in the joint training of Task forces - simulation exercises and -Participants of the round table on the project "Building forensic accounting capacities in Serbia". Pursuant to the new Law on the Organization and Jurisdiction of Government Authorities in Suppression of Organized Crime, Terrorism and Corruption it was envisaged that the Prosecutor for Organized Crime is the coordinator of the work of Special Departments of the Higher Public Prosecutor's Offices for combating corruption. Given the limitations due to the Covid-19 pandemic, the Prosecutor for Organized Crime and the Deputy Prosecutor, assigned by the Annual Working Plan to coordinate the work of special anti-corruption departments was in daily phone/email communication with the heads of special departments and with each of them met individually. During the reporting period, in March, 1 three-day workshop was conducted on the subject: ‘’Proactive investigation of corruption cases, financial fraud and economic crime cases: Fraud on added tax value (Module 3),’’ with the support of the United States Department of Justice (OPDAT) and OSCE, for a total of 24 participants. During first quarter of 2022, 10 two-day seminars of the international certification program in the field of fraud research and money laundering prevention (CFE and CAMS programs) was held. The seminar was attended by 131 participants from the ranks of basic and senior public prosecutors and their deputies, judicial and prosecutorial assistants and associates, police officers. During second quarter of 2022, 1 three-day workshop was conducted in Vršac on the subject: ‘’Proactive investigation of corruption cases, financial fraud and economic crime cases: Fraud on added tax value (Module 3),’’ with the support of the United States Department of Justice (OPDAT) and OSCE, for a total of 21 participants. In June 2022, Judicial Academy, with the support of the Council of Europe and the Swedish International Development Cooperation Agency, held a one-day seminar on the topic: “Prevention of money laundering and financing of terrorism in Serbia”, in Belgrade, for a total of 25 participants. During the reporting period, 13 two-day seminars of the international certification program in the field of fraud research and money laundering prevention (CFE and CAMS programs) were held. The seminars were attended by 188 participants from the ranks of basic and senior public prosecutors and their deputies, judicial and prosecutorial assistants and associates, police officers. In the II quarter of 2022, Judicial Academy in cooperation with the German Corporation for International Cooperation (GIZ), organized four one-day round tables on the topic: “Misuse of European Union funds”, for a total of 98 participants (judges, prosecutors, police officers, officials of the Ministry of Finance.) |  |
| 2.3.2.8. | Signing the Memorandum on cooperation between authorities responsible for implementation of the Law on Organisation and Competence of State Authorities in Suppression of Organised Crime, Terrorism and Corruption. |  |  |  |  | -Republic Public Prosecutors’ Office -Ministry of Interior -authorities enumerated in the Article 20 of the Law |  |  | I quarter of 2021 |  | Budget of the Republic of Serbia Budgeted in 2.3.2.6. | Memorandum on cooperation signed. |  |  |  |  | Activity is fully implemented. An Agreement on Cooperation was signed with the Tax Administration - Tax Police and the Republic Pension and Disability Insurance Fund. The final version of the agreement with the Customs Administration has been harmonized and their signing is in progress. |  |
| 2.3.2.9. | Developing the Methodology of the establishment and performance of the task forces. (link with AP for CH 24 activity 6.2.2.5.) |  |  |  |  | -Republic Public Prosecutors’ Office --Prosecutors’ Office for Organized Crime -Ministry of Interior -Ministry of Justice (state secretary in charge of anti- corruption) |  |  | I quarter of 2021 |  | Budget of the Republic of Serbia – 30.878 € | The Handbook on Methodology of the establishment and performance of the task forces developed and published. |  |  |  |  | Activity is partially implemented. The methodology on work and formation of working groups was adopted on November 9, 2021. The document was printed and forwarded to the competent state prosecutor's offices. |  |
| 2.3.2.10. | Strengthening the capacity of the Financial Forensics Service in the Prosecutors’ Office for Organized Crime and other bodies. (link with AP for CH 24 activity 6.2.2.6.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Republic Public Prosecutors’ Office --Prosecutors’ Office for Organized Crime |  |  | IV quarter of 2020, onwards |  | Budget of the Republic of Serbia – 122.544 € in 2021 -61.272 € in 2022 -61.272 € | The team of economic forensic experts in the Prosecutors’ Office for Organized Crime established. Training courses of the economic forensic experts delivered. Number of seminars held in relation to planned trainings. |  |  |  |  | Activity is being successfully implemented. During the 1st quarter of 2022, the financial forensic scientist participated in the following educational activities: - Webinar on presentation of the Report on illegal financial flows in the region held on January 26, 2022, organized the regional GIZ -Webinar on Investigation of misuse of virtual property for the purpose of money laundering, held on February 9, 2022, organized by the Council of Europe as a lecturer, in the following trainings: - at workshops on VAT fraud held in the period from 16 to 18 March 2022, organized by OPDAT - Training on Effective Public Procurement in the Service of Economic Growth, held on March 22, 2022, organized by NALED and the Swedish International Development Cooperation Agency (SIDA). The Financial Forensics Service has been operating in the Prosecutor's Office for Organized Crime since May 1, 2022, when the second vacant position of financial forensic scientist was filled. In the reporting period, financial forensic scientists participated, as lecturers or participants, in the following educational activities: -Webinar: Presentation of reports on illegal financial flows in the region; -On-line seminar on investigations of misuse of virtual assets for the purpose of money laundering; -As a trainer in training on proactive investigation of fraud related to value added tax (VAT); -As a lecturer at the training for judges and assistant judges of the Special Anti-Corruption Departments of the Higher Courts in the field of public procurement "Effective public procurement in the service of economic growth"; -As a lecturer on the topic of Risk Assessment of Money Laundering, Terrorist Financing and Proliferation: State Risk Assessment and Conduct of Obligors - Harmonization of Internal Acts -Training of trainers and preparation of training on money laundering -Workshop NRA Toolkit: New tools for specific risks Positions of financial forensic experts in the Special Departments for the Suppression of Corruption in the Higher Public Prosecution Office in Belgrade, Nis, Kraljevo and Novi Sad are still vacant. The main reason is the insufficient number of certified financial forensics and their lack of interest in working in public prosecution offices. Activities to fill the vacancies of financial forensic experts will continue until they are hired. In order to overcome this problem, the Republic Public Prosecution's Office with the Faculty of Economics, University of Belgrade, US Department of Justice and Ministry of Foreign Affairs - INL participates in the project "Strengthening the capacity of forensic accounting" which aims to launch one-year academic studies at the Faculty of Economics in Belgrade, which would educate staff - financial forensic experts needed to work in the competent public prosecution's offices. It is planned that the first generation of students will be enrolled in the school year 2022/23 in a capacity of about 40 students, whose education will be funded by the INL. After that, the program would continue on commercial basis. |  |
| 2.3.2.11. | Adopt the new Rulebook on sistematization of workplaces in the POOC and in Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption, in accordance with conducted needs assesment of the HR capacities in the Prosecutors’ Office for Organized Crime and Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption (link with AP for CH 24 activity 6.2.2.7.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) --Prosecutors’ Office for Organized Crime -Republic Public Prosecutors’ Office -Higher Public Prosecutors’ Offices in Belgrade, Novi Sad, Nis and Kraljevo -State Prosecutorial Council |  |  | IV quarter of 2020 |  | Budget of the Republic of Serbia Activity requiring insignificant costs. and IPA 2013 „Prevention and Fight Against Corruption“ project - 3.600.000 €. Funds within IPA 2013 were provided for this activity. | The needs assesment for the expansion of HRcapacities conducted. Amendments of the Rulebook on sistematization of workplaces in the Prosecutors’ Office for Organized Crime and in Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption adopted. |  |  |  |  | Activity is partially implemented. Amendments to the rulebook on the systematization of workplaces in the Prosecutors’ Office for Organized Crime and the Higher Public Prosecutor's Office in Belgrade were made during 2021. In the second quarter of 2022, the Ministry of Finance approved the proposed amendments and additions to the Rulebook on the systematization of the Higher Public Prosecutor's Office in Niš and the Higher Public Prosecutor's Office in Kraljevo. Adoption of the aforementioned regulations is in progress. The Higher public prosecutor's offices in Kraljevo and Niš have submitted to the Ministry of Justice for approval the draft personnel plan for the year 2022, after which they will proceed with the amendments to the Rulebook on internal organization and systematization. |  |
| 2.3.2.12. | Filling vacancies in accordance with the Rulebook on sistematization of the workplaces in the Prosecutors’ Office for Organized Crime and in Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption. (link with AP for CH 24 activity 6.2.2.8.) |  |  |  |  | -Prosecutors’ Office for Organized Crime -State Prosecutorial Council -Republic Public Prosecutors’ Office -Ministry of Justice (state secretary in charge of anti- corruption) |  |  | IV quarter of 2021 |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of Rulebook – activity 2.3.2.11. | The Administrative capacities of the Prosecutors’ Office for Organized Crime and Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption filled in accordance with the Rulebook on sistematization of the workplaces. |  |  |  |  | Activity is partially implemented. In the reporting period, there was an increase in administrative capacity in the Prosecutor's Office for Organized Crime - one deputy prosecutor began working,. In the reporting period, there was an increase in administrative capacity in the Prosecutor's Office for Organized Crime - one financial forensic expert started working, while preparatory activities are being undertaken to fill the remaining free vacancies. In this regard, it should be borne in mind that the current accommodation capacity of POOC is not sufficient to fill all planned jobs. This will be fully realized only after the construction of a new building that will house the Prosecutor's Office for Organized Crime in accordance with activity 6.2.2.14 of the Action Plan for Chapter 24. Activities on filling vacancies in the Special Departments for the Suppression of Corruption continued. Five deputy public prosecutors, as well as three associates and two administrative employees, were seconded to the Special Department for Suppression of Corruption in Novi Sad. Another deputy public prosecutor was seconded to the Special Department for Suppression of Corruption in Belgrade. Pursuant to Article 63, paragraph 1 of the Law on Public Prosecutor's Office, it is prescribed that at the proposal of the public prosecutor of special jurisdiction, the deputy public prosecutor may, with written consent, be sent to the public prosecutor's office of special jurisdiction, and paragraph 5 that the decision on referral is made by the Republic Public Prosecutors In 2022 5 deputy public prosecustors were sent to POOC. The number of seconded deputy public prosecutors in the Prosecutor's Office for Organized Crime is 10. |  |
| 2.3.2.13. | Conduct needs analysis of techical capacities in the Prosecutors’ Office for Organized Crime and Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption (link with AP for CH 24 activity 6.2.2.9.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) --Prosecutors’ Office for Organized Crime |  |  | IV quarter of 2020 |  | Budget of the Republic of Serbia 8.642 € | Needs analysis of techical capacities conducted. |  |  |  |  | Activity is fully implemented. An analysis has been done. Based on the analysis, the technical specification of the equipment was written and the public procurement JN 26/2021 was announced. |  |
| 2.3.2.14. | Procurement of the techical equipment for the Prosecutors’ Office for Organized Crime and Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption, in accordance with the results of the needs analysis. (link with AP for CH 24 activity 6.2.2.10.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) --Prosecutors’ Office for Organized Crime |  |  | IV quarter of 2021 |  | Budget of the Republic of Serbia Costs currently unknown. Will be known after completion of activity 2.3.2.13. and donor support – 500.000 € | Techical equipment for the Prosecutors’ Office for Organized Crime and Special Departments of Higher Public Prosecutor’s Offices for Suppression of Corruption purchased. |  |  |  |  | Activity is fully implemented. After the successfully conducted public procurement procedure, the Ministry of Justice concluded a contract with the best selected bidder on the purchase and sale of technical equipment for the needs of special departments of public prosecutor's offices on September 21, 2021 in the amount of 69,090,038.82 RSD with VAT. The contract has been fully realized and the equipment was delivered to the authorities. |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.3.3. Effectively investigate all allegations of corruption in privatization cases and ensure full transparency and accountability to avoid such cases in the future |  |  |  |  |  | All allegations of corruption in privatization cases are effectively investigated preventive measures are undertaken to ensure full transparency and accountability in acting. |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of initiated and finalized criminal proceedings against responsible persons for illegal actions carried out in privatization of state-owned capital; - Data on corruptive elements in privatization process can effectively collect and disclose at any moment; - Recommendations of Anti-corruption Council related to 24 controversial privatization cases assessed. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.3.1. | Design and implement programs of mutual professional development of authorities participating in the process of privatization and authorities responsible for the prevention and prosecution of the cases of corruption. |  |  |  |  | -Judicial Academy (director) -Ministry of Commerce (state secretary) -Anti-corruption Agency (director, deputy director) |  | IV quarter of 2021 |  |  | Budget of the Republic of Serbia Costs currently unknown. Will be known will after development of the training plan of the Judicial Academy. and IPA 2019 -5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Trainings conducted. Numbers of seminars held in relation to planned trainings on mutual professional development of authorities participating in the process of privatization and authorities responsible for the prevention and prosecution of the cases of corruption. |  |  |  |  | Activity is fully implemented. A training curriculum and case study with working material was done with the support of the GAI Project. It is an integral part of the basic training program, and in the 4th quarter, an analysis of further improvement of the project was done. |  |
| 2.3.3.2. | Regular meetings of the Anti-Corruption Council with the Republic Public Prosecutor's Office and the Prosecutor's Office for Organized Crime, in order to improve the implementation of the recommendations listed in the Anti-Corruption Council reports. |  |  |  |  | - Anti-Corruption Council - Republic Public Prosecutor's Office -Prosecutor's Office for Organized Crime |  | Continuously |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs. | Meetings are held regularly. |  |  |  |  | Activity is being successfully implemented. On March 23, 2022, a meeting was held with the representatives of the Anti-Corruption Council. Council's reports were discussed and further cooperation in the fight against corruption was agreed. The Council agreed with the Republic Public Prosecutor's Office to hold regular quarterly meetings in the coming period. |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |
| 2.3.4. Improve the collection of unified statistics on corruption, distinguishing clearly between different types of criminal activities and allowing for a detailed assessment of length of the cases, outcome etc.; |  |  |  |  |  | Established system for collection of unified statistics on corruption, distinguishing clearly between different types of criminal offences, length of the cases, outcome of the proceedings, etc. |  |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - At any time number of initiated and finalized criminal proceedings against responsible persons for criminal offences of corruption can be provided; - On that basis, an analysis of the proceedings for criminal offences of corruption can be made and conclusions drawn. |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.4.1. | Conduct an analysis of Feasibility studies for the establishment of the unified electronic register of criminal offenses related to corruption, conducted within IPA 2013 „Prevention and Fight Against Corruption“ project and USAI GAI Project. Act in accordance with analysis findings in terms of the most feasible solution. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) |  | IV quarter of 2021. |  |  | Budget of the Republic of Serbia 17.285 € | Analysis of Feasibility studies conducted. |  |  |  |  | Activity is fully implemented. The Analysis of Feasibility studies is conducted, software that is being successfully used was developed. |  |
| 2.3.4.2. | Amend the positive regulations in order to establish unique methodology for data collection, records keeping and statistical reporting on criminal offences of corruption. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Government of the Republic of Serbia -National Assembly |  | II quarter of 2022. |  |  | Budget of the Republic of Serbia Costs currently unknown, connected to software development. | Amendments to the regulations adopted. |  |  |  |  | Activity is fully implemented. A unique methodology of data collection, recording and statistical reporting on corrupt criminal acts was established based on the functional analysis developed within the IPA 2013 "Prevention and fight against corruption" and USAID GAI projects. There was no need to change positive regulations in this area. |  |
| 2.3.4.3. | Establish a model of unique records keeping (electronic register) for criminal offenses with an element of corruption, in accordance with the law governing the protection of personal data, which will be used in future for creating criminal policy. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Republic Public Prosecutors Office Partner institutions: -Ministry of Interior -Ministry of Finance -Law enforcement agencies -All relevant stakeholders |  | II quarter of 2022. |  |  | Budget of the Republic of Serbia Costs currently unknown, connected to software development. and IPA 2019 - 5.000.000 € (Support to AP 23 in Fight Against Corruption and Fundamental Rights - Flexible Facility) | Unique records keeping model is established. |  |  |  |  | Activity is partially implemented. An electronic register for criminal offenses with a element of corruption has been established, and data is collected in accordance with the provisions of the Law on Personal Data Protection. As part of the USAID's Project for Responsible Government, in cooperation with the Ministry of Justice of the Republic of Serbia, the Republic Public Prosecution's Office and the Supreme Court of Cassation, a project was implemented to develop the Electronic Register of Corruption Cases (ERCC). ERCC is a reporting software tool that will provide regular and ad hoc reports with timely information on the status of corruption cases, reveal ``bottlenecks'' in the investigation and court proceedings for this type of case and enable the identification of strategies to increase the efficiency of the work of four special departments for the suppression of corruption in Higher courts and Higher public prosecutor’s offices. The register will communicate with the existing case management systems in courts and public prosecutor's offices (AVP, SAPO) by generating reports based on the data stored in these systems. Using the application will not require the introduction of new or changes to existing work processes in register offices. For the purposes of developing the application, the Republic Public Prosecutor's Office created models of the necessary reports. Most of the reports were tested and confirmed, while a smaller number of reports could not be tested due to work on improving the SAPO program for case management in public prosecutor's offices. The work on the development of the new SAPO application is in the final phase and the introduction of additional functionalities of the program, which are also necessary for the operation of the Electronic Register of Corruption Cases, is in progress. After the introduction of these functionalities, the testing of the remaining reports within the ERCC will begin, and the reporting tool itself, due to its dependence on the SAPO program, will begin to be applied in four special anti-corruption departments in Higher public prosecutor's offices from January 1, 2023. |  |
| RECOMENDATION FROM THE SCREENING REPORT |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.5. Ensure that the legislative and institutional framework enables effective seizure, confiscation and management of the proceeds of crime resulting in an increased number of seizures and confiscations |  |  |  |  |  | Legislative and institutional framework enable effective seizure, confiscation and management of the proceeds of crime resulting in an increased number of seizures and confiscations |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Gradual increase in the number of decisions on seizure and confiscation and value of seized and confiscated assets derived from criminal activity. |  |  |  |  |  |  |  |
| Interim benchmark: Serbia establishes an initial track record of efficient and effective investigations (incl. financial investigations), prosecution, convictions and asset confiscations in corruption cases, including high level cases. (Serbia applies a zero tolerance policy towards leaks related to planned or ongoing corruption related investigations and ensures that these are sanctioned should they occur – addressed within 2.3.7.). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME /DEADLINE |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.5.1. | Strengthen the capacity of the Directorate for Administration of Seized Assets through training courses, particularly in the part relating to the management of property seized from legal entities. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Directorate for Administration of Seized Assets -Judicial Academy |  | Continuously |  |  | Budget of the Republic of Serbia- 900 € in 2020 - 300 € in 2021 - 300 € in 2022 - 300 € | Training courses conducted. Percentage of Directorate for Administration of Seized Assets employees trained in relation to those required/in needs of training. |  |  |  |  | Аctivity is being successfully implemented. The situation has not been changed since the last reporting period. |  |
| 2.3.5.2. | Advance international cooperation by signing contracts with the Directorates in the region and the EU. (link with Chapter 24, activity 6.2.6.6.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Directorate for Administration of Seized Assets |  | Continuously |  |  | Budget of the Republic of Serbia Activity requiring insignificant costs | Number of contracts concluded with the Directorates in the region and in the EU. |  |  |  |  | Activity is partially implemented. This procedure is in progress. A draft agreement on the division of property with foreign countries has been prepared and will be submitted as a proposal for the basis for negotiations with stakeholders. After receiving positive answers from the offered parties, the Government of the Republic of Serbia adopted the Draft Agreement and the Basis for conducting negotiations for concluding property sharing agreements with the Kingdom of Spain, Montenegro, Bosnia and Herzegovina and Republika Srpska. The Kingdom of Spain has submitted a response to the draft agreement and the harmonization of the proposed texts of both sides is in progress. |  |
| 2.3.5.3. | Strengthen capacity of Directorate for Administration of Seized Assets by recruiting new employees according to Rulebook on job classification. |  |  |  |  | -Ministry of Justice (state secretary in charge of anti- corruption) -Directorate for Administration of Seized Assets |  | IV quarter of 2021. |  |  | Budget of the Republic of Serbia 40.848 € | All positions filled in line with Rulebook on job classification. |  |  |  |  | Activity is partially implemented. The Ministry of Justice is in the process of amending the Rulebook on systematization, which should provide the basis for the implementation of this activity. |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  |  |  |  | IMPACT INDICATOR |  |  |  |  |  |  |  |
| 2.3.7. (Serbia establishes an initial track record of efficient and effective investigations (incl. financial investigations), prosecution, convictions and asset confiscations in corruption cases, including high level cases.- addressed within 2.3.5.) Serbia applies a zero tolerance policy towards leaks related to planned or ongoing corruption related investigations and ensures that these are sanctioned should they occur. |  |  |  |  |  | Measures to prevent leeks to the media of confidential information regarding the investigations are established and effectively implemented. |  |  |  |  | - Positive opinion of the European Commission stated in the Annual Progress Report on Serbia; - Number of proceedings for illegal distribution of information to the media about active investigation procedures. |  |  |  |  |  |  |  |
| ACTIVITIES |  |  |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME /DEADLINE |  |  |  | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |  |
| 2.3.7.1. | Adoption of new regulations and procedures aimed at introducing control and oversight mechanisms in line with the analysis of the current situation (normative, organisational and functional), identifying weaknesses and risks (level of data accessibility for the exact determination of availability in relation to time and content). |  |  |  |  | -Ministry of Interior | I quarter of 2021. |  |  |  | Budget of the Republic of Serbia - 17.285 € In 2021. | Amended or adopted new regulations and procedures in line with the analysis. |  |  |  |  | Activity is fully implemented. The Law on Confiscation of Criminal Property (Official Gazette of the RS, Nos. 32/13, 94/16 and 35/19) regulates the conditions, procedure and bodies responsible for detecting, confiscating and managing the property of natural and legal persons from a criminal offense. Article 2 prescribes the criminal offenses to which this law refers, among others to the so-called "Corrupt" crimes. In accordance with the mentioned law, an organizational unit in charge of financial investigation has been formed in the Ministry of the Interior as a specialized organizational unit of the Ministry of the Interior that detects property derived from criminal offenses and performs other tasks in accordance with this law. In accordance with this law, the Ministry of the Interior has established the Asset Recovery Office (AssetRecoveryOffice), which processes received and sent requests in the framework of international cooperation, for detecting and identifying property derived from crime, with the aim of temporary or permanent confiscation. The unit performs its duties ex officio or by decision of the public prosecutor or the court. The Department for the Fight against Corruption was formed on the basis of the Law on Organization and Competences of State Bodies in the Fight against Organized Crime, Terrorism and Corruption. The Department carries out its activities in coordination with four special departments for the suppression of corruption within the Higher Public Prosecutor's Offices in Belgrade, Novi Sad, Nis and Kraljevo. The police officers of the Department act on the orders of the competent prosecutor's offices and apply the procedures prescribed by the CPC. When it comes to preventing the leakage of information related to the investigation of all criminal acts, not only corruption, Article 7 of the Code of Police Ethics ("Official Gazette of RS", No. 17/17) prescribes the protection of official data, according to which police officers do not disclose and do not use unauthorized data obtained in the service or on the occasion of performing the service, and especially those that could jeopardize the course of legal proceedings, ie the rights of third parties. Article 12 of the Code stipulates that conduct contrary to the provisions of the Code is conduct that damages the reputation of the Ministry of the Interior and the police profession. The Law on Police ("Official Gazette of RS", No. 6/16, 24/18 and 87/18) envisages behavior that damages the reputation of the Ministry as a serious breach of official duty, so the disciplinary proceedings determine the disciplinary responsibility of a police officer for the violation official duties. |  |
| 2.3.7.2. | Establish the Working group in the Ministry of Justice for consideration of Republic Public Prosecutors’ Office initiatives for amendments to Criminal Procedure Code (based on Analysis of normative, organisational and functional framework - measures to prevent information leaks and repressive measures to suppress unauthorised communication of data relating to criminal proceedings), Criminal Code, and the Law on Public Prosecutor's Office (based on Analysis of the legislative framework regarding criminal, disciplinary and other types of liability in connection with the unauthorised communication of information). Act in accordance with Working group conclusions. (link with activity 2.2.10.23.) |  |  |  |  | -Ministry of Justice (state secretary in charge of anti-corruption) -Republic Public Prosecutors’ Office -Government of the Republic of Serbia -National Assembly | For establishing Working group: I quarter of 2021 For amendments and supplements: by IV quarter of 2022 |  |  |  | Budget of the Republic of Serbia - 30.878 € | Working group established. Amendments and supplements to the laws adopted, in line with Working group conclusions. |  |  |  |  | Аctivity is being successfully implemented. By the Decision of the Minister of Justice No. 119-01-126 / 2021-05 of 12 May 2021, a Working Group for the Analysis of Criminal Procedure was established in order to identify and eliminate its weaknesses and shortcomings and draft a working text of the Law on Amendments to the Criminal Procedure Code based on the results of the analysis. By the Decision of the Minister of Justice No. 119-01-125 / 2021-05 of 12 May 2021, a Working Group for the Analysis of the Effectiveness of the Criminal Justice System was established, based on completed cases in order to identify and eliminate its weaknesses and shortcomings and draft a working text Law on Amendments to the Criminal Code based on the results of the analysis. The situation has not been changed since the last reporting period. |  |
| 2.3.7.3. | Increase levels of IT protection by creating a so-called early warning system and alarm system. |  |  |  |  | -Ministry of Interior | Continuously |  |  |  | Budget of the Republic of Serbia - in 2020 Budgeted in 2.3.7.1. | Increased level of IT protection. Developed early warning system and alarm system. |  |  |  |  | Аctivity is being successfully implemented. In the reporting period, activities in the area of competence of CERT of the Ministry of the Interior were carried out in accordance with the competences and normative framework in the field of information security: Monitoring of information communication system of the Ministry of the Interior. |  |
| 2.3.7.4. | Monitor sanctioning of violations of regulations preventing disclosure of confidential information, along with the prepared analysis on the implementation of regulations and recommendations. |  |  |  |  | -Ministry of Interior -Republic Public Prosecutors’ Office | Continuously |  |  |  | Budget of the Republic of Serbia- 2. 553€ in 2020 - 851€ in 2021 - 851€ in 2022 - 851€ | Number of cases of violation of regulations preventing disclosure of confidential information. Conducted analysis on implementation with the recommendations. |  |  |  |  | Аctivity is being successfully implemented. In the Police Directorate, the Criminal Police Directorate, the Counter-Terrorism Service and the Directorate for Administrative Affairs, 1 (one) disciplinary procedure is underway for violation of official duty under Article 207, paragraph 1, item 10 of the Law on Police. One disciplinary procedure is conducted on the stated basis in the Police Administration for the City of Belgrade, in the Police Administration in Zajecar, Kraljevo, Novi Sad, Vranje and Nis. In second quarter of 2022, one disciplinary procedure was completed on the stated basis in the Police Administration in Leskovac, and a measure of a fine in the amount of 20% of the salary was imposed for a period of two months. No violations of regulations preventing the disclosure of confidential information have been reported to the Republic Public Prosecutor's Office. |  |

| 3. FUNDAMENTAL RIGHTS |  |  |
| --- | --- | --- |
| CURRENT STATE: |  |  |
| The Republic of Serbia will continue to improve its legal and normative framework for the protection and promotion of fundamental rights, in line with the EU Acquis, European and international standards and best practices. Prohibition of torture, inhuman or degrading treatment and punishment In the field of prevention and suppression of torture and ill-treatment, the Republic of Serbia plans to strengthen the capacities of the Ombudsman, especially in its role as the National Mechanism for the Prevention of Torture, by providing the necessary number and structure of employees for efficient performance of tasks within its competence and improvement of its organizational, financial independence. Also, through the definition of clear channels of communication between police officers, NPMs and civil society organizations, it is planned to achieve a higher level of coordination and raise the general level of awareness of the need to fully eliminate all forms of torture. The amendments and supplements to the Law on the Ombudsman are also planned in order to strengthen the independence and improve the efficiency of the work of the Ombudsman, especially in carrying out the tasks of the National Mechanism for the Prevention of Torture. Through initial and continuous training of police officers, staff of the system for enforcement of criminal sanctions, a higher level of expertise and awareness about the necessity of establishing a zero tolerance for torture shall be achieved. The existence of adequate infrastructure in facilities for enforcement of criminal sanctions is a significant aspect of the prevention of torture and the Republic of Serbia plans to make significant efforts in the construction of new institutions for the enforcement of criminal sanctions during the implementation of the Action Plan for Chapter 23, as well as renovate existing facilities. In addition to the renovation, significant attention will be paid to improving conditions at the Special Prison Hospital in Belgrade. Beyond the improvement of the infrastructure of the facilities for enforcement of criminal sanctions, significant efforts will be made to improve the infrastructure of detention facilities at the police stations. The problem of overcrowding of the institutions for the enforcement of criminal sanctions will be addressed both through infrastructure investments (District prison Belgrade, Criminal Correctional Facility Zabela, Criminal Correctional Facility for women Požarevac, Criminal Correctional Facility in Sremska Mitrovica, District prison Leskovac), as well as through the development and further improvement of the system of alternative sanctions. Implementation of staff training is planned for the application of specialized treatment programs for convicted persons and sensitive categories of convicted persons (juveniles, individuals with mental illness, individuals with substance misuse problems, women, persons with special needs, elderly people) in order to successfully reintegrate them. Moreover, adoption of a new Strategy for the Development of the System of Enforcement of Criminal Sanctions in the Republic of Serbia and the Action Plan for its implementation, as well as the establishment of effective monitoring over its implementation is also planned. The planned activities also involve strengthening the monitoring mechanism of the Ministry of Interior for the implementation of standards of police treatment in the area of prevention of torture through training, improvement of the complaint system, internal and external control as well as the adoption of by-laws. In the formulation of all measures in the field of prevention and suppression of torture, special attention has been paid to the recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment and Punishment and Implementation of the Recommendations is a fundamental focus of all activities in this field. Freedom of expression, including freedom and pluralism of the media The development of the Action Plan for the implementation of the Strategy for the Development of the Public Information System in the Republic of Serbia for the period 2020-2025, which was adopted on January 30, 2020 ("Official Gazette of the RS" No. 30/18) is in progress. Immediately after the adoption of the Action Plan, amendments to the set of media laws will be introduced. Frequent threats and violence against journalists are recognized as a serious threat to freedom of expression and media pluralism. In order to overcome this challenge, it is necessary to strengthen coordination of all competent authorities and to raise awareness of the importance of protecting journalists both through training and by giving priority to these cases, and these activities will be a focus in the forthcoming period. Information leaks about planned and ongoing criminal investigations has been spotted as a serious threat to the effectiveness of the investigation, the presumption of innocence and the confidentiality of personal data. It is planned to end these negative practices through new operational procedures, capacity building through training and more efficient coordination of competent authorities. The principle of non-discrimination and the position of vulnerable social groups In the following period, the Republic of Serbia plans to achieve full harmonization of the Law on the Prohibition of Discrimination with the acquis. The planned adoption of the new Strategy for the Prevention and Protection against Discrimination and the Action Plan and its consistent implementation and active monitoring shall improve the position of the most vulnerable social groups. Through its dedicated work, the Commissioner for the Protection of Equality as a central national body specialized in combating all types and forms of discrimination and its prevention, has led to a significant increase in awareness of discrimination. The continuation of its capacity building in the forthcoming period is necessary in order to further improve the protection and prevention of discrimination. Also, capacity building of the Office for Human and Minority Rights is planned. Positive progress made in improving the position of the LGBTI community will continue through the implementation of the Action Plan for the implementation of the Strategy for Prevention and Protection against Discrimination and through the consistent implementation of the Law on Anti-Discrimination. By continuing the implementation of an effective community policing model and continuous cooperation with representatives of the LBGTI community, the work on improving the security situation of all members of the LGBTI community will endure. In the following period, it is planned to continue with positive practice of raising awareness about prohibition of all forms of discrimination and methods of its prevention, which will be achieved through a series of educational events, training of citizens and civil servants, as well as printing and distribution of manuals for identification and response to discrimination. By adopting the Strategy for improving the position of persons with disabilities in the Republic of Serbia for the period up to 2024 and the Action Plan for its implementation, as well as efficient monitoring of the implementation of these documents, the position of persons with disabilities shall be improved, which will foster the implementation of the UN Convention on the Rights of Persons with Disabilities. Gender equality In the following period, the Republic of Serbia plans to pay due attention to improving the implementation and promotion of the principles of gender equality, both in the strategic and legislative framework, as well as by strengthening the coordination and capacity of institutions. The existing legislative framework did not adequately regulate the field of gender equality, it is incompatible with the undertaken international obligations in the area of ​​gender equality and subsidiary legislation and contains numerous deficiencies that prevent or significantly impede the comprehensive implementation of the principles of gender equality. The Government of the Republic of Serbia has established a Coordination Body for Gender Equality that will consider all issues and coordinate the work of state administration bodies in relation to gender equality in order to enable all existing mechanisms (at the state, provincial and local level) to function in an efficient and uniform manner. It is planned to adopt the new Law on Gender Equality in order to fully align with the acquis, and subsequently adopt a new Action Plan for implementation of the National Strategy for Gender Equality as well as the new National Strategy and Action Plan for the Prevention and Suppression of Domestic Violence and Violence in Partner Relations, as well as effectively monitor their implementation. Through the implementation of training of employees in public authority bodies in the field of gender equality, effective coordination and monitoring of the implementation of gender equality policies will be ensured. Rights of the child Through the strengthening of the role of the Council for the Rights of the Child, a higher level of coordination of all state bodies responsible for the implementation of strategic documents in the field of the rights of the child will be achieved. Also, through a broad, inclusive and transparent process, a new Strategic Framework for the Protection of Children against Violence will be implemented, which will continue to develop and improve the existing framework, based on previous experiences. Activities aimed at the increase in the number of children benefiting from family support measures in order to reduce the necessity of using alternative care, or the accommodation of children in residential institutions or foster care will continue; whereas in case of necessity for alternative care, attempts will be made to use family-type accommodation in the local community, with the gradual increase in the availability of alternative options of alternative care that are selected on a case-by-case basis. Efforts shall be made to strictly control and reduce the number of children residing in residential institutions. Also, efforts shall be made to increase the number and type of services targeting children in vulnerable situations (children living and working on the street, children with disabilities in development and disability, children living in poverty, etc.). Through the adoption of the Strategy for de-institutionalization and development of community services and strengthening of the capacities of social protection providers, the mechanisms for social reintegration shall be improved. Activities aimed at improvement of juvenile justice in order to fully implement European standards, particularly by enabling an annual increase in the number of children benefiting from a child oriented judiciary through widespread use and introduction of new diversionary schemes, specially adapted to the preparation for the release carried out by trained judicial and other experts, through the improvement of infrastructure and the widespread use of alternative sanctions. Training of staff for the application of specialized treatment programs for juvenile offenders for the purpose of successfull reintegration was performed in cooperation with Twinning project "Strengthening capacities for training, education and employment of convicted persons" funded by EU - IPA 2013. Procedural safeguards The establishment of a functional system of free legal aid will be accompanied by additional training of the providers and staff in local self-government units, as well as public awareness campaign, which will significantly improve access to justice for all citizens, and especially the most vulnerable ones. Implementation of the law shall be closely monitored by the Ministry of Justice and reports shall be publicly available. Amendments and supplements to the Criminal Procedure Code will result in full harmonization with the EU acquis in the field of procedural safeguards, which will provide greater guarantees for exercising the right of the suspects or accused persons to access to a lawyer, legal aid, the right to information and the right to interpretation and translation. This will be followed by training of all relevant stakeholders. By adopting a new strategic framework in the area of ​​rights of victims and witnesses, as well as amendments to the normative framework, full harmonization with Directive 2012/29 / EU on rights, support and protection of victims and witnesses will also be achieved. Through the establishment of victim support services, another aspect of access to justice will be improved. The position of national minorities With regard to the position of national minorities, the Republic of Serbia applies the Action Plan for the Exercise of the Rights of National Minorities. The Action Plan focuses on the implementation of the existing legal framework, as well as the improvement of the legislative framework in the areas where such a need has been identified. The implementation of the Action Plan is monitored by the Council for National Minorities, which ensures full inclusion of National Councils of National Minorities and relevant public authorities, while administrative support to the Council is provided by the Office for Human and Minority Rights. Every two months, all competent authorities submit reports on the implementation of activities prescribed in the Action Plan to the Office for Human and Minority Rights, and on this basis the reports on the status of implementation are prepared for the Council for National Minorities. In case of failure to meet the deadlines set by the Action Plan, the Council for National Minorities, based on its political authority, encourages effective implementation by the competent ministries. In the domain of freedom of thought, conscience and religion, the dialogue between the Churches and religious communities with the Serbian Orthodox Church will continue, based on the idea proclaimed in the Constitution of the Republic of Serbia which states that Churches and religious communities are equal and free to independently regulate their internal organization, religious affairs, publicly perform religious rituals; and bearing in mind the specificities of European legal traditions in this domain and the cultural specificities of the region to which Serbia belongs. The aim of this dialogue is to encourage the use of minority languages in ceremonies, in accordance with the possibilities and needs, by respecting the principle of state neutrality in relation to religious issues in order to ensure that there are no unjustifiable restrictions on the access of members of national minorities to religious rites in their mother tongue. As a part of the efforts to improve the position of the Roma national minority, a multi-annual Strategy and Action Plan for improving the situation of Roma are being implemented. The strategy covers the most important areas of life with special emphasis in the following areas: the issuance of personal documents, comprehensive measures against discrimination, compliance with international standards in forced displacement, equal access to health and social protection, education and labor market, as well as improved housing conditions. A new action plan for this Strategy will be developed that will enable the continuation of its efficient implementation. In developing the planned activities of the new Action Plan, the Operational conclusions of the Roma Seminar 2017-2019: Social inclusion: the situation of Roma in the Republic of Serbia will be taken into account. On behalf of the Government, the Deputy Prime Minister and the Minister of Construction, Transport and Infrastructure coordinates the activities of state bodies, local self-government units and public enterprises aimed at improving the position of Roma women and their full inclusion in social, economic, cultural and political aspects of life, with special emphasis in areas where they are particularly vulnerable (enrollment, education, housing, health care, social protection and employment). The position of refugees and internally displaced persons In the forthcoming period, significant efforts will be continued to improve the living conditions of refugees and internally displaced persons on two tracks. Significant financial resources will be invested in resolving the problems of housing for the most vulnerable families, especially those who are still in collective centers, both through the construction of new housing units and by providing the necessary building materials, which will enable the closure of all formal collective centers. Provision of complementary measures for the sustainable integration of refugees through programs aimed at economic empowerment shall continue. The introduction of a system of free legal aid available to refugees and internally displaced persons will provide a higher degree of legal certainty and facilitate access to personal documents, thus ensuring their full access to rights and promoting their social and economic integration. Measures against racism and xenophobia In the area of combating racism and xenophobia, training for judges, public prosecutors and police officers will be organized in the forthcoming period in order to improve the knowledge and skills necessary for the effective prosecution of hate crimes. Through the continuation of cooperation with international and regional organizations in the field of combating hate speech and hate crimes, as well as the organization of expert meetings aimed at establishing a mechanism to combat hate crime in the Republic of Serbia, the results in the area of prevention of racism and xenophobia will be improved. Through the work of the National Council for the Prevention of Negative Phenomena in Sports, the measures and activities of state administration bodies and competent national sports associations will be improved to prevent violence and misbehavior in sport events. Personal data protection Through the implementation of the new Law on Personal Data Protection, aligned with the EU acquis in the given area, shall ensure a higher level of protection of personal data. Moreover, by carrying out comprehensive training for the implementation of the new law, the necessary capacities will be provided for its effective implementation. Adoption of the Law on Personal Data Protection leads to changes in the competencies and organization of the Commissioner for Information of Public Importance and Personal Data Protection, hence requiring the continuation of strengthening of the Commissioner's capacity. |  |  |
| REFORM ACTIVITIES COMPLETED DURING THE IMPLEMENTATION OF THE ACTION PLAN |  |  |
| Prohibition of torture and inhuman or degrading treatment or punishment and reform of the prison system Reconstruction of existing facilities in accordance with European standards is being successfully implemented. So far, one block was renovated and inhabited in the Belgrade District Prison, as well as in the Special Prison hospital in Belgrade. Pavilion was built for persons sentenced with the measure of compulsory psychiatric treatment. The reconstruction of the existing accommodation capacities of the penitentiary institutions has been completed in accordance with European standards in the district prison in Užice, the Criminal Correctional Facilities in Valjevo, Ćuprija and Niš, as well as educational correctional facility Kruševac. Construction of new buildings and departments in order to improve living conditions in prisons has initiated. A new prison facility was built in Pancevo in order to improve living conditions. In order to ensure more effective judicial review and supervision over the rights of individuals deprived of liberty, the Law on Enforcement of Criminal Sanctions and the Rulebooks governing the status of persons deprived of liberty have been printed and distributed. In addition, a Manual and a Handbook for prisoners and detainees as well as forms for the complaints and appeals are printed and distributed. A methodology was prepared by the Prosecutors’ Office and the Police to investigate cases of abuse and torture in order to conduct effective investigations into allegations of ill-treatment and torture by the police. Within the framework of the joint project of the European Union and the Council of Europe "Strengthening the protection of human rights of persons deprived of liberty and convicts in Serbia" ("Horizontal Facility" for the Western Balkans and Turkey), strengthening the human rights of persons deprived of liberty and convicts with a focus on the problems identified in the reports of the European Committee for the Prevention of Torture and Judgments of the European Court of Human Rights, the key activities involved: expert analysis of the draft Rulebook on the application of police powers with detailed recommendations, expert analysis of complaints system, internal control and external control mechanisms, expert analysis of the Law on the Protection of Persons with Mental Disorders, expert analysis of the normative framework and practice regarding the human rights of persons with mental disorders in the institutions of social protection, expert analysis of the inspection of psychiatric and social protection institutions and measures aimed at harmonization with EU standards and best practice. Moreover, revision of the system of continuous training of police officers in order to prevent torture, inhuman or degrading treatment was performed, and expert support for the development of a new Strategy for the Protection of Mental Health in the Republic of Serbia was provided. Rulebook on police powers was adopted ("Official Gazette", no. 41/2019) and the Instruction on unified manner of records keeping in relation to applied powers, thus introducing clear procedures for treatment of detainees and persons in custody in order to ensure the exercise of their rights. An analysis of the current situation in the detention units was carried out, including recommendations for improvement of the situation in detention units, as well as for changing the normative framework and eliminating the weaknesses and risks in treatment of the arrested and detained persons. Numerous trainings have been conducted for treatment of the arrested and detained persons in accordance with international standards. A complete network of offices for alternative sanctions has been established at the state level, by opening the remaining nine offices, thus setting up the total network of 25 offices. The establishment of a network of alternative sanction offices was accompanied by continuous training for the judiciary and newly appointed commissioners for alternative sanctions. The Rulebooks governing the implementation of alternative sanctions and monitoring of implementation have been adopted. Activities were implemented in order to strengthen cooperation and provide conditions for effective social reintegration of prisoners after serving their sentence through the signing of agreements on cooperation with non-governmental organizations, including constant work on the sensitization of local self-governments and the public. Establishing cooperation at the local level was a prerequisite for successful implementation of measures to provide assistance and support to former convicted persons in order to ensure social reintegration after the expiry of the sentence and the reduction of recidivism. Through the conducted trainings, judges for the enforcement of criminal sanctions have improved knowledge in the field of the rights of persons deprived of liberty; contemporary trends in the enforcement of criminal sanctions; as well as accepted standards in the field of treatment and post-penal acceptance. A plan for extending the competencies of enforcement judges has been developed. The Strategy of Development of the System of Enforcement of Criminal Sanctions in the Republic of Serbia by 2020 was adopted. Position of the ombudsman, the provincial ombudsman and local ombudsmen Continuous efforts are being made to further strengthen the capacity of the Professional Service of the Ombudsman through hiring of full-time permanent staff, which will bring the total number of staff in line with current needs and provide the necessary number and structure of employees for efficient performance of tasks within its competence. Drafting of the new Law on Ombudsman is in progress. Freedom of expression and freedom and pluralism of media A set of media laws (Law on Public Information, Law on Electronic Media and the Law on public service media) has been adopted in 2014 and it is being implemented. The State Prosecutorial Council has adopted the Communication Strategy of the SPC and the Republic Public Prosecutor's Office for the period 2015-2020 in order to define the relationship, methods and scope of mutual communication in order to prevent information leaks about the course of criminal investigations in the media. A new multiannual Strategy for the Development of Public Information System has been adopted in January 30, 2020. An analysis of the Criminal Code was conducted regarding the need to establish a higher level of protection of journalists against threats of violence. The TAIEX mission organized for this purpose has not identified the need to amend the Criminal Code, but suggested amendments of other laws and practical guidelines. In order to increase the efficiency of the work of the public prosecutor's offices in criminal proceedings against the perpetrators of criminal offenses against journalists, the Republic Public Prosecutor issued an instruction envisaging that the appellate, higher and basic public prosecution offices keep separate records for criminal offences against persons performing activities of public interest in the field of information, in relation to actions undertaken and in connection with attacks on the media websites, in cases where urgent action is prescribed. The Agreement on Cooperation between the Republic Public Prosecutor's Office and the Ministry of Interior has been signed and is being implemented, stipulating priority treatment in investigating threats and violence against journalists in order to improve the efficiency of investigations into attacks against journalists and the prosecution of offenders. A Permanent Working Group was established to implement a cooperation agreement between the Republic Public Prosecutor's Office, the Ministry of Interior and representative associations of journalists, which meets regularly. Concurrently, the Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists continued to work and provides relevant institutions with its key findings. Principle of non-discrimination and social position of vulnerable groups The implementation of the Action Plan for Implementation of the Strategy for Prevention and Protection Against Discrimination was monitored by the body for oversight of the implementation of the Strategy and the AP for Prevention and Protection Against Discrimination. An analysis of the implementation of the Law on the Prohibition of Discrimination was conducted. Moreover, the mechanism of the Government of the Republic of Serbia for the implementation of all recommendations of the UN human rights mechanisms is established and operational. In order to further develop the community policing model, particularly in multiethnic and multicultural environments, the Ministry of Interior has developed the Action Plan for the Implementation of the Community Policing Strategy which is effectively implemented. Police officers as contact persons for work with socially vulnerable groups (women victims of domestic violence and partner relationships, LGBTI persons and other vulnerable groups, in accordance with the security needs of local communities), who were specially trained and selected, have been assigned and started operating. All liaison officers passed specialized two-day training, as well as other trainings focused on the work of police in the community, as well as communication skills. Representatives of the Ministry of the Interior hold regular meetings with representatives of socially vulnerable groups, the LGBTI community and civil society organizations aimed at sensitization and improvement of communication, in order to improve the security and protection of human and minority rights. Through active cooperation and organization of meetings between the police and representatives of socially vulnerable groups, LGBTI community and civil society organizations, mutual trust relationships have been established and preventive action has been improved in achieving protection of safety and protection of human and minority rights. New strategic Framework for the Protection of Children against Violence has been addpoted. In cooperation with UNICEF, a number of activities have been carried out to improve the foster care system by increasing the availability and quality of services for children with disabilities and their families, by strengthening the capacity of regional foster care centers and centers for social work and developing foster care procedures and guidelines as a shared care of foster parents and biological parents. Guidelines for the creation of a permanent child protection plan have been developed and distributed on the basis of existing measures for elimination of irregularities in the performance of the activities of accommodation of children and youth in social welfare institutions. As a part of the project “Strengthening the justice system and social protection in order to improve child protection in Serbia”, with the support of UNICEF, evaluation of existing resources in large and small residential institutions for children was conducted, recommendations on the methods of their use in the process of transition from institutional to community care were developed. Likewise, the project activities towards an improvement of the system of case management in the centres for social work were carried out, focusing on treatment planning for support to families at risk of separation instead of an institutionalization-oriented approach. Increasing use of diversionary schemes and prioritizing restorative approach to juvenile offenders to ensure their social reintegration and reduce recidivism rates was also initiated. Practical guidelines for hearing children based on examples of best practices in EU countries have been defined and adopted and accessible to all experts in the justice system and the guardianship body, as well as the conditions for uniform application of protective measures aimed at protecting the children victims/witnesses in criminal proceedings. Training on the protection of children victims/witnesses in criminal proceedings was conducted within the training program of the Judicial Academy and the educational material was distributed. The training of judges, prosecutors, lawyers and police officers in contact with juvenile offenders continued at the Judicial Academy. A new Council for Monitoring and Improving the Work of the Bodies in Criminal Proceedings and Enforcement of Criminal Sanctions against Juveniles was established. The increase in the use of diversionary schemes and the prioritization of the restorative approach in the treatment of juvenile offenders continued with the aim of their reintegration and reduction of recidivism. A special unit has been established to enforce the safety measure of compulsory psychiatric treatment and custody in a health institution for minors within the Special Prison Hospital. A detailed analysis of alignment of the criminal justice legislation with the Council of Europe Convention on Preventing and Combating Violence against Women and Domestic Violence (Istanbul Convention) has been carried out and recommendations have been made to amend criminal legislation. Amendments to the Criminal Code were adopted in accordance with the analysis of compliance with the provisions of the Council of Europe Convention on the Prevention and Combating Violence against Women and Domestic Violence (Istanbul Convention). A new National Strategy for the Improvement of the Status of Women and the Promotion of Gender Equality has been announced. A special law that regulates the prevention of violence against women in the family and partner relations has been adopted and is efficiently implemented. The Law on Peaceful Assembly, aligned with the recommendations of the Venice Commission and the ODIHR, as well as with Article 11 of the European Convention on Human Rights and Fundamental Freedoms and Article 12 of the Charter of Fundamental Rights of the European Union has been adopted and is being implemented. Procedural safeguards The Law on Free Legal Aid was adopted in November 2018 and its implementation started in October 2019. Training of staff in all local self-government units was organized with the support of MDTF JSS, resulting in over 300 individuals authorized to decide on free legal aid applications. All by-laws envisaged by law have been adopted and can be found at http://www.pravno-informacioni-sistem.rs/SlGlasnikPortal/eli/rep/sgrs/skupstina/zakon/2018/87/15/reg ). The register of providers of free legal aid and free legal support is published on the Ministry's website (https://www.mpravde.gov.rs/tekst/26350/registar-pruzalaca-besplatne-pravne-pomoci-i-besplatne-pravne-podrske.php ). The lists of providers of free legal aid and support are updated regularly. Entry into the Registry remains open. A comprehensive analysis has been developed with recommendations for improving procedural safeguards in order to align with EU acquis. Subsequently, an analysis has been prepared with recommendations for amending the normative framework in order to effectively apply minimum standards regarding the rights, support and protection of victims of crime/injured parties in line with Directive 2012/29/EU. A working group developed a Draft National Strategy for the Exercise of Rights of Victims and Witnesses with an accompanying Action Plan, with the support of the OSCE (IPA 2016). Position of national minorities/Roma A special Action Plan which corresponds to all the recommendations given in the Third opinion of Advisory Committee on Serbia in the context of the Council of Europe Framework Convention on the Protection of National Minorities, the second report of the Expert Committee on the Implementation of the European Charter for Regional and Minority Languages in the Republic of Serbia and reports on the implementation of bilateral agreements on the protection of national minorities, directed towards the implementation of existing legislation in the field of national minority rights, has been adopted through an inclusive process and is being implemented. The Action Plan specifically addresses the areas of education, the use of minority languages, access to the media and religious services in minority languages, and adequate representation in public administration. Implementation of the Action Plan is monitored by the Council for National Minorities. The Council meets regularly and representatives of National Councils of National Minorities participate in its work. Reports on the implementation of the Action Plan are regularly developed and publicly available. Funds from the Budget Fund for National Minorities are regularly allocated according to the program of priority areas, in accordance with the decision of the Council for National Minorities. Activities aimed at raising public awareness of the rights of national minorities and respect for cultural and linguistic diversity, through the support of the production of media content are being successfully implemented. Public calls for co-financing projects in the field of public information in the languages ​​of national minorities are published on a regular basis. The purpose of the public calls is to co-finance the production of media content in the field of public information which contributes to accurate, impartial, timely and complete information of members of national minorities; preserving the cultural and linguistic identity of national minorities in the Republic of Serbia and encouraging creativity in all areas of public life of national minorities. The new Law on Textbooks has been adopted and is being implemented, which ensures the availability of textbooks in the languages of national minorities for each school year. Activities aimed at raising the quality of primary and secondary education in the languages of national minorities are carried out regularly through the implementation of the competition for financing and co-financing activities, programs and projects of national councils of national minorities. In order to improve the exercise of the right to register in the birth registry in the language of the national minority, the Ministry of Public Administration and Local Self-Government has developed the instruction and submitted it to the bodies of the municipal and city authorities who perform the entrusted tasks of records keeping. All planned trainings of registrars and deputy registrars, as well as trainings for employees in centers for social work and police administrations have been carried out. Concurrently, the Ministry of Interior fully implements the legal provisions allowing registration of permanent residence in the Center for Social Work. Requests are solved urgently and applicants are provided with free legal aid during the application process. The new Law on Registries was adopted, which ensures voluntary registration of nationality. The lawful and efficient exercise of the right to register in birth registries within the stipulated deadline was facilitated through implementation of electronic procedures and efficient coordination of state bodies. Amendments to the Law on the Rights and Freedoms of National Minorities and the Law on National Councils of National Minorities have been adopted and are implemented. A new Strategy for Social Inclusion of Roma in the Republic of Serbia for the period 2016-2025 has been adopted and is being implemented. The drafting of a new Action Plan for its implementation is in progress. A comparative legal analysis was carried out regarding the regulation of the position of churches and religious communities in order to determine specific criteria based on the best practices of the member states of the European Union in the region (e.g. Romania, Croatia, Slovenia, Hungary) and implementation of solutions accepted in the region. The results of the analysis were presented to the competent employees of the Ministry of Justice and the Administration for Cooperation with Churches and Religious Communities. Staff capacity has been strengthened through training of staff in the normative sector of the Ministry of Justice and the registry of churches and religious communities, and through employment in the Administration for Cooperation with Churches and Religious Communities. The Rulebook on recognizing discrimination in education, aimed at preventing discrimination and segregation of national minorities in education, has been adopted and is being implemented, while measures for desegregation at the class level and at school level are also implemented. Likewise, the Rulebook on enrollment of Roma students in secondary schools through affirmative action measures was adopted and is implemented. The Center for Roma Language at the Faculty of Philology, University of Belgrade, actively implements measures aimed at training teachers and researchers for lectures and scientific work in the field of Roma language and culture. The Ministry of Education, Science and Technological Development continued to implement affirmative measures through a mentoring system and scholarships for education. With the support of international donors, a number of activities have been undertaken aimed at enrolling Roma children in kindergartens, as well as in another important area of prevention of school dropout. These activities are regularly and thoroughly reported. Legislative framework in the field of cooperatives that will improve the employment opportunities for Roma in accordance with the best practices of the European Union has been adopted. In order to improve the housing conditions for the Roma population, the Law on Housing has been adopted and is implemented in accordance with the provisions of the International Convention on Economic, Social and Cultural Rights. The position of refugees and internally displaced persons Regular activities are carried out in the framework of the implementation of the Regional Housing Program for Refugees and regular national care programs, aimed at providing permanent housing solutions for refugees. The Commissioner for Refugees and Migration, with the support of the UNHCR, produced a record of the situation and needs of internally displaced persons in 2017, and it is estimated that more than 17,000 families remain in need. The provision of complementary measures for the sustainable integration of refugees continued through programs aimed at economic empowerment. Measures against racism and xenophobia The Criminal Code has been amended and aligned with the Framework Decision 2008/913/JHA Art. 1 (paragraphs c and d). Also, amendments and supplements to the Criminal Code prescribe that the criminal offense of violation of equality (Article 128) can be carried out if, due to sexual orientation or gender identity, human or citizen rights are restricted or denied. The National Council for the Prevention of Negative Sports Events was established in 2018 and meets regularly. The purpose of the establishment of this Council is to initiate and propose measures and coordinate the activities of state administration bodies and competent national sports associations to prevent violence and misbehavior in sport events. Personal data protection The new Law on Personal Data Protection was adopted in November 2018, aligned with the EU acquis and the recommendations of the EUROJUST Expert. The start of implementation of the law was preceded by adoption of the necessary bylaws and training of more than 360 judges and prosecutors and relevant staff in courts/prosecutors’ offices. |  |  |
| 3.1. PROHIBITION OF TORTURE AND INHUMAN OR DEGRADING TREATMENT OR PUNISHMENT |  |  |
| INTERIM BENCHMARK | OVERALL RESULT | IMPACT INDICATOR |
| ### 3.1.1 Serbia implements all recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment (CPT) and invests in improving infrastructure and living conditions in prisons (including healthcare), detention centres and psychiatric institutions. Serbia actively works on reducing overcrowding and conducts training and awareness raising on the rights of persons in detention. | Implementation of the Recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment results in full elimination of torture and inhuman or degrading treatment or punishment and preconditions for its effective prevention. Living conditions in prisons improved in terms of accommodation, health care, training of convicted individuals, advanced staff training, and judicial review over the exercise of the rights of individuals deprived of liberty, supervision over the implementation of sanctions and improved treatment programs for convicted individuals and vulnerable categories of convicted individuals. Implemented measures to reduce the prison population, particularly through the widespread use of alternative sanctions. Measures to effectively reduce ill treatment in police custody undertaken Protection of the rights of persons sufferimng from mental disorders who are being treated in psychiatric institutions has been improved. | 1. Report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment stating significant progress of Serbia in terms of implementation of the recommendations of the CPT; 2. European Commission Annual Progress Report on Serbia stating significant progress in the part referring to prevention of torture and inhuman or degrading treatment or punishment and prison system reform; 3. Annual increase in level of alternative sanctions imposed ascertained in the reports of the Republic Institute of Statistics and reports by the Administration for enforcement of criminal sanctions; 4. Annual report of the Ombudsman stating progress of Serbia in terms of implementation of the recommendations of the CPT and overall safeguards against torture; 5. Annual report of the National Mechanism for the Prevention of Torture, which states a significant progress with regard to the implementation of the recommendations of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment; - Concluding remarks of the UN Committee Against Torture (CAT), as well as recommendations of the UN Special Rapporteur on torture. |

| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES |  | RESULT | IMPLEMENTATION STATUS |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1.1.1. | Introduce a system of mandatory education for new police officers and continuous education for current police officers regarding the treatment of detainees and persons remanded in custody in accordance with international standards in the field of human rights, professional ethics and acting in high risk situations. |  | -Ministry of Interior |  | Continuously |  | Budget of the Republic of Serbia- 6.300 € 2020. - 2.100 € 2021. - 2.100 € 2022.. 2.100 € Continuously, commencing from 2020. |  | Conducted training for 200 police officers on an annual basis; Decreased number of complaints about the conduct of police officers towards detainees and persons remanded in custody. |  |  | Аctivity is being successfully implemented. Newly employed police officers begin their employment in the Ministry of the Interior for a certain period of time as trainee police officers. The police officer-trainee is obliged to pass the training which includes the treatment of detainees and persons remanded in custody, which represents a condition for applying for the professional exam. Police officers who successfully pass the professional exam before the commission of the Ministry of the Interior receive the status of a police officer. Regarding the treatment of detainees and persons remanded in custody, Ministry of the Interior conducts the education of police officers continuously in accordance with the Program of professional training for police officers of the Ministry of the Interior. Having in mind that the Program of professional training of police officers of the Ministry of Internal Affairs for 2022 was adopted on March 1, 2022. year, the organizational units of the ministry were not able to approach the organization and implementation of specific trainings in the reporting period. In accordance with the provisions of the mentioned Program, the trainings will be organized in the following period. |  |
| 3.1.1.2. | In line with the new normative framework, establish Register containing information on all aspects of police detention in all police detention units. |  | -Ministry of Interior |  | By IV quarter of 2020. |  | -Budget of the Republic of Serbia-17.285 € In 2019. Horizontal Facility Phase II (tbc) |  | Records improved in line with the new normative framework. Register in all detention units established in line with the new normative framework. |  |  | Аctivity is being successfully implemented. Pursuant to item 52 of the Instruction on the unique manner of keeping records of applied authorizations from November 4, 2021, on detention of a person is formed a case containing files related to detention of persons (decision or order on detention of persons, record of detention of persons, certificate of temporarily seized and returned items, rights of brought or detained person and other files) and the case is in on duty of the organizational unit in which the detention is carried out. The mentioned instruction also prescribes keeping records on the applied authorizations of bringing and retaining, which is kept centrally electronically in the program system and is part of the unified information system of the Ministry (JIS). Records of applied authorizations for bringing and retaining are kept in the application "Brought and detained persons", which has been in use since January 1, 2013. Prior to the entry into force of the mentioned Instruction, the formation of cases on detention of persons was prescribed in the same way by item 33 of the Instruction on the unique manner of keeping records of applied authorizations, dated October 22, 2019. In addition to the above, Article 38, paragraph 1 of the Rulebook on Police Powers ("Official Gazette of the RS", No. 41/2019) stipulates that a police officer draws up a record of the detention of a person containing the information prescribed in Art. 111 of this Rulebook: -personal data of the detained person (name, surname, address, unique personal identification number); -time of the beginning of detention; -legal basis for detention; -data on the manner of informing the person about the reasons for detention and his rights; -data on the realized rights of the detained person; -data on informing family members, other persons and competent authorities about the detention of persons; -data on bringing the detained person to the competent authority; -data on visible bodily injuries, other information on the state of health and medical assistance provided to the detained person; -data on temporarily seized items suitable for attack, injury or self-harm; -data on the time and reasons for leaving and returning the person to the detention facility; -time of cessation of detention; -signature of the detained person and the police officer conducting the detention. |  |
| 3.1.1.3. | Construction, renovation and equipping of facilities for police detention in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman) in accordance with the identified needs in the analysis of current conditions of detention facilities in all regional police administrations and planned dynamics. |  |  | -Ministry of Interior | Continuously, commencing from IV quarter of 2015. |  | Budget of the Republic of Serbia - Donation of the Government of Norway - 800.000EUR in 2019, with the possibility of extension in 2020 |  | Number of constructed and restored facilities for police detention in accordance with the recommendations of the CPT and the analysis of current conditions of detention facilities in all regional police administrations. Baseline: It is necessary to perform full or partial adaptation of 184 detention facilities. Necessary equipment for detention facilities purchased in accordance with the recommendations of the CPT and the reports of the National Mechanism for the Prevention of Torture (Ombudsman). |  |  | Аctivity is being successfully implemented. With the funds of the Ministry of Interior of the Republic of Serbia, 3 detention facilities with the capacity for three persons were renovated in PD in Kraljevo – PO Kopaonik; 1 facility with the capacity for 1 person and in the PD in Užice – PO Zlatibor, 2 facilities were renovated, with the capacity for 1 person. |  |
| 3.1.1.4 | Improvement of the police conduct in the field of torture prevention through; -training of the members of the Commission for the implementation of standards of police conduct in the field of torture prevention in order to effectively perform their duties; -training of the detention units’ directors in order to effectively monitor police conduct; -training of police officers working in the police stations in order to prevent any prohibited treatment; -unexpected visits to places of detention in order to control the implementation of the recommendations of the National Mechanism for the Prevention of Torture. |  |  | -Ministry of Interior | Continuously, commencing from IV quarter of 2018. |  | Budget of the Republic of Serbia – Horizontal Facility Phase II 8.100 € in 2020. - 2.700 € in 2021. - 2.700 € in 2022.- . 2.700 € |  | Capacities of the supervision mechanism at the Ministry of Interior in the field of torture prevention strengthened through: Conducted training on the prevention of torture; Improved coordination of the Ombudsman and non-governmental sector; Unexpected visits to places of detention carried out regularly. |  |  | Аctivity is being successfully implemented. In accordance with the Program of Professional Development of Police Officers of the Ministry of the Interior for 2022, within the compulsory classes in the teaching area "Theoretical Teaching" the topic "Commission for the implementation of standards of police treatment in the field of torture prevention" was realized. In the reporting period, 26066 police officers attended the mentioned classes. In addition to the above, the topic "Police powers" was realized, which was attended by 26,122 police officers in the reporting period. In cooperation with the Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention, Uniformed Police Directorate visited detention facilities and performed the control over the conduct of police officers regarding the application of police powers "apprehension" and "detaining" in seven police directorates: PD in Smederevo, PD in Užice, PD in Prokuplje, PD in Požarevac, PD in Novi Pazar PD in Šabac and PD in Sremska Mitrovica. On this occasion, besides in police departments and police offices in the headquarters of police directorates, control was performed in four police stations. |  |
| 3.1.1.5. | Intensify cooperation with the National Mechanism for the Prevention of Torture (Ombudsman) by holding regular meetings and reporting on actions undertaken pursuant the recommendations of the National Mechanism for the Prevention of Torture (Ombudsman). |  |  | -Ministry of Interior -National Mechanism for the Prevention of Torture (Ombudsman | Continuously |  | Budget of the Republic of Serbia Activity requiring insignificant costs |  | Cooperation between the Ministry of Interior and National Mechanism for the Prevention of Torture (Ombudsman) intensified. Number of meetings held. Number of implemented NPM recommendations provided to Ministry of Interior, as stated in NPM report. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention received from the Internal Control Sector, General Police Directorate and regional police directorates 59 cases for informative purposes related to citizens reporting ill treatment by police officers. The performed analysis established that in each individual case, the Methodology for conducting investigations in cases of ill tratment was acted upon. In I quarter 2022, the Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention gave its opinion on the reports of organizational units of the MoI on their actions taken upon recommendations of the Protector of Citizens given in the reports on visits to PD for the City of Belgrade (PS Sopot, PS Mladenovac, PS Surčin, PS Lazarevac and PS Barajevo), PD in Zaječar (police directorate headquarters), PD in Prokuplje (police directorate headquarters), PD in Subotica (police directorate headquarters, PS Bačka Palanka, PS Mali Iđoš), PD in Bor (police directorate headquarters, PS Negotin and TPO Negotin) and organizational units of the Border Police Directorate (Shelter for Foreigners in Padinska Skela, BPS Beograd, BPS Sremska Rača and BPS Preševo). In II quarter 2022, Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention received from the Internal Control Sector, General Police Directorate and regional police directorates 48 cases for informative purposes related to citizens reporting ill-treatment by police officers. The performed analysis established that in each individual case, the Methodology for conducting investigations in cases of ill-treatment was acted upon. In II quarter 2022, Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention gave its opinion on the reports of organizational units of the MoI on their actions taken upon recommendations of the Protector of Citizens given in the reports on visits to PD in Subotica (PS Bačka Topola and PS Mali Iđoš), PD for the City of Belgrade (PS Grocka/PO Grocka and Kaluđerica), PD in Sremska Mitrovica (headquarters, PS Šid, PS Stara Pazova, PS Irig, PS Pećinci, PS Ruma and TPO Ruma), PD in Zaječar (PS Knjaževac and PS Sokobanja), and PD in Kragujevac (police directorate headquarters and Traffic police office). In I quarter 2022 the NPM issued 34 Recommendations to the Ministry of the Interior. Counting the recommendations issued previously which were due within the reporting period, the Ministry of the Interior followed up on 29 out of 30 due recommendations (96,67%). Within the reporting period, the NPM did not hold any meetings with the representatives of the Ministry of the Interior. In II quarter 2022 the NPM issued 26 recommendations to the Ministry of Interior. Including the recommendations sent earlier that were due for execution in the reporting period, the Ministry of Interior acted on 13 of the 13 due recommendations (100.00%). In the reporting period, the NPM held one (1) meeting with representatives of the Ministry of Interior. |  |
| 3.1.1.6. | Intensify cooperation between the Ministry of Interior with state authorities, National mechanism for the prevention of torture (Ombudsman) and civil society organizations in the field of torture prevention through: -Organization of workshops and discussions on the prohibition of torture in police, unprofessional behaviour of police officers and respect for the rights of detained persons and persons remanded into custody; -Establishment of a practice of the Ministry of Interior to report in writing on the measures taken in accordance with the recommendations of civil society organizations. -Raising awareness on prevention of torture in the police among police officers and provision of information to the public on the rights of detainees and persons remanded into custody. |  |  | -Ministry of Interior | Continuously, commencing from I quarter of 2019. |  | Budget of the Republic of Serbia- 4.053 € in 2020. - 1.351 € in 2021. - 1.351 € in 2022. - 1.351 € |  | Cooperation between the Ministry of Interior with state authorities, National mechanism for the prevention of torture (Ombudsman) and civil society organizations intensified through: -organized workshops and discussions on the prohibition of torture in police and awareness raising. - Number of signed cooperation protocols between the Ministry of Interior and civil society organizations. - regular reports of the Ministry of Interior on undertaken measures in accordance with the recommendations of civil society organizations. -Awareness raising campaign including development and distribution of brochures, leaflets, media announcements, and media statements. |  |  | Аctivity is partially implemented. Within the project of the Council of Europe "Strengthening the protection of human rights of persons deprived of their liberty and convicted persons in Serbia", on 10 February 2022, third meeting of the Steering Committee of beneficiaries of the project "Strengthening the protection of human rights of persons deprived of their liberty and convicted persons in Serbia" was held. On February 21, 2022, within the project "Strengthening the protection of human rights of persons deprived of their liberty and convicted persons in Serbia - Phase II" which is implemented by the Council of Europe, representatives of the RS MoI and the National Project Coordinator of the Council of Europe participated in a meeting, discussing the topic of the definition, role and possible introduction of a detention police officer in order to improve the detention system. On February 25, 2022, a representative of the Ministry of the Interior participated in a meeting organized by the Ministry of Human and Minority Rights and Social Dialogue on the occasion of the Decision of the Committee against Torture G/SO 229/31 SRB (9) dated 1 December 2021 adopted in the case against the Republic of Serbia. In the period April - June 2022, several meetings were held between representatives of the Uniformed Police Directorate and representatives of SATIT in order to monitor changes in the application “Detained and persons remanded in custody” by SATIT, in accordance with the proposals of the Uniformed Police Directorate. This activity is in its final stage. During May 2022, General Police Directorate submitted to the Ministry of Human and Minority Rights and Social Dialogue a list of MoI representatives to participate in the work of thematic working groups within the Council for Monitoring the Implementation of UN Recommendations on Human Rights, i.e. thematic working groups aimed at monitoring and working to meet the set goals and recommendations given in the Concluding Observations of the UN Committee against Torture (CAT). One of the members of the third thematic working group is the head of the Department for the Control of Police Work and the president of the Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention. |  |
| 3.1.1.7. | Systematically provide persons apprehended by the police, on whatever grounds, with a standard and comprehensive information sheet (“letter of rights”), setting out in a straightforward manner all their rights (including the right of access to a doctor): -in Serbian language - languages of national minorities -other language detained persons are actually able to understand In line with amendments and supplements to the CPC aimed at alignments with the acquis in the field of procedural safeguards. |  |  | -Ministry of Interior | Continuously, commencing from adoption of amendments and supplements to the CPC |  | Budget of the Republic of Serbia- Costs currently unknown |  | A standard and comprehensive information sheet (“letter of rights”) setting out in a straightforward manner all their rights systematically provided to persons apprehended by the police, on whatever grounds: in Serbian language - languages of national minorities -other language detained persons are actually able to understand. |  |  | Аctivity is being successfully implemented. Having in mind that the form "letter of rights" of the apprehended person pursuant to Art. 85 of the Law on Police and Art. 19 of the Rulebook on Police Powers, the form "rights of the detained person" pursuant to Art. 87 of the Law on Police and Art. 29. of the Rulebook on Police Powers, as well as the form "rights of the detained person" in accordance with Art. 294 of the Criminal Procedure Code, set out in the application "Records of apprehended and detained persons" which is kept at the JIS of the RS Ministry of the Interior, for the purpose of uniform treatment of police officers towards persons in police custody and detained persons. Also, this application contains the Notice of rights of a minor person in pre-investigation procedure (form No. 1) as well as the Notice of rights of a minor person in misdemeanor procedure (form No. 2) in accordance with the Rulebook on the manner and conditions of exercising police powers towards minors, in Cyrillic and Latin alphabets in Serbian, as well as in English language. In addition to this, in the previous period, the rights of apprehended and the rights of detained persons in accordance with the Rulebook on Police Powers were translated into English, Hungarian, Romanian, Roma and Albanian, after which they were posted in the application "Apprehended and detained persons" and now are available for all police officers to print them and hand them over to apprehended and detained persons. Except in the application "Records of apprehended and detained persons", examples of forms for detained persons in English, Albanian, Hungarian, Roma and Romanian are posted in the section "Documents" on the intranet site of the RS Ministry of the Interior, in the part that refers to the work of the Commission for the Implementation of Standards of Police Conduct in the Field of Torture Prevention. In accordance with the Program of Professional Development of Police Officers of the Ministry of the Interior for 2022, within the compulsory classes in the teaching area "Theoretical Teaching" the topic "Commission for the implementation of standards of police conduct in the field of torture prevention" was realized. clerk. In addition to the above, the topic "Police Powers" was realized, which was attended by 2,699 police officers in the reporting period. |  |
| 3.1.1.8. | Conduct training to investigate cases of abuse and torture in order to perform effective investigations into allegations of ill-treatment and torture by the police or other state bodies in accordance with the new methodology of investigation. |  |  | -Judicial Academy Partners: -Ministry of Interior -Republic public prosecutors’office -CSOs | Continuously, by IV quarter of 2020. |  | Budget of the Republic of Serbia- 1.702 € 8.100 € in 2020. - 2.700 € in 2021. - 2.700 € in 2022. - 2.700 € - "Supporting the protection of human rights for detained and convicted persons in Serbia" implemented within the framework of the joint program of the Council of Europe and the European Union entitled "Horizontal Facility for Support to the Western Balkans and Turkey” |  | Number of police officers and public prosecutors trained to investigate cases of torture and ill-treatment in order to conduct effective investigations into allegations of torture and ill-treatment by the police or other state bodies in accordance with the new methodology of investigation. |  |  | Activity is being successfully implemented. In the reporting period, the Republic Public Prosecutor's Office and the Ministry of Internal Affairs, in cooperation with the Judicial Academy and the OSCE Mission to Serbia, organized four seminars for public prosecutors and police officers in Kragujevac, Niš, Novi Sad and Belgrade on the topic of conducting investigations in cases of abuse by the police. Judicial Academy conducted five one-day seminars on the topic: “Conducting investigations in cases of abuse by the police’’, with the support of the OSCE Mission in Serbia, for a total of 120 participants. |  |
| 3.1.1.9. | Construction of new building in order to improve living conditions in prison in Kragujevac. |  |  | -Administration for enforcement of criminal sanctions | Finalization of works: 2021. |  | Budget of the Republic of Serbia- 28.457.774 € |  | Prison in Kragujevac constructed. |  |  | Аctivity is being successfully implemented. The works on the construction of the prison in Kragujevac, for the accommodation of 500 persons deprived of their liberty, are being carried out in accordance with the planned dynamics, with the deadline for implementation being October 2022. |  |
| 3.1.1.10. | Reconstruction of existing accommodation capacity of the current institutions in accordance with European standards and their alignment with existing standards, including the following institutions: - District Prison in Belgrade - Criminal Correctional Facility Zabela - Correctional Facility for Women Pozarevac - Criminal Correctional Facility Sremska Mitrovica - District prison Leskovac |  |  | -Administration for enforcement of criminal sanctions | By the end of 2021. |  | Budget of the Republic of Serbia- 16.339.022 € -IPА 2013- Contract for the execution of works for the women's penitentiary in Požarevac and the contract for the supervision of the execution of works -3.000.000 € 640 milion RSD Budget of the Republic of Serbia, 5.2 milion EUR for District prison Leskovac Belgrade District Prison 419,978€ KPZ Zabela 7,220,550€ Penitentiary in Sremska Mitrovica 3,498,485€ |  | Reconstruction of accommodation capacities of the current institutions in accordance with European standards finalized. |  |  | Аctivity is being successfully implemented. In I quarter 2022, The main project for the construction of two pavilions for the accommodation of convicted persons was completed in the Penitentiary in Požarevac-Zabela. In II quarter 2022, Work on the reconstruction of two detention blocks in the District Prison in Belgrade has been completed. |  |
| 3.1.1.11. | Conduct training of staff for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. |  |  | -Administration for enforcement of criminal sanctions | By IV quarter of 2020. |  | Budget of the Republic of Serbia 7.200 € in 2020. - 2.400 € in 2021. - 2.400 € in 2022. - 2.400 € |  | Staff training conducted. Number and structure of employees who participated in training. Relevant staff of the Administration for enforcement of criminal sanctions improved their knowledge and skills for the implementation of specialized treatment programs for convicted individuals and vulnerable categories of convicted individuals (juveniles, individuals with mental disorder, individuals with substance abuse problems, women, persons with disabilities, elderly persons) for the purpose of their successful reintegration. |  |  | Аctivity is being successfully implemented. Within the framework of the Council of Europe project, financed by the EU "Horizontal Facility for the Western Balkans and Turkey" in the part "Strengthening the protection of human rights of persons deprived of liberty", training was conducted for 60 employees in the treatment service for the implementation of five specialized treatment programs. Within the project "Improving the capacity of the prison administration in the area of ​​alternative sanctions, post-penal and health care" financed by the EU, in the part of improving health care, training was carried out for health workers in institutions for the implementation of new programs for reducing harm and preventing blood-borne diseases. |  |
| 3.1.1.12. | Continuous implementation of the provisions of the Rulebook on detailed conditions for the application of physical restraint and isolation of persons with mental disorders who are treated in psychiatric institutions and control of the implementation. |  |  | -Ministry of Health | Continuously |  | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € |  | Continuous implementation of the provisions of the Rulebook ensures adequate implementation of the procedures of physical restraint and isolation of persons with mental disorders, which is noted in the report of the National mechanism for the prevention of torture (Ombudsman). Number of visits. Number of determined breaches of the rulebook. |  |  | Аctivity is being successfully implemented. In the reporting period, not a single report was submitted to the health inspectorate regarding the physical restraint and isolation of persons with mental disorders undergoing treatment in psychiatric institutions. |  |
| 3.1.1.13 | Continuous implementation of the relevant provisions for the application of physical restraint and isolation of persons with mental disorders who are deprived of liberty (e.g. special prison hospital, institutes for social protection for placement of service users) and control of the implementation. |  |  | -Administration for enforcement of criminal sanctions -Ministry of Labour, Employment, Veterans and Social Affairs | Continuously |  | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € |  | Continuous implementation of the relevant provisions which is noted in the report of the National mechanism for the prevention of torture (Ombudsman). Number of visits. Number of determined breaches of the relevant provisions. |  |  | Аctivity is being successfully implemented. Institutions for the execution of criminal sanctions and the Special Prison Hospital apply the Manual for the work of health workers in institutions for the execution of criminal sanctions, which contains mandatory conditions and procedures for the application of measures of physical restraint and isolation of persons deprived of their liberty. The manual was prepared by the working group of the Administration for the Execution of Criminal Sanctions in cooperation with CoE experts within the project "Horizontal Facility for the Western Balkans in Turkey" in the section "Strengthening the protection of human rights of persons deprived of their liberty". Members of the working group, in an interactive dialogue, presented the manual to health workers from all institutes. In order to prevent abuse and neglect of beneficiaries of social protection services, the Rulebook on Prohibited Actions of Employees in Social Protection ("Official Gazette of RS", No. 8/2012 of 3 February 2012) was adopted, and in 2014, the Ministry of Labour, Employment, Veteran and Social Affairs, Department for Family Care and Social Protection issued an Instruction on Actions during Incidents to all social protection institutions. Residential social protection institutions for beneficiaries with intellectual and mental disabilities have adopted an internal procedure for the application of procedures and measures for restricting the movement, isolation or control of beneficiaries' behaviour. The institution prescribes the procedure, appoints the person (medical doctor in the institution or a specialist medical doctor from a health institution) responsible for approving the restrictive procedures and measures, and it keeps records of their application in accordance with the Law on Protection of Persons with Mental Disabilities ("Official Gazette of RS", No. 45/13). The competent ministry, through the control mechanism, the Department for Inspection Supervision, controls the work of institutions in the part of acting according to the internal procedure in order to protect the rights and interests of resident beneficiaries. Any deviation and gross violation of the rights of beneficiaries may lead to the loss of the service provider license, which granted them the permission to perform social protection activities. |  |
| 3.1.1.14 | Establishment of a functional system of deinstututionalization in line with the new Program for the Protection of Mental Health in the Republic of Serbia for the period 2019 - 2026 with its accompanying Action Plan. |  |  | -Ministry of Health | Continously, commencing from IV quarter of 2020 |  | Budget of the Republic of Serbia Horizontal Facility Phase II Costs currently unknown |  | Functional system of deinstututionalization established in line with the new Program for the Protection of Mental Health in the Republic of Serbia for the period 2019 - 2026 with its accompanying Action Plan. |  |  | Activity is partially implemented. Following the setting up of a functional system of deinstitutionalization in accordance with the Mental Health Protection Programme in the Republic of Serbia for the period 2019-2026, with the accompanying Action Plan for the implementation of programme, in the first half od 2022, five mental health centers have been opened so far on the territory of the Republic of Serbia, covering the cities where they were founded (Belgrade, Niš, Vršac, Kragujevac and Novi Kneževac) and which are an integral part of large psychiatric health institutions. Bearing in mind that within each health center in the territory of the Republic of Serbia there are services for mental health protection, as well as that there are mental health centers in the mentioned cities, it is concluded that there is satisfactory coverage of the population of the Republic of Serbia in terms of mental health protection. It is necessary to open 15 more centers for mental health in the following period (three on an annual level) with the previously completed training of the staff and obtained consent for the operation of the centers, in terms of fulfilling the legal requirements. The opening of two more centers for mental health is being prepared - one in Novi Sad and one in Pančevo. Also, in I quarter 2022 the Group for Adolescent Counselling started operating under the Centre for Mental Health Belgrade. The constituent team of the Adolescent Counselling Group consists of a physician-specialist in child and adolescent psychiatry, a nurse-technician and health associates (psychologist, social worker and defectologist). |  |
| 3.1.1.15 | Mandatory implementation of the developed models of individual treatment plans in line with the CPT recommendations |  |  | -Ministry of Health -Administration for Enforcement of Criminal Sanctions | Continuously, commencing from II quarter of 2019 |  | Budget of the Republic of Serbia 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € |  | Developed models of individual treatment plans continuously implemented in line with the CPT recommendations. |  |  | Аctivity is being successfully implemented. The Ministry of Justice-Administration for Enforcement of Criminal Sanctions in cooperation with the Ministry of Health implemented measures and activities prescribed by the Strategy for Development of the System of Enforcement of Criminal Sanctions in RS until 2020, in order to further develop health services in prisons, especially mental health of persons deprived of liberty. As part of the CoE project "Strengthening the Protection of the Rights of Persons Deprived of Liberty in RS", doctors from the Special Prison Hospital participated in workshops with Council of Europe experts and representatives of the Ministry of Health to develop individual treatment and treatment programs for persons deprived of liberty. The Special Prison Hospital in Belgrade is analyzing the implementation of treatment programs for patients who have been sentenced to mandatory psychiatric treatment and care in a health institution, based on which the working group will draw up a plan to improve existing treatment programs, with the support of the Council of Europe Office in Belgrade. project "Strengthening the protection of human rights of persons deprived of their liberty". Models of individual treatment plans are continuously implemented in accordance with the CPT's recommendations and are integrated into the current rulebook of the Serbian Ministry of Health, which implements the current Law on the Protection of Persons with Mental Disorders. In this regard, and based on additional recommendations of the CPT, the Republic Expert Commission for Mental Health of the Serbian Ministry of Health has drafted the Law on Amendments to the Law on Protection of Persons with Mental Disorders, which is currently under public discussion. The round table was attended by representatives of the non-governmental sector and the Protector of Patients' Rights, who praised the liberalization brought by the draft Law on Amendments to the Law on the Protection of Persons with Mental Disorders. Also, the Office of the Protector of Citizens (National Mechanism for the Prevention of Torture in the Republic of Serbia) conducts periodic monitoring of the implementation of the Law on Protection of Persons with Mental Disorders in Special Hospitals, Clinics and Psychiatric Departments at General Hospitals. Based on the report of the mentioned body, no cases of violation of the currently valid laws and bylaws have been identified, but advisory work has been performed. |  |
| 3.1.1.16. | Full implementation of the Action plan for the implementation of Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions. |  |  | -Administration for enforcement of criminal sanctions -other responsible authorities in line with AP | Continuously, commencing from IV quarter of 2016. |  | Budget of the Republic of Serbia Budgeted in the AP for implementation of the Strategy |  | Reports on implementation of Action plan for the implementation of Strategy for Reducing Overcrowding in Institutions for Enforcement of Criminal Sanctions AP indicate level of implementation. |  |  | Аctivity is being successfully implemented. In the process of preparing a new strategic document, the Ministry of Justice conducted a public debate on the text of the Draft Strategy for the Development of the System of Execution of Criminal Sanctions with the Action Plan for the period 2022-2027. year, in the period from January 20 to February 9, 2022. The process of adopting the Draft Strategy will be completed after the constitution of the new Government. |  |
| 3.1.1.17. | Amend the Law on enforcement of criminal sanctions in order to expand competencies of the enforcement judge. |  |  | -Ministry of Justice -Administration for enforcement of criminal sanctions -National assembly | By IV quarter of 2020 |  | Budget of the Republic of Serbia- 48.900 € |  | Amendments to the Law on enforcement of criminal sanctions adopted. |  |  | Activity is fully implemented. The Law on Amendments to the Law on Enforcement of Criminal Sanctions was adopted in May this year ("Official Gazette of RS" No. 35/2019). The new legal solutions extended the competencies of the judge for the enforcement of criminal sanctions, to make the following decisions: 1. issuing a decision to impose a sentence of imprisonment for a term not exceeding one year in the premises where the convicted person lives (house prison) if the purpose of punishment can be achieved by changing the manner of execution of the sentence; 2. making a decision that a convicted person who is classified in a semi-open or open department of the institution can be sent to work full-time outside the institution, while the remaining time he/she is at the institution. Work engagement will contribute to more efficient implementation of the program of treatment and easier inclusion in the society after the served sentence, so that the convicted person would not commit any criminal offenses in the future; 3. issuing a decision on the premature release of a prisoner from serving a prison sentence not more than 12 months prior to the expiration of the sentence, if the convicted person has served one half of the sentence of imprisonment for serious illness, serious disability or the age of the convicted person, if further execution of the prison sentence would constitute inhuman treatment. |  |
| 3.1.1.18. | Reorganization of existing services for the treatment and alternative sanctions within the Administration for enforcement of criminal sanctions by establishing a separated special department for alternative sanctions in accordance with the new job classification. |  |  | -Administration for enforcement of criminal sanctions | IV quarter of 2020. |  | Budget of the Republic of Serbia - 255.300 € |  | A special department for alternative sanctions within the Administration for enforcement of criminal sanctions established. |  |  | Activity is fully implemented. This activity ended with the adoption of the Rulebook on Amendments to the Rulebook on Internal Organization and Systematization of Workplaces in the administration for Execution of Criminal Sanctions, which entered into force on 21.05.2021 This Rulebook established a special department, the Department for Execution of Alternative Sanctions and Measures. With the new systematization of jobs, within the Department for Execution of Alternative Sanctions and Measures, new organizational units have been formed, which included the merging of certain probation offices. Thus, 16 organizational units for the execution of non-institutional sanctions and measures were created, which include the Probation Offices in 25 cities in the Republic of Serbia. In this way, better geographical coverage is provided with an optimal increase in the total number of employees. Amendments to the act on job systematization increased the total number of jobs in the Department from 43 to 74 jobs. The department is organized so that it has three sections. The first, the Department for Execution of Extra-Institutional Sanctions and Measures, supervises the work of 16 organizational units and a total of 61 commissioners. Second, the Registry Department is the administrative base of the department. Thanks to the improvement of the Information System of the Administration (SAPA), it has become significantly better and enabled the probation officers to be relived of administrative tasks and to focus more on the supervision and treatment of convicts. During 2020, SAPA is fully adapted to the needs of the Department, and has been working at full capacity since the beginning of this year. The Third Department is legal and deals with legal regulations, but also makes recommendations for improving the legislative framework in order to make the execution of non-institutional sanctions and measures as effective as possible. |  |
| 3.1.1.19. | Conduct training for new commissioners for alternative sanctions. |  |  | -Administration for enforcement of criminal sanctions -Judicial Academy | Continuously, by the end of 2021 |  | Budget of the Republic of Serbia - 3.600 € in 2020. - 1.200 € in 2021. - 1.200 € in 2022. . 1.200 € |  | Training for new commissioners for alternative sanctions conducted. 7 new commissioners per year trained by the end of 2021. |  |  | Аctivity is being successfully implemented. Ministry of Justice – Administration for Enforcement of Criminal Sanctions reported, in the I quarter 2022, that trainings for new commissioners for alternative sanctions were conducted; 7 new commissioners trained annually until the end of 2021. In the II quarter 2022, Within the framework of the EU-financed project Improving the capacity of the prison administration in the area of ​​alternative sanctions, post-penal and health care, training was conducted for 6 trainers-trustees for the implementation of pro-social programs for the execution of house arrest sentences and training for 6 trainers-trustees for the implementation of the Program of preparation for the release of convicts and post-penal reception. In II quarter 2022, Judicial Academy in cooperation with the Ministry of Foreign Affairs of the Netherlands, has organized 1 one-day seminar in Kragujevac on the topic: ”Application of alternative sanctions in the legal system of the Republic of Serbia.’’ The trainings were attended by a total of 26 participants from the ranks of basic court judges, basic public prosecutors and their deputies and judicial associates. |  |
| 3.2. POSITION OF THE OMBUDSMAN, THE PROVINCIAL OMBUDSMAN AND LOCAL OMBUDSMEN |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.2.1. Serbia further amends the law on the Ombudsman so as to strengthen its independence in line with international standards Serbia strengthens the institutional capacity of its ombudsman structures, including its role as National Preventive Mechanism for Torture. Serbia actively and continuously gives public support to relevant independent human rights institutions. |  |  |  |  |  | The capacity of the Ombudsman, the Provincial Ombudsman-Ombudsman and the local services of the Ombudsman are strengthened and these institutions perform duties in their competence in full capacity. The Ombudsman acts as a national mechanism for the prevention of torture in accordance with the Optional Protocol to the Convention against Torture - formed a separate organizational unit of the NPM with an adequate number of employees and full organizational, functional and financial independence. |  | 1. The report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment stating that the capacity of the Ombudsman as a National Prevention Mechanism, are significantly enhanced; 2. Annual Report of the Ombudsman noting the improvement of the capacity of the Ombudsman, especially with regard to the national preventive mechanism for torture; 3. European Commission Annual Progress Report on Serbia stating progress in the part relating to the capacity of the Ombudsman, the provincial ombudsman and local ombudsman services; 4. Annual report of the National Prevention Mechanism (Ombudsman) noting improvement of the capacity of the national preventive mechanism for torture. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |
| 3.2.1.1. | Further strengthening the capacity of the professional service of the Ombudsman through facilitating full employment status, bringing total employment in line with current vacancies securing the necessary number and structure of the (Ombudsman) office. |  |  | -Ombudsman -National Assembly of the Republic of Serbia |  | For bringing total employment to 106 employees in line with new Rulebook on internal systematization.By IV quarter of 2021. | Budget of the Republic of Serbia- 183.816 € in 2021. - 91.908 € in 2022. - 91.908 € | Baseline in 2019: 88 civil servants Target: 106 civil servants Employment of 18 new civil servants, bringing total employment to 106 employees in line with new Rulebook on internal systematization. No reductions. |  |  |  |  | Activity is not implemented. In the reporting period, no new persons were hired in the Secretariat of the Protector of Citizens, while one employee had her employment terminated at her personal request by concluding an Agreement on Termination of Employment and one employee’s employment was terminated because she retired.. After the adoption of the new Rulebook on the internal organization and systematization of job positions in the Secretariat, the Protector of Citizens will harmonize the number of its employees in accordance with the available financial resources and the legal limitations prescribed by Article 27k of the Law on the Budget. Given that the new Law on the Protector of Citizens stipulates that the Protector of Citizens performs the duties of the National Independent Mechanism for monitoring the implementation of the United Nations Convention on the Rights of Persons with Disabilities and the duties of the National Rapporteur on trafficking in human beings, the Protector of Citizens requested to be provided with funds from the current budget reserves for the employment of four employees in 2022 for an indefinite period of time, with the title of senior advisers, who would be engaged in these positions. |
| 3.2.1.2. | Enable the premises for adequate long-term placement of the Ombudsman. |  |  | -Government of the Republic of Serbia |  | By the end of 2021. | Budget of the Republic of Serbia- 69.324 € | Adequate long-term placement of the Ombudsman secured and functional. The Ombudsman and professional service of the Ombudsman started working in the premises provided for adequate long-term placement. |  |  |  |  | Activity is not implemented. There have been no changes in the reporting period and, despite staffing changes, i.e. new staff, the Protector of Citizens is still located in the same premises, the capacity of which does not correspond to either the number of employees or efficient organization of work. The Protector of Citizens continuously informs the relevant authorities of the need to provide premises for appropriate, permanent accommodation for the institution of the Protector of Citizens. |
| 3.2.1.3. | Amend and supplement the Law on Ombudsman in order to strengthen independence and improve efficiency of work of the Ombudsman, particularly with regard to its operation as National Prevention Mechanism. |  |  | -Ministry of State Administration and Local Self-government -Ombudsman -National assembly |  | By IV quarter of 2020. | Budget of the Republic of Serbia- 48.900 € | Law on amendments and supplements to the law on Ombudsman enabling increased autonomy and improvement of the efficiency of the Ombudsman, particularly with regard to its operation as National Prevention Mechanism adopted. |  |  |  |  | Activity is fully implemented. The National Assembly of the Republic of Serbia adopted the new Law on the Protector of Citizens on 3 November 2021, which entered into force on 16 November 2021 |
| 3.2.1.4. | Adoption of the new Rulebook on organization and job systematization at the technical service of the Ombudsman in line with the amendments and supplements to the Law on Ombudsman. |  |  | -Ombudsman -National assembly |  | II quarter of 2021. | Budget of the Republic of Serbia- 8.642 € | New Rulebook on organization and job systematization at the technical service of the Ombudsman in line with the amendments and supplements to the Law on Ombudsman adopted. |  |  |  |  | Activity is partially implemented. Bearing in mind that the new Law on the Protector of Citizens stipulates that the Protector of Citizens performs the duties of the National Independent Mechanism for monitoring the implementation of the United Nations Convention on the Rights of Persons with Disabilities and the duties of the National Rapporteur for trafficking in human beings, as well as a special body that takes care of children's rights, during the drafting of the new Rulebook on internal organization and systematization of job positions in the Secretariat, the descriptions of job positions for civil servants who would perform the duties of these specified new competencies are determined, which requires a longer period of competence checks for those job positions. Bearing in mind the prescribed procedures for checking competences, the Rulebook, which will determine the number of employees necessary for the efficient performance of tasks within the competence of this body, will be adopted during the 4th quarter of 2022. |
| 3.2.1.5. | Effective follow up of Ombudsman’s recommendations issued to the state authority bodies of in the process of control. |  |  | -Government of the Republic of Serbia -Controlled body -Ombudsman |  | Continuously | Budget of the Republic of Serbia - 95.739 € in 2020. - 31.913 €, in 2021. - 31.913 €, in 2022. - 31.913 € | The state authority bodies fully comply with Ombudsman’s recommendations. |  |  |  |  | Activity is being successfully implemented. In the reporting period, the Protector of Citizens issued 123 recommendations to public authorities in control investigations. In the same period, 108 recommendations were due for execution, including those that were issued earlier and for which the deadline for action expired in the observed period. In the same period, the Protector of Citizens issued 279 recommendations to public authorities in expedited control investigations, which the authorities carried out immediately after learning that the Protector of Citizens had initiated the control investigation. |
| 3.2.1.6. | Regularly monitor the effectiveness of acting of the state authority bodies in line with the recommendations of the National Prevention Mechanism. |  |  | -Government of the Republic of Serbia -Controlled body -National Prevention Mechanism |  | Continuously | Budget of the Republic of Serbia – 63.825 € in 2020. - 21.275 € , in 2021. - 21.275 € in 2022. - 21.275 € | Full implementation recommendations of the National Prevention Mechanism by state authority bodies. |  |  |  |  | Activity is being successfully implemented. In the reporting period, the Protector of Citizens issued 93 recommendations to public authorities in carrying out the activities of the National Preventive Mechanism (NPM). During the same period,104 recommendations were due for execution, and this number also includes recommendations issued in the previous reporting period, which were due for execution in this reporting period. Out of that number, 92 recommendations were implemented by public authorities |
| 3.2.1.7. | Regular review of the report of the Ombusman by the National Assembly. |  |  | -National assembly |  | Continuously commencing from III quarter of 2019. | Budget of the Republic of Serbia Activity requiring insignificant costs | Report of the Ombusman is regularly reviewed by the National Assembly . |  |  |  |  | Activity is being successfully implemented The National Assembly considered and adopted conclusions for the Regular annual report of the Protector of Citizens for 2020 (December 29, 2021). Prior to that, this report was considered by the parliamentary committees and draft conclusions adopted were adopted, which were forwarded to the National Assembly. |
| 3.2.1.8. | Regular reporting of the Government on conclusions of the National Assembly adopted upon review of the report of the Ombusman by the National Assembly. |  |  | - Government of the Republic of Serbia |  | Continuously commencing from III quarter of 2019. | Budget of the Republic of Serbia Activity requiring insignificant costs | Government regularly reports to the National Assembly on conclusions adopted upon review of the report of the Ombusman by the National Assembly. |  |  |  |  | Activity is not implemented. No new data was provided |
| 3.3. FREEDOM OF EXPRESSION AND FREEDOM AND PLURALISM OF MEDIA |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.3.1. Serbia fully respects the independence of media, applies a zero-tolerance policy as regards threats and attacks against journalists, and prioritising criminal investigations should such cases occur. Serbia provides an initial track record of progress in the work of the "Commission for consideration of the facts that were obtained in the investigations that were conducted on the killings of journalists" including further investigations, effective prosecution and deterrent sanctions for perpetrators |  |  |  |  |  | More efficient protection of journalists against threats and violence ensured through improvement of the system of preventive measures undertaken for the purpose of protecting journalists and prioritization of investigations of threats and violence against journalists in order to effectively sanction past attacks. Achieved higher level of cooperation between the jounalists’ associations, the police and public prosecutors in relation to the protection of jounalists’ safety. |  | 1. European Commission Annual Progress Report on Serbia stating higher extent of protection of journalists against threats and violence; 2.Annual report of the Ombudsman noting higher extent of protection of journalists against threats and violence; 3.Increased number of actions undertaken by the prosecutors’ office in order to ensure protection of journalists, as well as prosecution of the perpetrators of criminal offences against journalists; 4. Finalization of the investigation in three cases of killings of journalists within the scope of work of Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists. 5. Substantial improvement of the position of Serbia on internationally recognized press freedom indexes. Baseline: 2019 Press Freedom Index by Reporters without borders Serbia is positioned as 90 among 180 Countries with score of 31.18) 2019 Freedom in the World from Freedom house Serbia has score 2 in Freedom of expression segment (max score =1, min score =4) |  |  |  |  |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  |  |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |
| 3.3.1.1. | Analyze the relevant provisions of the Criminal Code in order to assess potential need for amendments and supplements that would lead to a higher level of protection of journalists from threats of violence, taking into account the results of the TAIEX Expert Mission on the Protection of Journalists in the Criminal Code JHA IND/ EXP 63971. | - Republic Public Prosecutor's Office in cooperation with a permanent working group that monitors the implementation of the Agreement on Cooperation and Measures for Improving the Safety of Journalists |  |  |  | By IV quarter of 2020. | Budget of the Republic of Serbia – 8.642 € | Analysis of the Criminal Code developed including recommendations for establishment of a more efficient protection of journalists against threats and violence. The conclusions arising from the analyses related to a potential need for amendments and supplements to the Criminal Code submitted to the Ministry of Justice for consideration. |  |  |  |  | Activity is fully implemented. The working subgroup for the analysis of the Criminal Code of the Republic of Serbia was established in accordance with the Agreement on Cooperation and Measures for Raising the Level of Safety of Journalists, signed on 26 December 2016. It consisted of representatives of all parties, mostly lawyers and attorneys who are legal representatives of journalists' and media associations. Representative of the OSCE Mission to Serbia also attended the meetings of the working subgroup. The working subgroup for the analysis of the Criminal Code held its first meeting on November 1, 2018, on which occasion the members of the subgroup agreed on expected results of the work: 1. Identification of criminal offenses that may be considered criminal acts against safety of journalists, in connection with the performance of their work; 2. Introduction of such identified criminal acts into the internal acts of the Ministry of Internal Affairs and the Republic Public Prosecution Office (mandatory instructions, guidelines for action); 3. Possible initiative for amendment of the Criminal Code. In accordance with the defined activities, the working subgroup in the period from 7 November to 27 December 2018 held three meetings and conducted an analysis of criminal offenses foreseen by the Criminal Code. At the fifth meeting, held on 31 January 2019, all criminal acts and legal issues in connection with which there were certain doubts were considered. Each article of the Criminal Code was analysed in details, act of execution of criminal act and passive subject (aggreieved party) were discussed and after sharing different opinions members of the working subgroup identified 35 criminal acts that can be committed against safety of journalists, in connection with the work they perform. The conclusion of the working subgroup was rendered on 1 February 2019. The members of the Permanent Working Group adopted the conclusion of the working subgroup for the analysis of the Criminal Code at the meeting held on 2 April 2019. Members of the working subgroup agreed that the signatory parties of the Agreement would submit any reasoned proposals for amendments to the Criminal Code later. So far no proposal has been made. It should be noted that the Republic Public Prosecutor, in accordance with the conclusion of the Working Subgroup for the Analysis of the Criminal Code, on 24 December 2020 passed the Mandatory Instruction on the performance of public prosecution's offices in criminal cases against safety of journalists by which the previous Instruction was repealed. |
| 3.3.1.2. | Continuation of the work of the Commission for consideration of the facts obtained during the investigations conducted on the killings of journalists and provision of regular reports. | -Government of the Republic of Serbia -Commission for consideration of the facts that were obtained in the investigations that were conducted on the killings of journalists |  |  |  | Continuously | Budget of the Republic of Serbia - 6.915 € in 2020. - 2.305 € in 2021. - 2.305 € in 2022. - 2.305 € | Annual reports on the work of the Commission submitted. Responsible authorities regularly follow up on the recommendations of the Commission through investigations and prosecution. |  |  |  |  | Аctivity is being successfully implemented. In the case of the murder of journalist Slavko Ćuruvija, after the second trial, the same first-instance verdict of a total of 100 years in prison was handed down for four defendants. The same court panel gave an identical rationale for the second time. The appeals were filed with the Appellate Panel by the defence of the accused and the prosecutor. A court panel has been formed to decide on these appeals. We expect the Appellate Chamber to give a final verdict and confirm the first-instance sentence. In the case of the unresolved death of journalist Radislava Dada Vujasinović, there was no progress. As has been repeatedly pointed out, given that this death case was conducted as a suicide for 12 years, and due to the fact that the on-site investigation was poorly done, with numerous pieces of evidence missing, the Commission could not do more than requesting super-expertise which was conducted in the Netherlands by the Netherlands Forensic Institute. However, it could not specify the cause of death. Based on the existing materials, it was determined that the only conclusion is that three options are possible: suicide, murder and accidental firing. The prosecution is still holding the case open. In the case of the murder of journalist Milan Pantić, the competent prosecutor has been changed, but there is no significant progress in the investigation. The Commission continues to insist that the Prosecutor's Office for Organized Crime take over jurisdiction over this case (which has been refusing to do so for years, explaining that there is not enough evidence that it is an organized crime group). Working group of the Ministry of the Interior is still working on the investigation. Due to the retirement, the Commission was left without two very important members who have been the supporting pillars of the Commission's work since its inception from the Security Information Agency and the Ministry of Interior. One of the members of the commission is also the head of the Working Group for solving the case of Milan Pantić. Chairman of the Commission will prepare proposals for the reconstruction of this body, which he will send to the new Government of the Republic of Serbia when it is formed. The Commission resumes its work. |
| 3.3.1.3. | Regular updating of special records in the appellate, higher and basic public prosecutor's offices in relation to criminal offences committed against persons performing occupations that are of importance to public information, in connection with the affairs they perform, as well as attacks on the media websites, in which cases urgent acting is prescribed. | - Republic Public Prosecutors’Office |  |  |  | Continuously | Budget of the Republic of Serbia - 2.553 € in 2020. - 851 € in 2021. - 851 € in 2022. - 851 € | Instructive guidelines on forming the separate records of criminal offenses committed against journalists and attacks on media internet sites, and designating priority in acting upon these criminal offenses adopted. Special records referred to in this activity are regularly updated. |  |  |  |  | Activity is being successfully implemented. The activity is carried out continuously. In this reporting period, the appellate public prosecutor's offices also submitted to the Republic Public Prosecutor's Office monthly reports of the regional public prosecutor's offices on the handling of cases against the safety of journalists, based on data from a special record on criminal offenses in this area. The consolidated records of the Republic Public Prosecutor's Office are updated monthly, as well as drafting of the report on the actions of the public prosecutor's office in this matter. |
| 3.3.1.4. | Implementation of a cooperation agreement of the Republic Public Prosecutor's Office and the Ministry of Interior, stipulating acting in the investigation of threats and violence against journalists as a priority in order to improve the efficiency of the investigation of the attacks on journalists and prosecution of the perpetrators. | -Republic Public Prosecutor's Office -Ministry of Interior |  |  |  | Continuously | Budget of the Republic of Serbia Activity requiring insignificant costs | Increased number of actions undertaken by the prosecutors’ office and the Ministry of Interior, on the basis of implementation of the cooperation agreement resulting in more efficient investigation and prosecution against defendant. Number of organized meetings of the Permanent Working Group; Contact points and coordinators for handling cases in this area designated. Number of criminal reports filed by the Ministry of the Interior at the request of the Republic Public Prosecutor's Office, against the perpetrators of criminal offenses to the detriment of journalists. The established obligation to act urgently in cases of criminal offences committed to the detriment of journalists implemented in practice; |  |  |  |  | Activity is being successfully implemented. In the period from March 9 to 10, 2022, a training "Protection and Security of Journalists" for 25 police officers was organized by the European Union and the Council of Europe "Freedom of Expression and Freedom of the Media in Serbia (JUFREH 2)". In I quarter 2022, no physical attacks on media representatives were registered, except for two verbal attacks, of which the competent prosecutor's office in Požarevac and Čačak was informed. Also, three threats were registered in Belgrade to media representatives by phone and social networks. In one case, the prosecutor's office qualified the event as a criminal offense of endangering security and criminal charges were filed against one person, and in two cases the police submitted reports to the competent prosecutor's office. In the period from May 11 to 12, 2022, the training "Protection and safety of journalists" was held for 25 police officers, organized by the European Union and the Council of Europe "Freedom of expression and freedom of the media in Serbia (JUFREX 2)". In the period from April to June 2022, no physical attacks were registered on media representatives while performing their professional activities, and four verbal attacks were reported (Belgrade - three, Niš - one). One criminal report was filed for the criminal offense of endangering security (Belgrade), and in other cases, reports were submitted to the competent prosecutor's office. One threat was registered via social networks (in Belgrade), about which a report was submitted to the competent prosecutor's office. |
| 3.3.1.5 | Implementation of the Cooperation Agreement among the Public Prosecutors' Office, Ministry of Interior and relevant associations of journalists. | -Republic Public Prosecutors' Office -Ministry of Interior -Representatives of the associations of journalists |  |  |  | Continuously | Budget of the Republic of Serbia 51.855 € 17.285 annually | Regular meetings of the permanent working group. Minutes from the meetings of the permanent working group. Annual report of the permanent working group publicly available. |  |  |  |  | Activity is being successfully implemented. The activity is carried out continuously. The permanent working group held a meeting on May 30, 2022 where statistical data on the actions of public prosecutors’ offices in criminal cases against the journalists' safety, as well as data on actions in individual cases of interest to representatives of journalistic and media associations, were presented. In addition, the meeting discussed the report of the Slavko Ćuruvija Foundation regarding the work of prosecutor's offices in cases from this area, as well as the question of the necessity of further training of journalists, representatives of the prosecutor's office and the police, and steps to improve the work of the Permanent Working Group. In addition, on June 15, 2022, members of the Permanent Working Group visited the employees of OK Radio in Vranje in order to learn in detail about the problems journalists are facing. On that occasion, meetings were held with the higher and basic public prosecutor in Vranje and representatives of the local media, while on the same day a meeting was held in Niš with the appellate, higher and basic public prosecutor in Niš. |
| 3.3.1.6. | Improve the system of measures taken to protect the safety of journalists through: - use of the established mechanism of cooperation between the public prosecutor's office, police, journalist associations and media associations; - training of journalists and media owners on the possibilities of criminal protection and the basics of information security; - training for members of the prosecution and police in order to better understand the issues and to act more effectively in cases where the security of journalists is compromised. | -Republic Public Prosecutor's Office in cooperation with a permanent working group that monitors the implementation of the Agreement on Cooperation and Measures for Improving the Safety of Journalists -Ministry of Interior |  |  |  | Continuously | Budget of the Republic of Serbia- 2.553 € in 2020.- 851 € in 2021. - 851 € in 2022. - 851 € | System of measures undertaken for the purpose of protection of journalists’ safety improved in cooperation with representatives of journalists’ associations. Regular consideration of the risk of threat to the safety of journalists through the work of the Permanent Working Group, which monitors the implementation of the Cooperation Agreement and measures to raise the level of journalists’ safety. Consideration of the work of the established mechanism of cooperation by the Permanent Working Group. Training of journalists and media owners on the possibilities of criminal protection and the basics of information security organized. Training for members of the prosecution and police held to better understand the issues and to act more effectively in cases where the safety of journalists is compromised. |  |  |  |  | Activity is being successfully implemented. Within the project "Freedom of expression and freedom of the media in Serbia JUFREX 2" in the period from 27 to 29 January 2021, a training for trainers on "Protection and security of journalists" was held, which was attended by 12 members of the Ministry of Interior. All participants received a handbook for trainers containing relevant information on international, European and domestic standards as well as methodology. The next joint training where the newly trained coaches will transfer their knowledge to other colleagues is planned for July 2021, and three more trainings are also planned by the end of this year. Deputy public prosecutors designated as contact points continued their cooperation with contact points in the police and journalistic and media associations. The subject of cooperation in most cases refers to the reporting of criminal offenses and the exchange of information. Members of the Permanent Working Group are involved if needed, for possible coordination of actions. |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.3.2. Through the implementation of the Strategy for the Development of Public Information System, Serbia takes active measures for reforming its media landscape thus creating an enabling environment for freedom of expression, based on transparency (including on ownership of media), integrity and pluralism |  |  |  |  |  | Improved legal and institutional framework for the protection of media freedoms. Achieved full withdrawal of state ownership of the media. Absence of unauthorized disclosure of information related to ongoing or planned criminal investigations to the media. |  | 1. European Commission Annual Progress Report on Serbia stating progress concerning freedom of expression and media; 2. Annual report of the Ombudsman noting higher level of protection of media freedoms; 3. Number of disciplinary proceedings regarding media leaks about ongoing or planned criminal investigations. 4 Substantial improvement of the position of Serbia on internationally recognized press freedom indexes. Baseline: 2019 Press Freedom Index by Reporters without borders Serbia is positioned as 90 among 180 Countries with score of 31.18) 2019 Freedom in the World from Freedom house Serbia has score 2 in Freedom of expression segment (max score =1, min score =4) |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  |  |  | IMPLEMENTATION STATUS |
| 3.3.2.1. | Implementation and efficient monitoring the implementation of the set of media laws and periodic reporting. |  |  | -Ministry for culture and information |  | Continuously, through annual reports. | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Reports of the Ministry for culture and information indicating effective implementation of the set of media laws are publicly available. |  |  |  |  | Аctivity is being successfully implemented. In this reporting period, ten calls for proposals were implemented for co-financing projects for the realization of public interest in the field of public information in 2022: 1. Open call for co-financing projects for production of media content for print media and news agencies in 2022; 2. Open call for co-financing projects for organizing and participating in professional, scientific and appropriate gatherings as well as the improvement of professional and ethical standards in the field of public information in 2022; 3. Open call for co-financing projects for production of media content in the languages of national minorities in 2022; 4. Open call for co-financing projects for production of media content intended for persons with disabilities in 2022; 5. Open call for co-financing projects for production of media content for internet media in 2022; 6. Open call for co-financing projects for the production of media content for radio in 2022: 7. Open call for co-financing projects for production of media content for Serbian people in the countries of the region in 2022; 8. Open call for co-financing projects for the production of media content that are implemented through electronic media whose publishers are based in the territory of AP Kosovo and Metohija in 2022; 9. Open call for co-financing projects for production of media content for televisions in 2022; 10. Open call for proposals for co-financing projects for production of media content that promote and affirm topics in the field of culture in 2022. The Ministry of Culture and Information continues with the implementation of activities in supervising the implementation of the law in terms of giving opinions on the application of certain provisions of the law. |
| 3.3.2.2. | Strengthening the capacities of the Ministry of Culture and Information in order to improve the monitoring and the quality of reports on implementation of the set of media laws. |  |  | -Ministry for culture and information |  | Commencing from IV quarter of 2020 | Budget of the Republic of Serbia IPA 2019-2020 | Increased number of staff. Number of professional trainings held for staff. The quality and type of information in periodic reports on the implementation of a set of media laws have improved. |  |  |  |  | Аctivity is being successfully implemented. In I quarter 2022, One person was hired on the basis of contracts for occasional and temporary jobs. Two representatives of the Ministry of Culture and Information participated in the Training for Reporting on the Implementation of the Action Plan for Chapter 23: Justice and Fundamental Rights (AP 23) supported by the EU for Justice project funded by EU IPA 2017 funds. The representative of the Ministry of Culture and Information attended the workshop of the Expert Group of the Coordination Flow for Improving the Position and Social Inclusion of Roma Men and Women and monitoring the implementation of the Strategy for Social Inclusion of Roma Men and Women in Serbia for 2016-2025, organized by the Ministry of Human and Minority Rights and Social Dialogue, with the support of the Regional Cooperation Council. The representative of the Ministry of Culture and Information attended the training "eInvoice - Application of electronic invoice system" which was held on February 28, 2022, in the building of the National Academy of Public Administration. The training was conducted as part of the training of civil servants for the implementation of the new Electronic Invoice System. A representative of the Ministry of Culture and Information attended the training "How to use pivot tables in excel", which was held on March 4, 2022 through the platform of the National Academy (NAPA webex). In II quarter 2022, one person was hired based on contracts for occasional and temporary jobs. The representatives of the Ministry of Culture and Information attended the following trainings: - Webinar "Instrument for Pre-Accession Assistance of the European Union (IPA II and IPA III)"; - Workshop of the Expert Group of the Coordination Flow for Improving the Position and Social Inclusion of Roma Men and Women and monitoring the implementation of the Strategy for Social Inclusion of Roma Men and Women in Serbia for 2016-2025, organized by the Ministry of Human and Minority Rights and Social Dialogue, with the support of the Regional Cooperation Council; - Monitoring of the online expert roundtable - The role of the public service media in countering disinformation organized by the OSCE. |
| 3.3.2.3. | Adopt Action Plan for implementation of the new multiannual Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025, in particular focusing on: -further enhancement of transparency of media ownership, -follow up on effects of media privatization, -prevention of media control resulting from excessive dependence on state financed advertising, -strengthening media pluralism, - strengthening media literacy, -strengthening co- and self-regulation. |  |  | -Ministry for culture and information - Government of the Republic of Serbia |  | IV quarter of 2020. | Budget of the Republic of Serbia Activity requiring insignificant costs | Action plan for the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025 adopted. |  |  |  |  | Activity is fully implemented. On December 3, 2020, the Government adopted an Action Plan for the implementation of the Strategy for Development of the Public Information System Republic of Serbia for the period 2020-2025, in the period 2020-2022. On December 10 2020, the Government passed the Decision on the formation of the Working Group for monitoring the implementation of the Action Plan for the implementation of the Strategy for the Development of the Public Information System in the Republic of Serbia for the period 2020-2025, in the period 2020-2022. Also, the Government passed the Decision on the formation of the Working Group for Security and Protection of Journalists. |
| 3.3.2.4. | Implementation of the new multiannual Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025 and its Action Plan. Establishing clear mechanism for monitoring implementation of the Strategy. |  |  | -Ministry for culture and information |  | For implementation: Continuously, commencing from II quarter of 2020 | Budget of the Republic of Serbia 17,285 € per year For the work of the working group: 17,285 € -The implementation budget will be specified in the AP of the Strategy IPA 2019 | Effective implementation of the Action Plan confirmed through monitoring precise indicators provided in the AP. Reports on implementation of the Action Plan publicly available. Alternative reports of the associations of journalists indicate level of implementation. |  |  |  |  | Аctivity is being successfully implemented. In I quarter 2022, one meeting was held of the Working Group for monitoring the implementation of the Action Plan for the implementation of the Strategy for the Development of the Public Information System in the Republic of Serbia for the period 2020-2025 and the report on the work of the Working Group for 2021 is in the finalization phase. In II quarter 2022, two meetings of the Working Group for monitoring the implementation of the Action Plan for the implementation of the Strategy for the Development of the Public Information System in the Republic of Serbia for the period 2020-2025 were held. When it comes to the safety of journalists, the Working Group for the Safety and Protection of Journalists held two meetings where cases of attacks and threats to which journalists are exposed were discussed. In order to strengthen media literacy, the Ministry of Culture and Information has conducted the following activities: - an intersectoral plan for the development of media and information literacy in the media environment was prepared; - the conference "Digital immunity - media culture in the digital age" was held, organized by the Ministry of Culture and Information. |
| 3.3.2.5. | Conditions created for the full functionality, transparency and update of the Media Registries and/or media registers in accordance with the activities of the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025 (Measure 2.1 in the Strategy) |  |  | -Ministry for culture and information -Business Registers Agency |  | Continuously, commencing from III quarter of 2019. | Budget of the Business Registers Agency * Costs are to be borne by Business Registers Agency | Efficient comprehensive and transparent Registry of the media ownership structure established in accordance with the new Strategy for the Development of the Public Information System in the Republic of Serbia for the period 2020-2025. Data on media ownership structure in the Registry regularly updated. Registry enables access to data on provision of public funds, the basis for the provision of public funds and the ownership. |  |  |  |  | Activity is partially implemented. The Action Plan for the implementation of the media strategy envisages that the technical improvement and search of the Media Register and its connection with other public registers will be carried out by the end of the fourth quarter of 2022. Only after the amendments of the relevant regulations, can the software solutions be developed to connect these registers. The Action Plan envisages that this activity will be realized by the end of the validity of the Action Plan (activity 2.1.2 in the Action Plan). |
| 3.3.2.6. | Efficient monitoring of the functioning of Registry of the media ownership in line with the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025, through data collection and follow up. |  |  | -Ministry for culture and information -Business Registers Agency |  | Continuously | Budget of the Republic of Serbia- 2.553 € in 2020. - 851 € in 2021. - 851 € in 2022. - 851 € | Published annual reports in accordance with the mechanism envisaged in the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025. Number of rejected media when applying for the competition as a result of the lack of registration in the Register. |  |  |  |  | Аctivity is being successfully implemented. The Ministry of Culture and Information regularly monitors the work of the Media Register both through electronic insight into registered data and through giving instructions to media service providers who have dilemmas regarding taking certain actions in the process of registering legally prescribed data. In the open calls for proposals announced by the Ministry of Culture and Information in 2022. in the field of public information, six decisions were made on the rejection of applications-requests for co-financing of projects because it was determined that the applicant did not have the right to participate in the open call for proposal considering that they did not have all the data entered in the Register media in accordance with the Law on Public Information and Media. |
| 3.3.2.7. | Ensure efficient functioning of a comprehensive and transparent Registry of media services and record of providers of on demand media services and regular update of the data, in line with Law on Electronic Media including data on ownership of the providers of media services, and data on the exercise of media pluralism. |  |  | -Regulatory authority of electronic media |  | Continuously | Budget of the Regulatory authority of electronic media * Costs are to be borne by Regulatory authority of electronic media | Relevant data on media services and record of providers of on demand media services publicly available at the website of Regulatory authority of electronic media, including data on ownership of the providers of media services, and data on the exercise of media pluralism. Data on media services and providers of media services in the Registry regularly updated. |  |  |  |  | Аctivity is being successfully implemented. Тhe Regulatory Authority of Electronic Media (hereinafter: Regulator) has established a Register of media services (hereinafter: Register), which contains all the information required by Article 86 of the Law on Electronic Media, including the data on ownership of every single media services provider, as well as register of MSPs that provide services solely via the global information network/internet (Web casting, live streaming, etc.) in accordance with Article 74, paragraph 1, item 2 and Article 86 of the Law on Electronic Media. The Register is available on the website of the Regulator and is regularly updated: http://rem.rs/sr/registar-pruzalaca-medijskih-usluga. In addition, any interested party may, at the premises of the Regulator, look over the Register or to request to make data (in the Register) available to them by other means. To date, no request has been submitted for the issuance of an authorization for the provision of on-demand media services, and therefore no authorization has been issued so far, in terms of Article 75 of the Law on Electronic Media. The Regulator does not have the legal possibility to sanction the possible broadcasting of media services on request without approval, because it is not prescribed as a offense in the Law on Electronic Media to broadcast without approval of the Regulator. In the Register, five MSPs are registered and they are providing on-demand media services exclusively through the global information network/internet (Web casting, live streaming, etc.). |
| 3.3.2.8. | Effective monitoring over the implementation of the Ethics code of Journalists of Serbia for the purpose of promoting self-regulation and respect of ethical and professional standards, strengthen professional integrity and increase visibility of the Press Council. Measures continuously pronounced by Regulatory authority for electronic media in line with the law. |  |  | -Press Council -Regulatory authority for electronic media, for the part of activity related to electronic media |  | Continuously | Budget of the Press Council * Costs are to be borne by the Press Council | Regular reports of the Press Council indicating efficient acting upon submitted complaints. Regular reports of the Regulatory authority for electronic media on imposed measures for electronic media. Number and structure of decisions on citizens' complaints filed for violation of the Code of Journalists of Serbia. Priority in the project co-financing of production of media content under equal conditions is given to the media that comply with the laws and the Code of Journalists of Serbia, that is, which have less pronounced measures by Regulatory authority for electronic media and less decisions and public reprimands by the Press Council. Reports of the Press Council containing statistics on the measures imposed published twice per year. |  |  |  |  | Аctivity is being successfully implemented. The Regulator imposed 1 measure in the reporting period. All measures imposed so far are publicly available and published on the website: http://rem.rs/sr/odluke/izrecene-mere |
| 3.3.2.9. | Enhance professional conduct of media service providers and journalists considering EU best practices, through training in the field of - human rights -media ethics -hate speech |  |  | -Ministry for culture and information Partners: --Press Council - CSOs -Anticorruption council -Regulatory authority of electronic media |  | Continuously | Budget of the Republic of Serbia 2.553 € in 2020. - 851 € in 2021. - 851 € in 2022.- 851 € IPA 2019-2020 | Number of trainings held. Number of complaints regarding professional conduct of journalists and media service providers. Reports of relevant watchdog organizations indicating higher degree of professional conduct of journalists and media service providers. |  |  |  |  | Аctivity is being successfully implemented. A workshop for journalists and media is being organized by the Ministry of Culture and Information, in the field of the impact of artificial intelligence on freedom of expression and freedom of media for media and journalist associations and state authorities. According to the latest Reporters Without Borders Report for 2022, the Republic of Serbia is in 79th place according to the media freedom index, which is 14 places better than the position it held in the previous year. Regarding the number of complaints on the work of media service providers, for the reporting period, it was 68. For each of the complaint/ application, Regulator’s expert department inspected the specific program content and prepared report for the Council, which further acted in accordance with legal powers. |
| 3.3.2.10. | Effectively monitor the functioning of the system of co-financing media projects from the budgetary and/or public financial resources pursuant to new legislation on project funding of media. |  |  | -Ministry for culture and information -Provincial secretariat for Culture and Information -Local self-government units |  | Continuously | Budget of the Republic of Serbia - 31.914 € In 2020-2022 10.638 € per year Budget of AP Vojvodina - costs currently unknown Local self-government budget - costs currently unknown | Efficient mechanisms for monitoring the functioning of the system of co-financing media projects from the budgetary and/or public financial resources pursuant to new legislation on project funding of media established through: -introduction and effective implementation of the obligation of public authority bodies to regularly submit reports on co-financing media projects. -analysis of public authority bodies on the quality of the supported projects based on beneficiaries’ reports on funds disbursement. Data from external evaluation of project implementation made available to the public through the publication of reports |  |  |  |  | Аctivity is being successfully implemented. In this reporting period, the Ministry of Culture and Information worked on reports of implemented projects, which were supported in 2021. The work on the preparation of the subject reports will continue in the following period after which will be published on the official website of the Ministry. Based on the results of the evaluation, the Ministry will project priority topics and missing media content for the upcoming call for proposals and will also base on it the planning of trainings for improving the professional and ethical capacities of journalists and media workers. In order to improve the transparency of project co-financing and better insight into the project implementation process, in January 2022, the Ministry of Finance adopted the Regulation on the conditions and criteria for the compliance with state aid in the field of public information. This Regulation also prescribes the obligation of the state aid provider to develop an effective mechanism for monitoring and reporting on the granted aid. Based on the Regulation on the conditions and criteria for compliance of state aid in the field of public information ("Official Gazette of the RS" No. 9/22), four tenders were announced, namely: Open call for co-financing projects for production of media content in the languages of national minorities in 2022, Open call for the co-financing of media content production projects intended for persons with disabilities in 2022, Open call for the co-financing projects for production of media content for televisions in 2022 and Open for proposals for co-financing projects for production of media content that promote and affirm topics in the field of culture in 2022, while the remaining six tenders were announced on the basis of the Regulation on the rules and conditions for the award of de minimis aid ("Official Gazette of RS", number 23/21). When considering the projects, the Commission also had in mind guidelines for defining and justifying the costs of projects for the production of media content and organizing professional, scientific and appropriate gatherings in the field of public information. Also, the Ministry has developed a single application form for members of the open call commissions in the field of public information of the Ministry of Culture and Information, which will enable all proposals for potential members of the commission to submit an identical set of data, which will facilitate easier selection of the most competent representatives and media experts. The Provincial Secretariat for Culture, Public Information and Relations with Religious Communities, as the administrative body announcing the competition of co-financing media projects from the budget, renders a decision on the allocation of funds on the basis of a reasoned proposal of the commission. Beneficiaries of funds to whom funds have been approved for the implementation of projects, submit a narrative and financial report on the implemented project activities, in accordance with the agreed obligations. And after the completion of project co-financing in the current year, the Secretariat reviews the narrative and financial report on the implemented project activities, as well as evidence of project implementation. |
| 3.3.2.11. | Create a regulatory framework in the field of public information and advertising by the public authority bodies and companies owned or funded mainly by the state (Measure 2.6. in the Media Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025). |  |  | - Ministry for culture and information - Ministry for Trade, Tourism, and Telecommunications |  | From 2021 | Budget of the Republic of Serbia – 51.855 € 17.285 € per year | Improved Media Registry in which all state subsidies are recorded (public procurement, competitions, other types of contracts with the media). |  |  | Аctivity is being successfully implemented. An analysis of the regulatory framework in the field of advertising is underway, with special reference to the problems related to advertising of public authorities and companies majority owned or financed by the state. The action plan envisages that after conducting an analysis of the regulatory framework in the field of advertising, with special reference to the problems related to advertising of public authorities and companies majority owned or financed by the state, an initiative to adopt a new or amend existing regulations, as a precondition for creating equal market conditions for all media (activity 2.3.2). The body that implements this activity is the Ministry of Culture and Information, which, after the analysis, will send proposals to the line ministries, in which way it would be most efficient to regulate this area. A working version of the Draft Law on Amendments to the Law on Public Information and Media has been prepared, comprising two parts - the part that all members of the Working Group agreed on and consensus was reached, and the second part of which no consensus has been reached. In the reporting period the Ministry of Culture and Information is undertaking the necessary activities in order to provide the necessary financial resources for the analysis of the regulatory framework in the field of advertising. |  |  |
| 3.3.2.12. | Effectively monitor the use of tax deductions, budgetary funds and/or other forms of state aid which represents potential source of influence on media independence, through: - Improving legal provisions regarding the entry of data into the Media Register; -Introduction of obligation for public authority bodies to report all state aid to media in the Media Registry - Clear specification of sanctions and sanctioning failure to report all state aid to Media Registry in line with Article 137 of the Law on Public Information and Media) |  |  | - Ministry for culture and information in cooperation with Commission for state aid control, based on the data of public authority bodies at all levels -Business Registers Agency |  | Continuously | Budget of the Republic of Serbia 31.914 € In 2020-2022 - 10.638 € per year | Efficient monitoring over use of tax deductions, budgetary funds and/or other forms of state aid which represents potential source of influence on media independence established and implemented through: - reports of public authority bodies on all state aid to media available in Media Registry -regular sanctioning of public authority bodies for a failure to report all state aid to media in the Media Registry Media Registry improved and data contained therein easily accessible, including information about all state aid provided to media.Analyses of relevant media market performed and published. Measures imposed in cases of unauthorised media concentration. |  |  | Аctivity is being successfully implemented. The Ministry of Culture and Information - Work on amendments to the Law on Public Information and Media will continue after the formation of the Government of the Republic of Serbia. Business Registers Agency - The Media Register does not contain data on tax relief and other forms of state aid as a possible source of influence on media independence, because these data are not prescribed as the subject of registration. The Media Register is not authorized to sanction public authorities for not reporting data on funds allocated for the purpose of co-financing of projects in the field of public information for the realization of public interest, nor to determine unauthorized concentration of media. |  |  |
| 3.3.2.13. | Monitoring of concentration in the media in accordance with the Law on Protection of Competition and the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025. |  |  | -Commission for Protection of Competition |  | Continuously | Budget of Commission for Protection of Competition * Costs are to be borne by Commission for Protection of Competition | Annual reports including an overview of the imposed sanctions, proceedings and opinions submitted to the National Assembly and publicly available confirms the monitoring of concentration in the media. Analyses of media concentration published. |  |  | Activity is being successfully implemented. In II quarter 2022, the Commission for the Protection of Competition adopted a decision on the suspension of the examination of the concentration of market participants in the media sector. On the last day of the reporting period (June 30, 2022), there were no ongoing procedures for examining the concentration of market participants in the media sector. |  |  |
| 3.3.2.14. | Established measurable criteria for determining the thresholds for permissible media concentration and the risk of media pluralism, in addition to the share in viewership, listening and circulation (Measure 2.2. in the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025) · |  |  | -Ministry for culture and information -Regulatory authority of electronic media - Republic Agency for Electronic Communications and Postal Services |  | In line with AP for Media Strategy | Budget of the Republic of Serbia 8.642 € | Analyses of relevant media market performed and published. Amended regulation in line with the results of media market analyses. Imposed measures in cases of unauthorized media concentration. |  |  | Activity is being successfully implemented. The Ministry of Culture and Information is working intensively on the implementation of activities related to the analysis of the relevant media market at the national, regional and local levels, and on that occasion sought technical support through IPA project proposal and PLAC instrument with the Ministry of European Integration. Work on amendments to the Law on ublic Information and Media will continue after the formation of the Government of the Republic of Serbia. In the reporting period, the Regulator did not impose any measure due to the established existence of violations of media pluralism. |  |  |
| 3.3.2.15. | Determining the existence of violation of media pluralism. |  |  | ### - Ministry for culture and information -Regulatory authority of electronic media |  | IV quarter of 2020. | Budget of the Republic of Serbia - 8.642 € | Performed and published analyses of the relevant media market with recorded cases of violation of media pluralism in accordance with European standards. |  |  | Аctivity is being successfully implemented Work on amendments to the Law on Public Information and Media will continue after the formation of the Government of the Republic of Serbia. In the reporting period, the Regulator did not impose any measure due to the established existence of violations of media pluralism. 16 requests were submitted for obtaining prior consent to the act on transfer of the license for providing media services and / or change of ownership structure, and for all, the Regulatory Council issued a decision approving the status change and / or planned change of ownership structure. |  |  |
| 3.3.2.16. | Develop Program of Communication of the Ministry of Interior with the media aimed at defining relationship, methods and scope of communication. |  |  | -Ministry of Interior |  | III quarter of 2021. | Budget of the Republic of Serbia – 8.642 € | Program of Communication of the Ministry of Interior with the media aimed at defining relationship, methods and scope of communication developed. |  |  | Activity is fully implemented. On October 18, 2021, the Minister of the Interior adopted the Directive on the Conduct of Police Officers and Other Employees in the Ministry of the Interior in Relation to the Media |  |  |
| 3.3.2.17. | Amendment and supplements to the Law on Public Prosecution which prescribe that disciplinarly offences in the part relating to the accountability of public prosecutors and deputy public prosecutors for unauthorized communication of information about ongoing or planned investigations to the media, in order to enable subsequent amendments and supplements to the Code of Ethics and the Rules of the disciplinary proceedings and disciplinary responsibilities of public prosecutors and deputy public prosecutors. . |  |  | -Ministry of Justice -State Prosecutorial Council |  | I quarter of 2021. | Budget of the Republic of Serbia – 8.642 € | Amendment and supplements to the Law on Public Prosecution which prescribe that disciplinarly offences in the part relating to the accountability of public prosecutors and deputy public prosecutors for unauthorized communication of information about ongoing or planned investigations to the media adopted. Amendment and supplements to the Code of Ethics and the Rules of the disciplinary proceedings and disciplinary responsibilities of public prosecutors and deputy public prosecutors adopted. |  |  | Activity is not implemented. Amendments and supplements to the Law on Public Prosecution are planned within the course of changes that will arise from constitutional amendments. |  |  |
| 3.3.2.18. | Monitoring implementation of the Law on Police stipulating that unauthorized communication to the media represents serious breach of duty. |  |  | -Ministry of Interior |  | Continuously | Budget of the Republic of Serbia – Budgeted in Chapter 24 | Number of disciplinary proceedings in cases of violations of the law initiated. |  |  | Аctivity is being successfully implemented. Тhere are no registered records in the reporting period. From 1st October to 31st December 2021 a total of 602 violations were recorded, 150 minor violations of official duty under Article 206 of the Law on Police, and 452 serious violations of official duty under Article 207 of the Law on Police. From Article 206 of the Law on Police, Item 19, which reads "Self-initiated appearance of police officers and other employees in the public and the media in connection with the work, which caused or could cause harmful consequences for the reputation of the Ministry" recorded one violation official duties. |  |  |
| 3.3.2.19. | Monitoring implementation of the Code of Police Ethics and law governing internal affairs in the part relating to the responsibility of police officers for unauthorized communication of information about ongoing or planned investigations to the media. |  |  | -Ministry of Interior |  | Continuously | Budget of the Republic of Serbia – Budgeted in Chapter 24. | Disciplinary proceedings in cases of violations of the law initiated. |  |  | Activity is partially implemented. Тhere are no registered records in the reporting period. |  |  |
| 3.3.2.20. | Amendments and supplements to the bylaws governing the procedures of confidentiality and safety of planning and conducting criminal investigations in order to improve the privacy and protection of police procedures for the planning and implementation of criminal investigations. |  |  | -Ministry of Interior |  | IV quarter of 2020. | Budget of the Republic of Serbia – 8.642 € | Amendments and supplements to the bylaws governing the procedures of confidentiality and safety of planning and conducting criminal investigations in order to improve the privacy and protection of police procedures for the planning and implementation of criminal investigations adopted. |  |  | Activity is fully implemented. Mandatory Instruction on Criminal Operational Work of the Police was adopted on the 19th of July 2021. Mandatory instruction on Crime-Operational Work of the Police determines the manner of organization and implementation of crime-operational work of the police in preventing, detecting and proving criminal acts and their perpetrators and it will be applied starting 45 days from the day of enactment. |  |  |
| 3.3.2.21. | Adopt a by-law which establishes procedures for issuing statements of police officers to the media. |  |  | -Ministry of Interior |  | IV quarter of 2020. | Budget of the Republic of Serbia – 8.642 € | By-law which establishes procedures for issuing statements of police officers to the media adopted. |  |  | Activity is fully implemented. On October 18, 2021, the Minister of the Interior adopted the Directive on the Conduct of Police Officers and Other Employees in the Ministry of the Interior in Relation to the Media. |  |  |
| 3.3.2.22. | Conduct training for public prosecutors, deputy public prosecutors, police officers and representatives of relevant associations of journalist, with regard to: - prevention of media leaks related to ongoing or planned criminal investigations - prevention of media leaks related to respect for privacy with regard to vulnerable persons (victims, children). |  |  | -Judicial Academy Partners: - Associations of journalists -Civil society organizations - Press council -Republic Public Prosecutors’ Office -Commissioner for Information of Public importance and personal data protection |  | Continuously, by IV quarter of 2021 | Budget of the Republic of Serbia - 3.600 € 1.200 € per year | Training for public prosecutors, deputy public prosecutors, police officers and representatives of relevant associations of journalist conducted. Participants improved their knowledge related to ongoing or planned criminal investigations and prevention of media leaks related to respect for privacy with regard to vulnerable persons (victims, children). |  |  | Аctivity is being successfully implemented. During the I quarter of 2022, the Judicial Academy, in cooperation with the joint project of the European Union and the Council of Europe, "Freedom of Expression and Freedom of the Media in Serbia (JUFREX 2)" organized two two-day trainings on "Protection and Security of Journalists" in Belgrade and Vrdnik for a total of 49 participants. In the I quarter 2022, Judicial Academy, in cooperation with a joint project of the European Union and the Council of Europe titled ‘’Freedom of Expression and Freedom of the Media (JUFREX 2)’’ has conducted 2 two-day trainings on the topic “Protection and safety of journalists’’, in Aranđelovac and at Kopaonik, for a total of 41 participants. Also, in the reporting period, a regional conference for judges, prosecutors and lawyers on the topic: “Freedom of Expression”, in Durrës, Albania, which was attended by representatives of the Judicial Academy. Also, in the reporting period, two online trainings of the HELP course program with the support of the Council of Europe were held, on the topic: “Freedom of Expression” and “Protection and Safety of Journalists”, for a total of 24 participants. In the II quarter of 2022, a total of four trainings were held on the topic: “Courts and public relations through the prism of Communication strategy and freedom of expression” and “The importance of strategic communication with the media and the public”, for judges, prosecutors and spokespersons in courts. In the II quarter of 2022, on 17/06 and 22/06/2022, two thematic trainings were held for employees of public prosecutor's offices (First, Second, Third Basic Public Prosecutor's Office in Belgrade and Higher Public Prosecutor's Office in Belgrade) on the topic of the application of the "Law on Personal Data Protection", with the total 42 participants. |  |  |
| 3.3.2.23. | Ensure independence of public media services, improve professionalism, exercise of program functions in the public interest, as well as accountability to the public in accordance with the activities defined in the Media Strategy |  |  | -National assembly (public information committee) -Assembly of Autonomous Province of Vojvodina (public information committee) -Ministry for culture and information -RTS, RTV -Regulatory authority of electronic media Partners for surveys |  | Continuously | Budget of the Republic of Serbia - 30.878 € Budget of the Autonomous Province of Vojvodina - Specific amounts shall be available in the AP for the Media strategy | Amended regulation in the field of public media services. Citizens' satisfaction and confidence in the quality of program content of public media services (to be measured through the surveys). Level of fulfillment of legal obligations in the production of media content (Report of the Regulatory authority of electronic media). Established channels of communication with the public. Developed internal Codes. |  |  | Аctivity is being successfully implemented. The Regulator continuously, i.e. on an annual level, prepares reports on the fulfillment of legal and program obligations of the public broadcasters - Radio-Television of Serbia and Radio-Television of Vojvodina, but also the obligations of commercial MSPs. The latest report was prepared and adopted by the Council for the year 2020, and all four are published on the website: http://rem.rs/sr/izvestaji-i-analize/izvestaji-i-analize-o-nadzoru-emitera/izveshtaji#gsc.tab=0 Amendments to the regulations, ie amendments to the Law on Public Service Media, which is envisaged through activity 3.3.2 of the Action Plan, by the end of the third quarter of 2022, will ensure the strengthening of the independence of public service media. The improvement of professionalism, realization of the program function and responsibility towards the public will be realized through the activities envisaged from 3.3.4-3.3.12, which will be implemented continuously until the end of the validity period of the said Action Plan. The Ministry of Culture and Information is in the process of conducting consultations and making proposals for the implementation of these activities. In accordance with Article 37 of the Agreement on Improving the Conditions for Holding Elections of October 29, 2021, concluded in the National Assembly between political parties participating in the Inter-Party Dialogue, amendments were made to the Law on Public Service Media, namely Article 7 of the Law, which deals with the public interest achieved by the public service media |  |  |
| 3.3.2.24. | Ensure unified treatment of all media with status of tax debtor or with an agreement on rescheduling of debt. |  |  | -Ministry of finance -Tax administration |  | Continuously | Budget of the Republic of Serbia – 3.063 € in 2020-2022 - 1.021 € per year | Unified treatment of all media with status of tax debtor or with an agreement on rescheduling of debt ensured. Annual reports of the Tax administration. |  |  | Activity is being successfully implemented. The Tax Administration undertakes all measures of regular and forced collection for all taxpayers that have a tax debt regardless of their predominant activity. Also, all of them are eligible for reprogram if they meet the terms proscribed by the law, regardless of their predominant activity. |  |  |
| 3.3.2.25. | Reduce and make transparent the influence of the state on the media market in order to ensure equal market conditions for all media (in accordance with the Measure 2.3. in the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025) |  |  | -Ministry for culture and information Partners: -Ministry of Finance, -Ministry of Trade, Tourism and Telecommunications |  | Commencing from III quarter of 2020 | Budget of the Republic of Serbia – 2520 € in 2020-2022 - 840 € per year | Amendments to the regulations adopted to ensure equal market conditions for all media. The number of companies in which the state has a stake in the founding rights of media publishers is reduced to zero. |  |  | Activity is partially implemented. When it comes to the privatization of publicly owned media publishers, it was not completed only in the case of Politika ad, while contracts on the sale of capital were terminated with Radio-Television Kragujevac and Nedeljne novine from Backa Palanka. Completion of the privatization process in the company Politika a.d. Belgrade, i.e. resolving the status of a company depends on regulating the relationship with the creditor through a reorganization plan prepared in advance in accordance with the Bankruptcy Law. A reorganization plan prepared in advance has been prepared and the approval procedure is underway. For media publishers whose contracts on the sale of capital have been terminated, a plan of activities has been prepared that will be undertaken in the coming period for the implementation of this activity and consists of the following: - In the Draft Law on Amendments to the Law on Public Information and Media, it is necessary to include provisions that would regulate the procedure of privatization of media publishers in relation to which contracts on sale of capital were terminated so that their privatization is finally completed by selling capital or transfer of capital without compensation to employees, ie liquidation or bankruptcy in case employees do not accept transfer of capital without compensation (define the deadline for publishing a public invitation for sale of media publishers in the production of media content to be changed to two instead of five years from the date of concluding the contract; in the event that the capital of the media publisher is not sold within the prescribed period, the capital shall be offered to employees free of charge; if employees do not accept the free transfer of capital, the media publisher is obliged to initiate liquidation or bankruptcy proceedings); - After the entry into force of that law, the Ministry of Economy will conduct the procedure of privatization of media publishers within the deadlines determined by legal provisions. |  |  |
| 3.3.2.26. | Making publicly available budget disbursement reports including: -50 largest buyers and suppliers -contracts with independent production and marketing agencies -official results of competitions for selection of program including selection criteria |  |  | -Public service broadcasters -Regulatory authority of electronic media |  | Continuously, in line with the dynamics of submiting the reports to the National Assembly | Budget of the Republic of Serbia – 1407 € in 2020-2022 - 469 € per year. Budget of the Public service broadcasters – regular activity | Publicly available budget disbursement reports including -50 largest buyers and suppliers -contracts with independent production and marketing agencies -official results of competitions for selection of program including selection criteria |  |  | Аctivity is being successfully implemented. Pursuant to the Law on Public Media Services, Article 19, paragraph 1, item 15, the Management Board adopts the report on the operation of public media service and submits it further on to the National assembly, Regulator's Council and informs the public. Article 52 of the same Law implies that RTS and RTV annually submit reports on previous year activities accompanied by the independent auditor's report to the national assembly for consideration and decision-making. This report is also submitted to Regulator's Council for informative purposes. Pursuant to the Article 51 of the Law on Public Media Services, RTS and RTV submitted to the Regulator Annual Report for 2019 with the Report of an independent auditor, adopted by the RTS and RTV Management Boards, for informative purposes. Pursuant to the Article 51 of the Law on Public Media Services, RTS and RTV submitted to the Regulator Annual Report for 2020 with the Report of an independent auditor, adopted by the RTS and RTV Management Boards (RTV also submitted for 2021, while it is still waiting for RTS - it is usually submitted during the first or second quarter of next year), for informative purposes. Pursuant to the Article 51 of the Law on Public Media Services, RTS and RTV submitted to the Regulator Annual Report for 2021 with the Report of an independent auditor, adopted by the RTS and RTV Management Boards, for informative purposes. |  |  |
| 3.3.2.27. | Complete the process of privatization of publicly owned publishers, in order to establish an equal market position of the media and to prevent inappropriate influence on editorial policy. |  |  | -Ministry of commerce |  | Until the finalization of privatization process | Budget of the Republic of Serbia- 5.745 € in 2020-2022 - 1915 € per year | Full transparency of media privatization procedure achieved. All relevant documents regarding privatization of media publicly available. Privatized media in line with the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025. |  |  | Аctivity is being successfully implemented. The privatization process of publicly owned publishers is conducted transparently, in accordance with the principle of ensuring publicity and transparency on which privatization is based. The sale of capital of media publishers is carried out in a transparent manner, by public collection of bids with public bidding. All contracts on the sale of capital of media publishers are published on the website of the Ministry of Economy. The five-year period of monitoring the implementation of contracts on the sale of capital of publicly owned publishers, which were concluded in 2015, in accordance with the Law on Privatization (“Official Gazette of RS”, No. 83/14, 46/15, 112/15 and 20/16 - authentic interpretation) and the Law on Public Information and Media (“Official Gazette of RS” No. 83/14 and 58/15), and the privatization of almost all publishers of publicly owned media was carried out. As of the date of this report, there are only three publicly owned publishers in the portfolio of the Ministry of Economy. Completion of the privatization process of publicly owned publishers is being conducted in accordance with the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025. We would like to point out that exit of the State from the „Politika“ Belgrade and resolving the status of the company „Politika“ Belgrade depends on defining Pre-packed plan for reorganization in accordance with the Bankruptcy Law. The privatization of media publishers whose contract have been terminated will be carried out in accordance with the privatization plan of media publishers Ministry of Economy and the Ministry of Culture and Information, which is yet to be defined. |  |  |
| 3.3.2.28. | Examine ex officio the conflict of interest in the media. Anti-corruption Agency and Anti-corruption Council hold periodical meetings and exchange relevant data in order to enhance coordination. |  |  | -Anti-corruption Agency -Anti-corruption Council |  | Continuously, until the conclusion of the examination. | Budget of the Republic of Serbia- 3.831 €– in 2020-2022 - 1.277 € per year | Potential breach of regulations by the officials in management bodies of the media with state capital in relation to conflict of interest as well as officials who concurrently own private media examined. Reports of ACA on potential conflict of interest in the media. Reports of Anti-corruption Council |  |  | Activity is fully implemented. The examination has been finalized and proceedings terminated. In the reporting period there were no meetings with the representatives of the Anti-Corruption Council. |  |  |
| 3.3.2.29. | Review of financial reports of parliamentary political parties in line with the Program adopted by the State Audit Institution. |  |  | -State Audit Institution |  | In each election circle | Budget of the Republic of Serbia – 3.831 € in 2020-2022 - 1.277 € per year | Financial reports of political parties reviewed in line with the Program adopted by the State Audit Institution. |  |  | Activity is being successfully implemented. In December 2021, the State Audit Institution adopted the Audit Program for 2022, in accordance with the Law on the State Audit Institution. The Audit Program contains appropriate number of political parties that will be audited during 2022. Hence, in April 2022, SAI commenced financial statement and compliance audit process with 4 political parties, namely: Socialist Movement, Belgrade, Democratic Party, Bujanovac, Alliance of Vojvodina Hungarians, Subotica and Alternative for Change, Presevo. The mentioned audit processes are in progress and will be completed in compliance with the Audit Program for 2022. |  |  |
| 3.3.2.30. | Ensure organizational, functional and financial independence of the Regulatory Body for Electronic Media and improve its professionalism, as well as its accountability to the public (Measure 3.2. in the Strategy for the Development of Public Information System in the Republic of Serbia for the period 2020-2025.) |  |  | -Ministry for culture and information Partners: -Ministry of Trade, Tourism and Telecommunications -Regulatory body for electronic media |  | Continuously | Budget of the Republic of Serbia - 25.926 € 8.642 € per year | Legal status and powers of the Regulatory body for electronic media adapted to its scope of work. Number of actions taken by Regulatory body for electronic media against media service providers who have breached their obligations. Level of independence of the Regulatory body for electronic media assessed by the INDIREG method; Established communication channels of the Regulatory body for electronic media with the public. |  |  | Activity is partially implemented. Work on amendments to the Law on Electronic Media is planned after the formation of the new Government. The Regulator imposed 1 measure. All measures imposed so far are publicly available and published on the website: http://rem.rs/sr/odluke/izrecene-mere. In connection with the violation of the Law on Advertising, the Regulator continuously, on a monthly basis, submits requests for initiating misdemeanour proceedings against commercial MSPs. All requests, as well as court decisions, are published on the website of the Regulator: www.rem.rs. The Regulator, in accordance with the law governing free access to information of public importance, on its website, makes publicly available all acts prescribed by Article 38 of the Law on Electronic Media. Also, on the Regulator's website, there is an e-mail address, as well as a telephone number, to which every citizen can call or send a complaint, suggestion, etc. |  |  |
| 3.3.2.31. | Undertaking activities involving trainings, seminars that contribute to the advancement of professional and ethical standards in the field of photography in the media through work on developing professional visual content and raising the level of media literacy. |  |  | -CSOs in cooperation with the Press Council journalists associations and photographers associations |  | During the year, in cycles until all media in Serbia are covered by education | Budget of the Republic of Serbia – through projects Apply for donor funds | Achieved competitiveness of the media through professional visual media content that sells the media product, concurrently attracting and educating the media consumer. Media professionals understand visual media literacy, its importance for freedom of expression, objective reporting, and apply acquired knowledge to an extent that meets the public interest. |  |  | Activity is not implemented. No data available. |  |  |
| 3.4. PRINCIPLE OF NON-DISCRIMINATION AND SOCIAL POSITION OF VULNERABLE GROUPS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.4.1. Serbia implements the Strategy and action plan on anti-discrimination and adopts amendments to the Law on Prohibition of Discrimination in line with the EU acquis. Serbia ensures adequate institutional capacity for their implementation. Serbia monitors closely the impact of these two instruments - including as regards the full respect of the rights of LGBTI persons - and takes remedial action where required. |  |  |  |  |  | Strategic and normative framework for anti-discrimination in line with the EU acquis adopted and implemented. Effective mechanism to monitor the situation in the field of discrimination operational. The position of the LGBTI community promoted and the respect of their rights and freedoms secured. |  | 1. European Commission Annual Progress Report on Serbia stating progress in part relating to anti-discrimination; 2. Annual report of the Commissioner for the Protection of Equality stating progress of Serbia in the field of anti-discrimination; 3. Concluding remarks of the UN Committee on the Elimination of Racial Discrimination (CERD), ascertaining the progress of Serbia; 4. Annual report of the Ombudsman noting higher level of protection of rights of vulnerable groups; 5. Report of the European Commission against Racism and Intolerance (ECRI) noting progress in the field of anti-discrimination; 6. Number of held and prohibited public gatherings. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.4.1.1. | Adoption of the new Strategy for prevention and protection from discrimination. |  |  | -Government of the Republic of Serbia -Ministry of Labour, Employment, Veterans and Social Affairs |  | IV quarter of 2020. | Budget of the Republic of Serbia – 17.285 € | Action Plan for the implementation of the Strategy for prevention and protection from discrimination adopted. |  |  | Activity is being successfully implemented. The Strategy for Prevention and Protection against Discrimination, for the period 2022 - 2030 was adopted at the Government session on 20 January 2022, and published in the "Official Gazette of the Republic of Serbia" no. 103 of 1 February 2022, and on the website of the Ministry, and the goals and measures defined in this public policy document have been entered into the Public Information System of the Republic of Serbia. The Ministry of Human and Minority Rights and Social Dialogue, with the support of the UN Human Rights Team, has started drafting the Action Plan (2022-2024) for the implementation of the Strategy for Prevention and Protection against Discrimination for the period 2022 - 2030. To this end, an expert team was formed with which the Ministry held three meetings, followed by a consultative meeting with representatives of civil society organizations. During the reporting period, the Proposal of the Action plan (2022-2023) for implementing the Strategy for prevention and protection from discrimination for period 2022-2030 has passed the consultation process (11-21 April) and the public debates (10-29 June). The meeting of the Special working group for drafting this document was held along with a number of meetings with the expert team with the largest focus on the budgeting elements of the document. |  |  |
| 3.4.1.2. | Monitoring implementation of the Strategy for prevention and protection from discrimination and its Action Plan. |  |  | -Council for monitoring implementation of the AP for the Strategy for prevention and protection from discrimination |  | Continuously, commencing from adoption of the AP | Budget of the Republic of Serbia 51.855 € 17.285 € per year | Reports on implementation of the Strategy for prevention and protection from discrimination and its Action Plan developed and publicly available. |  |  | Activity is not implemented. Given that the Action Plan (2022-2024) for the implementation of the Strategy for Prevention and Protection against Discrimination for the period 2022 - 2030 was not adopted in the reporting period, it was not possible to start the implementation of this activity. |  |  |
| 3.4.1.3. | Continuation of the work and strengthening capacities of mechanism of the Government of the Republic of Serbia for the implementation of all the recommendations of UN mechanisms for human rights. |  |  | -Government of the Republic of Serbia |  | Continuously | Budget of the Republic of Serbia- 6.915 € in 2020-2022 - 2.305 € per year | The mechanism of the Government of the Republic of Serbia for the implementation of all the recommendations of UN mechanisms for human rights functions effectively and holds regular meetings. |  |  | Activity is being successfully implemented. At the initiative of the Platform of Organizations for Cooperation with UN Mechanisms, the Council for Monitoring the Implementation of the United Nations Human Rights Recommendations held a thematic session on 7 February 2022, at which findings from the report "Forgotten Children of Serbia", prepared by Disability Rights International – DRI and the Mental Disability Rights Initiative of Serbia - MDRI-S, were discussed. The participants agreed that the issue of children in institutions is not a matter that can be resolved by a single sector, and that it requires multisectoral approach, but also cooperation between the Government and civil society organizations. At the second thematic session held on 9 February 2022, ten shadow reports were presented which civil society organizations and the Faculty of Law of the University of Belgrade had submitted to the Committee on Economic, Social and Cultural Rights. Ahead of the consideration of the Report on the implementation of the International Covenant on Economic, Social and Cultural Rights, the Council gathered for the first time in one place members of the state delegation, who will present the state report to the United Nations Committee on Economic, Social and Cultural Rights, and representatives of all CSOs and Faculty of Law who submitted shadow reports to the Committee on Economic, Social and Cultural Rights, to jointly discuss key findings of the Report. The session was also attended by representatives of the National Assembly of the Republic of Serbia, independent bodies (Commissioner for Information of Public Importance and Personal Data Protection, Commissioner for Protection of Equality and Protector of Citizens), United Nations Human Rights Team in Serbia, Council of Europe and OSCE Mission to Serbia. The participants concluded that this type of joint dialogue between state institutions and civil society is useful not only for presenting reports on the implementation of international obligations that our country has assumed by ratifying international human rights treaties, but also for finding adequate solutions for protecting and promoting human rights of all citizens, especially those belonging to most vulnerable social groups. The Third Periodic Report of the Republic of Serbia on the implementation of the International Covenant on Economic, Social and Cultural Rights was considered in the dialogue between the delegation of the Republic of Serbia and members of the Committee on Economic, Social and Cultural Rights, conducted online, from 21 to 23 February 2022. After considering the state report, on 4 March 2022, the Committee adopted Concluding Observations. These Observations contain 38 recommendations that Serbia should implement by the next reporting cycle, i.e. by 31 March 2027. The Committee requested the State party to report within 24 months on three priority recommendations given in paragraphs 17 (b) (human rights defenders), 19 (a) (national action plan on business and human rights) and 31 (b) and (c) (identification documents). On May 16, 2022 at the thematic session of the Council for monitoring the implementation of recommendation of the UN mechanism for Human Rights, the Ministry has presented the Draft Report of the 4th and 5th periodic report of the Republic of Serbia for implementation of the Convention on the Right of a Child. The representatives of the independent bodies, SCO, as well as children-representing the Child informative-cultural service DX operating within the framework of the Center for the Right of a Child were attending the meeting. They had the opportunity to express their views and standpoints on the implementation of the Convention on the Right of a Child in front of decision makers, being of particular importance and relevance to the recommendation of the Committee for the Right of a Child that encourages the State to pay special attention to the opinions of children and enhance the creation of a meaningful space for children to influence public policies. Their opinions and views are included in the State Report. For the first time since the beginning of the reporting process to UN Treaty Bodies, the Republic of Serbia has also submitted the Annex to the Report containing the views and opinions of the CSO on implementation of recommendations of the Committee in the Republic of Serbia. On May 19, 2022 the Government of the Republic of Serbia has adopted the 4th and 5th Periodic Report on the the implementation of the Convention for the Right of a Child. Following this Government session, the Reports were submitted to the UN Committee for the Right of a Child. The upated Common Core document on the Republic od Serbia has been submitted jointly with the Period Report, since the Governement of the Republic of Serbia has adopted it on May 26, 2022 and has thus fulfilled this obligation as well. |  |  |
| 3.4.1.4. | Amendments and supplements to the Law on Prohibition of Discrimination to fully align with the EU Acquis and in particular with regard to: -volume of exceptions from the principle of equal treatment, -definition of indirect discrimination -obligation to provide the reasonable accommodation for employees with disabilities. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs -Commissioner for the Protection of Equality -National assembly |  | IV quarter of 2020. | Budget of the Republic of Serbia – 48.900 € | Amendments and supplements to the Law on Prohibition of Discrimination adopted, enabling full alignment with the EU Acquis , in particular with regard to: -volume of exceptions from the principle of equal treatment -definition of indirect discrimination -obligation to provide the Reasonable accommodation for employees with disabilities. |  |  | Activity is fully implemented. The Law on Amendments and Addenda to the Law on Anti-Discrimination was adopted in the National Assembly of the Republic of Serbia in the Assembly sitting on May 20, 2021 and it entered into force on May 31, 2021. |  |  |
| 3.4.1.5. | Strengthening the capacity of the Office of Human and Minority Rights, in order to efficiently implement the tasks set in the Strategy for prevention and protection against discrimination through the recruitment of new employees. |  |  | -Office of Human and Minority Rights |  | IV quarter of 2020. | Budget of the Republic of Serbia- 21.275 € | Capacity of the Office of Human and Minority Rights to efficiently implement the tasks set in the Strategy for prevention and protection against discrimination strengthened through employment of new employees. |  |  | Activity is not implemented. The formation of the Ministry of Human and Minority Rights and Social Dialogue and the drafting of the Rulebook on Internal Organization and Job Systematization envisages additional capacity building in the area of monitoring anti-discrimination policies. In this regard, it should be underlined that the above regulation, inter alia, stipulates that this ministry shall take over from the Ministry of Labor, Employment, Veterans and Social Affairs employees working in the field of anti-discrimination policy and gender equality; seven employees were taken over on the take-over date. The Rulebook on Internal Organisation and Job Systematisation in the Ministry of Human and Minority Rights was adopted by the Government in the meeting held on May 20, 2021 and the Rulebook entered into force on May 26, 2021. The Rulebook envisages establishing of a Sector for Antidiscrimination Policy and Gender Equality Promotion within which a Department for Antidiscrimination Policy will be formed, with five working posts. The Sector is managed by the Assistant to the Minister and currently two employees are employed with the Department and in order to fill the remaining posts with the Department, it will be necessary to conduct a competition procedure, in compliance with the Law. * Note: this activity does no longer refer to the OHMR, given the establishment of the ministry |  |  |
| 3.4.1.6. | Strengthening the capacity of the Commissioner for the Protection of Equality in accordance with the existing job classification by hiring 23 new employees. |  |  | -Commissioner for the Protection of Equality |  | Continuously, by 2021 | Budget of the Republic of Serbia 382.950 € in 2020.- 191.475 € in 2021. - 191.475 €. | Capacity of the Commissioner for the Protection of Equality strengthened in accordance with the existing job classification by hiring 23 new employees. Baseline: currently employs 37 employees. Target: 60 employees. |  |  | Аctivity is being successfully implemented. In accordance with the law, the Commissioner has a Professional Service, which, since the establishment of the institution, has been constantly developing and strengthening its capacities, taking into account planned and rational staffing. The Professional Service has a total of 37 persons employed, two of whom are deployed in the Office of the Commissioner in Novi Pazar. During the reporting period, there were no takeovers of civil servant job positions, nor were there any invitations to public competitions. |  |  |
| 3.4.1.7. | Monitoring the implementation of the Law on Anti-discrimination. |  |  | -Commissioner for the Protection of Equality -Ministry in charge for anti-discrimination |  | Continuously | Budget of the Republic of Serbia- 159.564 € in 2020. - 53.188 € in 2021. - 53.188 € in 2022. - 53.188 € | Annual report of the Commissioner for the Protection of Equality indicating the state of play in the field of anti-discriminaton, with a particular focus on the most vulnerable groups. |  |  | Аctivity is being successfully implemented. In the period from January 1, 2022 to March 31, 2022, the Commissioner for the Protection of Equality acted in 137 cases, of which 129 were complaints, seven recommendations of measures and five opinions on draft acts were given. In the period from April 1, 2022 to June 30, 2022, the Commissioner for Protection of Equality acted in 281 cases, of which 97 were complaints, 178 recommendations of measures, eight opinions on draft laws and other general legal documents, six initiatives for amending regulations, one proposal for assessing constitutionality and legality and one criminal charge were given. |  |  |
| 3.4.1.8. | Conduct regular training and professional development of employees in the institution of the Commissioner for Protection of Equality in order to improve their professional skills in the field of anti-discrimination. |  |  | -National Academy for Public Administration -Commissioner for the Protection of Equality |  | Continuously, in line with annual training program | Budget of the Republic of Serbia - 3.600 € in 2020. -1.200 € in 2021. -1200 € in 2022. -1200 € | Training conducted and professional development sessions held. Percentage of employees in the institution of the Commissioner for Protection of Equality who participated in trainings. |  |  | Аctivity is being successfully implemented. During the reporting period, employees of the Commissioner for the Protection of Equality participated in numerous conferences, seminars and other gatherings dedicated to the fight against discrimination and the promotion of equality. |  |  |
| 3.4.1.9. | Training of civil servants in relation to legal and institutional framework in the Republic of Serbia, the concept and forms of discrimination, as well as the role and jurisdiction of the Commissioner for the Protection of Equality. |  |  | -National Academy for Public Administration |  | Continuously, in line with annual training program | Budget of the Republic of Serbia - 3.600 € in 2020. -1.200 € in 2021. -1200 € in 2022. -1200 € | Report on the number of civil servants who participated in the trainings, including the topics covered. |  |  | Аctivity is being successfully implemented. The National Academy for Public Administration has conducted the General Training Programme for civil servants, General Training Programme for employees in local self-government units, Training Programme for managers in government bodies and Training Programme for managers in local self-government units, adopted by the Government of the Republic of Serbia. The General Training Programme for civil servants for 2021, within the thematic area “Protection of human rights and data protection”, envisaged the following trainings: Protection against discrimination, Discrimination before public bodies, Gender equality. The Sectorial continuous professional development programme for employees in local self-government units, being the part of the General Training Programme for employees in LSGU for 2021, envisaged among others the following trainings: Gender equality in local self-government, Gender equality at local level – online training and Protection against discrimination in local self-government units within the thematic area “Exercise, protection and improvement of human and minority rights”. |  |  |
| 3.4.1.10. | Development and distribution of a manual ​​on identification and effective suppression of discrimination cases in Serbian and languages of national minorities for: - judges -public prosecutors and deputy public prosecutors, - police officers, -employees in the state administration and local self-government |  |  | -Commissioner for the Protection of Equality |  | Distribution of manual: Continuously For translation and printing in the languages of national minorities: from IV quarter of 2020 | Budget of the Republic of Serbia Costs currently unknown | Manual ​​on identification and effective suppression of discrimination cases developed and distributed in all courts, prosecutors' offices and police departments, as well as local self-government units. Number of trainings and workshops for staff in public authority bodies where the manuals were distributed to the participants. |  |  | Activity is being successfully implemented. The printing of the manual was completed and the training was organized. In the reporting period I quarter 2022, the Commissioner held the following trainings for employees of public authorities: 1. Young lawyers from the Prosecutor's Office, courts and lawyers from all over Serbia, within the program "Human Rights Defenders", in partnership with the Institute for European Affairs with the support of the Embassy of the United States of America in Belgrade in Kragujevac 2. The Club for Social Relations of the Faculty of Law, University of Belgrade paid a study visit to the Commissioner for the Protection of Equality, during which a lecture was held on the competencies of the institution and the procedure before the Commissioner. 3. Peer educators of the Autonomous Women's Center, within the preventive program "I can to not want" 4. Participants of the Academy of Equality, in cooperation with the Divac Foundation, online In II quarter 2022, the Commissioner held the following trainings for employees of public authorities, different professional groups and the general public: -Training on Gender Equality for 11. class of students at the Higher Studies of Security and Defense (20 participants); -Training "Discrimination, gender equality and protection mechanisms" for 4th grade students of the Elementary School "Rudjer Boskovic" (5 participants); -Training "Role and jurisdiction of the Commissioner for Protection of Equality" for employees of the Ministry of Trade, Tourism and Telecommunications (12 participants); -Training on gender equality within program "Gender equality in the practice of higher education and scientific-research institutions" for newly appointed Equality Commissioners at the University of Belgrade (20 participants); -Training "Prevention of violence and discrimination against Roma women living in rural areas" for Roma health mediators, local Roma coordinators, Roma activists and CSO representatives, National Employment Service and social work centers employees (15 participants); -Training "Assessment of the impact of regulations and public policies on sensitive social groups" for civil servants, CSO, Danish Refugee Council and IOM representatives (30 participants). |  |  |
| 3.4.1.11. | Development and distribution of a manual ​​on identification of discrimination cases and available mechanisms for protection of rights in Serbian and languages of national minorities for the citizens and particularly national minorities. |  |  | -Commissioner for the Protection of Equality |  | By IV quarter of 2020. | Budget of the Republic of Serbia Costs currently unknown | Manual ​​on identification of discrimination cases and available mechanisms for protection of rights developed and distributed in the premises of the local self- government units, educational institutions, health centres and hospitals and other institutions established by local self-government units and CSOs acting in the territory of local self-government. |  |  | Activity is fully implemented. Тhe Commissioner for the Protection of Equality has prepared a publication in Serbian and Romani "Recognize and report discrimination", which is intended to acquire basic knowledge about discrimination and protection mechanisms. Also, brochures on how to file complaints have been issued in Albanian, Bulgarian, Czech, English, Hungarian, Macedonian, Romani, Romanian, Ruthenian, Slovak, Bosnian and Croatian, which are available in electronic form. In addition, the leaflets "Who is the Commissioner" were published in the following languages: Serbian (Cyrillic and Latin alphabet), English, Bulgarian, Romani (for the area of Vojvodina and Arles), Albanian, Croatian, Hungarian and Bosnian. |  |  |
| 3.4.1.12. | Conduct media promotional campaign and organize roundtables aimed at promoting the Manual for identification and effective suppression of discrimination cases s and the Manual for identification of cases of discrimination and available mechanisms for protection of rights. |  |  | -Commissioner for the Protection of Equality |  | I and II quarter of 2021. | Budget of the Republic of Serbia Costs currently unknown | Media campaign conducted and roundtables aimed at promoting the Manual for identification and effective suppression of discrimination cases s and the Manual for identification of cases of discrimination and available mechanisms for protection of rights organized. |  |  | Activity is fully implemented. As of June 2021, the Commissioner for the Protection of Equality fully realized this activity. Namely, as stated in the submitted previous reports, in the period from January 2017 to June 2021, the Commissioner implemented activity 3.4.1.12. through the implementation of various round tables where the manual was presented, delivering numerous workshops for representatives of public authorities (line ministries, local governments), media, civil society organizations, trade unions, employers' associations, participation in various events and the like. |  |  |
| 3.4.1.13. | Organize workshops for journalists and programme editors aimed at preventing incitement to discrimination through media. |  |  | -Ministry for culture and information -Commissioner for the Protection of Equality -Representative Association of Journalists -Civil society organizations -Team for social inclusion and reduction of poverty (SIPRU) |  | At least one workshop per year, commencing from II quarter 2020. | Budget of the Republic of Serbia- 3.600€ in 2020.- 1.200 € in 2021.- 1200 € in 2022.- 1200 € | Workshops for journalists and programme editors in order to prevent incitement to discrimination through media organized each year across country. |  |  | Аctivity is being successfully implemented. Commissioner for Protection of Equality - During the reporting period, preparations were made for the upcoming two-day training for representatives of REM, UNS, NUNS, the Press Council, editors and journalists of print and electronic media, dedicated to combating discrimination and hate speech, with special reference to the position and rights of LGBTI people. Training will take place, as planned, in July 2022 within the project "Promotion of Diversity and Equality in Serbia", as a part of EU and CoE Program "Horizontal Facility for the Western Balkans and Turkey 2019-2022". The Ministry of Culture and Information is working on creating workshops that will be conducted by the end of 2022. |  |  |
| 3.4.1.14. | Continue the development of a model of community policing, particularly in multi-ethnic and multicultural communities, by implementing security prevention in partnership with other state and local entities and contributing to the development of tolerance in society. |  |  | -Ministry of Interior -Partners CSOs |  | Continuously. | Budget of the Republic of Serbia – 51.855 € 17.285 € per year and Donor funds within the Mixed Commission of the Government of Serbia and the Government of the Federal State of Baden Virtenberg IPA 2019 | Established and operational model of community policing, particularly in multi-ethnic and multicultural communities and in partnership with other state and local entities. |  |  | Аctivity is being successfully implemented. According to the Program of professional training of participants in basic police training for the position of police officer for community work, which was adopted on March 23, 2022, the training of 371 participants in basic police training for the specified position is in progress. With the aim of strengthening the capacity of police directorates for full implementation of measures and more efficient performance of tasks related to prevention and community policing, on 11 and 12 May 2022, representatives of the Uniformed Police Directorate held instructive meetings with officers for prevention and community policing from the Police Directorate for the City of Belgrade and regional police directorates, at the premises of the SIV-2 building. With relation to this, after those instructive meetings, in accordance with the Program content of the optional classes “Community policing”, during May 2022, delegated police officers conducted the so-called “Training of trainers” for managers in police stations/offices delegated for monitoring, directing and control of community policing who will, with the support of officers for prevention and community policing in UPD/PD, conduct optional classes for police officers of general jurisdiction in PS/PO, no later than 15 December 2022. In order to improve performing the tasks of prevention and community policing, Uniformed Police Directorate made a dispatch No 214-139319/2022 dated 30 May 2022, ordering police directorates to intensify their police activities in order to improve communication with citizens and representatives of minority, business, religious and other communities and associations by implementing door-to-door activities. Also, this dispatch orders daily planning, directing, monitoring and analysis of the work of police officers at the work position “community policeman”, as well as recording their undertaken activities and achieved results in the table set by SATIT on SharePoint platform, entitled “Weekly report - implemented community policing activities” on the intranet site of the Ministry of Interior. In the period from 24 to 27 May 2022, in the hotel “Solaris” in Vrnjačka Banja, the training entitled “Concept and practical aspects of community policing and Beccaria standards in crime prevention projects” was realized for 46 managers from PS/PO and Police Departments of the Police Directorates in Niš, Zaječar, Bor, Kikinda, Leskovac and Pirot. In the reporting period, proposals for the text of the flyer on the topic of community policing, prevention of property crimes, improvement of property protection during vacations, improvement of self-protection and prevention of robbery and prevention of violent behavior (peer violence), which would be used for the Police Day and later during promotional activities and campaigns of police directorates were submitted to the Department of Media and Communications. |  |  |
| 3.4.1.15. | Ensure co-operation and improve the security protection of human and minority rights of vulnerable social groups, through cooperation with civil society representatives, in particular with the engagement of trained and selected police officers for linking vulnerable social groups. |  |  | -Ministry of Interior -Civil society organizations engaged in the protection of socially vulnerable groups’ (women - victims of domestic violence and partner relationships, LGBTI persons and any other vulnerable groups) |  | Continuously | Budget of the Republic of Serbia – 7.200 € in 2020.- 1.800 € in 2021.- 1800 € in 2022.- 1800 € | Specially trained and selected police officers as contact points for the socially vulnerable groups actively cooperate with representatives of the civil society in order to improve the security of vulnerable social groups. The police holds regular meetings with representatives of socially vulnerable groups |  |  | Аctivity is being successfully implemented. On 21 January 2022, a video for the documentary "The Impact of the Covid-19 Pandemic on the Position of Persons with Disabilities" was filmed, with the participation of representatives of the National Organization of Persons with Disabilities of Serbia and with the support of the OSCE Mission. On 27 January 2022, police officers of the Police Directorate in Novi Sad secured a public gathering in the “Zenit” bookstore in Novi Sad, organized by the French Institute and the LGBTI association "Come Out" on the topic “drag performance”. The event was attended by 20 visitors, and on that occasion there was no violation of the public peace and order, nor endangering the safety of the participants in the event. On 14 April 2022, Deputy Head of the Uniformed Police Directorate, Police Colonel Aleksandar Vasilijević took part in a meeting between the Assistant Director of Police, Police Colonel Dragan Vasiljević, and the President of the European LGBTI Police Association, Alain Parmentier. On 30 May 2022, at the premises of the Government of Serbia, participation was taken in the first coordination meeting regarding the organization of EuroGayPride in Belgrade, in the period from 12 to 18 September 2022. |  |  |
| 3.4.1.16. | Conduct training of police officers in terms of keeping order at public gatherings and other mass events in accordance with international instruments for the protection of human and minority rights. |  |  | -Ministry of Interior |  | Continuously | Budget of the Republic of Serbia – 9.000 € in 2020.- 3.000 € in 2021.- 3.000 € in 2022.- 3.000 € | Police officers improved their skills on keeping order at public gatherings and other mass events in accordance with international instruments for the protection of human rights, through conducted training. |  |  | Аctivity is being successfully implemented In the reporting period there were no realized activities because the Program of professional training of police officers of the Ministry of the Interior for 2022 was adopted on March 1, 2022, so that organizational units, due to lack of time, were not able to organize and implement specific trainings. In accordance with the provisions of the mentioned Program, in the following period, the trainings will be organized. |  |  |
| 3.4.1.17. | Organisation of training for police officers on work of police in community that includes conflict management and mediation in the local community. |  |  | -Ministry of Interior -CSOs |  | Continuously | Budget of the Republic of Serbia – 9.000 € in 2020.- 3.000 € in 2021.- 3.000 € in 2022.- 3.000 € | Training for police officers on conflict management and mediation in the local community held. |  |  | Аctivity is being successfully implemented. On January 20, 2022, the Protector of Citizens, while performing the work of the National Mechanism for the Prevention of Torture, ie supervision over the forced removal of aliens in the period July - December 2021, made a report where in point 2.4. stated that "the National Mechanism for the Prevention of Torture would like to receive more information from the Ministry of the Interior on the training of police officers of the Shelter for Foreigners on the treatment of minors." Regarding the above, a statement was given that, in accordance with the Agreement on Cooperation in the Field of Training and Professional Development of Police Officers of the Ministry of Interior for the Implementation of the Law on Juvenile Delinquents and Criminal Protection of Juveniles, training of police officers for the implementation of the Law on Juvenile Delinquents and criminal protection of minors is realized by the Judicial Academy. During the reporting period, there was no realization of the mentioned seminar. |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.4.2. Serbia adopts a new Law on Gender Equality and a new National Strategy and Action Plan for Combating Violence against Women in Family and Partner Relationships. Serbia ensures adequate institutional capacity for their implementation as well as for implementing the National Strategy and Action Plan for improving the status of women and promoting gender equality. Serbia monitors closely their impact and takes remedial action where required. |  |  |  |  |  | Gender equality improved through implementation of new strategic and legislative framework. The status of women in relation to protection from violence improved through implementation of relevant legislative and operational measures. |  | 1. European Commission Annual Progress Report on Serbia stating progress in part relating to gender equality; 2. Improved Gender equality index for Serbia; Baseline 2018 Gender equality index: 55,8. 3. The Global Gender Gap Index rankings; Baseline 2019 Serbia is placed 39 (score 0.736) 4.Annual report of the Commissioner for the Protection of Equality stating progress in the field of gender equality; 5.Concluding remarks of the UN Committee on the Elimination of Discrimination against Women (CEDAW), ascertaining the progress of Serbia; 6.Report of the Group of Experts of the Council of Europe for the prevention of violence against women and domestic violence GREVIO confirming Serbia's progress; 7. Annual report of the Ombudsman noting higher level of gender equality; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.4.2.1. | Draft new Law on gender equality in order to fully align with EU acquis and the provisions of the Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) through introduction or improvement of availability and quality of: - safe houses - counselling services - state-wide round-the-clock (24/7) telephone helplines free of charge, -treatment support programs aimed at preventing perpetrators, in particular sex offenders, from re-offending, - due diligence principle - multi-sectorial cooperation and CSO involvement support services for victims of sexual violence and protection and support services for children witnesses of violence against women and domestic violence |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with the Coordination Body for Gender Equality -National Assembly of the Republic of Serbia Through inclusive participatory process in cooperation with CSOs engaged in women rights |  | By IV quarter of 2020. | -Adoption of the law: Budget of the Republic of Serbia – 71.136 € Implementation: Budget of the Republic of Serbia: Costs currently unknown, precise funds shall be provided in the process of adoption of the law | Law on gender equality fully aligned with EU acquis and the provisions of the Council of Europe Convention on preventing and combating Violence against women and domestic violence (Istanbul Convention) adopted. |  |  | Activity is fully implemented. On May 20, 2021, the National Assembly of the Republic of Serbia adopted the Law on Gender Equality, which entered into force on June 1, 2021. . |  |  |
| 3.4.2.2. | Perform impact assessment of the National Strategy for improving the status of women and promoting gender equality. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with the Coordination Body for Gender Equality |  | IV quarter of 2020 to II quarter of 2021. | Budget of the Republic of Serbia – 17.285 € | Impact assessment performed and publicly available. Recommendations for future actions provided. |  |  | Activity is fully implemented. The evaluation was conducted in accordance with the Law on Planning System, the Regulation on Public Policy Management Methodology, Analysis of the Effects of Public Policies and Regulations and the Content of Individual Public Policy Documents and the Policy and Regulatory Impact Analysis Handbook and Regulations of Republic Secretariat for Public Policies of the Serbian Government. The aim of the evaluation was to assess the relevance, effectiveness, efficiency and sustainability of the results of the Strategy, draw lessons and present recommendations for the next strategic cycle. |  |  |
| 3.4.2.3. | Development of a new strategic framework in the field of gender equality. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with the Coordination Body for Gender Equality |  | By IV quarter of 2021. | Budget of the Republic of Serbia – Budgeted in 3.4.2.2. | A new strategic framework in the field of gender equality developed. |  |  | Аctivity is being successfully implemented. On October 14, 2021, the Government adopted the Strategy for Gender Equality for the period 2021 by 2030. The proposal of the Action Plan (from 2021 to 2023) for the implementation of the Gender Equality Strategy was submitted for opinion. The deadline for giving opinions was December 31, 2021. After that, a meeting of the Special Working Group will be scheduled to agree on the final version of the text. During the reporting period (April-June 2022) the Draft Proposal of the Action plan (2022-2023) for the implementation of the Strategy for gender equality for period 2021-2030 has been fine-tuned based on the opinions of the relevant bodies/institutions for implementation of measures and activities. |  |  |
| 3.4.2.4. | Monitoring implementation of a new strategic framework in the field of gender equality. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with the Coordination Body for Gender Equality |  | By IV quarter of 2022. | Budget of the Republic of Serbia – 2.553 € in 2020. - 851 € in 2021. - 851 € in 2022.- 851 € | Regular reports on implementation, including specific measurable impact indicators which will be used for monitoring implementation developed and publicly available. |  |  | Activity is not implemented. During the reporting period (April-June 2022) it was not feasible to commence with implementation of this activity since the adoption of the Action plan (2022-2023) for implementation of the Strategic document did not take place. |  |  |
| 3.4.2.5. | Strengthening the role of the Coordination Body for Gender Equality and its role in monitoring the effects of reforms, further policy design, and by providing adequate resources for effective monitoring of the implementation of action plans and strategies in the field. |  |  | -Government of the Republic of Serbia -Coordination Body for Gender Equality |  | Continuously | Budget of the Republic of Serbia – 27.700€ IPA 2016 UN WOMEN | Coordinating Body for Gender Equality regularly and efficiently monitors reform processes and regularly reports on its work. |  |  | Аctivity is being successfully implemented. Board meeting of the project “Integrated response to Violence against Women and Girls in Serbia III” – May 19 The meeting discussed some of the main results of the project, joint project activities in 2021 as well as future steps. The project is implemented jointly by the Government of the Republic of Serbia, with the Coordination Body for Gender Equality as the main partner and UN agencies in Serbia (UNDP, UNICEF, UN Women and UNFPA), with the support of the Government of Sweden. Other project board members include relevant ministries, such as Ministry of Justice, Ministry of Interior, Foreign Affairs, Ministry of Labour, Ministry of Human and Minority Rights, Ministry of Education and others. The project is aimed at improving the legislative and strategic framework for the protection of women and girls from domestic violence, providing more effective protection and support to victims of violence through multisectoral cooperation of competent institutions, and providing information to the public to increase the visibility of the problem of violence and reducing tolerance to this phenomenon. The project is focused on providing continuous support to acting professionals implementing the Law on the Prevention of Domestic Violence, with a special emphasis on improving the reporting of violence, improving the escalation and recurrence of domestic violence risk assessment, ensuring long-term protection of victims and improving the criminal law response to violence. It seeks to change social norms that contribute to the continuation of justification and encouragement of violence against women and girls. Event to mark the first National Gender Equality Day (June 10, 2022) The aim of the event was to mark the first National Gender Equality Day celebrated on June 11, adopted by the Government of the Republic of Serbia at the session held on October 27, 2021, on the initiative of the Deputy Prime Minister and President of the Coordination Body for Gender Equality Prof. Zorana Mihajlović, PhD. The event was organized by the Coordination Body for Gender Equality, the EU Delegation and UN Women. June 11 is the day when the education of women in Serbia was first approved in 1842. By the decree of Prince Mihailo, Natalija Petrović, Sofia and Katarina Lekić were allowed to open a school for girls. This decree provided for six years of school for girls, which, in addition to general education, also included learning skills that were traditionally related to women (singing, handicrafts, good behaviour etc ...). The first female school was opened in Paraćin in 1845. Despite the opposition of the State Council and the opinion of the Belgrade establishment that higher education for girls will ruin families, the Law on Establishing a Women's School was passed in September 1863. The main goal of the school was to provide girls with higher general education and to provide trained teachers for female primary schools. Gender Equality Day aims to raise awareness of the general public about the importance of gender equality as a precondition for the progress of the entire society and the universal value that should permeate all spheres of a democratic society. The event was organized around the award ceremony for gender equality, and speeches of H.E. Emanuele Giaufret, Ambassador and Head of the Delegation of the European Union to the Republic of Serbia, Milana Rikanović, Head of UN Women in Serbia and Zorana Mihajlović, Deputy Prime Minister of the Republic of Serbia and President of the Coordination Body for Gender Equality of the Government of the Republic of Serbia. Awards for improving gender equality were given to individuals in these categories: -Contribution to the improvement of public policies, practices and influence on society - prof. Dr. Marijana Pajvančić -Contribution to the improvement of the position of young people from the perspective of gender equality - Miljana Pejić, KOMS -Contribution to the improvement of women's and men's labor rights and the reconciliation of private and professional life - AVON - Public advocacy for the promotion of gender equality - actor Milan Marić -Contribution to the improvement of gender equality in academia and science - prof. Dr. Ivanka Popovic Conference on Gender Responsive Budgeting (GRB) – May 30, 2022 The conference was organized by the Coordination Body for Gender Equality, Ministry of Finance and supported by UN Women, under the regional project “Transformative Financing for Gender Equality: Towards more Transparent, Inclusive and Accountable Governance in the Western Balkans”, which is financially supported by the Swedish Government – Swedish International Development Agency (SIDA). The Coordination Body for Gender Equality, in cooperation with the Ministry of Finance and UN Women has been continuously supporting the introduction of gender responsive budgeting in the public finance system of the Republic of Serbia since 2016. Through this process, budget users, within their competencies, plan various activities aimed at improving gender equality. The aim of the conference was to present the findings of the report on the implementation of the Sustainable Development Goal No.5, and the indicator 5.c.1, according to which the Republic of Serbia is among 19% of countries worldwide which have successfully introduced gender responsive budgeting and is now among eight countries in Europe which have successfully implemented this tool in order to improve gender equality. In addition to that, the goal of the conference was to present the progress made by the Government of the Republic of Serbia in the implementation of gender responsive budgeting, and to introduce key stakeholders and decision makers with examples of good practice, and the importance of GRB. Some of the topics covered during the conference include key results of introducing GRB at the national and provincial level and GRB as a tool for closing gender gap and improving the economic position of rural women. Round table discussion „Gender Equality and Economic Empowerment of women in Aleksinac“ – May 11 The round table discussion was organized by UN Women, as part of the three-year Project “Support to Priority Actions for Gender Equality in Serbia, phase II”. The project supports the Government of the Republic of Serbia in effective implementation of the EU Gender Equality Acquis. UN Women Serbia implements the project, in close cooperation with the Coordination Body for Gender Equality, the Ministry of European Integration, the EU Delegation in Serbia and other partner institutions and women's organizations. This was the second thematic meeting which was organized by UN Women in cooperation with “Društvo za razvoj kreativnosti”, an NGO from Aleksinac, and some of the main topics of the discussion were the position of women on the labour market in Serbia and measures for the economic empowerment of women. Additionally, a research on the position of women on the labour market in Aleksinac was presented, and representatives of female organizations presented their work, the challenges and obstacles that they face. Representatives of the municipal authorities talked about their local mechanisms for gender equality, and what measures and programs they have started to improve the position of women on the labour market in Aleksinac. Meeting of the National Coalition to End Child Marriage – June 30, 2022 In the reporting period, we held several meetings with members of the National Coalition to discuss the plan of activities for 2022 and to reflect on some of the main achievements in this field in 2021. Members of the Coalition gave detailed information about their individual plans for the ongoing year, and discussed potential joint activities of the whole Coalition. Some of the activities of members of the National Coalition planned for this year include: -Educational and creative workshops with children from Roma settlements in Belgrade focused on human rights, discrimination, risks of exploitation, negative impacts of early marriages, the importance of higher education and support in enrollment processes for children from Roma settlements -workshops with pupils from primary and high schools aimed at empowering children to recognize and report human trafficking -stronger coordination between relevant actors to provide support and protection to victims of human traffickingseminars for educational assistants aimed to strenghten their capacities and competencies in the area of early marriage prevention -promotion of the model of child marriage prevention at the local level which will be implemented in 8 new municipalities -advocating for changes in the normative framework in the area of early marriages and monitoring the implementation of the Strategy for the Prevention and Protection of Children from Violence -support for the education of professionals on child marriage as part of the training for the implementation of the Law on the Prevention of Domestic Violenc Other activities CBGE organized meeting with representatives of USAID about political participation of women in Serbia. The meeting was organized as part of the USAID periodically conducted assessments with stakeholders and decision-makers to discuss the topic of strengthening political processes in Serbia from the perspective of women’s participation in politics. The goal of the meeting was to better define and determine priorities for programs of USAID in improving the integrity of the electoral process, and strengthening political processes in general. In 2022, the EBRD and the Ministry of Mining and Energy signed a Memorandum of Understanding to scale up the integration of renewables into distant heating systems in Serbia. As the first step in the implementation of the MoU, the EBRD and the Ministry have formed the Renewable District Energy in Serbia Programme. The aim of the meeting with the EBRD was to discuss potential ways that renewable based district energy solutions in Serbia can contribute to socio-economic development, and how a gender perspective can be included in this process. CBGE signed Memorandum of Understanding with UNFPA. The purpose of this agreement was to provide a framework of cooperation between the CBGE and UNFPA and to facilitate collaboration in the implementation of measures to achieve gender equality and the advancement of the position of women and girls in relation to sexual and reproductive health, elimination of gender-based violence and the promotion of bodily integrity. |  |  |
| 3.4.2.6. | Development of new National strategy and Action Plan for combating violence against women in family and partner relationships. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with the Coordination Body for Gender Equality - Ministry of Justice - Ministry of Interior |  | IV quarter of 2020. | Budget of the Republic of Serbia – 30.878 € | National strategy and Action Plan for combating violence against women in family and partner relationships developed including specific measurable impact indicators which will be used for monitoring implementation. |  |  | Activity is partially implemented. The proposal of the AP has been made, but the AP has not been adopted yet, because based on the opinion of the Ministry of Finance, the procedure of obtaining financial effects from the competent authorities has been repeated, after which the opinion of the Ministry of Finance will be requested again. Ministry of Labour, Employment, Veteran and Social Affairs - As the contract of the previous expert team for drafting the AP expired, it is necessary to hire new experts who will work with the working group to harmonize the financial effects obtained from the competent authorities in order to finalize the AP, which will be sent to the Ministry of Finance again. |  |  |
| 3.4.2.7 | Monitoring implementation of the new National strategy and Action Plan for combating violence against women in family and partner relationships. |  |  | -Body determined by the National strategy for combating violence against women in family and partner relationships |  | Continuously , commencing from I quarter of 2021. | Budget of the Republic of Serbia – 2.553 € in 2020. - 851 € in 2021.- 851 € in 2022. -851 € | Reports on implementation of the new National strategy and Action Plan for combating violence against women in family and partner relationships are regularly adopted and publicly available, including specific measurable impact indicators which will be used for monitoring implementation. |  |  | Аctivity is not implemented. Even though the deadline for adoption of the Action Plan was 90 days following the adoption of the Strategy the AP has not yet been adopted. Monitoring of the Strategy is entrusted to the Coordination Body for Gender Equality. This body acts within the Government as a permanent working body, which enables multi-sector coordination between different ministries and when it comes to gender-based domestic violence. The mandate of this body is to coordinate activities in the field of gender equality, with violence against women and domestic violence being a form of gender-based violence and thus a specific area within gender equality. Monitoring the implementation of the Strategy is entrusted to the Coordination Body for Gender Equality. In the first quarter of 2022.the Ministry of Labor, Employment, Veterans and Social Affairs submitted its contribution to the CT on activities within the competence of this ministry. Based on all submitted contributions from the competent bodies and organizations, the CT will prepare a report for the RS Government. |  |  |
| 3.4.2.8. | Implementation of training for staff in public authority bodies in the field of gender equality in order to effectively coordinate the implementation and monitoring of the implementation of gender equality policies. |  |  | -National Academy for Public Administration --Ministry of Labour, Employment, Veterans and Social Affairs -Coordination body for gender equality |  | Continuously, in line with annual training program | Budget of the Republic of Serbia – 3.600 € in 2020.- 1.200 € in 2021.- 1.200 € in 2022.- 1.200 € | Training of the staff at the in public authority bodies in the field of gender equality conducted and their capacity strengthened with regard to implementation of gender equality policies. |  |  | Аctivity is being successfully implemented. In the reporting period, one training session on the topic "Gender Equality" was held, which was attended by 13 participants. |  |  |
| 3.4.2.9. | Monitoring of implementation of special law governing prevention of violence against women in the family and partner relationships. |  |  | -Ministry of Justice |  | Continuously | Budget of the Republic of Serbia – 2.553 € in 2020.- 851 € in 2021.- 851 € in 2022.- 851 €€ | Special law governing prevention in cases of violence against women in the family and partner relationships fully implemented. Quarterly reports on implementation of the law publicly available, including specific measurable impact indicators which will be used for monitoring implementation. |  |  | Аctivity is being successfully implemented. In the reporting period from April to June 2022 (April, May and June 2022), a total of 11939 cases of domestic violence were considered, in the same period, 5398 proposals for extending emergency measures were submitted, out of which 5217 were adopted. In this period, 4911 individual protection plans were drawn up. A total of 78 lawsuits were filed. |  |  |
| 3.4.2.10. | Conduct training of judges, public prosecutors and deputy public prosecutors focused on acting in the cases of violence against women in the family, partner relationships and gender based violence. |  |  | -Judicial Academy -CSOs -Republic public prosecutors’ office |  | Continuously, in line with the annual program of the Judicial Academy | Budget of the Republic of Serbia – Budgeted in 1.3.1.1. | Conducted training aimed at improvement of prosecution and protection of victims of violence against women in the family, partner relationships and gender based violence. |  |  | Аctivity is being successfully implemented. In I quarter 2022, 2 trainings on the topic of domestic violence (Phase 1), were conducted, which includes topics such as risk assessment, decisions of the participants in the procedure (order, proposal and decision), emergency measures (types, imposition and duration), cooperation among the institutions in the prevention of domestic violence- the group for coordination and cooperation and protection and support to victims. The trainings were attended by 37 participants from the ranks of judges of misdemeanor and basic courts, basic public prosecutors and their deputies, prosecutorial assistants and associates. During February and March 2022, 9 (nine) one-day workshops were conducted in total (for 202 participants) on the topic ‘’Joint training for judges, public prosecutors and police officers for the application of the Law on prevention of domestic violence (Phase 2).’’ In II quarter 2022, 2 one-day trainings on the topic of domestic violence (Phase 1), were conducted, which includes topics such as risk assessment, decisions of the participants in the procedure (order, proposal and decision), emergency measures (types, imposition and duration), cooperation among the institutions in the prevention of domestic violence- the group for coordination and cooperation and protection and support to victims. The trainings were attended by 33 participants from the ranks of judges of misdemeanor, basic and higher courts, basic public prosecutors and their deputies, prosecutorial associates. In April 2022, 6 (six) one-day workshops were conducted in total (for 133 participants) on the topic ‘’Joint training for judges, public prosecutors and police officers for the application of the Law on prevention of domestic violence (Phase 2).’’ |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.4.3. Serbia improves the situation of disabled persons, inter alia through the full implementation of the UN Convention on the Rights of Persons with Disabilities and closely monitors its results. |  |  |  |  |  | Legal safeguards for persons in specialized institutions reinforced in line with international human rights standards. Provision of adequate care and living conditions for residents and the parallel development of community-based care services in line with the UN Convention on the Rights of Persons with Disabilities. |  | 1. European Commission Annual Progress Report on Serbia stating progress in part relating to rights of persons with disabilities; 2. Concluding remarks of the UN Committee on the Rights of Persons with Disability note progress in implementation of the UN Convention on the Rights of Persons with Disabilities; 3. Annual report of the Ombudsman noting improved level of implementation of rights of persons with disabilities. 4. The report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment notes positive developments in Serbia regarding the treatment of persons with mental and/or physical disabilities; 5. Annual report of the Commissioner for the Protection of Equality stating progress in protection of persons with disabilities form discrimination; 6. Increased availability of community services for adults with disabilities, including the following: - Supported living: Baseline 9 licensed services in 2019; Target 20% increase by 2021 and 20% increase by 2023. - Home help for adults with disability: Baseline: 99 licensed services in 2019; Target: increase 20% by 2021 - Day-care: Baseline: 1 specialized day-care for adults only in 2018. Target: 20 municipalities have adults’ services by 2022; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.4.3.1. | Adopt the Law aiming at protecting persons with mental disabilities in institutions of social welfare in line with international standards. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | By IV quarter of 2020. | Budget of the Republic of Serbia – 71.136 € | Law aiming at protecting persons with mental disabilities in institutions of social welfare adopted and implementation commenced. |  |  | Аctivity is fully implemented The Law on Temporary Social Care Residents was adopted in December 2021 (Official Gazette of RS, No. 126/2021). It has been in force since 31 December 2021. This law regulates the manner of exercising the rights of beneficiaries of temporary accommodation services in social protection, as well as the rights of beneficiaries of temporary accommodation services in social protection institutions that are in the process of deinstitutionalization, and principles, accommodation procedure, preparation procedure for community living, protection against exploitation and neglect, as well as other rights and obligations of beneficiaries when using temporary accommodation services until the time when living conditions in the community can be provided, and ways of dealing with incidents of imminent danger to life or safety of the beneficiaries or other persons. |  |  |
| 3.4.3.2. | Strengthen the oversight of living conditions in psychiatric hospitals, in line with the Program for the protection of mental health in the Republic of Serbia 2019- 2026. Link with Chapter 28 |  |  | -Ministry of Health |  | Commencing from I quarter 2020. | Budgeted in Chapter 28 | Annual report on the oversight of living conditions in psychiatric hospitals, performed in line with the Program for the protection of mental health in the Republic of Serbia 2019- 2026. |  |  | Activity is not implemented. Regardless of the current epidemiological situation, in the period from 2019 until today, a total of 3 (three) psychiatric health institutions have been accredited in the city of Belgrade "Clinic for Psychiatric Diseases" Dr. Laza Lazarevic", Institute of Mental Health and Special Hospital for Addiction Diseases) by the Agency for Accreditation of Health Institutions of Serbia. Namely, the fulfillment of all general medical and special psychiatric accreditation standards by the Agency for Accreditation of Health Institutions of Serbia provided verification of the achieved quality of treatment, patient safety , living conditions, as well as working conditions for employees in psychiatric health care. Also, the Republic Expert Commission for Mental Health of the Serbian Ministry of Health has launched an initiative for accreditation of all major psychiatric institutions in the Republic of Serbia, in order to improve quality standards defined by the European certified body that will monitor the living conditions of patients in these health institutions. All large psychiatric healthcare institutions on the territory of the Republic of Serbia are currently getting ready for external evaluation by the Agency for Accreditation of Health Care Institutions of Serbia, which is expected to take place in the first half of 2022. The preliminary report of the Agency for Accreditation of Health Institutions of Serbia to the Republic Expert Commission for Mental Health of the Serbian Ministry of Health speaks in favor of the successful application of quality standards in all special hospitals for psychiatric diseases in Serbia. |  |  |
| 3.4.3.3. | Drafting and adoption of the Strategy for Improving the Position of Persons with Disabilities in the Republic of Serbia for the period until 2024 and the Action Plan for Implementation for the period until 2022. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | IV quarter of 2020. | Budget of the Republic of Serbia – 30.878 € | Strategy for Improving the Position of Persons with Disabilities in the Republic of Serbia for the period until 2024 and the Action Plan for Implementation for the period until 2022 adopted. |  |  | Activity is fully implemented. The Strategy for improving the position of persons with disabilities in the Republic of Serbia for the period from 2020 to 2024 was adopted on March 5, 2020 and published in the Official Gazette ("Official Gazette of RS", No. 44/20).The two-year Action Plan for the implementation of the Strategy for Improving the Position of Persons with Disabilities in the Republic of Serbia was adopted at the Government session on 8 April 2021, and published in the Official Gazette on 14 April 2021. |  |  |
| 3.4.3.4. | Monitoring implementation of the Strategy for Improving the Position of Persons with Disabilities in the Republic of Serbia for the period until 2024 and the Action Plan for Implementation for the period until 2022. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | Continuously, until the expiry of the Strategy | Budget of the Republic of Serbia – 6.915 € in 2020.- 2.305 € in 2021.- 2.305 € in 2022.- 2.305 € | Reports on implementation regularly developed and publicly available. |  |  | Аctivity is being successfully implemented. Pursuant to the provisions of Article 43 of the Law on Planning System, the results of the Strategy implementation are reported no later than 120 days after the end of the third calendar year from the day of its adoption, and the final report on its implementation is submitted up to six months after the application period ends. Bearing in mind that the Strategy for Improving the Position of PWDs in the RS for the period until 2024 was adopted in March 2020, the legal deadline for the preparation of the first report on its implementation is 30 April 2023. |  |  |
| 3.4.3.5 | Adoption of the Law on Amendments to the Family Law, aimed at abolishing the existing system of complete deprivation of legal capacity with the introduction of a model of “decision making with support”. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | By II quarter of 2021. | Budget of the Republic of Serbia – 17.285 € | Law on Amendments to the Family Law, aimed at abolishing the existing system of complete deprivation of legal capacity with the introduction of a model of “decision making with support” adopted. |  |  | Activity is not implemented. The Law on Amendments to the Family Law, the objective of which is to abolish the existing system of complete deprivation of working capacity through the introduction of the "supported decision-making" model, was not adopted. The Special Working Group for drafting amendments to the Family Law prepared a preliminary draft of the Law on Amendments to the Family Law at the end of 2021, and one of the changes defined by the Special Working Group is the cancellation of the institute of complete deprivation of working capacity and the introduction of the institute of limitation of working capacity and the "supported decision-making" model. For procedural reasons, the public hearing was not conducted. After the formation of the new Government, the process for passing the Law on Amendments to the Family Law will continue. |  |  |
| 3.4.3.6 | Adoption of the Law on Amendments to the Law on Non-contentious Proceedings. |  |  | -Ministry of Justice |  | By II quarter of 2021. | Budget of the Republic of Serbia – 17.285 € | Law on Amendments to the Law on Non-contentious Proceedings adopted |  |  | Activity is not implemented. The activity is related to changes in the Family Law that have not yet been implemented. |  |  |
| 3.4.3.7. | Strengthen supervision of living conditions in social welfare institutions in accordance with relevant regulations. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | Continuously | Budget of the Republic of Serbia – Regular activity | Annual report on the supervision of living conditions in social welfare institutions in accordance with the relevant regulations. |  |  | Аctivity is being successfully implemented. Inspections took place during the first quarter of 2022, were performed regularly and, if necessary, extraordinarily. Each inspection was accompanied by a report with an order of measures to eliminate irregularities. The total number of inspections performed in this quarter was 33. Another 20 licenses have been issued to social protection service providers. The total number of inspections carried out in 2021 was 132. For the month of April 2022 a meeting of the Ministry is planned with a group of interested civil society organizations in order to implement Article 38 of the Rights of the Beneficiaries of Temporary Residential Care Law (2021), which defines a mechanism for quality control of services to establish independent monitoring. According to the provisions of this law, inspection supervision in accommodation institutions in the process of deinstitutionalization will be performed, if possible, once a year. Independent monitoring will also be provided to civil society organizations, and they are obliged to report the findings from independent monitoring to the competent ministry within 60 days from the day of the monitoring. Inspections are carried out regularly and, if necessary, extraordinarily. Each inspection was accompanied by a report with an order of measures to eliminate irregularities. The total number of performed inspections in 2021 (republic inspection, provincial inspection and inspection for the City of Belgrade) in the field of social protection is 203. The Annual Report on the Work of the Social Protection Inspection for 2021 is also available on the Ministry's website at the following link https://www.minrzs.gov.rs/sites/default/files/2022-04/Godisni%20izvestaj%20o%20radu%20inspekcije%20socijalne%20zastite%20za%202021.%20godinu%20sken.pdf In April 2022, a meeting of the Ministry was held with a group of interested civil society organizations for the purpose of implementing Article 38 of the Law on Temporary Social Care Residents (2021), which defines a mechanism for quality control of services in order to establish independent monitoring. According to the provisions of this Law, inspections of the residential social institutions in the process of deinstitutionalization shall be performed, if possible, once a year. Independent monitoring will also be provided to civil society organizations, and they have the obligation to report the findings of this independent monitoring to the competent ministry within 60 days of the monitoring. It was agreed to jointly make a proposal for a quality control mechanism, which we will report on in the coming period. |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.4.4. Serbia steps up the respect of rights of the child, with particular attention for socially vulnerable children, children with disabilities and children as victims of crime. Serbia actively works on reducing institutionalisation to the benefit of increasing family care solutions. Serbia adopts and implements a Strategy and Action Plan for preventing and protecting children from all forms of violence. Serbia establishes a child friendly justice system, including through amending and implementing the Law on juveniles, improving the work of the Juvenile Justice Council, providing training on dealing with juvenile offenders, improving alternative sanctions for juveniles and measures to reintegrate juvenile offenders back into society. |  |  |  |  |  | Improved protection and enforcement of rights of the child and persons with disabilities by strengthening of relevant institutions ensuring better cooperation between the judiciary and the social sector. Social protection system implements solutions that give priority to family support while providing support for children at risk, or provide community living for people with disabilities. The judicial system applies adopted policies and regulations that ensure respect for the principle of the best interests of the child in accordance with EU standards. |  | 1. Increase in the number of families with children that benefit from newly designed family support through family outreach and parenting advisory services targeting the most vulnerable, including children with disability. Baseline: 698 in 2017. Target: 1000 by 2020 and 2000 by 2022; 2. Children with disability who are in need of alternative care are increasingly placed in family care (including kinship care, foster care and foster-care as shared parenting) and not in institutional care. - A rise of the ratio of children with disability in foster-care. Baseline: 8% of children that are in foster care are with disability (2017) Target – increase by 5% by 2020 and 5% by 2022. - Increased ratio of kinship care within total number of children in care: Baseline: 22% in 2018. Target 35% in 2021. - Increase in the number of families with children with disability benefiting from shared parenting. Baseline – 0 in 2019. Target: 200 families by 2021 and 300 by 2023 3. Options for alternative care are selected based on individual situations and needs of each child in accordance with international standards (including UN Guidelines on Alternative Care and the Convention on the Rights of Persons with Disability which prioritize family-based care and General Comment No. 5 (2017) of the United Nations Committee on the Rights of Persons with Disabilities (CRPD) regarding independent living and community involvement. The number of children entering institutions for the first time is strictly controlled and supervised, and decreases from year to year, in accordance with defined criteria for institutionalization; Baseline: 2018: Number of newly admitted children is 172 4. Number of children who use institutional care services decreases (target - decrease by 15% by 2020 and additional 15% by 2022 for children in comparison with 2018 data). Baseline: 2018 - the total numbers of children (705) in institutions. Target: children: 600 by 2020, and 510 by 2022; (source of data annual report of the Republic Institute for Social Protection) 5. The number of children who benefit from the child-oriented-justice increases annually: - Implementation of diversion orders increased – percentage of implementation in the total number of criminal cases for criminal offenses committed by juveniles, both by public prosecutors and judges. Baseline: 9.5% (330) for public prosecutors and judges 3.4% (68) in 2017. Target 15% increase by end of 2020 and 20% increase by 2022 - improved conditions for juveniles deprived of liberty (especially those in custody) by 2021 through access to quality education and improved contents for leisure time. - clear procedures established and implemented for the preparation of juveniles for release. Adoption of guidelines for Centers for social work for supporting reintegration of juveniles released from correctional institutions 6. The report of the European Committee for the Prevention of Torture and Inhuman or Degrading Treatment or Punishment notes positive developments in Serbia regarding the juveniles deprived of liberty; 7. Concluding remarks of the UN Committee on the Rights of the child notes progress in implementation of the UN Convention on the Rights of the child. 8. Annual report of the Ombudsman noting improved level of implementation of rights of the child. 9. European Commission Annual Progress Report on Serbia stating progress in part relating to rights of the child. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.4.4.1. | Strenghtening the Council for the Rights of the Child and ensure its role in monitoring the effects of the reforms and further policy making, including through adequate resources to effectively monitor and track implementation of the action plans and strategies in the area of rights of the child. |  |  | -Government of the Republic of Serbia -Ministry of Labour, Employment, Veterans and Social Affairs |  | Continuously. | Budget of the Republic of Serbia – 18.528 €, in 2020 - 6.176 € in 2021. - 6.176 € in 2022. - 6.176 € | Council for the Rights of the Child regularly and efficiently monitors the reforms and provides regular reports. |  |  | Аctivity is being successfully implemented. At its 113th session on February 10, 2022, the Government adopted a Conclusion adopting the General Protocol for the Protection of Children from Violence. The Council for the Rights of the Child in the new convocation was established by the decision of the Government on 01.04.2021. In the period since the formation of the Council for the Rights of the Child, two sessions of the Council were held. After both sessions, the Council submitted reports from the sessions to the Government and the Committee on the Rights of the Child of the National Assembly. After the formation of the Government, a new Council will be formed and work will continue on harmonizing activities with impact indicators and the results of benchmark implementation. |  |  |
| 3.4.4.2. | Improvement of support services for children, adults and older people with intellectual disabilities and their families, in order to prevent institutionalization by: -Organization of day care -Organization of inclusive workshops -Inclusion of children with developmental disabilities who are at risk of separation from families in existing services in the community -Organization of services for the early rehabilitation of children with disabilities and provision of support to remain in family -Organization of a network of clubs with inclusive content in local communities for children, adults and elderly people with intellectual disabilities and their parents -Organization of workshops for parents focusing on responsible parenthood and participation in the rehabilitation of children with disabilities. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | Continuously, by III quarter of 2021. | Budget of the Republic of Serbia – Regular activity | Support services for children, adults and older people with intellectual disabilities and their families organized in order to prevent institutionalization by: -Organization of day care -Organization of inclusive workshops -Inclusion of children with developmental disabilities who are at risk of separation from families in existing services in the community. -Provision of services for the early rehabilitation of children with disabilities and support to remain in family provided. -A network of clubs with inclusive content organized in local communities. -Workshops for parents focusing on responsible parenthood and participation in the rehabilitation of children with disabilities organized. |  |  | Аctivity is partially implemented . In January 2022, at the proposal of the Ministry of Labour, Employment, Veteran and Social Affairs, the Government of the Republic of Serbia adopted the Strategy for Deinstitutionalization and Development of Community-Based Social Protection Services 2022-2026 ("Official Gazette of RS" No. 12/2022 of 1 February 2022). The Strategy should contribute to the improvement of the social protection system through a harmonized system of measures, conditions and public policy instruments that the Republic of Serbia should implement in order to prevent institutionalization, i.e. reduce the number of citizens using residential social protection services and enable the development of community-based services. This will contribute to the wellbeing of beneficiaries of the social protection system who need more intensive support to meet most of their needs in the natural environment. It is primarily aimed at people with intellectual and mental disabilities who are at the highest risk of institutionalization and social exclusion. In June 2022, a Working Group was formed to draft the AP for the period 2022-2023, which will operationalize the activities of the Strategy, and the first meeting of the WG is scheduled for the end of June, thus beginning the process of drafting the AP. During 2021, there were a total of 62 licensed day care providers for people with disabilities. During the year, the services of day care centres (licensed) were used by a total of 1,599 people, of whom 259 children (under 18 years of age), and on 31 December 2021, a total of 1,543 beneficiaries, of whom 247 children. The total number of licenses issued for services that prevent institutionalization and provide support for independent living, such as: day care, home help, shelter, personal companion to a child, personal assistant, drop-in centre, telephone helpline, supported housing, respite accommodation, etc. is constantly increasing and has a positive trend from the very beginning of the licensing process, but is still not sufficient in relation to the needs of the beneficiaries. It is a continuous process. These services are provided by the local self-governments, and the Republic of Serbia supports their financing through earmarked transfers. The list of all licensed social protection service providers is publicly available on the Ministry's website. There are currently about 700 licensed providers of social protection services (of which 370 are providers of home accommodation services - private and state). Amounts for earmarked transfers (funds transferred from the budget of the Republic to local self-government units for the development of community-based social protection services) have been significantly reduced compared to previous years. Namely, for 2022, a total of 500 million dinars has been allocated in the budget, while in previous years about 700 million dinars were allocated for these purposes. These will certainly have negative effects on the further process of deinstitutionalization in Serbia. |  |  |
| 3.4.4.3. | Establishment of the centers for children, young people and families in order to target the population from multiple deprivation environments (paying special attention to the availability for Roma families and children) in order to: -Support a parent who suffers domestic violence -Support children at risk of dropping out of school -Support families at risk of separation (children and parents) -Support children victims of crime -Support children with disabilities from vulnerable families and at risk of placement in institution. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Children's homes in transformation -Republic institute for social protection -CSOs Partners: -Ministry of Health -Ministry of Education |  | For establishment of legal framework: II quarter of 2021. For the start of implementation: I quarter of 2022 | Budget of the Republic of Serbia – Costs currently unknown | Number of family support centres established in the context of the transformation of institutions. Baseline: 0, target: 4 Defined standards for intensive family support services Established financing system of intensive family support services. |  |  | Activity is not implemented. Centres for children, youth and family have not been established yet, considering that it is necessary to create a legal basis for their establishment, which is the Law amending the Law on Social Protection. The reason for the delay in the adoption is the lack of financial resources in the budget allocated for social protection, needed for all the necessary changes that would be regulated by the Law. |  |  |
| 3.4.4.4. | Improvement of the system of cash benefits for vulnerable families of children with disabilities in accordance with the principles of social inclusion, through amendments to the Law on social protection, as well as through the adoption of the new Social Protection Development Strategy. |  |  | -Ministry of Labour, Employment, Veterans and Social Affair |  | IV quarter of 2020. | # Budget of the Republic of Serbia – # 57.793 € | New Social Protection Development Strategy adopted and ensures implementation of the principles of social inclusion. Amendments to the Law on social protection adopted in line with the principles of social inclusion. Amendments to the Law on Financial Support for Families with Children altering the existing legal solution which may be discriminatory against certain categories of parents and mothers adopted. |  |  | Activity is not implemented. The Social Protection Strategy and amendments to the Law on Social Protection are still in the process of being drafted. The following were performed: ex post analysis of the current Law on Social Protection, ex ante analysis of the effects of the new Law as well as ex post analysis of the previous Social Protection Strategy. An ex ante analysis of the effects of the new Social Protection Strategy is under way. |  |  |
| 3.4.4.5. | Improving foster care system by increasing the availability and quality of services for children with disabilities and their families through full implementation of procedures and guidelines for foster care as shared care between foster and biological families. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Regional fostering centres -Centres for social work -Institutes for social protection |  | Continuously, by 2021. | Budget of the Republic of Serbia – Costs currently unknown | Foster care as a shared care approach defined through the normative framework. Specialized guidance and capacity building programs available in all fostering centers and Centres for social work. Centres for foster care and centres for social work are used as a shared care mechanism through which families with children with disabilities receive additional support. Target: 200 families included by 2021. |  |  | Activity is partially implemented. A new Rulebook on Foster Care was adopted (published in "Official Gazette of the RS", No. 66/2022 dated 10.06.2022, and entered into force on 18.06.2022.). The Rulebook improved the standards and procedures of foster care, including foster care for children with developmental disabilities. However, a very important matter is fees for foster care (including specialized ones). The Ministry of Family Welfare and Demography is not responsible for determining the fees for foster care, but it is the responsibility of the Ministry of Labor, Employment, Veteran and Social Affairs, which is regulated by the Rulebook adopted by that ministry and which must be changed if we want higher fees for foster parents who deal with specialized foster care. Guidelines for temporary family placement are available to family placement and adoption centers and social work centers, to support working with children with developmental disabilities and their families. |  |  |
| 3.4.4.6. | Improve the quality of work with inpatient service users to enable more efficient engagement in the community through: -Provision of psychosocial support for social reintegration; -Organization of contacts outside of the institution and participation in local support services such as day care centres and clubs; -Participation in cultural and sporting events and camps. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with CSOs |  | Continuously | Budget of the Republic of Serbia Costs currently unknown. | The quality of work with inpatient service users improved to enable more efficient engagement in the community. |  |  | Аctivity is being successfully implemented. Providing beneficiaries of accommodation services with recreational, occupation-educational and cultural-entertainment activities is included in the programme of each accommodation service provider, with the aim of developing the potential and maintaining the functionality of the beneficiaries. The Law on Temporary Social Care Residents ("Official Gazette of RS" No. 126/2021) was also adopted, and came into force on 31 December 2021. This Law improves the position of beneficiaries of temporary accommodation services in social protection, through the process of preserving the quality of their life and their potential, development and preparation of beneficiaries for life in the community, without discrimination and under equal conditions with their active, effective and informed participation, including their persons of trust who provide them with decision-making support, in line with a human rights-based approach. Exercising the rights of temporary social care residents means continuous training of beneficiaries for independent living and full and equal participation in society, and achieving social inclusion through the process of deinstitutionalization, and it is aimed at empowering beneficiaries in order to preserve and develop potential, and achieve long-term stay out of temporary accommodation and involvement in the local community through the use of community-based services. When deciding on the accommodation of a beneficiary, with the informed consent of the adult beneficiary, the legal representative of a minor, and when the competent centre for social work makes a decision, this institution is obliged to examine all possibilities of support for the beneficiary, using daily community-based services, independent living services or using other non-institutional support or protection services. This Law also regulates: Time limit of accommodation; Introducing beneficiaries to their rights and obligations; Statement of consent to accommodation; Selection of a person of trust; Review of the decision on accommodation; Termination of accommodation; Appeal against the decision on accommodation. The Law also covers protection against abuse, exploitation and neglect, the rights and obligations of beneficiaries when using the accommodation service; actions in incident situations and also regulates the quality control mechanism for services, implemented by the Ministry responsible for social protection. |  |  |
| 3.4.4.7. | Improvement of existing resources in large and small residential institutions for children and drafting recommendations on the methods of their use in the process of transition from institutional to community care through the adoption of the Strategy of de-institutionalization and development of community-based services |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs |  | By IV quarter of 2020. | Budget of the Republic of Serbia Costs currently unknown. | Plans to reduce the accommodation capacity in two large residential institutions developed and adopted. Funding for the implementation defined. |  |  | Activity is not implemented Development of plans for the transformation of institutions in accordance with the newly adopted Strategy for Deinstitutionalization and Development of Community Based Social Welfare Services 2022-2026 (2022) as well as the accompanying AP for its implementation (not adopted) is planned through IPA 2020 and will be adopted first General plan for the transformation of placement institutions on the basis of which each institution will adopt its own transformation plan. Through IPA 2020, 5 pilot plans will be made for 5 institutions where people with disabilities are accommodated. Regarding children, the largest number of children without parental care in Serbia is not placed in residential institutions, but in foster families (90%). There are about 600 children in the homes. Serbia is still among the countries with the lowest level of institutionalization of children. Recently, however, there has been an obvious lack of foster families, which is partly due to the lack of media campaigns to promote foster care. |  |  |
| 3.4.4.8. | Strengthen capacity of providers of social services in accordance with the processes of deinstitutionalization and system decentralization by organizing staff training for the provision of psychosocial support for service users’ reintegration. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs in cooperation with CSOs |  | Continuously | Budget of the Republic of Serbia – 5.400 € in 2020. - 1.800 € in 2021. - 1.800 € in 2022. - 1.800 € | Education of providers of social services are realized. Number of participants and institutions. Professional and technical resources of the community are placed in supporting reintegration. |  |  | Activity is not implemented. In the Register of Accredited Programmes at the Republic Institute for Social Protection, there are three programmes whose contents relate to the above issues: "Support Programme to Young People Leaving Protection for Independence and Family Life", "Towards Deinstitutionalization and Transformation of Institutions", and "Reintegration of Juveniles in the Social Environment". These programmes did not have any realization since the beginning of 2022 until today. |  |  |
| 3.4.4.9. | Analysis of the effects of the applied organizational model in the centers for social work and on this basis, an introduction of the necessary changes in the normative framework that prescribes the organization of professional work in the centers for social work |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Centres for social work -Professional associations in the field of social protection |  | By I quarter of 2020 | Budget of the Republic of Serbia – 8.642 € | Case management system improved in centres for Social Work. Impact assessment of the Guidelines for making permanency plan for the child in the protection system developed based on the existing "Measures to eliminate irregularities in performing placement of children and youth in social care institutions. |  |  | Activity is partially implemented. The analysis of the effects of the applied organizational model in centers for social work has not been done. Through the Association of Centers for Social Work, a memo was sent to all centers for social work, in order for them to provide proposals and comments on the current Rulebook, which will serve as material for creating an analysis of the effects and the start of the working group's work on amendments to the Rulebook on Organization, Norms and Standards of the Work of the Center for Social Work. |  |  |
| 3.4.4.10. | Adopt amendments and supplements to the Law on Juveniles in order to: -Review the type and system of criminal sanctions for juveniles: -Introduce a broader spectrum of specific obligations; -Introduce the new diversion orders; -Comply with the provisions of the new Criminal Procedure Code - (primarily in relation to the stage of the procedure and the altered role of the officials in the procedure in the specific procedural stages). |  |  | -Ministry of Justice -National assembly |  | IV quarter of 2020. | Budget of the Republic of Serbia – 71.386 € | Amendments and supplements to the Law on Juveniles adopted enabling simplified and efficient implementation of diversion orders. |  |  | Activity is not implemented. The working group of the Ministry of Justice has prepared a draft of amendments to the Law, which was sent to the European Commission for an opinion. The work on the Draft is to continue for the purpose of alignment with the comments of the EC. |  |  |
| 3.4.4.11. | Improve the work of the Juvenile Justice Council in order to achieve the coordination of state bodies, the judiciary and the non-governmental sector in dealing with juvenile offenders by: -holding regular meetings of the Council; -holding regular meetings of the Council with other relevant agencies and non-governmental sector; -launching initiatives for amendments of the normative framework, the adoption of best practices and other steps necessary for the development of the child friendly judiciary. |  |  | -Ministry of Justice -Supreme Court of Cassation |  | Continuously | Budget of the Republic of Serbia- 18.528 € in 2020. - 6.176 € in 2021. - 6.176 € in 2022. - 6.176 € | Council for the monitoring and improvement of work of the bodies in criminal proceedings and the enforcement of criminal sanctions against juveniles holds regular sessions and launches initiatives for amendments of the normative framework, the adoption of best practices and other steps necessary for the development of the child friendly judiciary. Biannual report of the Juvenile Justice Council published. |  |  | Аctivity is being successfully implemented. In I quarter 2022. a conference was held on February 24, 2022, organized by the Council for Monitoring and Improving the Work of Criminal Procedure Bodies and Execution of Criminal Sanctions against Juveniles ("Juvenile Council") and the UNICEF - "Children in contact with the law - improving the exercise of rights, prevention and protection." The conference was opened by the President of the Supreme Court of Cassation, Jasmina Vasović. This gathering was dedicated to the promotion of the rights of children - perpetrators and victims and witnesses of crimes. Special attention was paid to improving the implementation of rehabilitation order and improving the program of work with juvenile offenders, especially those who had mental health problems. The aim of the conference was to get acquainted with the progress made in the field of child justice in the previous period and planned initiatives, and to exchange experiences of experts in order to strengthen cross-sectoral cooperation. During II quarter 2022, the Council continued its activities and held two sessions during the second quarter of 2022. The council is being chaired by the Justice Biljana Sinanović, from the Supreme Court of Cassation. |  |  |
| 3.4.4.12. | Increasing use of diversionary schemes and prioritizing restorative approach to juvenile offenders to ensure their social reintegration and reduce recidivism rates, by: - Piloting the draft by-law governing implementation of diversionary schemes in Belgrade, Nis, Novi Sad and Kragujevac - Defining the role of the guardianship authority as the organization responsible for the implementation of diversionary schemes; - Defining mechanisms for long-term funding of diversionary schemes; - Improving the use of alternative sanctions; - Better data collection measures implemented with introduction of any new mechanisms to monitor effectiveness over time and document impact on children. |  |  | -Ministry of Justice -Ministry of Labour, Employment, Veterans and Social Affairs -Republc institute for social protection |  | Continuously, until an adequate rate of application of diversionary schemes is reached. | IPA 2019 | Use of diversionary schemes increased. Percentage of implementation of diversion orders in the total number of criminal charges for criminal offenses committed by juveniles (Baseline: 9.5% (330) for public prosecutors and judges 3.4% (68) in 2017. Target 15% increase by end of 2020 and 20% increase by 2022 The role of social protection systems specified, including through the promotion of the guardianship procedures related to guardianship bodies The issue of funding implementation of diversion schemes regulated. Percentage of the use of specific obligations increased. Baseline 2017 30.8% |  |  | Activity is partially implemented. There were no activities aimed at achieving this goal, since the beginning of the implementation of these activities is planned for the second part of this year. |  |  |
| 3.4.4.13. | Improving the competencies of professional staff in the field of social protection for the application of diversionary schemes. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Republc institute for social protection |  | Continuously | Budget of the Republic of Serbia - 5.400 € in 2020. - 1.800 € in 2021. - 1.800 € in 2022. -1.800 € | Number of professional staff who improved competencies for the application of diversionary schemes. |  |  | Аctivity is being successfully implemented. During the fourth quarter, the cycle for the second accredited program “Role of CSWs and other social protection service providers in the application of educational orders” was realized. 10 trainings were conducted: •13-15 October - Zrenjanin •4 November – Čačak •10 November – Valjevo •16 and 17 November – Leskovac •22 November – Šabac •25 November – Sremska Mitrovica •2 December - Kruševac The total number of professionals who have completed this accredited program in this cycle is 170. It can be concluded that the implementation of these activities has improved the competence of 326 professionals from the centres for social work of 36 municipalities. |  |  |
| 3.4.4.14. | Adopt bylaws specifying the implementation of diversionary schemes in line with the approach placing the implementation of diversionary schemes in the context of community responsibility. |  |  | -Ministry of Justice |  | By II quarter of 2021. | Budget of the Republic of Serbia – 8. 642 € | Bylaws specifying the implementation of diversionary schemes adopted. |  |  | Activity is not implemented. As the amendments to the Law on juvenile criminal offenders and criminal protection of juveniles were not adopted, the accompanying bylaws were not adopted either. |  |  |
| 3.4.4.15. | Conduct training and support continued certification of judges, prosecutors, lawyers and police officers in contact with juvenile offenders. |  |  | -Judicial Academy |  | Continuously, in line with annual training program of the Judicial Academy | Budget of the Republic of Serbia – Budgeted in activity 1.3.1.1. | All judges and prosecutors who handle juvenile cases attended training at the Judicial Academy and are licensed to work with juveniles. For police officers: Target: 30 police officers per year to undergo certification |  |  | Аctivity is being successfully implemented. According to the Programme of the Judicial Academy, seminars were held on 5 June, 4 June, 2 June, 22 May, and 23 April 2021 in the area of criminal law on the topic of: juveniles as perpetrators of criminal offences and juveniles as injured parties of a criminal offence. The trainings were attended by: Basic Court judges – Criminal Department (16), Misdemeanour Appellate Court judges and Misdemeanour Court judges (103), Basic Public Prosecutors and Deputies (1), Lawyers (65). All participants received certificates of seminar attendance. In II quarter 2022, 9 one-day seminars were conducted on the topic: ‘’Juveniles as offenders and as victims of criminal offence (Phase 1 and 2)’’, for the total number of 327 participants, of which 164 were from the ranks of attorneys-at-law and 163 from the ranks of judges. |  |  |
| 3.4.4.16. | Develop and implement specialized treatment programs and programs for release preparation of juvenile offenders. |  |  | -Administration for enforcement of criminal sanctions Partners: -Ministry of Health -Ministry of Education -Ministry of Labour, Employment, Veterans and Social Affairs |  | Continuously | Budget of the Republic of Serbia – 51.855 € 17.285€ per year | Specialized treatment programs and programs for release preparation of juvenile offenders developed and implemented in all institutions housing juvenile offenders. NPM report stating the successful implementation of these treatment programs. |  |  | Аctivity is being successfully implemented. The Republic Institute for Social Protection applied for and received from the EU project (REC project) which refers to the examination of needs, creation of programs and implementation of new treatment programs in all three Institutes of Education in Serbia: Belgrade, Nis, Knjazevac. Its realization began in February 2022. Accredited programs "Intensive treatment program for children with multiple behavioral disorders, emotional and social development and functioning and" Reintegration of minors in the social environment "in the I quarter of 2022 had no implementation. Within the project "Improvement of the capacity of the Administration for Execution of Criminal Sanctions in the Area of ​​Alternative Sanctions, Post-Penal and Health Protection", training of 13 treatment officers was held at the Educational Correctional Facility in Krusevac. Administration for Enforcement of Criminal Sanctions - As part of the project "Improving the capacity of the Administration for the execution of criminal sanctions in the area of ​​alternative sanctions, post-penal and health protection", the training of 6 trustees-trainers was held for the implementation of the program of providing assistance after the release of minors. Within the project of the Council of Europe, financed by the EU "Horizontal Facility for the Western Balkans in Turkey" in the part "Strengthening the protection of human rights of persons deprived of liberty", training was carried out for 12 employees of the treatment service in the Correctional Home in Kruševac and the Penitentiary for Juveniles in Valjevo for the application of new specialized treatment programs.In the correctional facility in Kruševac, starting in June 2022, a three-month training for employees from all services in the institution on the topic "Prevention of suicide and self-harm" is being conducted. Ministry of Labour – In II quarter 2022, focus groups were held with representatives of educational institutions, centres for social work, representatives of the judiciary, and the development of three roadmaps began, which will trace the introduction of new treatment programmes in educational institutions in Serbia. |  |  |
| 3.4.4.17. | Introduction of post-traumatic counselling and support for children victims / witnesses in criminal proceedings in the context of family support services. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs -Ministry of Justice - Republc institute for social protection |  | I quarter of 2016 to I quarter of 2020. | Budget of the Republic of Serbia – 8. 642 € | Post-traumatic counselling and support for children victims / witnesses in criminal proceedings introduced and service is clearly defined. |  |  | Activity is not implemented. Family support centres, and centres for children, youth and family, will be established after the adoption of amendments to the Law on Social Protection and the creation of a legal basis for their establishment. Post-traumatic counselling and support services for child victims/witnesses in criminal proceedings will also be introduced within these centres. |  |  |
| 3.4.4.18. | Improving regulations and practices for managing data in the courts by records keeping in compliance with the principle of 'best interests of the child' in civil proceedings. |  |  | -Ministry of Justice -Supreme Court of Cassation |  | Continuously, by IV quarter of 2020 | Budget of the Republic of Serbia – 8. 642 € | Regulations and practices for managing data in the courts by records keeping in compliance with the principle of 'best interests of the child' in civil proceedings improved. A unique report form for first instance courts developed and included in applications for case management, enabling the registration of all civil cases in which children appear as participants, with a special inquiry on "the best interest of the child". |  |  | Activity is partially implemented. The Working Group developed Guidelines for child participation in all civil proceedings. The Guidelines include: a) assessing ability of the child to give his/her opinion; b) how to prepare and introduce a child to the legal process and wider context of statement-giving, and c) the way in which the child’s opinion is sought, as well as the Instrument for assessing the best interest of the child. The Guidelines have been printed and distributed to all courts acting in civil proceedings and all centers for social work. Regarding this activity the Supreme Court of Cassation indicates that it could be envisaged to introduce the report for first instance courts within the case management system, and enable recording of all civil cases wherein the children participate. Whether, “the best interest of the child” has been assessed could not be registered in the case management application, and might only be the subject of consideration in the proceedings on legal remedies. The changes in the case law management system are in the competence of the Ministry of Justice. Ministry of Justice - Bearing in mind that the project of establishing a system for managing cases in courts of general jurisdiction and commercial courts (IPA2017 - SUPERSAPS) is underway, this issue will be part of the analysis and functional specification for the development of new software, so for reasons of efficiency, the modification of the current software (avp) is not planned, because it will be replaced by the mentioned software. |  |  |
| 3.4.4.19. | Monitor implementation of new multiannual Strategy for prevention and protection of children from violence and its Action Plan. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Monitoring mechanism defined by the Strategy |  | Commencing from II quarter of 2020. until the expiry of the Strategy | Budget of the Republic of Serbia- 6.915 € in 2020. - 2.305 € in 2021.- 2.305 € in 2022.- 2.305 € | Reports on implementation of new multiannual strategy for prevention and protection of children from violence and its Action Plan regularly developed and publicly available. |  |  | Аctivity is not implemented. The Minister of Family Care and Demography, as the President of the Council for the Rights of the Child, submitted to the Government the initiative for the formation of the Working Group for the implementation and monitoring of the Strategy for the Prevention and Protection of Children from Violence for the period from 2020 to 2023. |  |  |
| 3.4.4.20. | Adoption of the new General Protocol for the protection of children from abuse and neglect in order to align with EU best practices. |  |  | - Ministry of Labour, Employment, Veterans and Social Affairs -UNICEF |  | Adoption of the Protocol: IV quarter of 2020. Continuous monitoring and reporting on the results | Budget of the Republic of Serbia – 17.285 € | New General Protocol for the protection of children from abuse and neglect adopted, aligned with EU best practices and its implementation is monitored. |  |  | Activity is fully implemented. The new General Protocol for the Protection of Children from Abuse and Neglect was adopted at the Government session on 10th February 2022. |  |  |
| 3.4.4.21. | Development of new special protocols for the protection of children from abuse and neglect and establishment of conditions for their mandatory implementation, particularly in the areas of: -Acting of judicial authorities to protect children from abuse and neglect; -Protection of children in institutions of social care from abuse and neglect; -Acting of police officers to protect children from abuse and neglect; -Protection of children from abuse and neglect in the health care system; -Protection of children and students from violence, abuse and neglect in educational institutions. |  |  | -Ministry of Justice -Ministry of Labour, Employment, Veterans and Social Affairs -Ministry of Education -Ministry of Interior -Ministry of Health -UNICEF |  | – By II quarter of 2021(harmonization of the protocol) 2021. (harmonization of sectorial bylaws). | Budget of the Republic of Serbia – 17.285 € | Special protocols to protect children from abuse and neglect developed and their implementation is monitored. The adoption of sectorial bylaws establishing mechanism for their mandatory implementation. |  |  | Activity is not implemented Ministry of Justice – This issue will be considered through the work on amendments to the Criminal Procedure Code. Additionally, bearing in mind that the adoption of amendments to the Law on Civil Procedure is planned, this issue will also be considered during the work on amendments to this law. Ministry of Interior - Continuous work is being done on the preparation and drafting of a proposal for a Special Protocol on Police Actions in Protecting Children from Violence in accordance with the new General Protocol for the Protection of Children from Violence adopted by the Government of the Republic of Serbia on February 10, 2022. Ministry of Education, Science and Technological Development - Amendments to the General Protocol for the Protection of Children from Violence have been adopted (with the entry into force of the General Protocol for the Protection of Children from Violence, the General Protocol for the Protection of Children from Abuse and Neglect, which was adopted by Government Decision 05 No. 011-5196/2005 of 5 August 2005 and which is an integral part of the aforementioned decision, ceases to be valid), whose general objective is to ensure the systematic continuous prevention of all forms of violence against children and to ensure efficient, intersectoral protection measures when there is suspicion or knowledge of violence involving children. By the end of June 2022, a total of 12,859 participants have passed the online training for the implementation of the Rulebook on the Protocol of Acting of the Institution in relation to Violence, Abuse and Neglect, https://www.youtube.com/watch?v=XIVXRxiSYwk Three online trainings of national importance for education have been developed, which aim to improve the competencies of employees in education for the application of procedures for protection against violence and preventive work with students. The Protocol on providing intersectoral services through software solution “I Protect You” has been adopted. The development of part of the platform's software solution related to reporting cases of violence and monitoring of the system's actions is in progress. Until the end of June 2022, a total of 34,804 employees from educational institutions, 2,864 parents and 4,855 students have attended trainings via the platform. The trainings via the platform include information on the application and procedures prescribed by the Rulebook on the Protocol of Acting of the Institution in relation to Violence, Abuse and Neglect. |  |  |
| 3.4.4.22. | Implementation of a mechanism for resolving cases of missing infants from maternity hospitals in relation to the decision of the ECHR Zorica Jovanovic vs. Serbia (no. 21794/08) to enable all parents in similar situations to get adequate answers and compensation, in accordance with the Law on Determining the Facts on the Status of Newborn Children Suspected of Missing from Maternity Hospitals in the Republic of Serbia ("Official Gazette of RS", No. 18 of March 3, 2020). |  |  | - Higher courts -Ministry of Interior -Republic Public Prosecutor's Office -Ministry of Health |  | Continuously | Budget of the Republic of Serbia – Regular activity | Mechanism for resolving cases of missing infants from maternity hospitals functional. Number of cases reviewed on the basis of the established mechanism |  |  | Аctivity is being successfully implemented. The mechanism established by the Law has been implemented. According to the Anual Report on Work of Courts for 2021, before higher courts ruling in the first instance in this type of cases, 189 cases were resolved, and there were pending 532 cases. Before appellate courts 47 cases were resolved, and three cases were pending at the end of the year. Supreme Court of Cassation – New statistical data will be available upon the adoption of the novel six-month report on the work of the courts. Ministry of Interior -In II quarter 2022, police officers of the criminal police continued to work in 302 cases to establish the facts about the status of newborn children who are suspected of having disappeared from a maternity hospital in the Republic of Serbia at the request of the High Court in Belgrade, Kragujevac, Niš and Novi Sad. |  |  |
| 3.5. PROCEDURAL SAFEGUARDS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  | OVERALL RESULT |  |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.5.1. Serbia adopts a new Law on Legal Aid and establishes a well-resourced legal aid system. Serbia amends its legislation (including the Criminal Procedure Code) so as to align it with the EU acquis on procedural rights and on victim's rights. Serbia provides the necessary training and monitors the implementation of EU compatible procedural safeguards legislation and takes remedial action where needed. |  |  |  |  | The principle of the right to a fair trial is effectively implemented. Access to justice is guaranteed through the establishment of a functional free legal aid system and greater guarantees recognized for the suspect or accused persons to exercise the right to have access to a lawyer, the right to information and the right to interpretation and translation in line with the relevant EU Acquis. Minimum standards on rights, support and protection of victims of crime implemented in practice. |  |  | 1.European Commission Annual Progress Report on Serbia stating progress in the part relating to access to justice; 2.Reports from international and non-governmental organizations and CEPEJ indicating progress in the part relating to access to justice; 3.Statistical and qualitative data in the Annual report of the Ministry of Justice on the number and structure of beneficiaries, proceedings in which free legal aid was provided and costs of the provision of free legal aid; 4.Increased number of approved requests for exercising the right to free legal aid in 2020; 5.Increased number of suspect or accused persons exercising the right to have access to a lawyer through free legal aid system; 6. The average duration of court proceedings (per subject). 7. Significant improvement of victims' rights confirmed through development/increased number of specialist and general victims' support services, increased number of victims of crime benefitting from free legal aid, increased number of victims of crime being treated according to their needs (following individual assessment of victims of crime). |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADLINE |  | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.5.1.1. | Analysis of alignment of procedural laws with the Law on Free Legal Aid and subsequent amendments. |  |  | -Ministry of Justice | By I quarter of 2021 |  | Budget of the Republic of Serbia 15.439 € -MDTF - 284,475.62 € | Analysis of alignment of procedural laws with the Law on Free Legal Aid conducted and the need for amendments identified. Procedural laws amended in line with identified needs for alignment. |  |  | Аctivity is fully implemented. Analysis of the necessary amendments was provided to the MoJ. The proposed amendments to the Civil Procedure Code are included in the Draft CPC. |  |  |
| 3.5.1.2. | Anticipate effective allocation of budget to fund the free legal aid system, in particular when it comes to obligations of the local self-government units. |  |  | - Local Self-government units – identification of eligible beneficiaries and determination of the right to free legal aid - Ministry of Justice -disbursement of fees and other expenses based on the right to free legal aid -Ministry of Finance- establishment of a framework for public expenditure to finance the legal aid system, especially in terms of financing the competence of local self-government units | Continuously, commencing from the adoption of the law |  | Budget of the Republic of Serbia- 7.923.372€ а) payments of the rights - 7.859.546 € and б) administration in Ministry of Justice - 63.825 € in 2020.-2.641.124 € in 2021.-2.641.124 € in 2022.-2.641.124 € | Effective allocation of budget to fund the free legal aid system anticipated. |  |  | Аctivity is being successfully implemented. The new annual report of the MoJ with new data is available at https://www.mpravde.gov.rs/files/Godisnji%20izvestaj%20o%20pruzanju%20besplatne%20pravne%20pomoci%202021.pdf New data for 2021 were published on March 31, 2022 at the website of the Ministry of Justice. In the reporting period, the total number of submitted requests for free legal aid was 4,601, while the number of approved requests was 4,345. Data indicate that over 90% of applications have been approved. When it comes to forms of free legal aid such as legal advice and free legal support that are not subject to approval, the data indicate that the number of beneficiaries who were provided legal advice is 20,470, while the number of beneficiaries who provided general legal information is 7,360 and legal assistance provided in compiling forms was provided to 1325 beneficiaries. It is important to note here that these are registered users, while a large number of local self-government units state that they provide these types of legal assistance and support to all citizens who apply. In the period from 01.01.2020. until 31.12.2020, the total amount of 344,000 dinars was paid based on the request for the return of funds paid by the local self-government unit for free legal aid. In the period from 01.01.2021. until 31.12.2021, 123 requests, in the total amount of 1,321,000 dinars, were paid based on requests for the return of funds paid by the local self-government unit for free legal aid. In the period from 01.01.2022. until 31.03.2022, 29 requests were paid based on the request for the return of funds paid by the local self-government unit for free legal aid, in the total amount of 265,000 dinars. In the period from 01.01.2022. until 31.03.2022, 29 requests were paid based on the request for the return of funds paid by the local self-government unit for free legal aid, in the total amount of 265,000 dinars. In the period from 01.04.2022. until 14.06.2022, 172 requests were paid based on requests for the return of funds paid by the local self-government unit for free legal aid, in the total amount of 1,836,410 dinars. The total amount paid in the period from 01.01.2022. until 13.06.2022. year is 2,101,035 dinars. |  |  |
| 3.5.1.3. | Conduct training of: - free legal aid providers in relation to the start of implementation of the Law on Free Legal Aid - staff in local self-government units who decide on free legal aid applications. |  |  | -Ministry of Justice | Continuously, commencing from III quarter of 2019. |  | - Budget of the Republic of Serbia- 3.600 € in 2020.-1200 € in 2021.-1200 € in 2022.-1200 € -MDTF- 284,475.62 € | Training of all groups of free legal aid providers and staff in local self-government units who decide on free legal aid applications conducted. Number of participants. |  |  | Аctivity is being successfully implemented. On February 23, 2022, the first part of the training was held for 30 employees of LSGs. On April 14, 2022, the second part of training was held for 30 employees of LSGs, who were then received the authorization of the Minister of Justice to decide on requests for free legal aid. The Ministry is in daily contact with staff in local self-government units who decide on free legal aid applications. Training for additional staff in LSG to be authorized to decide on FLA applications was organized in April 2021, due to stuff turnover in LSGs. |  |  |
| 3.5.1.4. | Conduct a campaign to provide information to citizens about the Law on Free Legal Aid. |  |  | -Ministry of Justice | Continuously, commencing from I quarter of 2020. |  | Budgeted in activity 3.5.1.2 -MDTF- 284,475.62 € | Campaign to provide information to citizens about the Law on Free Legal Aid conducted. Free legal aid application forms available to vulnerable groups, in particular to convicted persons and persons in institutions of social protection. |  |  | Аctivity is being successfully implemented. Representatives of MoJ continuously provide information regarding the possibility to use free legal aid. Concurrently, LSGs provide information to citizens. A broader campaign has been postponed due to epidemiological situation. In December, YUCOM organized a conference for LSG staff and the MoJ representatives participated. The focus was on wider knowledge of the citizens regarding the availability of free legal aid. |  |  |
| 3.5.1.5. | Monitoring of the implementation of the FLA Law and analysis of the results and the cost of implementation. |  |  | -Ministry of Justice | Continuously, commencing from II quarter of 2020. |  | Budget of the Republic of Serbia Budgeted in activity 3.5.1.2 MDTF- 284,475.62 € | Analysis of the implementation of the FLA Law available to the public. Number of submitted applications for FLA. Number and type of beneficieries who were provided free legal aid. Number of registered providers per type. Data on provided free legal aid in criminal, civil and administrative proceedings. |  |  | Аctivity is being successfully implemented. The annual report of the MoJ with new data is available as of March 31, 2022 (https://www.mpravde.gov.rs/files/Godisnji%20izvestaj%20o%20pruzanju%20besplatne%20pravne%20pomoci%202021.pdf ). Monitoring of the implementation of the law is performed regularly, including ex officio supervision by the Ministry, as well as acting upon complaints of the citizens. |  |  |
| 3.5.1.6. | Analysis of the effects of implementation of the Law on a trial in reasonable time. |  |  | -Ministry of Justice -Supreme court of Cassation | I -III quarter of 2021. |  | Budget of the Republic of Serbia - 17.285 € | Analysis of the effects of implementation of the Law on a trial in reasonable time conducted, including the number of complaints addressed, duration of trial and average compensation awarded. |  |  | Аctivity is fully implemented. Although the activity was implemented, the Ministry of Justice, with the support of the Council of Europe, began to prepare an additional analysis, which is in the final stage. The analysis is expected to be presented in the III quarter of 2022. In I quarter 2022, it was reported that previous activities on Analysis of the effects of implementation of Law on Protection of right to trial in a reasonable time have been continued ( with support of the project „Strengthening the effective legal remedies to human violation in Serbia “ within a joint program of the European Union and the Council of Europe „Horizontal Facility for the Western Balkans and Turkey 2019-2022"). Within the Annual Report on Work of Court for 2022, the data on implementation of the Law on Protection of right to trial in reasonable time are analyzed. A total of 13,109 cases in which the parties claimed just satisfaction for non-pecuniary damages were received pursuant to the decisions of court presidents upholding objections requesting acceleration of proceedings and finding infringement of the right to a trial within reasonable time before Basic Courts in the Republic of Serbia, as well as 7,821 new lawsuits for compensation of pecuniary damages, due to the infringement of the right to a trial within reasonable time (total of 20,930 pecuniary and non-pecuniary damage cases). |  |  |
| 3.5.1.7. | Adopt the Criminal Procedure Code amendments based on the recommendations in the analysis to align with: - Directive 2013/48/EU on the right of suspect or accused persons to have access to a lawyer, in terms of strengthening the right of suspects and accused persons to access to a lawyer without delay and before any questioning by investigators in criminal proceedings and proceedings by the European arrest warrant. - Directive 2010/64/EU on the right to interpretation and translation, in order to precisely define the withdrawal from the right to translation- Directive 2012/13/EU on the right to information, in order to improve the exercise of the right to information, - Directive (EU) 2016/343 of the European Parliament and of the Council of 9 March 2016 on the strengthening of certain aspects of the presumption of innocence and of the right to be present at the trial in criminal proceedings - Directive (EU) 2016/800 of the European Parliament and of the Council of 11 May 2016 on procedural safeguards for children who are suspects or accused persons in criminal proceedings, - Directive (EU) 2016/1919 of the European Parliament and of the Council of 26 October 2016 on legal aid for suspects and accused persons in criminal proceedings and for requested persons in European arrest warrant proceedings, and two recommendations (1) on procedural safeguards for vulnerable persons [C(2013) 8178], (2) on the right to legal aid for suspects or accused persons in criminal proceedings [C(2013) 8179. |  |  | - Ministry of Justice -National Assembly | By IV quarter of 2021. |  | Budget of the Republic of Serbia - 71.136 € | Criminal Procedure Code amendments adopted enabling alignment with the EU acquis on procedural safegurds. |  |  | Activity is not implemented. Extensive changes of criminal legislation are planned to be implemented by the IV quarter of 2022. |  |  |
| 3.5.1.8. | Analysis of the effects of implementation of the amendments and supplements to the Criminal Procedure Code with regard to procedural safeguards focusing on legislative, operational and financial aspects. |  |  | -Ministry of Justice | Continuously, commencing from I quarter of 2022. |  | Budget of the Republic of Serbia – 2.305 € | Reports on the implementation of the amendments and supplements to the Criminal Procedure Code with regard to procedural safeguards focusing on legislative, operational and financial aspects developed and publicly available. |  |  | Activity is not implemented. Extensive changes of criminal legislation are planned to be implemented by the IV quarter of 2022. |  |  |
| 3.5.1.9. | Amend and supplement Criminal Procedure Code in order to provide temporary legal aid granted without undue delay after deprivation of liberty and before any questioning by the police, other law enforcement authorities or court authority for the purposes of criminal proceedings which involve a suspect or defendant. |  |  | - Ministry of Justice -National Assembly | By IV quarter of 2021. |  | Budget of the Republic of Serbia – Budgeted in 3.5.1.7. | Amendments to the Criminal Procedure Code adopted enabling temporary legal aid in criminal proceedings. |  |  | Activity is not implemented. Extensive changes of criminal legislation are planned to be implemented by the IV quarter of 2022. |  |  |
| 3.5.1.10. | Design a ‘Letter of Rights’ that shall be provided to an arrested person, suspect or an accused person by the police/prosecution. |  |  | -Ministry of Justice -Republic public prosecutors’ office -Supreme Court of Cassation | By IV quarter of 2021. |  | Budget of the Republic of Serbia- 8.642 € | Letter of Rights designed and provided to an arrested person, suspect or an accused person by the police/prosecution. |  |  | Activity is not implemented. Extensive changes of criminal legislation are planned to be implemented by the IV quarter of 2022. |  |  |
| 3.5.1.11. | Distribute „Letter of Rights” in all police stations and prosecutor's offices in order to enable its permanent availability in: - Serbian language - language of national minorities throughout the country - English language Ensure translation of the letter of rights by the official court translator to a language that the suspect or accused person understands if that language differs from the ones mentioned above. |  |  | - Ministry of Justice | Continuously, commencing from I quarter of 2022. |  | Budget of the Republic of Serbia Costs currently unknown Apply for IPA 2021 | Letter of Rights distributed and permanently available in all police stations and prosecutor's offices and used for informing persons about their rights. Translation of the letter of rights by the official court translator to a language that the suspect or accused person understands provided. |  |  | Activity is not implemented. Extensive changes of criminal legislation are planned to be implemented by the IV quarter of 2022. |  |  |
| 3.5.1.12. | Conduct training of the police officers, prosecutor’s and deputy prosecutors and judges in terms of stronger procedural safeguards. |  |  | -Judicial academy | Continuously, commencing from I quarter of 2022. |  | Budget of the Republic of Serbia- Budgeted in activity 1.3.1.1. Apply for IPA 2021 | Training conducted. Knowledge of the police officers, prosecutor's and deputy prosecutors and judges in terms of stronger procedural safeguards improved. |  |  | Activity is being successfully implemented. The activity is foreseen by the program of the initial and continuous training of the Judicial Academy. During the reporting period, the trainings were conducted through online courses of the HELP program. |  |  |
| 3.5.1.13. | Amend normative framework in order to effectively implement minimum standards concerning the rights, support and protection of victims of crime / injured parties in accordance with Directive 2012/29/EU and in line with the analysis. |  |  | -Working group established by the Ministry of Justice -National assembly | IV quarter of 2021. |  | Budget of the Republic of Serbia- 71.136 € | Normative framework aligned with the Directive 2012/29/EU. |  |  | Activity is not implemented. The deadline is postponed to IV quarter of 2022. |  |  |
| 3.5.1.14. | Design and distribute a brochure/ booklet containing information on victims’ rights (legal aid, psychological support, protection, etc.) in line with Art. 4 of the Directive 2012/29/ ЕU. |  |  | - Ministry of Justice -In cooperation with civil society organizations | Continuously, commencing from II quarter of 2021. |  | Budget of the Republic of Serbia Costs currently unknown Apply for IPA 2021 | Brochure/ booklet containing information on victims’ rights (legal aid, psychological support, protection, etc.) in line with Art. 4 of the Directive 2012/29/ ЕU designed and distributed. |  |  | Activity is not implemented. As the Criminal Procedure Code has not yet been amended, it was not possible to start implementation of this activity. |  |  |
| 3.5.1.15. | Strengthening of professional capacities in the area of exercising the rights of victims and witnesses of criminal offenses in the Republic of Serbia (judges, prosecutors, members of judicial police, attorneys and police officers). Link with Victims Strategy measure 1.4. |  |  | -Judicial Academy -Criminalistic police university | Continuously commencing from IV quarter of 2020. |  | Budget of the Republic of Serbia- Budgeted in activity 1.3.1.1 | Judges, prosecutors, members of judicial police, attorneys and police officers improved their skills regarding the implementation of minimum standards regarding the rights, support and protection of victims in accordance with Article 25 of Directive 2012/29 / EU. |  |  | Аctivity is being successfully implemented. In I quarter 2022, 2 one-day trainings on domestic violence (Phase 1) were conducted, in which a significant part of the training was dedicated to the protection and support of victims. The trainings were attended by the following participants: 11 judges, 5 assistant judges, 16 prosecutorial associates, 4 deputy public prosecutors, 1 court secretary. During II quarter 2022, 2 one-day trainings on domestic violence (Phase 1) were conducted, in which a significant part of the training was dedicated to the protection and support of victims. The trainings were attended by the following participants: 26 judges, 1 assistant judge, 5 basic public prosecutors and deputy public prosecutors, 1 beneficiary of the JA. |  |  |
| 3.5.1.16. | Adoption of the National Strategy for the Exercise of the Rights of Victims and Witnesses with the accompanying Action Plan. |  |  | -Government of the Republic of Serbia -Ministry of Justice -Ministry of Interior -High Judicial Council -State prosecutorial council -Republic public prosecutors’ office -Supreme Court of Cassation -Prosecutors office for war crimes | III quarter of 2020. |  | Budget of the Republic of Serbia – 30.878 € IPA 2016 "Support to Victims and Witnesses of Criminal Offenses in Serbia" Implementing Partner OSCE Mission in the Republic of Serbia | National Strategy for the Exercise of the Rights of Victims and Witnesses with the accompanying Action Plan adopted. |  |  | Activity is fully implemented. National Strategy for the Exercise of the Rights of Victims and Witnesses with the accompanying Action Plan have been adopted in July 2020. |  |  |
| 3.5.1.17. | Full implementation and regular monitoring of the National Strategy for the Exercise of the Rights of Victims and Witnesses and its accompanying Action Plan. |  |  | - Ministry of Justice -Ministry of Interior -High Judicial Council -State prosecutorial council -Republic public prosecutors’ office -Supreme Court of Cassation -Prosecutors office for war crimes | Continuously, commencing from IV quarter of 2020 |  | For monitoring: Budget of the Republic of Serbia - 9,468€ in 2020 3,156€ in 2021 3,156€ in 2022 3,156€ For implementation: Budgeted in the AP of the National Strategy for the Exercise of the Rights of Victims and Witnesses IPA 2016 "Support to Victims and Witnesses of Criminal Offenses in Serbia" Implementing Partner OSCE Mission in the Republic of Serbia | Coordination body for support to victims and witnesses established and holds regular meetings. Reports on implementation of the Strategy regularly developed and publicly available. |  |  | Activity is being successfully implemented. The second session of the Coordination Body for the Support of Victims of Criminal Acts and Witnesses in Criminal Proceedings was held on March 22, 2022. The first report on the implementation of the National Strategy on the Rights of Victims and Witnesses of Crime, for the period from the adoption of the Strategy until the end of I quarter of 2022, which was compiled by all relevant institutions, was adopted on June 30, 2022. |  |  |
| 3.5.1.18. | Establishment of a network of services for the support to victims, witnesses and injured parties across the country in investigation phase and all phases of criminal proceedings. Link: the same activity in APCH 23 – War crimes |  |  | -Ministry of Justice -Ministry of Interior -High Judicial Council -State prosecutorial council -Republic public prosecutors’ office -Supreme Court of Cassation -Prosecutors office for war crimes | Gradually, commencing from IV quarter of 2020 |  | Budget of the Republic of Serbia- Budgeted in activity 1.4.1.1 IPA 2016 "Support to Victims and Witnesses of Criminal Offenses in Serbia" Implementing Partner OSCE Mission in the Republic of Serbia | A network of services for the support to victims, witnesses and injured parties across the country established. Baseline: 0 in 2019 Target: By IV 2022 – 15 support serices for victims and witnesses |  |  | Activity is partially implemented. The Ministry of Justice has already started implementing numerous activities related to this area: - by amending the Rulebook on systematization and organization of workplaces, the Ministry of Justice established the position of coordinator of support services for victims and witnesses of criminal acts; - after obtaining the approval of the Ministry of Finance on the proposed personnel plans of judicial authorities, through amendments to the Rulebook on systematization, workplaces of support for victims and witnesses of criminal acts will be introduced at the higher courts in the Republic of Serbia; the implementation of this activity has already begun. |  |  |
| 3.5.1.19. | Fully implement stronger procedural safeguards for the victims of war crimes in accordance with the National Strategy for the Exercise of the Rights of Victims and Witnesses and its accompanying Action Plan and the amendments to the Criminal Procedure Code in the part relating to procedural safeguards. (Linked with the part on war crimes) |  |  | -Special prosecutors’ office for war crimes | Continuously, in accordance with the dynamics of the implementation of amendments to the Criminal Procedure Code |  | Budget of the Republic of Serbia- Budgeted in 1.4.7.7. | Stronger procedural safeguards for the victims of war crimes are fully implemented. |  |  | Activity is being successfully implemented. The War Crimes Prosecutor's Office continues to implement relevant laws and by-laws and strategic documents with the aim of implementing existing procedural guarantees for victims of war crimes and procedures in accordance with Directive 2012/29/EU. Also, the special section Organization – “Support for Victims and Witnesses of Crime” on the OWCP website presents the most important information about the work of that service. Among other things, it contains the contact information of the members of the service, the brochure of the Republic Prosecutor’s Office for witnesses and victims, as well as strategic documents of importance for that area, all with the aim of faciliating the access of interested parties to this service. Harmonization of further proceedings will be started after the implementation of the planned changes to the normative framework in the field of criminal law in the part related to procedural guarantees, in accordance with the National Strategy on the Rights of Victims and Witnesses. |  |  |
| 3.5.1.20. | Continuation of cooperation with CSOs specialized in victim support to enable stable functioning of general and specialist support services. |  |  | -Republic public prosecutors’ office -CSOs | Continuously |  | Budget of the Republic of Serbia- Activity requiring insignificant costs. | Cooperation protocols with CSOs specialized in victim support signed and are fully inplemented in order to enable stable functioning of general and specialist support services. |  |  | Activity is being successfully implemented. Implementation of this activity is ongoing. In the reporting period the Republic Public Prosecution Office continued cooperation with civil society organizations specialized in providing support to victims such as the Victimology Society, Astra, Atina based on previously signed cooperation agreements. Furthermore, The Republic Public Prosecution Office continued participation in the implementation of the project "Capacity Building and Support to Coordination and Cooperation Groups in Response to Domestic Violence and Other Forms of Gender-Based Violence", in cooperation with the Victimology Society of Serbia and UN Women. The overall goal of the project is to strengthen the capacity of the Coordination and Cooperation Groups formed in the basic public prosecutions in Serbia to assess the needs of victims and develop individual plans of support and protect victims of domestic violence and other forms of gender-based violence. In order to implement the project, over twenty Basic Public Prosecution Office submitted anonymized individual plans for protection and support of victims developed in the period between January 1 and June 30, 2021, as well as anonymized minutes from meetings of Coordination and Cooperation Groups when these individual plans were made. The Republic Public Prosecutor's Office continued the previously established cooperation with civil society organizations specialized in providing support to victims. |  |  |
| 3.5.1.21. | Amend legislative framework to define the concept of the victim in order to be aligned with relevant international treaties. |  |  | -Ministry of Justice | IV quarter of 2020. |  | Budget of the Republic of Serbia- 17.285 € | Legislative framework to amended and defines the concept of the victim aligned with relevant international treaties. |  |  | Activity is not implemented. The activity will be implemented together with other normative amendments to the Action Plan for the implementation of the National Strategy for the Realization of the Rights of Victims and Witnesses. |  |  |
| 3.6. POSITION OF NATIONAL MINORITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.6.1. Serbia implements its legal framework on the rights of persons belonging to minorities as well as "The action plan for the realisation of the rights of national minorities" in its entirety, contributing to the effective and equal implementation throughout its territory of the recommendations of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities. Particular emphasis is put on education, the use of minority languages, access to media and religious services in minority languages and adequate representation in the public administration. Serbia closely monitors its implementation in an inclusive and transparent manner, assesses its impact by the end of 2018 and reports on progress. |  |  |  |  |  | A specific action plan taking into account the recommendations issued in the third Opinion on Serbia in the context of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities, second report of the expert committee on implementation of the European Charter on Regional and Minority languages in the Republic of Serbia and on implementation of bilateral agreements on the protection of national minorities, focused on the effective implementation of existing rights of national minorities adopted through an inclusive process and implemented. |  | 1. Report of the Advisory Committee of the Council of Europe Framework Convention for the Protection of National Minorities noting progress in exercise of right of national minorities; 2. Report of the expert committee on implementation of the European Charter on Regional and Minority languages in the Republic of Serbia stating that there has been progress with regard to implementation of the minority language rights undertaken as a Charter obligation; 3. Reports on implementation of bilateral agreements on protection of national minorities stating higher level of implementation of bilateral agreements; 4. Quarterly reports on implementation of AP for exercise of the rights of national minorities stating 80% or more level of implementation; 5. Annual report of the Commissioner for Equality noting improvements in the field of protection of rights of national minorities; 6. Annual report of the Ombudsman noting improved level of implementation of rights of national minorities. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.6.1.1. | Monitoring implementation of the Special Action plan for the exercise of the rights of national minorities. |  |  | -Council for National Minorities, with the administrative support of the Office for Human and Minority Rights; -Ministry of State Administration and Local Self-government. |  | Continuously, until the expiry of the Action Plan | Budget of the Republic of Serbia- 6.915 € 2.305 € per year | Meetings of the Council for National Minorities are regularly held. Reports on implementation of the Action Plan are regularly developed and publicly available. |  |  | Activity is being successfully implemented. The 19th report on the implementation of the Action Plan for the exercise of the rights of national minorities has been prepared, which refers to Q1 and Q2 2021. The report was forwarded to national councils for information and comment, and is also available on the website of the Ministry of Human and Minority Rights and Social Dialogue. The second meeting of the Special Working Group for the development of the draft Action Plan was held on 23 – 25 February 2022. In addition to the members of the Special Working Group, the meeting was attended by representatives of national councils assigned by the Coordination of National Councils for each of the four areas in which national councils exercise powers (culture, information, official use of language and script and education). At this meeting, a working version of the future Action Plan was prepared, which envisages a large number of activities aimed at improving the position of national minorities. The third meeting of the Special Working Group was held on 31 March - 1 April 2022. At the third meeting of the Working Group, the comments and suggestions of the competent state bodies on the working version of the text of the Draft Action Plan for Exercising the Rights of National Minorities were discussed and it was aligned with the proposed measures and activities. In addition to the members of the working group, the meeting was attended by other representatives of relevant state bodies. In addition to the meetings of the members of the Special Working Group, with the view of more precisely defining Action Plan measures and activities, individual consultative meetings were held with representatives of relevant state bodies and representatives of national councils of national minorities. The eleventh session of the National Minority Council was held on May 27, 2022. The session was presided by Madame Prime Minister with all the members of the Council, representatives of state institutions and all representatives of National Councils of the National Minorities present. The number of reports (16th, 17th 18th and 19th) on implementation of the Action plan for exercising the rights of National Minorities were presented along with the draft Action plan for exercising the rights of National Minorities, Apart for the above-mentioned, the Proposal of the Programme for allocation of funds pertaining to the Budget fund for National Minorities for 2022 was unanimously adopted, along with the priority area for financing- culture, with an aim to promote, nurture and strengthen the cultural- linguistic identity of National Minorities in the Republic of Serbia. |  |  |
| 3.6.1.2. | Analysis of the effects of implementation of the Special Action Plan for the Exercise of the Rights of National Minorities, including recommendations for further activities to improve the exercise of the rights of national minorities. |  |  | -Office for Human and Minority Rights |  | For the analysis: III-IV quarter of 2020 | Budget of the Republic of Serbia 8.642 € Horizontal Facility II | Independent analysis of the effects of implementation of the Special Action Plan for the Exercise of the Rights of National Minorities performed, taking into account impact indicators. Recommendations for further activities to improve the exercise of the rights of national minorities provided. |  |  | Activity is fully implemented. The analysis of the effects of the implementation of the Action Plan for the Exercise of the Rights of National Minorities was prepared by independent experts within the Joint Program of the European Union and the Council of Europe, Promotion of Diversity and Equality in Serbia. The main goal of the analysis was to provide an assessment of the effects of the Action Plan, i.e. to assess its relevance, effectiveness, efficiency and sustainability, in order to decide on future steps in planning public policies in the field of national minority rights. The monitoring of quarterly reports served to conclude how the Action Plan was implemented in practice, i.e. whether the planned activities were implemented according to the planned dynamics, what progress was achieved and whether the indicators set at the level of activities were met. Based on the findings, it was assessed whether the General Results and the indicators set along the results have been achieved. The analysis of the effects of the implementation of the Action Plan was presented on September 9, 2021. The presentation of the Analysis was attended by representatives of relevant state bodies, independent bodies, international organizations and representatives of national councils of national minorities. On November 30, 2021, the Ministry of Human and Minority Rights and Social Dialogue established a Special Working Group to prepare the text of the Draft Action Plan for the Realization of the Rights of National Minorities. Expert support of national consultants has been provided for the work on the preparation of this strategic document, within the project "Promotion of Diversity and Equality in Serbia", which is part of the joint program of the European Union/Council of Europe "Horizontal Facility for the Western Balkans and Turkey 2019-2022". The Action Plan will be based, inter alia, on the Progress Report on Serbia's Accession to the European Union, on recommendations from the Fourth Opinion of the Advisory Committee on the Implementation of the Framework Convention for the Protection of National Minorities, and on the conclusions and recommendations from the Ex-Post Analysis. exercising the rights of national minorities. The first meeting of the Special Working Group for the preparation of the text of the Draft Action Plan for the Exercise of the Rights of National Minorities was held on December 20, 2021. |  |  |
| 3.6.1.3. | Identification of adequate model among various options such as: -project financing, -increased number of programs in languages of national minorities at public service broadcast providers (RTS/RTV) by declaring such content to be public service remit, in line with the new Media Strategy: -.monitoring the broadcasting of program content in the languages of national minorities in privatized media, who are obliged to broadcast in the languages of national minorities pursuant to their program plans, in the context of monitoring contractual obligations assumed by owners; Concurrently reviewing the impact of privatization and the introduction of digital television broadcasting on minority media, in consultation with all national minorities. |  |  | -Ministry of Culture and Information -Regulatory authority of electronic media -National councils of national minorities |  | For the Identification of adequate model: in line with new Media Strategy For implementation:Continiously | Budget of the Republic of Serbia - 25.926 € 8.642 € per year | Amendments to the Law on Public Information and Media. Increased amount of content in the languages of national minorities on public media services. |  |  | Activity is being successfully implemented. An open call was announced by the Ministry of Culture and Information in I quarter 2022, for co-financing projects for the production of media content in the languages ​​of national minorities. In 2022, for this open call 41,000,000.00 dinars were allocated. In II quarter 2022, the Ministry of Culture and Information implemented ten open calls for co-financing of projects for the realization of public interest in the field of public information. One of the implemented open calls is intended for co-financing of projects for the production of media content in the languages of national minorities, with 78 supported projects in the total amount of 41,000,000.00 dinars. Regulator generates reports on the activities of public service broadcasters on an annual basis, in which, inter alia, it identifies the duration of broadcast program in the languages of national minorities. Regulator's expert department has composed 2019 annual report for the public broadcasters “Radio Television of Serbia” (hereinafter referred to as RTS) and “Radio Television of Vojvodina (hereinafter referred to as RTV): http://rem.rs/sr/izvestaji-i-analize/izvestaji-i-analize-o-nadzoru-emitera/izveshtaji#gsc.tab=0 Regulator's expert department has composed 2020 annual report for the public broadcasters “Radio Television of Serbia” and “Radio Television of Vojvodina: http://rem.rs/sr/izvestaji-i-analize/izvestaji-i-analize-o-nadzoru-emitera/izveshtaji#gsc.tab=0. The Regulator supervises the work and monitors the broadcasting of program content in the languages of national minorities for privatized media, which in their program studies had the obligation to broadcast in the languages of national minorities, in terms of fulfilling contractual obligations. |  |  |
| 3.6.1.4. | Regular provision of sufficient and stable funding guaranteeing the sustainability of media in languages of national minorities through: -Continued budgetary support for media owned by the National Minority Councils; -Launching public call for co-financing of media in the languages of national minorities, with full respect of the opinions and proposals of national minority councils on funds distribution and guaranteeing respect of public procurement rules and principles. -co-financing of media in the languages of national minorities from the Budgetary Fund for national minorities; -Ensuring the participation of national minority councils in the council of the regulatory body for electronic media, based on transparent selection criteria. |  |  | -Ministry of Culture and Information -Government of the Autonomous Province of Vojvodina -Local self-government units |  | Continuously | Budget of the Republic of Serbia -Fund for National Minorities according to the program of priority areas, in accordance with the decision of the Council for National Minorities 252,101€ in 2020 -Budget Government of the Autonomous Province of Vojvodina- costs borne by Government of the Autonomous Province of Vojvodina 517.647 € in 2020 -Budget Local self-government units- costs borne by Local self-government units according to funds availability | Funds provided in the Budgetary Fund for National Minorities to provide co-financing of media in the languages of national minorities. Councils of national minorities participate in the work of the council of the regulatory body for electronic media on the basis of transparent rules. |  |  | Аctivity is being successfully implemented. In the I quarter 2022, an open call was announced by the Ministry of Culutre and Information for co-financing projects for the production of media content in the languages ​​of national minorities. In 2022, for this open call 41,000,000.00 dinars were allocated. In the reporting period, Provincial Secretariat for Culture, Public Information and Relations with Religious Communities 1. For the purpose of financing the media in languages of national minorities, owned by national councils of national minorities, the total amount of the funds allocated was 390,000,000.00 RSD. 2. For co-financing projects for the production of media content in the field of public information in 2022, the total of 7,500,000.00 RSD was allocated for the production of media content in the languages of national minorities - 3,500,000.00 RSD for private companies, and 4,000,000.00 for non-government organizations. Pursuant to the Provincial Assembly Decision on the Method and Criteria for Allocating Budgetary Funds for National Councils of National Minorities (“Official Journal of the APV”, No. 8/2019), the Provincial Secretariat for Education, Regulations, Administration and National Minorities - National Communities has planned funds to the national councils of national minorities in 2022, in the total amount of 61,600,000.00 RSD. For the purpose of performing the regular activities, which include financing the work of institutions, foundations and companies, whose founder or co-founder is the national council or whose founding rights have been partially or fully transferred to the national council, the Secretariat allocated 30,800,000.00 RSD in 2022. In the previous three months, the Secretariat signed grant contracts and transferred the funds for this purpose to those national councils based in the territory of APV, for the first and second quarters of 2022, in the amount of 15,375,000.00 RSD. On this basis, among other things, the work of newspaper publishing institutions, i.e. the media owned by national councils of national minorities, is indirectly co-financed. In II quarter 2022, the open call by the Ministry for Culture and Information for co-financing projects for the production of media content in the languages of national minorities was held, which was announced in the period from February 21, 2022 to April 6, 2022, for which funds in the total amount of 41,000,000.00 dinars were allocated. In accordance with the Law on Public Information and Media, 19 national councils of national minorities were asked for their opinion on the projects submitted to the open call. A total of 17 national councils submitted their opinions which were then submitted to the Commission that considered the projects. Out of a total of 206 applications-requests for co-financing of projects received at this public call, after checking whether the conditions for participation in the open call have been fulfilled, 13 applications-requests were rejected by a decision. Out of a total of 193 requests for co-financing that were decided upon, 78 projects were supported. In II quarter 2022, Pursuant to the Provincial Assembly Decision on the Method and Criteria for Allocating Budgetary Funds for National Councils of National Minorities (“Official Journal of the APV”, No. 8/2019), the Provincial Secretariat for Education, Regulations, Administration and National Minorities - National Communities has planned funds to the national councils of national minorities in 2022, in the total amount of 61,600,000.00 RSD. For the purpose of performing the regular activities, which include financing the work of institutions, foundations and companies, whose founder or co-founder is the national council or whose founding rights have been partially or fully transferred to the national council, the Secretariat allocated 30,800,000.00 RSD in 2022. In the previous three months, the Secretariat transferred the funds for this purpose to those national councils based in the territory of APV, for the second quarters of 2022, in the amount of 7.687.500,00 RSD. On this basis, among other things, the work of newspaper publishing institutions, i.e. the media owned by national councils of national minorities, is indirectly co-financed. |  |  |
| 3.6.1.5. | Raising public awareness about the rights of national minorities and respect for cultural and linguistic diversity by supporting the production of media content in order to achieve equal rights. |  |  | -Ministry of Culture and Information Partners: -Provincial Secretariat for Culture, Public Information and Relations with Religious Communities -Local government units -Public media services RTS and RTV |  | Continuously | Budget of the Republic of Serbia – 654.222 € 218.074€ per year | Number of supported projects in competitions for co-financing media content in the languages of national minorities Number of minutes on public service broadcasters focused on raising awareness on the rights of National minorities and promoting cultural and linguistic differences and culture of tolerance. Particular attention is given to the proposals and opinions of the councils of national minorities in the process of funds allocation for the media content on the rights of National minorities and promoting cultural and linguistic differences and culture of tolerance. |  |  | Аctivity is being successfully implemented. In I quarter 2022, an open call was announced by the Ministry for Culture and Information for co-financing projects for the production of media content in the languages ​​of national minorities. In 2022, for this open call 41,000,000.00 dinars were allocated. In the I quarter 2022, Provincial Secretariat for Culture, Public Information and Relations with Religious Communities for the purpose of financing media in the languages of national minorities, owned by national councils of national minorities, the total amount of the funds allocated in 2021 was 312,000,000.00 RSD. In the I quarter 2022, The Provincial Secretariat for Culture, Public Information and Relations with Religious Communities announced a competition for co-financing the production of media content in the languages ​​of national minorities and supported a total of 46 projects. Out of that, 21 projects of private companies were supported, in the following languages: four - Hungarian; five - Slovak; one - Romanian; three -Ukrainian; one- German; three Bunjevac; one- Czech and three multilingual projects. A total of 25 projects implemented by citizens' associations were supported in the following languages: six - Hungarian; six - Croatian; two -Bunjevac; one- Romani; one- Czech; one- Russian; three -German; one -Ukrainian; one -Romanian; two -Macedonian ​​and one multilingual project. In II quarter 2022, the Ministry of Culture and Information implemented this activity through the open call for co-financing of projects for the production of media content that promotes respect for differences due to the particularities of ethnic, cultural, linguistic or religious identity. Namely, in the aforementioned open call a total amount of 2,958,000.00 dinars was distributed for five projects that will be implemented in various languages of national minorities. In this reporting period, the Public Media Institution "Radio-Television of Vojvodina“ broadcast program content in the languages ​​of national minorities, namely: - During April, May and June, the second channel of Television Vojvodina broadcast 97,677 minutes of programs in the languages ​​of national minorities; - The second program of the radio broadcasts 24 hours of programs in the Hungarian language every day, which in total amounts to 131,040 minutes of programs; - The third program of the radio broadcasted 24 hours of programs every day, in 14 languages ​​of national minorities, totaling 131,040 minutes of programs. Meanwhile the Public Media Institution "Radio-Television of Serbia“ had 9,317 minutes of broadcast programs in Albanian, Roma, Hungarian, Croatian, Slovenian and Serbian languages. |  |  |
| 3.6.1.6. | Full implementation of the Law on textbooks which permanently ensures the required number of textbooks in languages of national minorities for each school year. |  |  | -Ministry of Education -National Education Council -Institute for educational resources -Institute for Evaluation of Quality of Education |  | Continuously, commencing from II quarter of 2018. | For monitoring implementation: Budget of Republic of Serbia- 17.931 € in 2020.- 5.977 € in 2021.- 5.977 € in 2022.- 5.977 € | Textbooks in minority languages adequately reflect the needs expressed by national minorities, remaining obstacles are removed and exercise of the right to education in minority languages is ensured. % completion of the textbook plan for teaching in the languages of national minorities according to the reformed school-based teaching and learning programs by school year; |  |  | Аctivity is being successfully implemented. In I quarter 2022 In order to improve the availability of textbooks in the languages of national minorities, the Ministry of Education, Science and Technological Development has prepared a Catalogue of textbooks in the languages of national minorities for preschools, primary and secondary schools for the school year 2022/23. The new Catalogue contains textbooks published by 24 publishers. Moreover, in the next school year 2022/23, the good practice of providing textbooks in the languages of national minorities under the free textbooks programme shall continue. This programme additionally provides support to students from socially and financially vulnerable families. The Ministry of Education, Science and Technological Development is making additional efforts in order to improve the quality and accessibility of education in the languages of national minorities, whereby the textbooks in the languages of national minorities are a significant part of such efforts. Students who attend all classes in one of the eight languages of national minorities (Albanian, Bosnian, Bulgarian, Hungarian, Rusyn, Romanian, Slovak and Croatian), as well as students who attend classes in Serbian language but are members of national minorities and attend the subject Mother tongue/speech with elements of national culture, have a total of 946 textbook units at their disposal, of which 482 have been published under reformed curricula. It is important to emphasize that with the increase in the number of textbooks published under the reformed curricula, the total number of textbooks decreases, because the textbook units according to the old curriculum are removed from the Catalogue. In II quarter 2022, MESTD makes additional efforts to provide as many textbooks as possible according to the reformed curricula, because textbooks in the languages of national minorities contribute to higher quality and availability of education in their mother tongue. For the school year of 2022/23, the Ministry has published the Catalogue of Textbooks in the Languages of National Minorities, at https://mpn.gov.rs/wp-content/uploads/2022/03/Katalog-udzbenika-na-jezicima-nacionalnih-manjina.pdf. For students who attend all classes in one of the eight languages of the national minorities, as well as for students who attend classes in Serbian language and are members of national minorities and attend an elective subject/programme “Mother tongue/speech with elements of national culture”, a total of 946 textbook units are available, of which 482 have been published under reformed curricula. We would like to stress that with the publication of textbooks approved under the reformed curricula, the total number of textbooks is reduced, because textbooks created before the education reform are erased from the Catalogue, while the number of reformed textbooks increases. The current catalogue of textbooks in the languages of national minorities contains textbooks published by 22 publishers. Having in mind the importance of access to education for all, the Ministry had also provided textbooks in the languages of national minorities under the Free Textbooks Programme, for the next school year 2022/23. This Programme additionally provides support to students from socially/materially disadvantaged families. For the current school year, a total of 62,452 textbook units have been provided under the Free Textbooks Programme. |  |  |
| 3.6.1.7. | Adopt and monitor the implementation of a new bylaw that regulates the response of the institution in case of doubt or an established discriminatory behavior. |  |  | -Ministry of Education |  | For adoption: By II quarter of 2019. For monitoring implementation: Continuously, through annual reports | Budget of Republic of Serbia- 9.468 € 3.156 € per year | Annual report on the work of the schools submitted to Ministry of Education which contains reports prepared by school teams for protection from discrimination indicating determined discrimination or segregation. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the topic of prevention of segregation and taking measures for desegregation are part of the continuation of the training "Let anti-discrimination be our inspiration - prevention and overcoming discrimination in kindergartens and schools", which is provided under the MESTD's budget for 200 new employees in the education system. The organization of the training is in progress. So far, the training has covered 650 employees in the education system. In II quarter 2022, the implementation of the training "Let anti-discrimination be our inspiration - prevention and overcoming discrimination in kindergartens and schools", which is provided under the MESTD's budget for 200 new employees in the education system, is in progress. |  |  |
| 3.6.1.8. | Introduction of the contents and topics that develop knowledge about rights of national minorities and the basic characteristics of national minorities living in the Republic of Serbia, promotion of culture of tolerance between members of the majority and national minority communities and inclusion of such content into the formal education system. Conduct ongoing performance evaluation, monitoring and improving the effects of introduced programs. |  |  | -Ministry of Education -National Education Council -Institute for Evaluation of Quality of Education -Institute for educational resources -CSOs -National Councils of national minorities |  | Introduction of topics and forms of work in formal education: Continuously, commencing from adoption of new Law on textbooks Performance evaluation and monitoring: Continuously, commencing from its introduction | -Introduction of topics and forms of work in formal education: Budget of Republic of Serbia- 11.706 € in 2020. - 9.663 € in 2021.- 1021 € in 2022.- 1022 € | Determined content themes and forms of work that promote a culture of tolerance between members of the majority and national minority communities. Themes and forms of work introduced into formal education at different levels. Performance evaluation and monitoring actively performed. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the Institute for the Improvement of Education, in cooperation with the Ministry of Education, Science and Technological Development, has developed a systemic training titled Training for pedagogical assistant for children and students of Roma nationality who need additional support in education. The programme is intended for pedagogical assistants who provide help and additional support to groups of children and students within the institution, as well as assistance and support to teachers, educators and professional associates in teaching and extracurricular activities, in order to improve their work with children and students of Roma nationality. The training programme is organized in four modules, and includes improving the competencies of pedagogical assistants in preschool and primary education. Special attention was paid to the treatment of topics dedicated to the history, language and culture of the Roma national minority. The second cycle of training titled Our Students in the World of Critical Thinking and Media Literacy was organized, which offers practical examples which are immediately applicable in practice, and which promote the values of democratic culture in schools and within the community. The goal of the programme is, inter alia, to improve the competencies of teachers in the process of planning, achieving and evaluating teaching and learning, which together with professional knowledge also develops the knowledge and skills necessary for intercultural learning. Of the total number of registered participants, one third are teachers who are members of national minorities in the Republic of Serbia. In II quarter 2022, the Institute for the Improvement of Education, in cooperation with the Ministry of Education, Science and Technological Development, has implemented a systemic training titled Training for pedagogical assistant for children and students of Roma nationality who need additional support in education. The programme is intended for pedagogical assistants who provide help and additional support to groups of children and students within the institution, as well as assistance and support to teachers, educators and professional associates in teaching and extracurricular activities, in order to improve their work with children and students of Roma nationality. The training lasted from 18 April to 18 June 2022. Pedagogical assistants, employed at educational institutions, took part in the training. During the training, the participants acquired a wide repertoire of skills and competencies, necessary for work and improvement of educational practice and cooperation and work with parents and family, cooperation with the Local Self-government Unit, institutions, organizations, associations and the National Council of the Roma National Minority. In order to further support their work, a Manual was prepared with a didactic-methodical presentation of each topic and content that was represented in the training, while all accompanying materials were uploaded to the online platform of Institute for the Improvement of Education (ZUOV) (https://obuke.zuov.gov.rs/). The evaluation of the participants' works is underway, and the best works – examples of good practice – shall be included in the database of works and a special section titled Pedagogical Assistants, which will be organized on the Institute's website. The second training cycle titled Our students in the world of critical thinking and media literacy, which offers practical examples immediately applicable in practice, and which promote the values of democratic culture in schools and the community, was successfully completed on 15 April 2022. The aim of the programme is, inter alia, to improve the competencies of teachers in the process of planning, implementation and evaluation of teaching and learning, which, together with professional knowledge, develops the knowledge and skills necessary for intercultural learning. Out of the total number of participants (690), 260 of them are teachers, members of national minorities in the Republic of Serbia. In order to strengthen and improve the competences for democratic culture, the advisers at the Institute for the Improvement of Education designed the Manual titled Guidelines for the Integration of the Reference Framework of Competences for Democratic Culture. The said Manual offers suggestions for activities suitable for working in class with students, which connect the contents of the course with democratic competences, and represents a starting point for the further development of educational practice based on universal democratic values. The document can be downloaded from the Institute's website (file:///C:/Users/Korisnik/Downloads/COE_Kvalitetno-obrazovanje-za-sve_publikacija.pdf). As a special form of support for educational practice, a unique platform, Learning Passport, is organized on the Institute's website https://srbija.learningpassport.org/. The platform was developed in cooperation with Microsoft and UNICEF, for the needs of professional development of employees in preschool education and education in the Republic of Serbia, adapted in cooperation with the Ministry of Education, Science and Technological Development, the Institute for the Improvement of Education, the Centre for Interactive Pedagogy and UNICEF. It is easily accessible to everyone, and is set in Serbian as well as in nine languages of national minorities (Roma, Albanian, Hungarian, Bulgarian, Croatian, Bosnian, Ruthenian, Slovak and Romanian). |  |  |
| 3.6.1.9. | Improving the quality of the content of textbooks, curricula and other educational materials at all levels of education and the elimination of discriminatory content related to national minorities, through: -continuous monitoring of the content of textbooks and teaching materials at all levels of education; -development of standards and technical guidelines; |  |  | -Institute for improvement of education and upbringing - National educational council -CSOs |  | Monitoring content in line with standards, guidelines and reporting: Continuously, in accordance with the dynamics of approving new textbooks | Budget of Republic of Serbia- 11.706 € in 2020.- 9.663 € in 2021.- 1021 € in 2022.- 1022 € | Quality of the content of textbooks, curricula and other educational materials at all levels of education improved in terms of removal of any discriminatory content. Standards and technical guidelines are implemented. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the Institute for the Improvement of Education has formed a Working Group for reforming the curricula of specialized grammar schools for the third and fourth grade, in accordance with the requirements of the new educational paradigm, i.e. with the teaching oriented towards learning outcomes which ensures the development of interdisciplinary competencies. In that sense, curriculum proposals for the third grade of specialized grammar schools have been prepared, while the curriculum proposal for the fourth grade is being prepared. In that sense, the reformed curricula are also prepared by specialized grammar schools where teaching is conducted in the mother tongue. Monitoring of the curriculum for the subject Serbian as a non-mother tongue according to new models, which the Institute for the Improvement of Education is implementing in cooperation with the OSCE Mission to the Republic of Serbia, due to the newly-arisen circumstances, continues to be conducted in online format via the Institute's platform http://portal.zuov.gov.rs/. A plan for monitoring the curricula for the 4th and 8th grade and for the 4th grade of grammar schools has been prepared, and it shall be implemented in the same schools as in the previous period. A new Rulebook on textbook quality standards is in the process of being adopted. The proposed standards improve the quality of textbooks, which, on the basis of the procedure prescribed by law, are approved for use in preschool education, i.e. in primary and secondary education. In II quarter 2022, The Institute for the Improvement of Education, in accordance with the requirements of the new educational paradigm, i.e. teaching oriented towards learning outcomes, which ensures the development of cross-curricular competencies, has prepared programme proposals for the fourth grade of specialized high schools. In this sense, the reformed curricula are also prepared by specialized grammar schools where classes are taught in the mother tongue. Monitoring of the curriculum “Serbian as a non-mother tongue” according to the new models, which the Institute for Improvement of Education implements in cooperation with the OSCE Mission to Serbia, due to new circumstances, continues to be conducted in online environment on the Institute's platform http://portal.zuov.gov.rs/. Tests for the second round of testing for the 4th and 8th grade of primary education and the 4th grade of grammar school have been prepared and uploaded on the platform. The students took the entrance exam at the beginning of the school year, while the exit exam is in progress. Evaluation of the exams shall be performed after all students (schools) have finished with testing. |  |  |
| 3.6.1.10. | Raising the quality of primary and secondary education in minority languages by launching the competition for financing and co-financing activities, programs and projects of organizations established by national councils of national minorities and civil society organizations engaged in protection and improvement of the rights of national minorities. |  |  | -Government of the Autonomous Province of Vojvodina -Budgetary Fund for National Minorities, administered by the Ministry of State Administration and Local self-government |  | Continuously, launching the competition each year | Budget of the Autonomous Province of Vojvodina- 14.829€ Budgetary Fund for National Minorities - according to the program of priority areas, in accordance with the decision of the Council for National Minorities | Programs and projects organizations established by national councils of national minorities and civil society organizations engaged in protection and improvement of the rights of national minorities are funded through project financing and co-financing. |  |  | Аctivity is being successfully implemented. In 2022, the amount of 1,000,000.00 RSD, based on the Call for proposals for financing and co-financing the activities of programmes and projects of the national councils of national minorities in the field of primary and secondary education in the AP Vojvodina for 2022, were planned and ensured. Funds have been provided for subsidising the preparation and creation of tests and assignments in minority languages.The call for proposals mentioned above will be launched in the third quarter of 2022. The Ministry of Education, Science and Technological Development has provided funds and held a Public competition for the allocation of funds for programme promotion or the missing part of funds for financing programmes of public interest which are important for education, which are realized by associations in 2021. The competition was published on the official website of the Ministry of Education, Science and Technological Development and on the e-Government portal. The Minister of Education, Science and Technological Development had formed a Competition Commission to determine the list of evaluations and rankings for the registered programmes. Out of a total of 98 programmes, 37 programmes were supported. Of the supported programmes, 8 are organizations dealing with the improvement of education of the Roma national minority, 6 are organizations working in the field of development of education in the Hungarian language, 1 programme concerns the improvement of education in Romanian language, and 2 programmes are in the field of education in Croatian language. Of the total amount budgeted for the Public competition, 20% was allocated for improving the education of members of national minorities, 37% for the promotion of sports in schools, and 10% for programmes of prevention and protection against violence and discrimination. A number of supported programmes deal with digitalization, while the programmes which contribute to the improvement of the position of students with disabilities in the education system are also supported. In the 2021, the amount of 1,000,000.00 RSD, based on the Call for proposals for financing and co-financing the activities of programmes and projects of the national councils of national minorities in the field of primary and secondary education in the AP Vojvodina for 2021, were planned and ensured. Funds have been provided for subsidising the preparation and creation of tests and assignments in minority languages 30.000,00 - Society for Ruthenian Language, Literature and Culture – fostering of the Ruthenian language – Call for proposals for financing and co-financing programmes and projects in the field of primary and secondary education in the AP Vojvodina for 2021- fostering of the Ruthenian language. Ministry for Human and Minority Rights and Social Dialogue reported in II quarter 2022 that the Ministry of Education, Science and Technological Development have provided us with the positive opinion on the report on expenditures and accomplishing of goals set in the Open call for allocation of funds from the Budget Fund for National minorities in 2020, having education in focus of the programs and project reporting. The institutions and associations that have signed the MoU with the Ministry for Human and Minority Rights and Social Dialogue having education in the focus of their activities, have continued to implement their related project activities. The institutions and associations that have implemented all the project activities, have submitted their final narrative and financial reports. Based on the reports of the 44 associations, the Ministry continues to monitor the expenditure manner, as well as the level of reaching of goals via implementation of the activities and with the use of funds granted by the Ministry. |  |  |
| 3.6.1.11. | Promotion of learning Serbian as a second language in accordance with the methodology for studying foreign language. |  |  | -Ministry of Education -Government of the Autonomous Province of Vojvodina |  | Continuously | Budget of the Republic of Serbia- Costs will depend on the number of schools with module for Serbian as a second language | Learning Serbian as a foreign language takes place in accordance with the Rulebook on General Achievement Standards for the subject Serbian as a Foreign Language and the curriculum for teaching Serbian as a foreign language. Increased number of pupils from among national minorities enrolled in a module Serbian as a second language. |  |  | Аctivity is being successfully implemented. The Rulebook on textbook quality standards is in the process of being adopted. With the said act, the line minister improves the quality of textbooks, which, on the basis of the procedure prescribed by law, are approved for use in preschool education, i.e. in primary and secondary education. On the website of the Institute for the Improvement of Education, in the section National Educational Portal, the portal Serbian as a Foreign Language has been set up - https://zuov.gov.rs/srpski-kao-strani-jezik/, which was previously supplemented with materials useful for the implementation of educational practice. In the period from January - March 2022, the Pedagogical Institute of Vojvodina had, in accordance with the Law on the Fundamentals of the Education System ("Official Gazette of the RS", No. 88/2017 and 27/2018 and other laws), performed a check-up regarding the implementation of 4 programmes of continuous professional development of teachers, educators and professional associates for 97 participants. In the period from January – March 2021, the Pedagogical Institute of Vojvodina had, within its competencies, approved and monitored the implementation of 6 professional meetings with a total of 348 participants (2 conferences – 217 participants, 2 forums – 63 participants, 1 consultations – 22 participants, and 1 round table – 46 participants) in Hungarian and Croatian language, with the aim of continuous professional development and acquiring of the title of teacher, educator and professional associates. Within its competencies, the Institute for Education Quality and Evaluation conducts ICCS 2022, an international study that deals with students' knowledge and attitudes regarding civic obligations and active participation in the society. Training for school coordinators and test administrators was conducted. Six schools, in which students from the sampled classes took tests in the Bosnian language, were used for sampling. The Institute for Education Quality and Evaluation is conducting a PISA 2022 study. Training for school coordinators and test administrators was conducted. Two schools, in which students from the sampled classes took tests in the Hungarian language, were used for sampling. The Institute for Education Quality and Evaluation has prepared an instrument for the mock final exam in the school year 2021/2022 in Serbian language and in the languages of national minorities. The mock final exam was conducted on 25 March 2022. Instruments for the final exam, which is to be conducted in June of school year 2021/2022, i.e. on 27, 28 and 29 June 2022, were prepared in the Serbian language and in the languages of national minorities. Provincial Secretariat for Education, Regulations, Administration and National Minorities – National Communities In II quarter of 2022, there were no activities related to the planned measure and activity at the level of the Secretariat, having in mind that this activity, for the territory of the AP Vojvodina, falls under the jurisdiction of the Pedagogical Institute of Vojvodina. The Institute for Education Quality and Evaluation has in II quarter 2022, conducted ICCS 2022, an international study which deals with the knowledge and attitudes of students regarding civic duties and active participation in society. A total of 6 schools have participated in this study, at which 153 students from the sampled classes took tests in the Bosnian language. The Institute for Education Quality and Evaluation has conducted the PISA 2022 study; a total of 146 students from the sampled classes took tests in Hungarian language. Instruments for the final exam to be taken in the June exam term of the school year 2021/2022, which is to be held on 27, 28 and 29 June 2022, were prepared in Serbian language as well as in the languages of national minorities. |  |  |
| 3.6.1.12. | Providing basic and further training of the teachers in charge of education on languages of national minorities. |  |  | -Ministry of Education Partners -State Universities |  | Continuously | State Universities- costs borne by State Universities | Training of the teachers in charge of education on languages of national minorities available and operational. A program of professional development of teachers of the mother tongue in secondary schools for the application of educational standards prepared. Cathedra for studying Croatian language at the University of Novi Sad established. Improved work of the Romani Language Centre at the Faculty of Philology of the University of Belgrade. |  |  | Activity is being successfully implemented. In I quarter 2022, the Institute for Improvement of Education and Upbringing announced the Call for approval of programs of permanent professional training for teachers, preschool teachers and expert associates for the school years of 2022/2023, 2023/2024 and 2024/2025. Legal persons registered to pursue the business activities in the field of education and upbringing are eligible to participate in the Call. Currently, there are two programs in the Catalogue of Permanent Professional Training related to education and upbringing in national minority languages, and these are: Cross over... Get acquainted with the speech and culture of the Vlachs, organized by the National Council of the Vlach national minority and Nurturing the language and multiculturality through teaching contents of the Bosnian language and literature, that was prepared by the Society for Bosnian Language and Literature. Information on programs is available at: http://zuov-katalog.rs/. Materials for the training program for pedagogical assistants for children and pupils of Roma nationality in need of additional support in education have been prepared (two training models have been prepared: a training for pedagogical assistants engaged in institutions providing upbringing and education, and a training for pedagogical assistants engaged in institutions providing education and upbringing). The objective of the training program is to train the pedagogical assistants to improve the work with groups of children and pupils of Roma nationality in need of additional support in education, provision of assistance to teachers, preschool teachers and expert associates, cooperation and work with parents and families, cooperation with the local self-government units, institutions, organisations, associations and the National Council of the Roma national minority. Preparation for online realisation of the said training is underway and it will be uploaded on the web portal of the Institute for Improvement of Education and Upbringing. In II quarter 2022, the Pedagogical Institute of Vojvodina has, in accordance with the Law on the Fundamentals of the Education System ("Official Gazette of the RS", no. 88/2017, 27/2018 (other law), 27/2018 (other law), 10/2019, 6/2020, 129/2021), in the period from April - June 2022, checked the implementation of 5 programmes of continuous professional development of teachers, educators and professional associates for 113 participants. Within its competences, the Pedagogical Institute of Vojvodina has approved and monitored the implementation of 6 expert meetings with a total of 195 participants in the period from April - June 2022 (two forums – 35 participants, two round tables – 84 participants, one consultation – 13 participants, and one meeting – 63 participants) in Hungarian and Slovak language. |  |  |
| 3.6.1.13. | Improve awareness among the wider public and civil servants at all levels of the presence of national minorities in the country and of their rights, including right to positive measures as appropriate, |  |  | -Office for Human and Minority Rights -National Academy for Public Administration |  | Continuously | -Training sessions and public debates: Budget of the Republic of Serbia- 21.000€ in 2020- 2022. - 7.000€ per year | Number of training sessions organised for civil servants at all levels. Number of round tables, conferences, public presentations, working meetings, media campaigns, public debates, focused on promotion of rights of national minorities. |  |  | Activity is being successfully implemented. In I quarter 2022. Ministry of Human and Minority Rights and Social Dialogue continued to organize thematic social dialogues, such as the thematic social dialogue "Serbia and the Digital Decade 2030". Another thematic social dialogue was held regarding the 7-point Plan. On 6 April 2022, in the context of implementing Binding actions adopted within the social dialogue on Representation / integration into state institutions, held on 11 March 2022 in Bujanovac, the Service of the Coordination Body of the Government of the Republic of Serbia for the Municipalities of Presevo, Bujanovac and Medvedja issued a Decision on the establishment of a Working Group, tasked to develop action plan, harmonized with the defined measures and objectives under the Action Plan for Exercising the Rights of National Minorities, which shall define special objectives agreed with the National Council of the Albanian National Minority. The constitutive meeting of the Working Group was held on 11 April 2022 , when all its members were introduced to Working Group tasks and time framework for their performance. Within the project "Promotion of Diversity and Equality in Serbia", which is part of the joint program of the European Union / Council of Europe "Horizontal Facility for the Western Balkans and Turkey 2019-2022", capacity building trainings are delivered to Council for Interethnic Relations. Within the public competition "Implementation of anti-discrimination policies in the Republic of Serbia for 2021", two projects of citizens' associations aimed at national minorities or implemented in order to raise awareness of the rights of national minorities living in the Republic of Serbia were supported. In II quarter 2022, by the Ministry for Human and Minority Rights and Social Dialogue, a social dialogue was organized in order to review the results of providing additional support in educating children from vulnerable groups as a result of the implementation of the project “Social inclusion of Roma and other vulnerable groups in Serbia 2019-2022”. Ministry for Human and Minority Rights and social dialogue, in partnership with GIZ and the Office for Roma inclusion from the Authonomous Province of Vojvodina and the Association of Roma students has initiated the Programme “Stimulating the employment of highly educated Roma men and women in local self-governments” as part of the wider project of the GIZ “Inclusion of Roma and members of other vulnerable groups in Serbia”. The Closing conference of the “100 for future “ provided an overview of the results achieved during the project conducted as part of the wider GIZ Programme “Inclusion of Roma and members of other vulnerable groups in Serbia”. The Ministry for Human and Minority Rights and Social Dialogue and the Protector of Citizens continued to conduct training for capacity building of the Councils for interethnic relations, supported by the Council of Europe via “Project for promotion of diversity and equality in Serbia” as part of the joint EU/CoE Horizontal Facility for Western Balkans and Turkey 2019-2022. The “Intership Programme in state institutions supporting higher representation of young representatives of minority and underdeveloped communities from South and Southeast Serbia” conducted by the Ministry for Human and Minority Rights and Social Dialogue and supported by the OSCE Mission to Serbia has been successfully completed in May 2022. In II quarter 2022, National Academy for Public Administration reported that there have been 13 participants who finished the online course “Rights of persons belonging to national minorities – Official use of language and script of national minorities” since the beginning of 2022, while 77 participants in total finished it since the uploading of the course to the platform. |  |  |
| 3.6.1.14. | Conduct effective investigation and sanctioning of inter-ethnic incidents, particularly those characterized by the elements of the criminal offence of racial, national and religious hatred and intolerance. |  |  | -Republic Public Prosecutors’ Office |  | Continuously | Budget of the Republic of Serbia– 3.063 € 2020 – 2022 - 1.021 € per year | Effective detection, discovery and arrest of the perpetrators of crimes involving violence caused by personal capacity towards national minorities. Increased number of detected offenses involving violence caused by personal characteristics. Increased number of actions undertaken by the Republic Prosecutor's Office in order to increase the efficiency of the investigation and sanctioning of inter-ethnic incidents. |  |  | Activity is being successfully implemented. Implementation of this activity is ongoing. Public prosecutor's offices continued to investigate and prosecute perpetrators of crimes related to inter-ethnic incidents. In order to conduct effective investigations of crimes with elements of discrimination and crimes motivated by hatred, the Republic Public Prosecutor's Office, in cooperation with the Judicial Academy and the OSCE Mission to Serbia, scheduled the continuation of the training for July 15, 2022, when a conference "Hate crimes" will be held, and which is intended for deputy public prosecutors designated as contact points for hate crimes, in the sense of Article 54a of the Criminal Code. |  |  |
| 3.6.1.15. | Implementation of the Rulebook on the criteria for assessing qualifications, competence and worthiness for nomination and selection of candidates for the holders of public prosecutorial functions, including the provisions relating to the application of Art. 82 of the Law on Public Prosecution, which states that in the nomination and election of public prosecutors and deputy public prosecutor, the ethnic composition of the population, adequate representation of national minorities and knowledge of professional legal terminology in the language of national minority in official use in court shall be taken into account. |  |  | -State Prosecutorial Council |  | Continuously, in each election procedure | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Annual report on the implementation of the Rulebook on the criteria for the assessment of qualification, competence and worthiness for nomination and selection of candidates for the holders of public prosecutorial functions. |  |  | Activity is being successfully implemented. Implementation of this activity is ongoing. Additionally, this issue will be regulated within the framework of changes to the relevant normative framework, which will result from constitutional amendments. |  |  |
| 3.6.1.16. | Effective implementation of the Rulebook on Criteria and Measures for evaluation of qualifications, competence and worthiness for the election of judges and presidents of courts, including provisions on the application of Art. 46 of the Law on Judges, which prescribes that the national composition of the population, the adequate representation of members of national minorities and the knowledge of professional legal terminology in the languages of national minorities that is in official use in court shall be taken into account in the nomination and selection of judges, |  |  | -High Judicial Council |  | . Continuously, in each election procedure | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Annual report on the implementation of the Rulebook on Criteria and Measures for evaluation of qualifications, competence and worthiness for the election of judges and presidents of courts. |  |  | Activity is being successfully implemented. Implementation of this activity is ongoing. Additionally, this issue will be regulated within the framework of changes to the relevant normative framework, which will result from constitutional amendments. |  |  |
| 3.6.1.17. | Conduct training of judges on international instruments and standards in the field of protection of national minorities from discrimination and ECHR practice. |  |  | -Judicial Academy |  | Continuously, in line with annual training plan | Budget of the Republic of Serbia- Budgeted in activity 1.3.1.1. | Training of judges on international instruments and standards in the field of protection of national minorities from discrimination and ECHR practice regularly performed. |  |  | Аctivity is being successfully implemented. In I quarter 2022, A five-week online training on non-discrimination was held for the first group of trainees (16 beneficiaries of the initial training of the XI generation). Having in mind the professional obligations and duties of each trainee, the training was organized in an asynchronous form, with the support of mentors. The progress of the trainees is continuously monitored through the forms of testing knowledge at the end of each processed topic, but also by checking the changes in knowledge after the training. In II quarter 2022, an online meeting was held between the representative of the Judicial Academy and the Project partners where the results of evaluation research were presented in order to improve the quality of future online trainings on the topic of non-discrimination. It is planned that during the III and IV quarter, two more groups of the beneficiaries (holders of judicial office and beneficiaries of the initial training) undergo a five-week training on this topic. |  |  |
| 3.6.1.18. | Announcement and implementation of public calls for the cofinancing of national minority organizations in Autonomous Province of Vojvodina for the projects of a multicultural nature, with an aim to develop the spirit of tolerance and encourage the promotion of cultural diversification. Announcement and implementation of public calls for the cofinancing of programs and projects of organizations established by national councils of national minorities and and civil society organizations engaged in protection and improvement of the rights of national minorities in other areas inhabited by national minorities, by allocating funds in Budgetary Fund for the projects of a multicultural nature, with an aim to develop the spirit of tolerance and encourage the promotion of cultural diversification. |  |  | -Government of the Autonomous Province of Vojvodina - Budgetary Fund for national minorities, administered by the Ministry of State Administration and Local self-government -Organizations of national minorities |  | For public calls in Autonomous Province of Vojvodina: Continuously For public calls in other areas inhabited by national minorities: Continuously | -Budget of the Autonomous Province of Vojvodina - 182.310€ -Budgetary Fund for National Minorities – according to the program of priority areas, in accordance with the decision of the Council for National Minorities | Public calls for the cofinancing of organizations of national minorities in Autonomous Province of Vojvodina for the projects of a multicultural nature are regularly announced and implemented. Public calls for the cofinancing of organizations established by national councils of national minorities and and civil society organizations engaged in protection and improvement of the rights of national minorities in other areas inhabited by national minorities, by allocating funds in Budgetary Fund for the projects of a multicultural nature are regularly announced and implemented. |  |  | Аctivity is being successfully implemented. The implementation of projects funded from the Budget Fund for National Minorities in 2021 in the field of education has started, including those with multicultural content. In 2021, based on the results of the calls for proposals and concluded grant agreements, the Provincial Secretariat for Education, Regulations, Administration and National Minorities – National Communities transferred funds to beneficiaries who applied for the following calls for proposals of the Secretariat, announced in February 2021: - The Call for proposal for co-financing programmes and projects aimed at improving the rights of national minorities - national communities in the AP Vojvodina in 2021 (available amount: 33,000,000.00 RSD, the amount paid until 31/12/2021 being 31.808.000,00 RSD, of which 25.596.000,00 RSD was paid in the third and fourth quarter (and 6,212,000.00 RSD in the first and second quarter). Reimbursement of transferred funds in the amount of 608,463.59 RSD was made, so the amount of the total realization of this Call for proposal is 31,199,536.41 RSD; - The Call for proposal for co-financing programmes and projects for preserving and fostering of multiculturalism and interethnic tolerance in the AP Vojvodina in 2021 (available amount of 14,000,000.00 RSD, the amount paid until 31/12/2021 being 11.810,000,00 RSD, of which 4.130.000,00 RSD was paid in the third and fourth quarter (and 7,680,000.00 RSD in the first and second quarter of 2021). Reimbursement of the transferred funds in the amount of 94,734.92 RSD was made, so the amount of the total realization of this Call of proposal is 11,715,265.08 RSD; The difference between the planned and paid аmount in 2021 remained in the provincial budget, due to the lack of grounds for transfer. The funds for which the reimbursement was made, remained also in the provincial budget. In the first 3 months of 2022, the Secretariat has announced the following calls for proposals in January 2022: - The Call for proposal for co-financing programmes and projects aimed at improving the rights of national minorities - national communities in the AP Vojvodina in 2022 (announced the amount of 33,000,000.00 RSD) - The Call for proposal for co-financing programmes and projects for preserving and fostering of multiculturalism and interethnic tolerance in the AP Vojvodina in 2022 (announced the amount of 14,000,000.00 RSD) - Call for proposal for the allocation of budgetary funds to authorities and organisations in the Autonomous Province of Vojvodina, which officially use languages and scripts of national minorities - national communities in their work, for 2022 (announced the amount of 7,500,000.00 RSD). The results of these calls for proposals are published on the website of the Secretariat. In II quarter 2022,, the Provincial Secretariat has signed contracts with users of funds and made payments for the following calls for proposals, announced in januar 2022: - The Call for proposal for co-financing programmes and projects aimed at improving the rights of national minorities - national communities in the AP Vojvodina in 2022 (paid the amount of 4.015.000,00 RSD) - The Call for proposal for co-financing programmes and projects for preserving and fostering of multiculturalism and interethnic tolerance in the AP Vojvodina in 2022 (paid the amount of 325.000,00 RSD) - Call for proposal for the allocation of budgetary funds to authorities and organisations in the Autonomous Province of Vojvodina, which officially use languages and scripts of national minorities - national communities in their work, for 2022 paid the amount of 999.000,00 RSD). |  |  |
| 3.6.1.19. | Enabling full implementation of the Law on Local Self-Government in particular relating to establishment of the councils for multi-ethnic relations in all ethnically mixed areas in line with the Law. Conduct monitoring over the implementation of the Law on Local Self-Government in this regard, through reporting on the activities and outputs of the councils for multi-ethnic relations. |  |  | -Ministry of State Administration and Local self-government |  | Continuously | Implementation: Budget of Local self-government- costs borne by Local self-government Monitoring: Budget of the Republic of Serbia - 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Increased number of councils for multi-ethnic relations in all ethnically mixed areas established. Reports on the activities and outputs of the councils for multi-ethnic relations prepared and publicly available at the websites of the respective local self-government units. The number of opinions obtained from the councils for interethnic relations related to the process of changing the name of streets, squares, town districts, villages and other parts of settlements, in units of local self-government where language of national minority is in the official use. |  |  | Activity is being successfully implemented. Ministry of Public Administration and Local Self-Government is in the process of collecting data on the work of the Council for Interethnic Relations for the period June 2021/ April 2022 (whether they were established, whether they were active or not, if so - how many sessions of the council were held). 37 local self-government units have informed us so far that they have established a council for inter-ethnic relations, in 13 of them at least one session was held, while in 5 local self-government units the mandate of the members of the council has expired and new ones have not been elected. In one local self-government unit, the council is being formed, and in 7 local self-government units the council has not been formed. Twenty local self-government units that had the obligation to establish a council have not yet submitted the requested data, noting that in some of them elections were held in April 2022. |  |  |
| 3.6.1.20. | Provide special funds in the budget of the Autonomous Province of Vojvodina for the financial support of the work of national councils of national minorities. Provision of funds in the Budgetary Fund for the financing of programs and projects of national minorities organizations established by national councils of national minorities and and civil society organizations engaged in protection and improvement of the rights of national minorities |  |  | - Budgetary Fund for national minorities, administered by the Ministry of State Administration and Local self-government -Government of the Autonomous Province of Vojvodina |  | For funds allocated in the Budgetary Fund for national minorities: Continuously, upon its establishment For APV: Continuously | Budgetary Fund for national minorities: according to the program of priority areas, in accordance with the decision of the Council for National Minorities Budget of the Autonomous Province of Vojvodina- 610.607€ | Special funds in the budget of the Autonomous Province of Vojvodina for the financial support of the work of national councils of national minorities provided. Provided funds in the Budgetary Fund for national minorities for the financing of programs and projects of national minorities organizations established by national councils of national minorities and civil society organizations engaged in protection and improvement of the rights of national minorities |  |  | Activity is being successfully implemented. The Ministry for Human and Minority Rights and Social Dialogue has continued to monitor the expenditure manner of the allocated funds as well as the level of achieving of goals set in the Budget Funs for National Minorities in 2021 based on reviewing the narrative and financial reports submitted by 44 organisations implementing the projects. The Provincial Secretariat for Education, Regulations, Administration and National Minorities - National Communities, pursuant to the Provincial Assembly Decision on Method and Criteria for Allocation of Budget Funds for National Councils of National Minorities (“Official Journal of the APV”, number 8/2019) allocated to the National councils of national minorities, in 2022, the total funds in the amount of 61.600.000,00 RSD has been planned. The funds were allocated according to the concluded agreements on the allocation of funds with national councils based in the territory of the Autonomous Province of Vojvodina, in equal parts out of total funds, for a dual purpose: fixed costs and regular activity. The fixed costs include: costs for renting and use of premises of national councils; salaries, taxes and contributions on behalf of the employees in a national council; fees and contributions for work performed for the needs of national councils; travel expenses and per diems for business trips; procurement of office supplies and work equipment for the national councils’ operations; bookkeeping services; annual audit costs; costs of maintaining the Internet web pages of national councils. The scope of regular activities includes financing and co-financing costs for programmes and projects in the field of education, culture, information and official use of languages and scripts of national minorities and financing the work of institutions, foundations and business entities founded or co-founded by a national council or whose founder’s rights are partially or fully transferred to a national council. In the previous three months, the Secretariat has transferred the funds for both purposes for the second quarter in the amount to 30,750,000.00 RSD. |  |  |
| 3.6.1.21. | Analysis of the effects of the implementation of the mandatory instruction regarding the exercise of the right to register personal data in the relevant registers in the language and script of national minorities. |  |  | - Administrative Inspectorate |  | Continuously, through annual report | Budget of the Republic of Serbia- 2.553 € In 2020 – 2022 - 851 €per year | Analysis of the effects of implementation of the mandatory instruction in connection with the exercise of the rights to the entry of personal data in the relevant registry books in the language and script of the national minority conducted. Administrative inspection of the work of the local self-government units regarding the exercise of the right to register a personal name in the register in the language and script of national minorities is actively performed and corrective measures to eliminate deficiencies are imposed. |  |  | Аctivity is being successfully implemented. In I quarter 2022, within the inspection control in the field of the official use of languages and scripts, conducted by the Inspection of the Secretariat, pursuant to Article 76 of the Law on Establishing the Competences of the Autonomous Province of Vojvodina ("Official Gazette of the RS” no. 99/2009 and 67/2012 - Constitutional Court Decision), the inspection, among other issues related to the official use of languages and scripts, supervised, on the basis of a check-list, the issue of whether persons belonging to national minorities were granted the right to enter names and surnames of their children in all public documents, official records and collections of personal data according to the language and spelling of persons belonging to a national minority and did not find any irregularities in the implementation of this right. In II quarter 2022, Provincial Secretariat for Education, Regulations, Administration and National Minorities, National Communities - within the two realised inspection control carried out in the second quarter 2022 in the field of the official use of languages and scripts, conducted by the Inspection of the Secretariat, pursuant to Article 76 of the Law on Establishing the Competences of the Autonomous Province of Vojvodina ("Official Gazette of the RS” no. 99/2009 and 67/2012 - Constitutional Court Decision), the inspection, among other issues related to the official use of languages and scripts, supervised, on the basis of a check-list, the issue of whether persons belonging to national minorities were granted the right to enter names and surnames of their children in all public documents, official records and collections of personal data according to the language and spelling of persons belonging to a national minority and did not find any irregularities in the implementation of this right. |  |  |
| 3.6.1.22. | Full implementation of the Law on the Central Register of Compulsory Social Insurance in connection with the establishment of a register of public administration bodies and organizations and employees in the public administration system within which the possibility of voluntary declaration of employees in public administration bodies on national affiliation is introduced, in order to collect data on appropriate representation of national minorities in public administration bodies, local level, police and judiciary, in accordance with the rules on personal data protection. |  |  | -Ministry of Finance |  | For establishment: Until I quarter of 2021. For the availability of statistical data: starting from II quarter of 2021. | Budget of the Republic of Serbia - 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 €. | Register of bodies and organizations of public administration and employees in the public administration system established. The normative framework ensures the incorporation of the Register of employees, elected, appointed and engaged persons at organizations using public funds in the information system CROSO. Data on the representation of national minorities in public administration bodies, local and provincial bodies, police and judiciary available. |  |  | Activity is fully implemented. The activity was implemented in the first quarter of 2021 by establishing the Register of employees, elected, appointed, appointed and engaged persons with users of public funds within the CROSO information system. Data on the national affiliation of employees of users of public funds are optionally submitted on the basis of the explicit consent of employees in public administration bodies, in accordance with the rules on personal data protection. Based on the generated report, it was determined that no user of public funds filled in this field. |  |  |
| 3.6.1.23. | Analysis of the effects of implementation of the Regulation governing, inter alia, the language and script of national minorities, as a special condition for the performance of tasks at the individual workplaces for the purpose of proportional representation of ethnic minorities among civil servants and clerks. |  |  | - Ministry of state administration and local self-government, in cooperation with the Standing Conference of Towns and Municipalities |  | For analysis: III quarter of 2021. | Budget of the Republic of Serbia – 17.285 € | Regulation governing, inter alia, the language and script of national minorities, as a special condition for the performance of tasks at the individual workplaces for the purpose of proportional representation of ethnic minorities among civil servants and clerks implemented. Analysis of the effects of the implementation of the normative framework conducted. |  |  | Activity is fully implemented. In accordance with the obligation envisaged by the Action Plan for Chapter 23, the Ministry of Public Administration and Local Self-Government has prepared an Analysis of the effects of the implementation of bylaws adopted on the basis of the Law on Employees in Autonomous Provinces and Local Self-Government Units (Official Gazette of RS, No. 21/16, 113 / 17, 113/17 - second law and 95/18, hereinafter: Law on Employees in AP and JLS). For the needs of conducting the mentioned analysis, the Ministry of Public Administration and Local Self-Government sent a letter to all local self-government units (145), and the answers were submitted by 100 local self-governments, which makes (68.96%). Out of the total number of local self-government units, 43 local self-government units introduced some of the languages and scripts of national minorities into official use, either on the whole or part of the territory (according to data available to the Ministry of Public Administration and Local Self-Government), the answers were submitted by 40 local self-governments units, which makes (93.02%), and represents a satisfactory result for the analysis. By analyzing the data obtained from the answers to the questionnaire, it can be concluded that local self-government units, as a rule, apply bylaws adopted in order to implement the Law on Servants in AP and LSGUs, i.e. the Regulation on Criteria for Job Positions Classification and Criteria for Job Descriptions of Servants in Autonomous Provinces and Local Self-Government Units and the Regulation on Criteria for Job Positions Classification and Criteria for Job Description of General employees in Autonomous Provinces and Local Self-Government Units, which prescribe affirmative action measures aimed at exercising the right of citizens to official use of languages and scripts of national minorities, and to contribute to a more adequate representation of persons belonging to national minorities among the employees of the AP and LSGU bodies. The analysis showed that out of 40 local self-government units (93.02%) that submitted answers to the questionnaire, and in which the language and script of the national minority /minorities is in official use, in 28 local self-government units the rulebook on organization and systematization of job position(s) for which knowledge of the languages and scripts of national minorities in official use is prescribed as a special requirement (70%), which is a significant percentage, especially since only 3 local self-government units (6.98%), which according to the records of the Ministry of Public Administration and Local Self-Government have the language and script of the national minority in their official use in their territory, did not submit answers to the questionnaire. Regarding the analysis of the application of the Regulation on enforcing internal and public vacancies in autonomous provinces and local self-government units, among the LSGUs which introduced some of the languages and scripts of national minorities into official use, it can be concluded that the provisions of this Regulation are directly applied in the implementation of affirmative action measures in local self-government units. Namely, the analysis showed that out of 36 local self-government units, which submitted answers to the questionnaire and which provided an answer to the question whether Article 7 para. 2-4, and Article 23, paragraph 6, of the Regulation, it was determined that 16 LSGUs gave an affirmative answer (44.44%), while 20 LSGUs (55.56%) gave a negative answer. The reasons for the insufficient possibility of applying this regulation can be found primarily in the ban on employment in the public sector, which was introduced by the Law on Determining the Maximum Number of Servants in the Public Sector, which was in force until December 31, 2019 and continued with restrictions, which is prescribed by the Law on Budget System, in the sense that it is necessary to obtain the consent of the Commission for giving consent for new employment and additional employment with the budget funds users for each new employment. A number of local self-government units already have an adequate representation of members of national minorities in local self-government bodies, and in this regard there is no need to apply the prescribed affirmative measures. In addition, one of the significant reasons for non-compliance of local self-government units with the prescribed affirmative measures is the insufficient percentage of employees who declared their ethnicity (it is necessary that at least 30% of the total number of servants declare their ethnicity), which is a prerequisite for proper application of the aforementioned provisions which prescribe affirmative measures for the employment of members of national minorities. The analysis also provides recommendations to local self- government units for improvement the implementation of these regulations. |  |  |
| 3.6.1.24. | Announcement of a public call for the allocation of budgetary resources to the local authorities in order to: -Educate the staff in bodies and organizations of local self-government units where minority languages ​​and scripts of national minorities are in the official use; -Improve the electronic administration system to work in conditions of multilingualism in areas inhabited by national minorities; -Secure funding for preparing and setting up bilingual topographic signs and printing of bilingual or multilingual forms, official journals and other publications for public use. |  |  | -Government of the Republic of Serbia -Government of the Autonomous Province of Vojvodina -Local self-government units |  | Continuously | Budget of the Autonomous Province of Vojvodina - 87.230€ Budget of the Republic of Serbia – Costs currently unknown * Costs depend on the number of local self-government units that will apply | Public call for the allocation of budgetary resources to the local authorities announced. |  |  | Аctivity is being successfully implemented. A total of 111 beneficiaries submitted applications for the Call for proposals for the allocation of budget funds to authorities and organisations in the Autonomous Province of Vojvodina, which officially use languages and scripts of national minorities - national communities in their work in 2022, which was announced in the first quarter of 2022 (19.01.2022) for the total amount of 7.500.000,00 RSD. The funds were allocated to 90 beneficiaries. Regarding the Call for proposals for the allocation of budget funds to authorities and organisations in the Autonomous Province of Vojvodina, which officially use languages and scripts of national minorities - national communities in their work in 2022, during the second quarter of 2022, contracts were concluded with the beneficiaries of the funds and the amount of RSD 999,000.00 was paid. |  |  |
| 3.6.1.25. | Providing support to the National Councils of National Minorities in the implementation of their jurisdiction, through: - provision of financial resources for functioning of National Councils of National Minorities - strengthening the managerial capacities and financial reporting capabilities of NCNMs. |  |  | -Office for Human and Minority Rights |  | Continuously | -Budget of the Republic of Serbia- 2.340.630 € in 2020. | Continuous provision of support to the National Councils of National Minorities in the implementation of their jurisdiction. Representatives of NMCs improved knowledge regarding managerial capacities and financial reporting. Provided financial resources for functioning of National Councils of National Minorities |  |  | Аctivity is being successfully implemented. In I quarter 2022. the support to the national councils of national minorities in the exercise of their powers has continued and stable financing of their work has been provided from the budget of the Republic of Serbia. Under the Law on the Budget of the Republic of Serbia for 2022, the amount of RSD 255,000,000.00 has been allocated for financing the work of national councils. In the period January - March 2022, out of the total funds provided for financing the work of national councils, RSD 62,913,025.00 were disbursed. The National Councils approved translation of the text "Guidelines for work of the national councils of national minorities in the Republic of Serbia". Guidelines in the languages ​​of national minorities will be available in electronic format during April. In II quarter 2022, the Ministry for Human and Minority Rights and Social Dialogue continued to support the National Councils of the National Minorities in implementing their mandate and provided a stable financing from the state budget for the work of the Council. In the period April-June 2022, out of total of funds allocated for financing the work of National Councils, 62913048.00 dinars have been transferred. The translations into minority languages of the “Manual for the work of National Councils of National Minorities in the Republic of Serbia” have been provided to the National Councils for publishing at their web presentations and are also available at the website of the Ministry for Human and Minority Rights and Social Dialogue at https://www.minljmpdd.gov.rs/nacionalni-saveti-nacionalnih-manjina.php The Provincial Secretariat for Education, Regulations, Administration and National Minorities - National Communities, pursuant to the Provincial Assembly Decision on Criteria for Allocating Budgetary Funds for National Councils of National Minorities (“Official Journal of the APV”, number 8/2019) provides financial support to National councils of national minorities based in the territory of AP Vojvodina by financing their work in accordance with the criteria stated in the above mentioned Decision, and on the basis of the provincial budget. See item 3.6.1.20. of this report. |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.6.2. Serbia adopts and implements the action plan (accompanying the new strategy) to improve living conditions of Roma, with a special focus on registration, comprehensive measures on non-discrimination, compliance with international standards on forced evictions, guaranteed socio-economic rights, education, health, employment and housing, including access to basic public services (water and electricity). Serbia ensures a measurable improvement of the situation of Roma, reducing the gap with the rest of the population in the above areas. |  |  |  |  |  | New multi-annual strategy and action plan to improve living conditions of Roma adopted through an inclusive process and implemented. Efficiently implemented comprehensive state policies ensure: - access to personal documents/ registration - improved tolerance -implementation of international standards in the case of forced evictions - equal access to health care and social protection - equal access to education - equal access to labor market - improvement of housing conditions. |  | 1. European Commission Annual Progress Report on Serbia stating progress in part relating to the position of Roma national minority; 2. Annual report of the Ombudsman stating lesser degree of discrimination of Roma; 3. Annual report of the Coordination body for social inclusion of Roma on the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia 2016-2025 stating high level of implementation in all priority arias; 4. Achievement of the Poznan declaration objectives: Employment: Increase the employment rate of Roma in the public sector to the rate proportional of the participation of Roma in the overall population; Increase the employment rate among Roma to at least 25 per cent; Housing: Wherever possible, legalize all informal settlements where Roma live; or provide permanent, decent, affordable and desegregated housing for Roma currently living in informal settlements that cannot be legalized for justified reasons; Education: Increase the enrolment and completion rate of Roma in primary education to 90 per cent and the enrolment and completion rate of Roma in secondary education to 50 per cent; Health: Ensure universal health insurance coverage among Roma of at least 95 per cent or to the rate equal to the rest of the population; Civil registration: ensure all Roma are registered in the civil registries. Non-discrimination: Strengthen the government structures to protect against discrimination and establish a specific sub-division for non-discrimination of Roma within the formal non-discrimination bodies to process complaints by Roma, provide legal support to alleged victims and identify discrimination schemes, including institutional and hidden discrimination; |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.6.2.1. | Development and full implementation of Action Plan for the implementation of the new Strategy for social inclusion of Roma in the Republic of Serbia 2016-2025, containing SMART indicators. |  |  | -Ministry of Labor, Employment, Veterans and Social Affairs - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025. -Political authority responsible for coordination of implementation: -Deputy Prime Minister and Minister of Construction, Transport and Infrastructure. -Team for Social Inclusion and Reduction of Poverty |  | For adoption: By IV quarter of 2020 For implementation: Continuously, commencing from adoption of the Action plan. | For development: Budget of the Republic of Serbia - 17.285 € | Action Plan for the implementation of the new Strategy for social inclusion of Roma in the Republic of Serbia 2016-2025, containing SMART indicators adopted and implemented. Annual reports on the progress of Strategy implementation publicly available. |  |  | Activity is partially implemented. The fifth meeting of the Expert Group of the Coordination Body for Improving the Position and Social Inclusion of Roma Men and Women and Monitoring the Implementation of the Strategy for Social Inclusion of Roma Men and Women in the Republic of Serbia for the period 2016 - 2025 was held, at which the second draft Action Plan, by areas, was presented. The meeting was also attended by representatives of the civil sector and international organizations. It is planned that the Expert Group will hold a third meeting in the coming period, after which the final draft of the Action Plan will be presented. The Proposal of the Action plan has been finalized following the process of public debate. At the moment the Ministry is in the phase of obtaining opinions from relevant institutions. The Ministry plans for the document to be adopted in III quarter 2022. |  |  |
| 3.6.2.2. | Monitoring the achievement of the objectives of a new Strategy for social inclusion of Roma in the Republic of Serbia 2016-2025 through: -continuous work of the Coordination body for social inclusion of Roma, - regular meetings with responsible authorities including local governments and public enterprises, - regular reporting. |  |  | - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025. -Ministry of Labor, Employment, Veterans and Social Affairs -Team for Social Inclusion and Reduction of Poverty -Office for Human and Minority Rights -Political authority responsible for coordination of implementation: Deputy Prime Minister and Minister of Construction, Transport and Infrastructure. |  | Continuously, until the expiry of the Strategy | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € Supported by: Regional Cooperation Council Roma Inclusion 2020 | Regular reports on implementation of the Action Plan submitted by responsible authorities. Efforts of public authorities, including local governments and public enterprises effectively coordinated which is confirmed in reports on implementation of the Action Plan. Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 provides recommendations for overcoming potential obstacles in the implementation of the Strategy and Action Plan. |  |  | Activity is not implemented. Seven meetings of the Expert group of the Coordination body and the two sessions of the Coordination Body have been held so far. The Expert group meetings produced the Proposal of the Action plan. |  |  |
| 3.6.2.3. | Coordination meetings on projects focused on improvement of the situation of Roma regularly held. |  |  | - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025. -Ministry of European Integration -Ministry of Labor, Employment, Veterans and Social Affairs -Team for Social Inclusion and Reduction of Poverty -Office for Human and Minority Rights |  | Continuously | Budget of the Republic of Serbia- 25.926 € 8.642 € per year | Regular coordination meetings on projects focused on improvement of the situation of Roma are quarterly held. Bi-annual reports to the European Commission on the implementation of ongoing IPA projects and their link with the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 and Action Plan priorities, using existing mechanisms of coordination in order to secure efficiency and avoid overlapping. |  |  | Activity is partially implemented According to information provided in the reporting period I quarter 2022 by the Ministry for Human and Minority Rights and Social Dialogue, this activity will be discussed at the next meeting of the Coordination Body for Improving the Position and Social Inclusion of Roma Men and Women and monitoring the implementation of the Strategy for Social Inclusion of Roma Men and Women in the Republic of Serbia for the period 2016 - 2025. The Expert group of the Coordination Body exchanged information on implementation of current projects as well as on the future projects that are in the programming phase for the area of inclusion of Roma men and women in the Republic of Serbia. In order to achieve better coordination and overview of the projects, the Ministry held a number of meetings with the Delegation of EU in Serbia, council of Europe, OSCE Mission to Serbia, GIZ and the RCC. |  |  |
| 3.6.2.4. | Monitoring the implementation of measures from five priority areas (education, employment, housing, health and social protection) at the local level through the collection and processing of data through the "one-stop-shop" body. |  |  | - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 -Office for Human and Minority Rights - Team for Social Inclusion and Reduction of Poverty |  | Continuously, in line with the dynamics of reporting | Budget of the Republic of Serbia- 25.926 € 17.285 € per year | Data on implementation of measures in five priority areas (education, employment, housing, health and social protection) are regularly updated. |  |  | Activity is being successfully implemented. At the second meeting of the Coordination Body, its members discussed the revision of the system for monitoring the collection and processing of data through a single Database. Data on implementation of the Strategy are collected in line with the adopted methodology from state institutions, organisations and local self-government units mandated for implementation of activities. The conclusion of the meeting is that it is necessary to establish a Database within the Ministry for Human and Minority Rights and Social Dialogue, with the support of the German Cooperation Agency (GIZ) during the third quarter. The establishing of the Database will be done with participation and monitoring of the Ministry for Human and Minority Rights and Social Dialogue. |  |  |
| 3.6.2.5. | Development and further strengthening of the network of Roma coordinators including an increase of their number, according to the local needs, in order to closely cooperate with other relevant state mechanisms to improve the position of the Roma. |  |  | - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 -Team for Social Inclusion and Reduction of Poverty, based on data from -Local self-governments |  | By 2021. | Budget of the local self-governments | Network of Roma coordinators further strengthened. Baseline: 47 municipalities Target: 60 municipalities by 2021. |  |  | Activity is being successfully implemented. This activity is envisaged by the new Strategy and the accompanying Action Plan, the development of which is in the final phase, and it will be discussed at the meeting of the Expert Group of the Coordination Body. It is noted that the field activities are continued to assess the situation and strengthen the capacity of local self-government units to better respond to the requirements of members of the Roma population. |  |  |
| 3.6.2.6. | Establish mechanisms for an integrated social services delivery model by searching more actively for solutions for the activation of clients who are fit for work, yet continually receive financial social assistance, in order to promote active inclusion of the Roma. |  |  | -Centres for social work -National Employment Service |  | Continuously, by 2021. | Budget of the Republic of Serbia- Regular activity (falling within the scope of regular duties of staff employed in respective institutions) | Mechanisms for an integrated social services delivery model established and operational. Reports on the number of activated clients who are fit to work yet receive financial social assistance. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the Republic Institute for Social Protection has prepared an analysis "Implementation of social inclusion measures" in order to have a more comprehensive view of the current application of activation measures defined by the Decree on measures of inclusion of beneficiaries of financial social assistance based on annual reports of social work centers. The analysis pointed to the weak application of the Regulation: in 2020, out of a total of 170 CSR departments, 23 CSRs, i.e. 13.5% applied activation measures, in 2019 21 CSRs applied activation measures, i.e. 12.4% of the total number and in 2018, activation measures were applied by 25 CSRs or 14.7% of the total number of CSRs. After the ex post analysis of the previous effects of the implementation of the Regulation, which was completed at the end of 2021. Amendments to the Regulation will be made, in which it will be necessary to further develop measures to ensure social inclusion of beneficiaries of financial social assistance, criteria for selection and engagement of beneficiaries, provide mechanisms for activating able-bodied beneficiaries of financial social assistance and define best forms of cooperation with other institutions. with the National Employment Service (individual employment plans and individual activation plans). Constitutional Court at its session on 21 April 2022, in the case of constitutional review of the Law found that the provisions of Article 80, paragraphs 3 and 4 of the Law on Social Protection were not in accordance with the Constitution of the Republic of Serbia and postponed the publication of the said Decision in the "Official Gazette of the Republic of Serbia" for six months from the date of its adoption. The provisions of Article 80, paragraph 3 of the Law on Social Protection, which the Constitutional Court has determined are not in accordance with the Constitution, read as follows: “Centre for social work may conclude an agreement with beneficiaries of financial support on active overcoming of their unfavourable social situation, which contains the beneficiaries’ activities and obligations, as well as a possibility to limit or cancel the right to financial support in the case of unjustifiable failure to meet the obligations under the agreement (hereinafter: individual activation plan).” The provisions of Article 80, paragraph 4 of the Law on Social Protection, which the Constitutional Court has determined are not in accordance with the Constitution, read as follows: “Measures of social inclusion shall be prescribed by the Government.” With the termination of the provisions of Article 80, paragraphs 3 and 4, the legal basis for the Government to prescribe measures of social inclusion ceases, i.e. the Regulation on measures of social inclusion of beneficiaries of financial social assistance, already adopted by the Government on the basis of the above provisions of the Law on Social Protection, ceases to be valid because the Constitutional Court found that they were not in conformity with the Constitution. The number of beneficiaries of financial social assistance who are able to work is around 100,000, depending on the period of the year, considering that these beneficiaries are entitled to financial social assistance for only 9 months during the year. This is about 50% of all FSA beneficiaries. |  |  |
| 3.6.2.7. | Access to personal documents. Monitoring of the situation in the field of exercising the right to register in the registry books in accordance with: -The Law on Birth Registries, -The Law on Non-Contentious Proceedings, including the number of persons enrolled in this record. - The Law on Citizenship - The Law on residence of citizens. | -Ministry of Interior -Ministry of State Administration and Local self-government -Ministry of Labour, Employment, Veterans and Social Affairs -Ministry of Health |  | Continuously, in line with Operational Conclusions | Budget of the Republic of Serbia- Regular activity(falling within the scope of regular duties of staff employed in public registries, courts and municipality policy directorates) | Report on the number of persons registered in the registry books in accordance with the Law on Birth Registers, as well as the Law on Non-Contentious Proceedings,, the Law on Citizenship, the Law on Residence of Citizens, including data on determining the time and place of birth. |  |  | Аctivity is being successfully implemented. By monitoring the situation in exercising the right of citizens to be entered into the birth register, based on the data collected by the Administrative Inspectorate in the administrative procedure of subsequent registration of the fact of birth, a total of 316 persons have exercised the right to entry into the birth register in 2021. Persons who could not provide evidence of the fact of birth in the administrative procedure have exercised the right to entry into the birth register in the procedure for determining the time and place of birth in accordance with the Law on Extra-Judicial Proceedings; hence, according to the Ministry of Justice, a total of 221 court decisions have been reached in 2021 on the basis on which the fact of birth was entered into the birth register. In the period from April 1, 2022 until Junе 17, 2022, related to the Rulebook on residence application form at the address of an institution or centre for social work, a place of residence was established by the Ministry of Interior for 108 persons, of which most live in informal settlements, after which they also obtained personal identity documents. Since the Ministry of Public Administration and Local Self-Government annually monitors the situation related to the number of persons registered in the birth register, in the administrative procedure of subsequent registration of the fact of birth in the birth register, these data will be available after the current year ends, by obtaining data from the Administrative Inspectorate, as well as from the Ministry of Justice. |  |  |
| 3.6.2.8. | Amendments to the by-laws governing the procedure of birth registration and entry into the birth registry (items 10 and 24 of the Instruction on keeping birth registers and birth certificate forms and Article 5 of the Rulebook on the procedure for issuing a birth certificate and a child birth registration form in a health institution) in order to enable registration in the birth registry immediately after the birth of children whose parents do not have personal documents. |  |  | -Ministry of State Administration and Local self-government -Ministry of Health |  | By II quarter of 2021 | Budget of the Republic of Serbia- 17.285 € | The by-laws regulating the procedure of birth registration and entry into the birth registry amended. Registration in the birth registry immediately after the birth of children whose parents do not have personal documents enabled. |  |  | Аctivity is being successfully implemented. Ministry of Public Administration and Local Self-Government emphasized that the normative framework in the Republic of Serbia provides every child with the right to be entered into the birth register. The identification of parents, i.e. of a mother in the manner provided by items 10 and 24 of the Instructions on Keeping Civil Records and Forms of Civil Records, and Article 5 of the Rulebook on the Procedure for Issuing Birth Certificates and the Form of Birth Registration in a Healthcare Institution, is harmonized with the positive regulations of the Republic of Serbia in regards to the identification of persons. In that way, the legal security of the child is ensured, and in no way is it an obstacle for the registration of birth of a child immediately after its birth. On 10 February 2022, the third Memorandum of Understanding was signed between the Ministry of Public Administration and Local Self-Government, the Protector of Citizens and the UNHCR in order to resolve the remaining cases in which members of the Roma national minority did not exercise their right to entry into the birth register, with a special focus on the registration of newborn children. The activities from the said Memorandum are related to the end of the ten-year global campaign "I belong" (#IBelong), which UNHCR is conducting as part of its activities with governments, international organizations, NGOs and influential individuals, with the goal of eradicating statelessness worldwide by November 2024. The operational group, which was formed by the decision of the Minister of Public Administration and Local Self-Government on 8th March 2022, and which, in addition to representatives of the Agreement Parties, also consists of representatives of the relevant ministries (Ministry of Interior; Ministry of Family Welfare and Demography; Ministry of Human and Minority Rights and Social Dialogue; Ministry of Labour, Employment, Veteran and Social Affairs; Ministry of Health; Ministry of Justice), as well as the City Administration of the City of Belgrade and UNICEF, held the first meeting where further activities were agreed (continuation of online training, media campaign, etc.) which will be implemented in the coming period in order to realize the goals set in the third Memorandum of Understanding. |  |  |
| 3.6.2.9. | Continue to inform the Roma about their civil status rights and provide free legal aid to members of the Roma community in these proceedings by the relevant authorities and CSOs active in the promotion of human and minority rights. Strengthen the access to free legal aid in line with the Law on Free Legal Aid to ensure full access to rights of the Roma community |  |  | -Local self-government units -Ministry of Interior -Ministry of Justice - CSOs |  | Provision of legal aid by the relevant authorities and CSOs: Continuously Provision of legal aid in line with FLA Law: Continuously, commencing from the start of implementation of the law. | Provision of legal aid by the relevant authorities and CSOs: Budget of the Republic of Serbia Regular activity (falling within the scope of regular duties of staff employed in respective institutions) Provision of legal aid in line with FLA Law: Budgeted in activity 3.5.1.2. | Relevant authorities and CSOs active in the promotion of human and minority rights regularly inform the Roma about their civil status rights and provide free legal aid to members of the Roma community in these proceedings. Number of beneficiaries of the Law on Free Legal Aid who were granted free legal aid to exercise the right to have the time and place of birth established under the Law on non-adversarial proceedings |  |  | Аctivity is being successfully implemented. The Proposal of the Action Plan for the Implementation of the Strategy for the Social Inclusion of Roma and Roma Women in the Republic of Serbia, which will cover the period from 2022 to 2024, envisages the Ministry of Justice both as responsible institution for implementation and a partner in the implementation of activities related to information and provision of free legal aid to Roma men and women. The Ministry of the Interior of the Republic of Serbia undertakes the activities of identification and addressing the identified issues the Roma in the form of a prioritized decision – making on the basis of applications for acquisition of Serbian citizenship filed by the Roma, timely and full informing of the Roma on the procedures for the issuance of identity documents, as well as on other measures to be taken which allow that every individual case of the granting of identity document to this category of persons is conducted in a simplified and efficient way. |  |  |
| 3.6.2.10. | Providing the opportunity to register the place of residence at the Centre for Social Work, enabling the fulfilment of the requirements for the registration of address or residence when applying for personal documents. Monitoring the exercise of the right to permanent residence registration at the address of a centre for social work by persons who are unable to register their permanent residence on any other grounds. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Ministry of Interior |  | Continuously | Budget of the Republic of Serbia- Activity requiring insignificant costs | Exercise of the right to permanent residence registration at the address of a centre for social work by persons who are unable to register their permanent residence on any other grounds fully ensured. Annual reports of the responsible ministries indicate number of persons who exercised this right. |  |  | Аctivity is being successfully implemented. In the period from January 1, 2022 until April 1, 2022, related to the Rulebook on residence application form at the address of an institution or centre for social work, a place of residence was established by the Ministry of the Interior for 89 persons, of which most live in informal settlements, after which they also obtained personal identity documents. In the period from April 1, 2022 until June 17, 2022, related to the Rulebook on residence application form at the address of an institution or centre for social work, a place of residence was established by the Ministry of Interior for 108 persons, of which most live in informal settlements, after which they also obtained personal identity documents. |  |  |
| 3.6.2.11. | Education. Further expand the teaching assistants' network on the basis of an analytical survey carried out by the relevant government bodies. | -Ministry of Education |  | Analytical survey: III quarter of 2020. Expansion of network: Continuously, until 2022. | Budget of the Republic of Serbia- Costs currently unknown -Pending analytical survey results | Teaching assistants' network expanded on the basis of an analytical survey carried out by the relevant government bodies. |  |  | Аctivity is being successfully implemented. The Training programme for pedagogical assistant for children and students of Roma nationality in need of additional support in education was prepared in cooperation with the Institute for the Improvement of Education and the Ministry of Education, Science and Technological Development. All materials and the complete programme environment for the online implementation of the programme have been posted on the following link https://obuke.zuov.gov.rs/. The selection of training participants (240), i.e. of pedagogical assistants from all school administrations of the Republic of Serbia, has been performed. The training programme aims to train a pedagogical assistant to improve his/her work with a group of children and students of Roma nationality who require additional support in education, provide assistance to teachers, educators and professional associates, cooperate and work with parents and families, cooperate with LSU, institutions, organizations, associations and the National Council of the Roma National Minority. |  |  |
| 3.6.2.12. | Monitoring implementation of a by-law specifying teaching assistants' scope of work with specific tasks, performance quality standards, continued building of teaching assistants' capacities and contractual modality |  |  | -Ministry of Education |  | IV quarter of 2020. | Budget of the Republic of Serbia- 8.642€ | By-law specifying teaching assistants' scope of work with specific tasks, performance quality standards, continued building of teaching assistants' capacities and contractual modality adopted and implemented. |  |  | Аctivity is being successfully implemented. The Training programme for pedagogical assistant for children and students of Roma nationality in need of additional support in education was prepared in cooperation with the Institute for the Improvement of Education and the Ministry of Education, Science and Technological Development. All materials and the complete programme environment for the online implementation of the programme have been posted on the following link https://obuke.zuov.gov.rs/. The training participants (240) were selected, i.e. pedagogical assistants from all school administrations of the Republic of Serbia, who shall attend four modules of the programme which shall provide them with development (of new) and improvement (of the existing) competencies in regards to planning, implementation and evaluation of their work in the institution. The Institute for the Improvement of Education, in cooperation with the Ministry of Education, Science and Technological Development, has implemented a systemic training titled Training for pedagogical assistant for children and students of Roma nationality who need additional support in education. The programme is intended for pedagogical assistants who provide help and additional support to groups of children and students within the institution, as well as assistance and support to teachers, educators and professional associates in teaching and extracurricular activities, in order to improve their work with children and students of Roma nationality. The training lasted from 18 April to 18 June 2022. Pedagogical assistants, employed at educational institutions, took part in the training. During the training, the participants acquired a wide repertoire of skills and competencies, necessary for work and improvement of educational practice and cooperation and work with parents and family, cooperation with the Local Self-government Unit, institutions, organizations, associations and the National Council of the Roma National Minority. In order to further support their work, a Manual was prepared with a didactic-methodical presentation of each topic and content that was represented in the training, while all accompanying materials were uploaded to the online platform of Institute for the Improvement of Education (ZUOV) (https://obuke.zuov.gov.rs/). The evaluation of the participants' works is underway, and the best works – examples of good practice – shall be included in the database of works and a special section titled Pedagogical Assistants, which will be organized on the Institute's website. |  |  |
| 3.6.2.13. | Monitoring the implementation and impact of the bylaw that defines the prevention and prohibition of discriminatory behavior in the education system. |  |  | -Ministry of Education |  | Continuously, through annual reports | Budget of the Republic of Serbia- 2.553 € in 2020. - 851 € in 2021. - 851 € in 2022. - 851 € | Annual report on the work of the schools submitted to Ministry of Education which contains reports prepared by school teams for protection from discrimination indicating determined discrimination or segregation.. |  |  | Activity is being successfully implemented. The implementation of the training "Let anti-discrimination be our inspiration - prevention and overcoming discrimination in kindergartens and schools", which is provided under the MESTD's budget for 200 new employees in the education system, is in progress. |  |  |
| 3.6.2.14. | Developing a system for monitoring the effects of implementation of affirmative measures of enrollment of Roma students in secondary schools, with an aim of closing the gap between Roma and non Roma children. Developing a system of support for Roma students enrolled in secondary school using affirmative measures, with an aim of closing the gap between Roma and non Roma children. |  |  | -Ministry of Education |  | Continuously, until 2021 | Budget of the Republic of Serbia- 8.642€ | Monitoring of the effects of affirmative action on Roma education continuously performed, with an aim of closing the gap between Roma and non Roma children, and results published on an annual basis. A unique education code (JOB) for students in pre-university education introduced. |  |  | Activity is being successfully implemented. The application of the affirmative measure for secondary school enrolment for students of the Roma national minority has continued for the school year 2022/23. |  |  |
| 3.6.2.15. | Establishment of a mechanism to prevent drop-outs and early school drop-outs, along with the support to transition at all levels of education. |  |  | -Ministry of Education |  | Continuously | Budget of the Republic of Serbia- 51.855 € 17.285 € per year | The percentage of children whose early school drop-out is prevented through an early identification instrument for students at risk of drop-out. |  |  | Activity is being successfully implemented. In this period, the educational institutions, in accordance with the regulations, have continuously worked on identifying students at risk of dropping out and on planning and implementing dropout prevention measures. The preparation of the training for the application of the dropout prevention instrument is underway. |  |  |
| 3.6.2.16. | Formulation of systemic support measures at school level and local government level on the basis of findings and recommendations of the analysis, subsequent piloting and mainstreaming systemic measures in order to support the education of Roma children at the local level and at the school level. |  |  | -Ministry of Education |  | Continuously, by IV quarter of 2020. | Budget of the Republic of Serbia- 25.926 € 8.642€ per year | Defined measures of ‘alert system’ of an early drop-out and response at the school level that can be applied to other schools. % of schools implementing an early drop-out risk identification tool and preparing a School Action Plan for dropout prevention. |  |  | Activity is being successfully implemented. In I quarter 2022, a total of 5 instalments of student scholarships have been paid to high school students of Roma nationality in the Republic of Serbia: in January – two instalments, in February – two instalments, and in March – one instalment. The monthly instalment amounts to RSD 5,400.00, and is enough to cover the costs of food and accommodation in the student's dormitory for a month. In II quarter 2022, MESTD has included in its financial plan the provision of at least 1100 scholarships for students of Roma nationality for the next school year 2022/23. |  |  |
| 3.6.2.17. | Further strengthen early education of children of age 3 to 5 under a support system targeting the child, rather than the institution, and developed through: -support to early childhood development programs, -the introduction of integrative specialized and additional programs in preschool education, -enabling active inclusion of more Roma children and parents in early development programs. |  |  | -Ministry of Education -Government of the Republic of Serbia – Team for Social Inclusion and Reduction of Poverty |  | Continuously | Budget of the Republic of Serbia- Specified within special action plan in 3.6.2.2 | Increased enrolment of children from the Roma population aged 3 to 5 in pre-school education achieved. Current situation: for the general population coverage is 50.2 %, while for Roma coverage is 5.7%. At least 40% of Roma children (of which at least 40% girls) of age 3 to 5 included in pre-school education. |  |  | Activity is being successfully implemented. During 2020 and 2021, a total of 145 educational institutions have been trained to implement the System for early identification of students in risk of dropping out. |  |  |
| 3.6.2.18. | Increase the coverage of children by the education system, from the mandatory preschool programme to higher education, through: -development of a support system including active involvement of Roma parents -adoption of by-laws on students' living standard. |  |  | -Ministry of Education Partners: -Local self-government units |  | Contionuously, commencing from III quarter of 2018 | Budget of the Republic of Serbia- Specified within special action plan in 3.6.2.2 | At least 60% of pupils from vulnerable groups, amongst which many are Roma (of which at least 40% girls) will have reached the average academic achievement of students of the educational institution they attend. By-laws on students' living standard adopted. |  |  | Аctivity is being successfully implemented. As part of the project "Inclusive Preschool Education", three fairs were held in Čačak, Vranje and Sombor as part of the implementation of the activity – Parenting Fairs. |  |  |
| 3.6.2.19. | Improvement of the educational status of the Roma on the basis of improved cooperation among all existing mechanisms by: - providing support for enrolment of Roma in schools and preventing dropout by the scholarship programme for high school students with average marks higher than 2.5, which will contribute to dropout prevention. -ensuring the universal enrolment of Roma children in regular schools and the Preparatory Preschool Programme - monitoring the implementation of the actions and warning of potential shortcomings in the system |  |  | -Local self-government units -Local Inter-Sector Commissions -Ministry of Education - CSOs |  | Continuously | Budget of the Republic of Serbia Specified within special action plan in 3.6.2.2 | % of Roma children who enroll and complete primary and secondary schools increased, which should also help to decrease the number of early school leavers. Regular enrolment of Roma children in regular schools and the Preparatory Preschool Programme achieved. Civil society reports on monitoring the implementation of the actions publicly available. Number of scholarships given for high school students with average marks higher than 2.5. |  |  | Аctivity is being successfully implemented. In I quarter 2022, a total of 5 instalments of student scholarships have been paid to high school students of Roma nationality in the Republic of Serbia: in January – two instalments, in February – two instalments, and in March – one instalment. The monthly instalment amounts to RSD 5,400.00, and is enough to cover the costs of food and accommodation in the student's dormitory for a month. MESTD has included in its financial plan the provision of at least 1100 scholarships for students of Roma nationality for the next school year 2022/23. |  |  |
| 3.6.2.20. | Provide funds for community services aimed at social inclusion of Roma children through the provision of support to Roma children in learning, inclusion in extra-curricular activities and the development of additional skills necessary for the labour market. |  |  | -Local self-government units Partner: -Ministry of Education |  | Continuously | Budget of the Republic of Serbia Specified within special action plan in 3.6.2.2 | % municipalities who provided funds for the Centres for Social work for services aimed at social inclusion of Roma children through the provision of support to Roma children in learning, inclusion in extra-curricular activities and the development of additional skills necessary for the labour market. |  |  | Аctivity is being successfully implemented. Activities within the project "Bridging the Digital Divide in Serbia for the Most Vulnerable Children" continued, psychosocial support has been provided for almost 3000 students. |  |  |
| 3.6.2.21. | Continue the implementation of affirmative measures through the mentoring system and scholarships for education. |  |  | -Ministry of Education |  | Continuously | Budget of the Republic of Serbia Total amount depends on the number of candidates who will fulfil the conditions (High-school scholarship – 47€ per month University student scholarship - 73€ per month University student credit – 73€ per month) | Scholarships for students from the Roma population are awarded annually. Scholarships provided for: -around 30 university students starting from the second year of studies who have average marks higher than 9 and exams passed from the previous year. -for the school year 2019/2020, 704 scholarships are planned for students of the Roma community and other vulnerable groups. The ranking list includes students with an average grade above 3.5; - through IPA 2014 - 500 scholarships will be awarded to Roma students with an average grade above 2.00 and a grade of at least good (3) for the 2019/2020 school year. - Provision of mentoring for the grantee All others can apply for loans that are coming from the state budget but those that have marks higher than 8.5 and graduate within the normal timeframe will be exempted from paying back the loans. |  |  | Аctivity is being successfully implemented. In I quarter 2022, a total of 5 instalments of student scholarships have been paid to high school students of Roma nationality in the Republic of Serbia: in January – two instalments, in February – two instalments, and in March – one instalment. The monthly instalment amounts to RSD 5,400.00, and is enough to cover the costs of food and accommodation in the student's dormitory for a month. In II quarter 2022, MESTD has included in its financial plan the provision of at least 1100 scholarships for students of Roma nationality for the next school year 2022/23. Students who are members of the Roma national minority (and students with disabilities) are ranked separately by applying milder criteria in accordance with affirmative measures in the field of education, from the second year of studies, if they did not lose an academic year during their studies, regardless of the average grade and ECTS credits. In the academic year 2021/22, a total of 9 student loans and 90 student scholarships have been awarded. |  |  |
| 3.6.2.22. | Adoption of an annual plan of adult education based on experience gained through “Second Chance” IPA project that allows: -persons who complete primary education to continue their education with the support of affirmative measures, or -for persons older than 17 to graduate from secondary school with additional financial support. |  |  | -Ministry of Education |  | Continuously | Budget of the Republic of Serbia- 51.855 € 17.285 € per year | Realization of basic adult education in the territory of 15 school administrations - in 64 primary schools for adult education. Planned number of adult elementary education students in the 2019/2020 school year is 5,912. % of Roma students who enroll and finish high school after Functional basic adult education. |  |  | Activity is being successfully implemented. In the school year of 2021/22, in 65 primary schools that are realizing the Program of functional primary adult education in the territories of 16 school administrations, 5,773 attendees have been enrolled in all the three educational cycles, of which 4,803 are members of Roma population (approximately 83%). In the school year of 2021/22, 276 attendees were enrolled in the penitentiary institutions, of 250 are members of Roma population (approximately 90%). Part-time secondary adult education, for the adult students older than 17, is realized in 40 secondary schools in the territories of 16 school administrations, and it has covered the total of 77 students. The first grade of the secondary part-time education was completed by 140 adult students, and 131 of them was enrolled in the second grade in this school year. According to the enrolment plan for the school year of 2021/22, the approved number for enrolment of adult students in retraining program is 11,995, for additional training programs 7,785 and for specialisations 3,307 adult students. The option for enrolment of adult students who are older than 18 years of age has also been made available within the accredited training programs which were prepared based on the adopted qualifications standards. The decision on determining the Annual Plan for Adult Education in the Republic of Serbia for 2022 was made at the Government session on 30 March 2022. In 2022, the implementation of formal secondary adult education is planned on the territory of 16 school administrations, in 110 secondary schools. The plan is to enrol 77 students, who are older than 17, in the first grade of secondary education as part-time students in secondary education. In II quarter 2022, monitoring of the implementation of the Annual Plan of Adult Education has continued, namely in 65 primary schools which implement the Programme of Functional Primary Education of Adults in the territory of 16 school administrations. Analysis of the mock final exam in the school year 2021/22, conducted during April and May 2022, has shown a slight increase in attendance compared to the last year, while key barriers to regular attendance and taking the final exam have been identified, and the Action Plan of the school team for planning and conducting the final exam and the Action Plan of the andragogical assistant for overcoming the barriers of students in respect of regular attendance and taking the final exam have been created, with the aim of increasing the attendance as well as the quality of the final exam. The Ministry of Education, Science and Technological Development has undertaken steps in order to improve the organization of the final exam in schools which implement the Functional Primary Education of Adults Programme. There are 1,729 Roma nationals in the third cycle of education (82% of the total number of participants in the third cycle). |  |  |
| 3.6.2.23. | Development of systemic models of support to migrant/reintegration returnee children in line with Readmission Agreement and pupils through programs of the Serbian language as a non-mother tongue and support to learning during summer holidays, as well as programs aimed at supporting and assisting school children in improving the school curriculum and materials. |  |  | -Ministry of Education -Commissariat for Refugees and Migration |  | For development of systemic models of support: III quarter of 2016 For implementation: Continuously, commencing from IV quarter of 2016. | For Development of systemic models of support: Budget of the Republic of Serbia- 8.642€ For implementation: Budget of the Republic of Serbia - depends on the number of returnee children utilizing the measures | Systemic models of support to migrant/reintegration returnee children and pupils development and implemented. Number of migrant/reintegration returnee children and pupils benefiting from the measures presented in annual reports. Data comparing number of returnee children who arrive annually and number of those who successfully complete the school reintegration. |  |  | Activity is being successfully implemented. In I quarter 2022, the public call for financing the program of civil society organizations of pertinence for the population of refugees, internally displaced persons and returnees based on the Readmission Agreement was published, but there were no significance programs aimed at supporting and assisting returnee children under the readmission agreement through learning non-native Serbian language and learning during the summer holidays. In II quarter 2022, the public call for financing the program of civil society organizations of pertinence for the population of refugees, internally displaced persons and returnees based on the Readmission Agreement was published, but there were no significance programs aimed at supporting and assisting returnee children under the readmission agreement through learning non-native Serbian language and learning during the summer holidays. During the school year 2021/22, a total of 49 students (returnees on readmission), of which 21 girls and 28 boys, have been enrolled in primary schools in the territory of the Republic of Serbia. Having in mind the unstable epidemiological situation during 2021, as well as the affirmative action of schools during the absence of students, the number of students returned on readmission is decreasing. All students returned based on the Readmission Agreement during 2021 (school years 2020/21 and 2021/22) are enrolled in an age-appropriate class. During the current school year 2021/22, students returned on readmission are included in 13 primary schools and 5 secondary schools in the following school administrations: Belgrade, Novi Sad, Niš, Sombor, Zrenjanin, as well as in schools on the territory of the Group for Professional Pedagogical Supervision in Novi Pazar. The highest concentration of returnees was recorded on the territory of the Group for Professional Pedagogical Supervision in Novi Pazar. The Ministry of Education, Science and Technological Development followed a simplified procedure during the school year 2021/22 when it comes to fulfilment of 38 requests for degree equivalency, i.e. requests for validation of degrees, which greatly facilitated class attendance. An additional measure of support was provided for 36 students through the free textbooks programme. The Ministry of Education, Science and Technological Development, through a competition for the use of budget funds, had allocated funds for 2021 and supported 1 project whose beneficiaries, among others, are students and returnees on readmission. A special measure of support for returnee students in the system of education and upbringing is represented by pedagogical assistants (PA), whose engagement mitigated the consequences of class absence and contributes to the regularity of class attendance. For the school year 2021/22, 21 new PAs have been hired. |  |  |
| 3.6.2.24. | Continue to improve the work of the Center for Lifelong Learning of the Faculty of Philology, University of Belgrade in order to train teachers and researchers for lectures and scientific work in the field of Romani language and culture. |  |  | -Ministry of Education -Faculty of Philology of the University of Belgrade |  | Continiously | Budget of the Faculty of Philology of the University of Belgrade * Costs are to be borne by Faculty of Philology of the University of Belgrade | Teachers of Romani language received certificates and introduced into the primary education system. Baseline: 50 Target: 55 |  |  | Activity is being successfully implemented. The professional development programme for employees in education titled Teaching methodology for the elective programme - Roma language with elements of national culture was implemented for 15 teachers who teach the elective programme Roma language with elements of national culture. The teachers of the elective programme Roma language with elements of national culture from 14 primary schools in the territory of AP Vojvodina have rated the programme as “very successful” and would recommend it to their colleagues, and they consider the knowledge they have acquired to be applicable in educational work. Also, the teachers have expressed great satisfaction with the fact that the training was conducted in their mother tongue, Roma language. |  |  |
| 3.6.2.25. | Improving the teaching quality of the elective subject Roma language with elements of national culture |  |  | -Ministry of Education -Faculty of Philology of the University of Belgrade -Institute for the Improvement of Education |  | By the end of 2021. | Budget of the Republic of Serbia Currently unknown *Depends on the number of schools in which the subject 'Romani Language with Elements of the National Culture' will be introduced. | The curricula and programs for the implementation of the elective subject Roma language with elements of national culture implemented. Improved quality standards for textbooks by removing discriminatory content from textbooks at all levels of education. |  |  | Activity is being successfully implemented. Data on the number of students attending the elective programme Romani language with elements of national culture in the school year 2021/22 will be available in the next reporting period. Information on the number of pupils/students attending the elective study program of Roma Language with Elements of National Culture in the school year of 2021/22 will be available in the next reporting period. Following the educational reform, the MPNTR, with the participation of the National Council of the Roma National Minority, developed reformed teaching and learning programs for the Roma language with elements of national culture for all grades of primary school. These programs have been adopted by the National Education Council. For the elective subject / program Romani language with elements of national culture, four textbooks for the first four grades were printed and are in the Catalog of textbooks in the languages of national minorities for preschool, primary and secondary education - school 2020/2021. year, http://www.mpn.gov.rs/udzbenici/: Romani language with elements of national culture, textbook for the fourth grade of primary school in Romani; Romani language with elements of national culture, textbook for the third grade of primary school in Romani language; Romani language with elements of national culture - Primer for the 2nd grade of primary school for teaching in Romani language; Picture book for the 1st grade of primary school - Romani language with elements of Roma national culture. In the school year 2020/21. annual elective subject / program Romani language with elements of national culture is attended by 2,467 students in 68 primary schools in Serbia. The Ministry of Education, Science and Technological Development had also, for the next school year of 2021/22, submitted a questionnaire for the selection of an elective subject/programme Mother tongue/speech with elements of national culture. The questionnaire contains 16 languages/dialects, one of which is the Romani language with elements of national culture. In the school year 2021/22, a total of 2566 students attend the elective programme Roma language with elements of national culture. On 13 April 2022, the Pedagogical Institute of Vojvodina organized a professional development programme for employees in education titled "Teaching methodology for the elective program - Roma language with elements of national culture". By decision of the Minister of Education, Science and Technological Development (no: 610-00-00171/2022-07), this programme received the status of a programme of public interest, and is intended for teachers who teach the elective programme Roma language with elements of national culture and aims to improve the methodological and pedagogical competences of teachers of the Roma language for the implementation of this elective programme. The programme was implemented by the author, Marija Aleksandrović, PhD, professor of vocational studies, Preschool Teacher Training College "Mihailo Palov", Vršac, and the implementer, Eldena Stanić, associate in teaching, Preschool Teacher Training College "Mihailo Palov", Vršac. The participants of the programme (15 teachers of the Roma language) were presented with different methodical procedures in the analysis of literary works, ways of motivating students to read and analyse a prosaic text, as well as functional procedures in the teaching of grammar and various lexical and semantic exercises. The teachers of the elective programme Roma language with elements of national culture from 14 primary schools in the territory of AP Vojvodina have rated the programme as “very successful” and would recommend it to their colleagues, and they consider the knowledge they have acquired to be applicable in educational work. Also, the teachers have expressed great satisfaction with the fact that the training was conducted in their mother tongue, Roma language. |  |  |
| 3.6.2.26. | Employment Establishment of a legislative framework in the field of social entrepreneurship that will enable an increase in the labor activation of working age persons in the social protection system and hard-to-employ unemployed persons, in accordance with the regulations in the field of employment (including Roma) and other hard-to-employ persons from particularly vulnerable categories, in line with the best practices of the European Union. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -Ministry of Tourism, Trade and Telecommunication |  | IV quarter of 2020. | Budget of the Republic of Serbia – 17.285 € | Legislative framework for social entrepreneurship, particularly in terms of social enterprises that employ Roma population in accordance with the best practices of the European Union developed. |  |  | Activity is fully implemented. The Law on Social Entrepreneurship ("Official Gazette of RS", No. 14/22) was adopted on February 7, 2022. Through the normative regulation of the field of social entrepreneurship, it will contribute to its development in order to achieve a greater degree of social inclusion of members of socially vulnerable groups and their integration into society, increase employment and their economic empowerment. The aim of the Law is to create a favourable business environment for the development of social entrepreneurship, develop awareness of the importance of the social economy and social entrepreneurship and meet identified social needs. |  |  |
| 3.6.2.27. | Actively promote and implement the policies and measures aimed at increasing employment of the Roma, with special emphasis on Roma women, in particular through: -public calls for applications of self-employment -public works activities targeting hard-to-employ populations including the Roma population. |  |  | -Ministry of Labour, Employment Veterans and Social Affairs -Public authorities at the central and local levels -National employment service |  | Continuously | Budget of the Republic of Serbia - regular activity Costs currently unknown - the total amount will be known after the end of the public call procedure | Public calls for applications of self-employment performed. Public works activities targeting hard-to-employ populations including the Roma population organized. Number of persons belonging to Roma community, with special emphasis on Roma women, benefiting from the undertaken policies and measures. |  |  | Аctivity is being successfully implemented. In accordance with the provisions of the Law on Employment and Unemployment Insurance ("Official Gazette of RS", no. 36/09, 88/10, 38/15, 113/17-other laws, 113/17 and 49/21), The National Employment Service (NES) also keeps records of unemployed persons - persons from 15 years of age until they meet the conditions for pension, i.e. up to 65 years of age at the latest, who are capable and immediately ready to work, who have not established an employment relationship or otherwise have achieved the right to work, and are kept on the unemployment register and are actively looking for employment. According to data for the situation as of June 30, 2022, the number of unemployed in the NES records was 444,213 persons (249,385 women or 56.1%), which represents a decrease of 6,806 persons (3,582 women) compared to the month of May 2022., i.e. a decrease of 96,526 persons (50,017 women) compared to the same month of the previous year. When it comes to the age structure of registered unemployment, the share of young people (15-29 years old) in total registered unemployment is 19.2%, while the share of the 50-65 age group is 38.3%. Observed according to the length of the job search, there were 305,317 persons in the long-term unemployed status, which makes up 68.7% of the total registered unemployment. When it comes to the registered unemployment of Roma and Roma women, it is indicated that the registration of a person to the NES records, i.e. the way of keeping records and the content of data about a person is defined by the Law on Employment and Unemployment Insurance and the Rulebook on the detailed content of data and the way of keeping records in the field of employment ("Official Gazette of RS", number 15/10). Nationality or ethnic affiliation is only one of the personal data provided for in Article 5 of the said Rulebook. The data is recorded based on the person's statement, that is, the statement is not mandatory, bearing in mind the legal provisions related to the prohibition of discrimination when looking for a job and employment. As of June 30, 2022, there were 28,668 persons (14,525 women) who declared themselves as members of the Roma national minority, which represents a share of 6.5% in the total registered unemployment. Observed according to age, young people up to 30 years of age account for 14.2% of the total registered unemployment of Roma/Roma women, while the share of those over 50 is 24.6%, which is more favorable compared to the characteristics of total registered unemployment. Observed according to the level of education, persons without qualifications or with a low level of education make up 88.6% of the total registered unemployment of Roma/Roma women, 10.4% are made up of persons with secondary education, while the share of Roma/Roma women with higher education is 1.0%, which is significantly less favorable in relation to the qualification structure of total registered unemployment. |  |  |
| 3.6.2.28. | Launch concrete projects linking education (vocational, university) to concrete employment. |  |  | -Ministry of Education -Ministry of Labour, Employment Veterans and Social Affairs -National employment service |  | Continuously | Budget of the Republic of Serbia Costs depend on annual priorities | Concrete projects linking education (vocational, university) to concrete employment available and sustainable. |  |  | Activity is being successfully implemented. In I quarter 2022, the following activities have been implemented: 3 qualification standards have been developed and adopted, Conclusions on the adoption of the Report on the work of the Qualifications Agency for 2021, on the adoption of the Report on the implementation of the Financial Plan of the Qualifications Agency for 2021, on the adoption of the Report on the NQFS Council for 2021, and on the adoption of the Annual Reports on the work of 12 sectoral councils for 2021 have been adopted, the Rulebook on Standards for Self-Evaluation and External Assessment of the Quality of Work of Publicly Recognized Organizers of Adult Education Activities has been adopted, and a draft Rulebook on Amendments to the Rulebook on the Content and Manner of Keeping the Register of the National Qualifications Framework of the Republic of Serbia has been drafted. Currently, 4633 qualifications, 66 qualification standards, and 102 publicly recognized organizers of adult education have been entered into the NQFS Register. A total of 32 dual study programmes have been accredited; promotion of dual education has been organized; a Memorandum of Cooperation between the Ministry of Education, Science and Technological Development, the Aviation Academy and Airbus has been signed; visit of the Slovenian delegation has been organized in order to provide support to the training centre of the Aviation Academy in the certification process before the European aviation authorities - European Union Aviation Safety Agency (EASA). As part of the "Inclusion of Roma and other marginalized groups in Serbia" project, implemented by GIZ, phase 3 of support to local self-government units for the implementation of innovative and sustainable measures to increase employability and employment of less employable persons is underway, which is being implemented in cooperation with SCTM. Phase 3 is implemented in the period November 2021 - November 2022, and the beneficiaries of the support are Bač, Bor, Kula, Novi Pazar, Novi Sad, Mladenovac, Požarevac, Valjevo, Sremska Mitrovica and Zvezdara. Also, as part of the mentioned project, activities were started in the identification of innovative models of support for unemployed Roma men and women, which are implemented in FR Germany, and can be an example of good practice for the development of the Package of services for Roma in the Republic of Serbia. As part of the "Migration for Development" program, implemented by GIZ, preparatory activities for the implementation of the Public Call for local self-government units for the allocation of funds for the pilot implementation of innovative solutions in the area of local employment policy are being finalized. One of the identified target groups of users of innovative solutions are unemployed Romani men and women. In II quarter of 2022, the following activities have been carried out by the Ministry of Education: 11 qualification standards have been developed and adopted. 4,632 qualifications, 66 standard qualifications, and 109 publicly recognized organizer of adult education activities are currently entered in the NQFS Register. Activities on the implementation of the ERASMUS-AGENDA-IBA and ERASMUS-EQF-IBA projects within the ERASMUS + Programme have been commenced, with the aim of connecting the NQFS Register with the Europass online platform, as well as for improving the adult education system. The Enrolment Plan for the school year 2022/2023 for dual educational profiles has been drawn up; the Working Group for Amendments to the Law on Dual Education and the Law on Secondary Education has been formed; Conclusion on determining the Basis for concluding an Agreement on cooperation between the Ministry of Education, Science and Technological Development of the Republic of Serbia, the Civil Aviation Agency of the Republic of Slovenia and the Aviation Academy Belgrade has been adopted; an initiative was submitted for declaring the investment project for increasing the construction and infrastructural capacities of the Aviation Academy in the City of Belgrade and in the City of Vršac as a project of importance for the Republic of Serbia, on the basis of which the Conclusion which establishes the investment project for increasing the construction and infrastructure capacities of the Aviation Academy in the City of Belgrade and to the City of Vršac as a project of importance for the Republic of Serbia was adopted. |  |  |
| 3.6.2.29. | Enhance involvement of local government in reducing Roma unemployment through implementation of local action plans for employment. |  |  | -Local self-government units -National Employment Service -Ministry of Labour, Employment Veterans and Social Affairs |  | Continuously | Budget of the local self-government- Costs depend on adopted local employment action plans | Assessment of the local labour market situation conducted. Measures that will yield the best results in terms of Roma employment at the local level proposed. Number of persons belonging to Roma community benefiting from the implemented measures. |  |  | Аctivity is being successfully implemented. On March 30, 2022, the Minister in charge of employment passed a Decision on participation in financing active employment policy measures envisaged by local planning documents in the field of employment in 2022, which supported 95 requests submitted by local self-government units. This decision approved the amount of up to 401,499,606.93 dinars from the NES funds for participation in the co-financing of active employment policy measures. By June 30, 2022, 94 agreements on cooperation between the NES and local self-government units on the implementation of local planning documents in the field of employment were concluded, one agreement was terminated. For the implementation of 93 agreements, LS funds amount to 346,668,332.10 dinars, while NES funds amount to 395,999,606.93 dinars. The process of preparing an agreement on cooperation between the NES and local self-government units on the implementation of local planning documents in the field of employment is underway. |  |  |
| 3.6.2.30. | Developing affirmative measures, financial and non-financial incentives such as self-employment subsidies, in order to support employment of Roma and the launching of sustainable business activities of Roma. |  |  | -Ministry of Labour, Employment Veterans and Social Affairs -National employment service |  | Continuously | Budget of the Republic of Serbia Costs depend on annual priorities Donor funds | Application of affirmative measures, financial and non-financial incentives. Assigned subsidies for Roma self-employment. Sustainable Roma business activities launched. |  |  | Аctivity is being successfully implemented. On January 31, 2022, the NES issued a Public Call for Roma Unemployed for a Subsidy for Self-Employment in 2022 and a Public Call for Unemployed for a Subsidy for Self-Employment in 2022. The deadline for submitting applications with a business plan is March 31, 2022, and accordingly, data on self-employment subsidies granted to Roma men and women in 2022 are still not available within the active employment policy system. The deadline for submitting requests with a business plan was March 31, 2022, and a total of 494 requests were submitted. Until 30.06.2022. year, 180 decisions on subsidy allocation were made, and 162 contracts were signed. |  |  |
| 3.6.2.31. | Provision of information on the available measures of active employment policy (in line with current public calls and vacancies) and employment opportunities. |  |  | -Ministry of Labour, Employment, Veterans and Social Affairs -National employment service -Office for cooperation with civil society -Civil society organizations, in particular Roma organizations |  | Continuously | Budget of the Republic of Serbia - regular activity | Greater availability of information about employment opportunities of the Roma provided. |  |  | Аctivity is being successfully implemented. In accordance with the provisions of the Law on Employment and Unemployment Insurance, the NES determines an individual employment plan (IEP), no later than 90 days from the entry into the unemployment register, and it adjusts to the characteristics of the unemployed and labour market needs, at least once in six months. IEP is the basic instrument in working with the unemployed and the basis for inclusion in ALMPs. The IEP determines the occupations in which the person will be mediated, the activities that the person will undertake and the ALMPs of the in which they will be involved in order to improve employability or employment. During the expert counselling conversation with the employment counsellor, the unemployed person is informed about the situation and demand on the labour market, as well as about the available ALMPs. Also, unemployed people have the opportunity to use the services of information on career development opportunities, counselling on career development opportunities and information and counselling services in the Business Centre. In the period January-March 2022, 14,058 Roma (6,787 Roma women) used employment counseling services, while 57 Roma (33 Roma women) used information and counseling services on career planning opportunities. In the period January-June 2022, employment counseling services were used by 26,077 Roma (12,858 Roma women), while 57 Roma (33 Roma women) used information and counseling services about career planning opportunities. |  |  |
| 3.6.2.32. | Housing Development of manual and guidelines on the competent authorities' procedures for the relocation of informal settlements, with particular emphasis on the roles and obligations of local self-governments, -distribution of manual and guidelines to all relevant administrative actors. -clear monitoring and reporting mechanism. |  |  | -Ministry of Construction, Transportation and Infrastructure |  | IV quarter of 2020. | Budget of the Republic of Serbia- 1.702 € | Manual and guidelines, with particular emphasis on the roles and obligations of local self-governments developed and distributed. Report of the Government on implementation submitted before the next Roma seminar, including the results of legislation implementation by all municipalities across the Republic of Serbia. |  |  | Activity is being successfully implemented. A draft of the Guidelines has been prepared. It will be submitted to civil society organizations for review by mid-April at the latest. As this is not a planning document or a regulation, there is no obligation for public consultation or public hearing, so the document will then be posted on the website of the Ministry, which contains instructions on the application of regulations: https://stanovanje.gov.rs/ By the end of the year, a shortened Manual based on the guidelines will be prepared and will be distributed to local self-government units by the end of the I quarter of 2023. The monitoring and reporting mechanism will be established after the adoption of the amendments to the Law on Housing and Building Maintenance and the amendment of the by-law that prescribes the report form on housing needs and living conditions in LGUs from Art. 115 and 121 of the Law. |  |  |
| 3.6.2.33. | Resolution of existing informal substandard Roma settlements through: -provision of support for the production of technical documentation for a total of 60 sub-standard settlements, -planning documentation for 10 substandard settlements, -professional support in the process of legalization for 10 local self-government units - the formation of 30 new mobile teams. |  |  | -Ministry of Construction, Transport and Infrastructure - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 -Local self-government units |  | IV quarter of 2020. | Budget of the Republic of Serbia The costs will be specified within the Special AP for the Strategy for Improving the Position of Roma in the Republic of Serbia for the period 2015-2025 IPA 13, IPA 14 and IPA 16 | Provided support for the production of technical documentation for a total of 60 substandard settlements, planning documentation for 10 substandard settlements, as well as expert support in the process of legalization for 10 units of local Established and empowered 30 new mobile teams |  |  | Аctivity is fully implemented. Support for the preparation of technical documentation for 60 sub – standard settlements – completed Planning documentation for 10 substandard settlements – completed for 38 sub.-standard settlements. Professional support in the process of legalization for 10 local self-government units is in progress. So far 2,153 requests for legalization have been submitted (individually or through the municipal / city administration). Legal aid was provided to 247 members of the Roma population. 37 mobile teams were formed. |  |  |
| 3.6.2.34. | Address the situation of the internally displaced Roma from Kosovo and Metohija who largely do not plan to return there by financing programs for enhancement of the living conditions of internally displaced people, with focus to Roma. |  |  | -Commissioner for Refugees and Migration |  | Continuously, until 2021 | Budget of the Republic of Serbia The costs will be specified within the Special AP for the Strategy for Improving the Position of Roma in the Republic of Serbia for the period 2015-2025 | Living conditions of the internally displaced Roma from Kosovo and Metohija improved while in displacement. |  |  | Аctivity is being successfully implemented. When planning and implementing both national and donor funds, the Commissariat for Refugees and Migration pays special attention to cover local self-governments (LSGs) where a large number of internally displaced persons (IDPs) reside. Roma IDPs are eligible to apply for all programs for the improvement of living conditions of IDPs. Bearing in mind the fact that all stated below refers to the most vulnerable IDPs, Roma included, please see the point 3.7.1.4. Remark: There is no obligation for IDPs to declare themselves by ethnicity. |  |  |
| 3.6.2.35. | Identify new substandard settlements in which living conditions require improvement, including: -preparation of planning documentation, -provision of conditions for improving infrastructure networks, -actions to relocate the inhabitants to new social housing. |  |  | - Ministry of Construction, Transport and Infrastructure IPA unit |  | I quarter of 2019 - 2021 | Budget of the Republic of Serbia The costs will be specified within the Special AP for the Strategy for Improving the Position of Roma in the Republic of Serbia for the period 2015-2025 | New substandard settlements in which living conditions require improvement, identified including: - planning documentation prepared, -conditions for improving infrastructure networks provided, - relocation of the inhabitants to new social housing. |  |  | Аctivity is being successfully implemented. In I quarter 2022, through the IPA 2013 project "Technical support for improvement of the living and housing conditions of Roma population currently residing in informal settlements", technical assistance was provided for the preparation of planning documentation for 11 local self-government units. Through the implementation of the IPA 2013 project "Implementation of durable solutions for housing and improvement of physical infrastructure in Roma settlements" - Grant scheme, 11 grant agreements were implemented and 114 housing units were built in houses and 12 apartments, and 59 houses were reconstructed. The total number of members of Roma population with resolved housing issues is over 750. Over 5,000 people have benefited from the improvement of communal and road infrastructure. Through the implementation of the IPA 2018 project "European Union Support to Social Housing and Active Inclusion" - Grant scheme, the construction of social housing is planned (421 families with about 1500 household members) through 19 grant agreements with municipalities / cities Cacak, Ljubovija, Svilajnac , Topola, Pancevo, Gadzin Han, Loznica, Sabac, Odzaci, Kula, Vrnjacka Banja, Novi Pazar, Zagubica, Raska, Vrsac, Lebane, Boljevac, Koceljeva and Vladicin Han. The preparation of secondary public procurement for works and supervision, as well as for other mechanisms of social inclusion in local self-government units is underway. The second public call for interested municipalities / cities to submit applications for grants expired on November 15, 2021. 15 applications were accepted and 5 were rejected. The evaluation procedure was completed. The final meeting of the evaluation commission to determine the status of the evaluation was held on March 4. Grant agreements are expected to be signed with the selected LSGs by the end of March / beginning of April 2022. The value of the grant agreement within the second public call is EUR 4.4 million. In II quarter 2022, grant contracts were signed with selected local self-government units (Bujanovac, Sombor, Pirot and Opovo) in April 2022. The value of the grand contract within the second public call is 4.4 million euros. The third public call for interested municipalities/cities to submit applications for grants was published on March 15, 2022, and expired on April 15, 2022. During the month of May, the evaluation of the received offers was carried out, and the field evaluation is planned for the month of June. After that, it is planned to sign the grant contract with the selected applicants in July. |  |  |
| 3.6.2.36. | Update or adopt where missing local strategies and action plans to also include more accurate data on Roma residents in informal settlements, as well as to propose measures to regulate and consolidate living conditions within existing informal settlements. |  |  | - Ministry of Construction, Transport and Infrastructure based on data gathered from Local self-government units - Coordination body for monitoring the implementation of the Strategy for social inclusion of Roma in the Republic of Serbia for the period from 2016 to 2025 |  | I quarter of 2020. | Budget of local self-governments- 4.321€ per municipality - | Local strategies and action plans updated, or adopted where missing, including: -more accurate data on Roma residents in informal settlements, -proposed measures to regulate and consolidate living conditions within existing informal settlements. |  |  | Activity is not implemented. The proposal of the Action plan for Social Inclusion of Roma Men and Women defines the adoption of new and updating of existing action plans. Also, the aforementioned document foresees the legalization of buildings in substandard Roma settlements, as well as the equipping of complete communal infrastructure and the renewal of the existing one, which means meeting basic living standards. |  |  |
| 3.6.2.37. | Social protection and health care Improving the social protection system in the community relevant for the detection and protection against child labor abuse, with a special emphasis on Roma children (expanding the shelter network for children, drop-in centers for children, living quarters, family support services, etc.) |  |  | -Ministry of Labour, Employment, Veteran and Social Affairs based on data gathered from centers for social work |  | Continuously | Budget of the local self-government units – Total amount depends on the number of service users For accommodation: Per child 1362€ per year For professional work: Per social worker 1056€ | Sustainable financial support for social protection community services such as drop-in centres, shelter network for children, living quarters, family support services, etc. regularly provided on annual basis. |  |  | Аctivity is being successfully implemented. In II quarter 2022, sustainable financial support for the development of community-based services such as shelters for children, drop-in centres for children, day care centres, etc. is regularly provided on an annual basis through the mechanism of earmarked transfers by which funds from the republic budget are transferred to those local self-governments that are below the republic level of development and cannot provide funds for these purposes on their own. On average, it was around 700 million dinars a year (around 6 million euros) starting in 2016. For 2021, the allocated funds were reduced compared to previous years, so that a total of 556 million dinars was allocated. For 2022, the planned funds were reduced again by the Budget Law to 500 million dinars. This trend of decreasing funds will certainly have an adverse effect on the deinstitutionalization process. The number of licensed shelters for children and youth is 4 while the number of licensed drop-in centres for children is 3. The number of licensed day care centres for children and youth with behavioural problems is 3. The establishment of these services is the responsibility of local self-governments that clearly do not sufficiently recognize the importance and needs for these services in their communities. |  |  |
| 3.6.2.38. | Organizing support assistance to children living and/or working on the street, with increased reliance on the capacities of social protection institutions providing services of temporary and permanent residence, including the services of intensified treatment of children with structural behavioral and personality problems (PIT programme) |  |  | -Ministry of Labour, Employment, Veteran and Social Affairs -Centers for Social Work |  | Continuously, commencing from I quarter of 2016. | Budget of the Republic of Serbia- 5.744€ Budget of Centers for Social Work * Regular activity (falling within the scope of regular duties of staff employed in respective institutions). | Assistance to children living and/or working on the street enhanced through greater availability of services of temporary and permanent residence, and services of intensified treatment of children with structural behavioral and personality problems (PIT programme). |  |  | Аctivity is being successfully implemented. In I quarter 2022, accredited programs aimed at this user group are: "Program of intensive treatment of children with multiple disabilities in behavior, emotional and social development and functioning - PIT" and the program "Family Support Program", which has end users as families of children. live and / or work on the streets. Neither of these two programs was implemented in the first quarter of 2022. There are currently 4 licensed shelters for children and youth: 2 in Belgrade, 1 in Kragujevac and 1 in Nis, as well as 3 licensed drop-in shelters for children and youth - all three in Belgrade. |  |  |
| 3.6.2.39. | Intensifying the inclusion of Roma children in local social care services, improve the support programs for mothers and strengthen counselling role in working with Roma families. |  |  | - Ministry of Labour, Employment, Veteran and Social Affairs based on data gathered from Centres for social work |  | Implementation: Continuously, commencing from I quarter of 2019. | Budget of the Centres for social work | Increased number of Roma children included in local social care services. Local support programs for mothers improved. Rulebook on intensive family support adopted. Funds for "Family Advisor" service provided. |  |  | Activity is not implemented. The family assistant service will be established in the centers for children, youth and family after the adoption of the legal basis for their formation through amendments to the Law on Social Protection. Amendments to the Law on Social Protection are still ongoing. After the adoption of the amendments to the HSE, there would be the establishment of centers for children, youth and family that would develop the service of a family associate and have an advisory role in working with Roma families. These centers would be located in current institutions for children without parental care and would be a step towards deinstitutionalization. |  |  |
| 3.6.2.40. | Analysis of the proposal of the model of sustainable institutionalization of health mediators. |  |  | -Ministry of Health -UNICEF |  | III quarter of 2020 | Budget of the Republic of Serbia - 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | An adequate model of sustainable institutionalization of health mediators identified. |  |  | Activity is not implemented. No new information was provided. |  |  |
| 3.6.2.41. | Implementation of the adopted sustainable model of institutionalization of health mediators which will include: - appropriate form of employment and adequate compensation; - appropriate job descriptions; -Institutions compatible with their role. |  |  | -Ministry of Health |  | II quarter of 2021. | Budget of the Republic of Serbia- Depends on the number of approved jobs of health mediators | The adopted model of sustainable institutionalization of health mediators implemented. |  |  | Activity is not implemented. No new information was provided. |  |  |
| 3.6.2.42. | Earmark additional funds to gradually increase the number of health mediators, based on needs assessment. |  |  | -Ministry of Health |  | By 2021. | Budget of the Republic of Serbia The costs will be specified within the Special AP for the Strategy for Improving the Position of Roma in the Republic of Serbia for the period 2015-2025 | Additional funds gradually earmarked to increase the number of health mediators, based on needs assessment. The number of hired health mediators increased to 85 with the tendency of growth during 2019 and 2020. |  |  | Аctivity is not implemented. No new information was provided. |  |  |
| 3.6.2.43. | Enhance system of protection and support measures for victims of domestic violence, in line with new Strategy for Prevention of Violence in the Family and Partner Relations. |  |  | -Ministry of Labour, Employment, Veteran and Social Affairs Partners: -Ministry of Interior -Ministry of Justice -CSOs -International organizations |  | Continuously | For reporting: Budget of the Republic of Serbia 25.926€ 8,642€ per year For implementation: The costs will be specified within the Special AP for the Strategy for Prevention of Violence in the Family and Partner Relations . | System of protection and support measures for victims of domestic violence improved. Reports on implementation of the Strategy for Prevention of Violence in the Family and Partner Relations. |  |  | Аctivity is being successfully implemented. The National Strategy for Prevention and Combating Gender-Based Violence Against Women and Domestic Violence 2021-2025 was adopted at the Government session on 22 April 2021. In I quarter 2022, within the Program of Professional Development of Police Officers of the Ministry of the Interior for 2022, in order to improve the system of protection and support of victims of domestic violence, through compulsory classes in the field of "Theoretical classes", the topic "Police action in cases of domestic violence partnership, which was attended by a total of 2,827 police officers during the reporting period. In I quarter 2022, 972 criminal offenses of Domestic Violence were committed under Article 194 of the Criminal Code. The police filed 990 criminal charges against 960 perpetrators, and the number of injured persons is 1,072. Also, within the family and partnerships, 6 fatal events were recorded: 4 females and 3 males. 6,437 events with elements of domestic violence were reported to the police. In I quarter 2022, 7,014 urgent measures were imposed on the basis of the Law on Prevention of Domestic Violence, of which 2,169 urgent measures Temporary removal of the perpetrator from the apartment, as well as 4,845 urgent measures Temporary prohibition of the perpetrator to contact and approach the victim. A total of 4,719 emergency measures were extended, and 289 emergency measures were violated. In April and June 2022, the Ministry of Justice of the Republic of Serbia, in partnership with the United Nations Development Program in Serbia - UNDP, held two workshops on the topic "Effective institutional response to domestic violence" for members of coordination and cooperation groups in the area of Kolubara and Toplica district. On 5th and 6th of April 2022, the workshop in Kolubara district was attended by 40 representatives from the prosecutor's office, centers for social work, police, health and educational institutions from the territory of Kolubara district, as well as representatives of members of the Council for the Suppression of Domestic Violence. The workshop that was held on 2nd and 3rd of June for the area of Toplica district was attended by 42 representatives from the prosecutor's office, centers for social work, police, health and educational institutions from the territory of Toplica district. The Ministry of Justice of the Republic of Serbia is in partnership with the United Nations Agency for Gender Equality and Empowerment of Women (UN WOMEN), in cooperation with the Embassy of Austria in Belgrade, on June 23, 2022, in the premises of the Embassy of Austria organized the webinar "Exchange of good practices in dealing with cases of violence against women and domestic violence". The webinar was attended by 20 judges and public prosecutors from the areas of Belgrade, Novi Sad, Kragujevac, Mladenovac, Lazarevac, Pančevo and Smederevo. Within the Program of Professional Development of Police Officers of the Ministry of the Interior for 2022, in order to improve the system of protection and support of victims of domestic violence, through compulsory teaching in the teaching area "Theoretical teaching", the topic "Police action in cases of domestic violence and in partnership ”which was attended by a total of 26,092 police officers during the reporting period. In II quarter 2022, 1,231 criminal acts of domestic violence were committed. The police filed 1,210 criminal reports against 1,200 perpetrators, and the number of injured persons is 1,349. Also, within the framework of family and partnership relations, a total of 14 events with fatal consequences were recorded, during which 9 female and 8 male persons lost their lives. 9,148 events with elements of domestic violence were reported to the police. In the mentioned period, 9,940 emergency measures were issued on the basis of the Law on Prevention of Domestic Violence, of which 2,981 emergency measures were temporary removal of the perpetrator from the apartment, as well as 6,959 emergency measures were temporary ban on the perpetrator from contacting and approaching the victim of violence. In total, 6,484 emergency measures were extended, and 717 emergency measures were violated. The Ministry of Internal Affairs, in cooperation with the Judicial Academy and the Criminalistics and Police University, implemented the fifth cycle of training for the implementation of the Law on Prevention of Domestic Violence, in the period from November 22, 2021 to April 16, 2022. Within this cycle, 574 police officers were trained. A total of 2,007 police officers were trained in the first four training cycles. After the completion of the fifth training cycle, a total of 2,581 police officers were trained. |  |  |
| 3.6.2.44. | Improving the system of prevention, protection, support and reintegration of victims of human trafficking in accordance with the new Strategy for the Prevention and Suppression of Trafficking in Persons, Especially Women and Children and Protection of Victims 2017-2022. Link with AP Chapter 24 |  |  | -Ministry of Interior -Office for Coordination of Activities in Combating Human Trafficking -Center for protection of victims of human trafficking Partners: -Ministry of Labour, Employment, Veteran and Social Affairs -CSOs -International organizations |  | Continuously, by 2022. | For reporting: Budget of the Republic of Serbia 25.926€ 8,642€ per year For implementation: The costs will be specified within the Special AP for the Strategy for Prevention of Violence in the Family and Partner Relations . | Prevention, support, protection and reintegration services for victims of human trafficking improved. Reports on implementation of the Strategy for the Prevention and Suppression of Trafficking in Persons, Especially Women and Children and Protection of Victims 2017-2022. |  |  | Аctivity is being successfully implemented. In I quarter 2022, an identification process has been launched for 39 victims and all of them are included in support programs. 20 victims of human trafficking have been identified. In 20 cases, support was provided to users for giving statements and testifying. The centre proposed granting the status of a particularly sensitive witness to 19 victims of trafficking. The shelter of the Centre for the Protection of Victims of Trafficking in Human Beings, as the only one of its kind in Serbia, has received a license for accommodation services for a period of 5 years. Cooperation has been established with the National Association of Youth Offices and joint work on the prevention of human trafficking among children and youth has been agreed. Work has begun on the development of regional standard operating procedures for the treatment of victims of trafficking and the regionalization of health indicators for the preliminary identification of victims of trafficking. The project "Mental Health of Victims of Trafficking in Human Beings and Service Providers" has been launched, which the Centre is implementing with the support of the German International Cooperation Organization GIZ and will provide psychotherapy for shelter users, training. In II quarter 2022, the Shelter for Victims of Trafficking received the first beneficiaries and so far 3 victims of trafficking have been accommodated there, including one baby - a child of a trafficking victim. During this period, 9 victims of human trafficking were identified (we note that the month of June is not over yet and that several identification procedures are nearing completion, so it is possible that the number will increase). The Centre for the Protection of Victims of Human Trafficking participated in three trainings held in cooperation with the NGO Atina and with the support of the IOM, on the topic of practical application of the Standard Operating Procedures for the Treatment of Victims of Trafficking. The trainings were held in Niš, Novi Sad and Subotica and were attended by representatives of the judiciary, police, health care, social protection and the non-governmental sector. The Centre for the Protection of Victims of Human Trafficking participated in 2 trainings for the application of indicators for preliminary identification of victims of trafficking in human beings for the education system, organized with the support of the Council of Europe, and attended by 50 representatives of the education system. Within the Program of Professional Development of Police Officers of the Ministry of the Interior for 2022 in order to improve the system of prevention, protection, support, and reintegration of victims of human trafficking, through compulsory teaching in the teaching area "Theoretical teaching", the topic "Concept, recognition and action" police for the crime of trafficking in human beings”, attended by a total of 26,158 police officers in the reporting period. |  |  |
| 3.6.2.45. | Improvement of the software to enable data exchange of information from the Ministry of Health database on the Roma, among relevant sectors, in line with Law on the Protection of Personal Data, in order to facilitate a more comprehensive response to Roma inclusion by social services. |  |  | -Ministry of Health -Ministry of Labour, Employment, Veteran and Social Affairs -Ministry of Education |  | Continuously | Budget of the Republic of Serbia- 25.926 € 8.642 € per year | Data exchange on information from the Ministry of Health database on the Roma enabled. |  |  | Activity is partially implemented. The project "Supporting the work of health mediators - monitoring and education" has been implemented in cooperation with the Institute of Social Sciences and UNICEF. The software for reporting on the work of health mediators has been created. From September 2022. it is planned to train health mediators to work on data entry. |  |  |
| 3.7. POSITION OF REFUGEES AND INTERNALLY DISPLACED PERSONS |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.7.1. Serbia improves the situation of refugees and IDPs by providing permanent housing solutions and improving living conditions, improving their access to justice through free legal aid, provision of civil documentation to undocumented persons ensuring their full access to rights and fostering their social and economic integration |  |  |  |  |  | Position of refugees and internally displaced persons improved by ensuring their full access to rights, including civil documentation and housing solutions for the most vulnerable ones. |  | 1. The number of housing solutions for refugees and IDPs provided by the Regional Programme for housing refugees and Commissariat for Refugees and Migration; 2. Annual report of the Ombudsman stating improved position of refugees and IDPs. 3. Closure of all formal collective housing centers; 4. European Commission Annual Progress Report on Serbia stating progress in part relating to rights of refugees and IDPs. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.7.1.1. | Providing permanent housing solutions for refugees through the implementation of the Regional Programme for housing refugees and regular national housing programs. |  |  | -Commissioner for Refugees and Migration -Regional Programme for housing refugees |  | Continuously, until 2022. | Regional housing program Total - 169.155.809 EUR Donor funds - 132,108,947 EUR RS Contribution - EUR 29,146,862 By year 2019 - 48,591,958 EUR 2020 - 39,695,000 EUR 2021 - 4,300,000 EUR Budget of RS (regular national program): 2018 -195.000.000 RSD, 2019 - 195,000,000 RSD, 2020 - 195.000.000 RSD, 2021 - 195.000.000 RSD. | Permanent housing solutions for refugees provided through the implementation of the Regional Programme for housing refugees. |  |  | Аctivity is being successfully implemented. The Republic of Serbia continues to implement approved subprojects under the Regional Housing Program (RHP) which provides 7,550 housing solutions for refugees. So far, within the RHP a total of 6,393 housing solutions have been delivered. RS Budget – Based on public calls for local self-government units from the previous reporting period, a total of 83 packages of building materials and 64 village houses were allocated for refugees. |  |  |
| 3.7.1.2. | Provide free legal aid in order to ensure full access to rights including personal documents for internally displaced persons and refugees. |  |  | -Ministry of Justice |  | Continuously, commencing from IV quarter of 2019. | Budget of the Republic of Serbia- Budgeted in activity 3.5.1.2. | Law on Free Legal Aid adopted and implemented. Number of internally displaced persons and refugees who were provided free legal aid on the basis of data from the providers. |  |  | Activity is being implemented successfully. Law on Free Legal Aid is effectively implemented. Link with section 3.5.1. |  |  |
| 3.7.1.3. | Effective implementation of the Law on Non-contentious proceedings especially in the part related to the provision of civil documentation to undocumented persons. |  |  | -Ministry of Justice -Supreme Court of Cassation |  | Continuously | Budget of the Republic of Serbia. Activity requiring insignificant costs | Proceedings related to the provision of civil documentation to undocumented persons effectively implemented. |  |  | Аctivity is being successfully implemented. Ministry of Justice - Courts in the Republic of Serbia act on this issue based on the provisions of the Law on Non Litigious Procedure and the conclusion of the Civil Department of the Supreme Court of Cassation. |  |  |
| 3.7.1.4. | Improvement of the living conditions of internally displaced persons while in displacement by: - Aid allocation to improve housing conditions; - Provision of building materials to start construction of real estate; - Aid allocation for the purchase of village house with garden; - Aid allocation for obtaining and construction of prefabricated houses and other residential premises; - Aid allocation for resolving the issue of informal collective centres. |  |  | -Commissioner for Refugees and Migration |  | Continuously, until 2022. | -Budget of the Republic of Serbia- 2018 - up to 300.000.000 RSD 2019 - up to 300.000.000 RSD 2020 - up to 300.000.000 RSD 2021 - up to 300.000.000 RSD IPA 2014 - 175,000 EUR | Housing conditions for internally displaced persons improved during the period of displacement. All official collective centers closed by the end of 2019. In accordance with the 2017 survey of the situation and needs of internally displaced persons, made by the Commissariat together with the UNHCR, it is estimated that over 17,000 more families are in need. |  |  | Аctivity is being successfully implemented. Within the reporting period I quarter 2022, the Commissariat for Refugees and Migration has announced 2 public calls for local self-governments in the Republic of Serbia for granting funds to implement projects aimed to create and improve the housing conditions of IDPs. Public calls from 2022 were completed and beneficiary selection and supporting activities are ongoing. In II quarter 2022, based on public calls for local self-government units from the previous reporting period, a total of 71 packages of building materials and 62 village houses were allocated for IDPs. |  |  |
| 3.7.1.5. | Providing complementary measures aimed at sustainable integration of refugees through programs for economic empowerment through income generating activities |  |  | -Commissioner for Refugees and Migration |  | Continuously, until 2022. | Budget of the Republic of Serbia– Financial resources from the RS budget - 2018 - 420,168.00€ 2019 - 420,168.00€, 2020 - 420,168.00€ 2021 - 420,168.00 € 2022 - 420,168.00€ | Sustainable integration of refugees facilitated. |  |  | Аctivity is being successfully implemented. During the reporting period there were no public calls for the allocation of funds intended for the economic empowerment of refugees. Note: The plan is to Commissariat announce public calls for spending funds intended for economic empowerment with the aim of sustainable integration of refugees. |  |  |
| 3.7.1.6. | Establishment of a mechanism for regular monitoring of the exercise of the rights of Roma internally displaced persons in cooperation with the health mediators, educational assistants, to assess their equal exercise of rights and potential improvements. |  |  | -Coordination body for the social inclusion of Roma |  | Continuously | Budget of the Republic of Serbia- The costs will be specified within the Special AP for the Strategy for Improving the Position of Roma in the Republic of Serbia for the period 2015-2025 | Mechanism for reporting on the exercise of the rights of refugees and internally displaced persons established. |  |  | Activity is being successfully implemented. The aforementioned activity is provided for by the new Strategy and the related Action Plan, the preparation of which is in the final phase, and will be the subject of consideration at the meeting of the Expert Group of the Coordination Body. On the ground, the assessment of the situation and the strengthening of the capacity of local self-government units are continuing in order to respond as best as possible to the demands of members of the Roma population. |  |  |
| 3.7.1.7. | Conduct an information campaign to raise awareness of refugees and internally displaced persons to ensure their social integration and awareness on the mechanisms available for the exercise of rights. |  |  | -Commissioner for Refugees and Migration -CSOs |  | Continuously, until 2022. | Budget of the Republic of Serbia- Financial resources from the RS budget - up to 42,016.00€ per year until 2022 | Information campaign to raise awareness of refugees and internally displaced persons to ensure their social integration and awareness on the mechanisms available for the exercise of rights conducted. |  |  | Аctivity is being successfully implemented. In I quarter 2022, Commissariat for Refugees and Migration has announced a public call for financing the program of civil society organizations of importance for the population of refugees, internally displaced persons. The procedure is ongoing. In II quarter 2022, in accordance with the public call from February for financing the program of civil society organizations of importance for the population of refugees, internally displaced persons, RSD 2,89 million was distributed to 16 civil society organizations that will implemented programs important for the refugee population and IDPs. Also, with the public call from April for financing the program of civil society organizations of importance for the population of refugees and internally displaced persons, RSD 600.000 was distributed to 2 civil society organizations that will implemented programs important for the refugee population. |  |  |
| 3.8. MEASURES AGAINST RACISM AND XENOPHOBIA |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.8.1. Serbia amends its Criminal Code so as to fully align it with the acquis and ensures also in practice an effective criminal law approach towards certain forms and expressions of racism and xenophobia. Serbia undertakes measures aimed at increasing tolerance among citizens, including through training and awareness raising on countering hate crime and ensuring effective investigation of cases. Serbia implements the Strategy and Action Plan against Violence and Misbehaviour at Sports Events (2013-2018). |  |  |  |  |  | Adequate prosecution of hate crime ensured. Increased tolerance among citizens. The mechanism for combating violence and misbehavior at sport events established and operational. |  | 1. European Commission Annual Progress Report on Serbia stating progress in prosecuting hate crime; 2. Report of the European Committee for Racism and Tolerance (ECRI) stating that Serbia has made progress in prosecuting hate crime and hate speech; 3. Concluding remarks of the UN Committee on the Elimination of Racial Discrimination (CERD), ascertaining the progress of Serbia; 4. Number of court decisions where Article 54a CC was implemented. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.8.1.1. | Conduct joint training of the judges, prosecutors and deputy prosecutors and police officers, to advance their knowledge and skills for efficient suppression of hate crime. |  |  | -Judicial Academy |  | Continuously, in line with annual program of the Judicial Academy | Budget of the Republic of Serbia – Budgeted in activity 1.3.1.1. | Joint training conducted. Judges, prosecutors and deputy prosecutors and police officers, advanced their knowledge and skills for efficient suppression of hate crime. |  |  | Аctivity is being successfully implemented. In I quarter 2022, Meetings were held between the representatives of the Judicial Academy and project partners, at which the activities for the next period were defined. During the second quarter, three trainings are planned for the contact points in prosecutor’s offices in the Republic of Serbia for hate crime for all four appellate territories. In order to further support the contact points, after the trainings, it is planned to organize periodic meetings in order to resolve controversial issues and problems in practical work. In the next period, it is planned to organize a study visit to the prosecutor’s office in Barcelona for the contact points for hate crime. In II quarter 2022, a meeting of representatives of the Judicial Academy and project partner organizations and future lecturers was held in order to agree on all organizational and methodological aspects of future trainings. The first training for contact points from area of the appellation of Novi Sad is planned for mid-July in Vršac. In June, a coordination meeting of the representatives of competent state authorities and civil society organizations with the aim of preventing hate crimes in the Republic of Serbia was held. The representatives of the Judicial Academy briefly presented the curriculum of future trainings and the implementation plan. It was concluded that the trainings are of high quality and necessary, as well as that the further continuous development of the holders of judicial office is needed. With the aim of more effective prevention of hate crimes, as well as better quality of work of all institutions, it is proposed to hold thematic meetings. |  |  |
| 3.8.1.2. | Raise awareness on elimination of hate crime through: Organization of expert meetings with the aim of establishing a mechanism for combating hate crime in the Republic of Serbia. Cooperation with international and regional organizations in the field of combating hate speech and hate crimes. |  |  | -Office for Human and Minority Rights |  | Continuously, commencing from II quarter of 2019. | Donor funds | Regular organization of professional meetings with the aim of establishing a mechanism for combating hate crime. Active cooperation with international and regional organizations in the field of combating hate speech and hate crimes. |  |  | Аctivity is being successfully implemented. On 16 and 17 June 2022, the Ministry for Human and Minority Rights and Social dialogue has organized the 17th coordination meeting of representatives of relevant state institutions and civil society organizations (CSO), with the assistance of the OSCE Mission to Serbia, in order to contribute to prevention of hate crime in the Republic of Serbia. Concretely, the meeting was planned to provide the continued cooperation, exchange of experiences and also explore the possibilities of reaching closer cooperation between relevant state institutions and SCO with the aim to form the mechanism for combating hate crime in the Republic of Serbia. The attendees were representatives of the Supreme Cassation Court, Commissioner for equality, Judicial Academy, while the SCO were represented by Yucom-Committee of lawyers for Human Rights, The Key organization of the Youth of Servia, To be known, Duga Association, Monitor, Yurom and Association of Roma of Prokuplje municipality. |  |  |
| 3.8.1.3. | Improving the coordination of activities of public administration bodies and relevant national sports associations to prevent violence at sports events through the activities of the National Council for the Prevention of Negative Phenomena in Sports |  |  | - National Council for the Prevention of Negative Phenomena in Sports -Ministry of Interior |  | Continuously, commencing from I quarter of 2018. | Budget of the Republic of Serbia Regular activity | Regular meetings of the National Council for the Prevention of Negative Phenomena in Sports are held. Reports on undertaken measures and activities developed and publicly available. |  |  | Аctivity is not implemented. The instruction on the manner of acting during sports events was issued on January 28, 2021. |  |  |
| 3.9. PERSONAL DATA PROTECTION |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTERIM BENCHMARK |  |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |  |  |  |  |
| 3.9.1. Serbia adopts and implements a new Law on Personal Data Protection in line with the EU acquis, monitors its implementation and takes remedial action where needed. Serbia also provides training and strengthens the independence, resources and administrative capacity of the Commissioner for Information of Public Importance and Personal Data Protection. |  |  |  |  |  | Legislative alignment with the Acquis in the area of protection of personal data ensured. Commissioner for Information of Public Importance and Personal Data Protection has sufficient financial and human resources to work. |  | 1. European Commission Annual Progress Report on Serbia stating progress in relating to personal data protection; 2. Annual report of the Commissioner for Information of Public Importance and Personal Data Protection assessing the level of compliance with the Personal data protection law. |  |  |  |  |  |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/DEADLINE | FINANCIAL RESOURCES | RESULT |  |  | IMPLEMENTATION STATUS |  |  |
| 3.9.1.1. | Training for the implementation of the new Personal Data Protection Law. |  |  | -Ministry of Justice -National Academy for Public Administration -Commissioner for Information of Public Importance and Personal Data Protection -Judicial Academy |  | Commencing from III quarter of 2019 | Budget of the Republic of Serbia- 7.200 € in 2020. - 2.400 € in 2021. - 2.400 € in 2022. - 2.400 € | Training on the implementation of the new Law on Personal Data Protection implemented. Number of participants trained. |  |  | Аctivity is being successfully implemented. In I quarter 2022, Commissioner organized four trainings: - Four trainings were held in February (3/10/17 / 24.2.2022) for representatives of students of the Faculty of Security, Belgrade, organized by the Commissioner for 36 persons– - Two trainings were held in March (3 / 10.3.2022) for representatives of students of the Faculty of Security, Belgrade, organized by the Commissioner for seven persons. In II quarter 2022, the Commissioner for Information of Public Importance and Personal Data Protection organized: - On April 14, 2022, а training for 13 student representatives of the Faculty of Law of the University in Belgrade. - On April 15, 2022, а training for 13 student representatives of the Faculty of Law of the University in Belgrade. - On May 18, 2022, a training held in Tara for 100 employees of the Pension and Disability Insurance Fund of the Republic of Serbia . - On June 17 and 22, 2022, two thematic trainings held for employees in public prosecutor's offices (First, Second, Third Basic Public Prosecutor's Office in Belgrade and Higher Public Prosecutor's Office in Belgrade) on the topic of the application of the "Law on Personal Data Protection, with the total of 42 participants. - On May 26 and 27, 2022, two trainings held in Vrnjačka banja for 100 employees of the Association of Serbian Banks. Two trainings were conducted by the Judicial Academy on the topic of implementation of the Law on Personal Data Protection for a total of 60 participants (judges and prosecutors. |  |  |
| 3.9.1.2. | Analysis of sectoral regulations and development of a plan for their alignment with the new Law on Personal Data Protection |  |  | -Ministry of Justice -Commissioner for Information of Public Importance and Personal Data Protection |  | II – IV quarter of 2020. | Budget of the Republic of Serbia – 17.285 € | Analysis of sectoral regulations and a plan for their alignment with the new Law on Personal Data Protection developed. |  |  | Аctivity is partially implemented. In I quarter 2022, the Working Group for the preparation of the Proposal of the Strategy for Personal Data Protection with the Action Plan, which was established by the Government, continued work on the development of the Strategy and Action Plan. The working group consists of numerous representatives of relevant institutions and business associations. In May 2022, the third session of the Working Group for the development of the Personal Data Protection Strategy for the period 2022-2030 was held. At the session, it was concluded that the Personal Data Protection Act must be amended and supplemented, and that this should be the first step in the development of the Strategy. In I quarter 2022, in the course of his regular activities, the Commissioner gave his opinion on 24 draft laws, from the point of view of compliance with the provisions of the law within his competence. In the course of his regular activities, the Commissioner gave his opinion on seven draft laws, from the point of view of compliance with the provisions of the law within his competence. In II quarter 2022, the Commissioner, within his regular activities, gave an opinion on by-laws and other acts, from the compliance with the provisions of the law under his jurisdiction point of view, concerning: - Ministry for Human and Minority Rights and Social Dialogue - Opinion on the Draft of the Fourth and Fifth Periodic Report of the Republic of Serbia on the Implementation of the United Nations Convention on the Rights of the Child; - Ministry of Human and Minority Rights and Social Dialogue - Opinion on the Proposal report on the achievement of gender equality in the Republic of Serbia for 2021. |  |  |
| 3.9.1.3. | Strengthen the human resource capacity of the Commissioner for Information of Public Importance and Personal Data Protection based on current Rulebook on internal organization and jobs systematization, taking into account limitations arising from fiscal consolidation. |  |  | -Commissioner for Information of Public Importance and Personal Data Protection -National Assembly – Board for Administrative matters |  | Continuously, commencing from I quarter of 2016. until the fulfilment of current vacancies | Budget of the Republic of Serbia- 750.000 € in 2020 – 377.120 € in 2021 – 186.440 € in 2022 – 186.440 € | Number of staff employed pursuant to current Rulebook on internal organization and jobs systematization, taking into account limitations arising from fiscal consolidation. Baseline: 90 employed staff. Target: 129 employed staff. |  |  | Аctivity is being successfully implemented. Current number of permanently employed staff is 107. |  |  |
| 3.9.1.4. | Conduct analysis on potential needs to strengthen human resource capacity due to additional competencies of the Commissioner for Information of Public Importance and Personal Data Protection, after the adoption of the new Law on personal data protection especially in terms of: -organizational structure, -number of employees, -level of training so that they coincide with the competencies prescribed by the new Law on personal data protection. |  |  | -Ministry of Justice -Commissioner for Information of Public Importance and Personal Data Protection |  | Analysis: I quarter of 2021. Acting in line with the analysis: III quarter of 2021. | For analysis: Budget of the Republic of Serbia – 17.285 € For acting in line with the analysis: budget depends on the results of the analysis | Conducted analysis. Needs for additional employment and training at the Commissioner for Information of Public Importance and Personal Data Protection identified. Recommendations from the analysis implemented. |  |  | Аctivity is partially implemented. No new information in I and II quarter of 2022. The Commissioner prepared the Analysis of needs to strengthen human resource capacity in September 2021. |  |  |
| 3.9.1.5. | Conducting promotional activities for the general public on rights and obligations regarding personal data protection as prescribed in the new Law on Personal Data Protection. |  |  | -Ministry of Justice -Commissioner for Information of Public Importance and Personal Data Protection Partners: CSOs |  | From III quarter of 2019 | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Promotional activities for the general public on rights and obligations regarding personal data protection as prescribed in the new Law on Personal Data Protection conducted. |  |  | Аctivity is being successfully implemented. In I quarter 2022, the Commissioner published on his website Publication no. 7 - Data protection - Attitudes and opinions of the Commissioner. In II quarter 2022, the Commissioner for Information of Public Importance and Personal Data Protection, with the support of the OSCE Mission in Serbia, launched a media campaign called "Keep it personal." In order to bring the right to personal data protection closer to the citizens and to point out the risks of violating this right, five TV spots were made, which are being broadcast on national and local stations from May 16, 2022. These videos are designed to indicate easily and simply: what is personal data, who can process it, what are the dangers of citizens' reckless personal data behavior, as well as the role of the Commissioner in personal data protection. The videos were also published on the Commissioner's website. |  |  |
| 3.9.1.6. | Monitoring of the implementation of the new Law on Personal Data Protection. |  |  | -Commissioner for Information of Public Importance and Personal Data Protection |  | From IV quarter of 2019 | Budget of the Republic of Serbia- 31.914 € in 2020. - 10.638 € in 2021. - 10.638 € in 2022. - 10.638 € | Number of Commissioner's cases in the field of personal data protection as stated in Annual report of the Commissioner. |  |  | Аctivity is being successfully implemented. Commissioner for Information of Public Importance and Personal Data Protection regularly performs monitoring of the implementation of the new Law on Personal Data Protection, as a part of its core jurisdiction. Based on data submitted for the purpose of this report, in the period January /June 2022 there were 1484 cases received and 1457 resolved cases. |  |  |
| 3.9.1.7. | Develop and adopt relevant laws and bylaws on video surveillance for the purpose of alignment with the Law on Personal Data Protection. |  |  | -competent ministries, -Commissioner for Information of Public Importance and Personal Data Protection -Government of the Republic of Serbia -National Assembly |  | II quarter of 2021 | Budget of the Republic of Serbia - 17.285 € | Law(s) and bylaws on video surveillance adopted for the purpose of alignment with the Law on Personal Data Protection. |  |  | Activity is partially implemented. The process of considering the adoption of several laws and by-laws on the use of video surveillance with facial recognition software is underway, with the aim of harmonizing it with the Law on the Protection of Foreign Data. Several working groups related to the work of the Ministry of Interior and the protection of personal data were formed, which collect data on good practice and comparative solutions of other EU countries. |  |  |

ANEX: COMPARATIVE PRESENTATION OF ACTIVITIES

| ACTIVITY IN AP23 – APRIL 2016 | ACTIVITY IN REVISED AP 23 – JUNE 2020 | NEW ACTIVITY IN AP23 – JUNE 2020 |
| --- | --- | --- |
|  | INDEPENDENCE |  |
| 1.1.1.1. 1.1.1.2. 1.1.1.3. 1.1.1.4. 1.1.1.5. 1.1.1.6. | Activities from 1.1.1.1. to 1.1.1.6. are covered by one new activity | 1.1.1.1. |
| 1.1.1.7. (split into two activities) | 1.1.1.2. 1.1.1.3. |  |
|  |  | 1.1.1.4. |
| 1.1.1.8. | 1.1.1.5. |  |
| 1.1.2.1. deleted activity |  |  |
| 1.1.3.1. | 1.1.2.1. |  |
| 1.1.3.2. deleted activity |  |  |
| 1.1.3.3. | 1.1.2.2. |  |
|  |  | 1.1.2.3. |
| 1.1.3.4. (split into two activities) | 1.1.2.7. 1.1.2.8. |  |
| 1.1.3.5. | 1.1.2.4. |  |
|  |  | 1.1.2.5.(as a new activity, a part of the old one 1.1.3.3. was taken) |
|  |  | 1.1.2.6. (as a new activity, a part of the old one 1.1.3.5. was taken) |
| 1.1.3.6. (split into two activities) | 1.1.2.9. 1.1.2.10. |  |
| 1.1.4.1. Deleted activity |  | 1.1.3.1. (it also relates to old activity 1.1.4.4.) |
| 1.1.4.2. deleted activity |  | 1.1.3.2. (it also relates to old activity 1.1.4.7.) |
| 1.1.4.3. deleted activity |  |  |
| 1.1.4.4. deleted activity |  |  |
| 1.1.4.5. | 1.1.3.3. |  |
| 1.1.4.6. deleted activity |  |  |
| 1.1.4.7. deleted activity |  |  |
| 1.1.4.8. | 1.1.3.4. |  |
| 1.1.5.1. | 1.1.4.1.(slightly amended) |  |
|  |  | 1.1.4.2. |
|  |  | 1.1.4.3. (as a new activity, a part of the old one 1.1.5.1. was taken) |
| 1.1.5.2. deleted activity |  | 1.1.4.4. (as a new activity, a part of the old one 1.1.5.2. was taken) |
| 1.1.6.1. deleted activity |  |  |
| 1.1.6.2. deleted activity |  |  |
| 1.1.6.3. deleted activity |  |  |
|  |  | 1.1.5.1. |
|  |  | 1.1.5.2. |
| 1.1.6.4. | 1.1.5.3. |  |
| 1.1.6.5. | 1.1.5.4. |  |
| 1.1.6.6. | 1.1.5.5. |  |
| 1.1.6.7. deleted activity |  |  |
| 1.1.7.1. | 1.1.6.1. |  |
| 1.1.7.2. | 1.1.6.2. |  |
| 1.1.7.3. | 1.1.6.3. |  |
| 1.1.7.4. | 1.1.6.4. |  |
| 1.1.8.1. deleted activity |  |  |
| IMPARTIALITY AND ACCOUNTABILITY |  |  |
| 1.2.1.1. | 1.3.8.1. 1.3.8.4. 1.3.8.5. 1.3.8.10. |  |
| 1.2.1.2. | 1.3.8.2. 1.3.8.7. |  |
| 1.2.1.3. deleted activity |  |  |
|  |  | 1.2.1.4. |
| 1.2.1.4. | 1.3.8.6. |  |
| 1.2.1.5. deleted activity |  |  |
| 1.2.1.6. | 1.3.8.9. |  |
| 1.2.1.7. | 1.3.8.9. |  |
| 1.2.1.8. | 1.3.6.5. |  |
| 1.2.1.9. | 1.3.8.12. |  |
| 1.2.1.10. | 1.3.8.1. |  |
| 1.2.1.11. | 1.2.1.1. 1.2.1.3. |  |
| 1.2.1.12. | 1.2.1.1. |  |
| 1.2.1.13. deleted activity |  |  |
| 1.2.1.14. | 1.2.1.2. |  |
| 1.2.1.15. | 1.2.1.5. |  |
| 1.2.1.16. | 1.2.1.6. |  |
| 1.2.1.17. | 1.2.1.7. |  |
| 1.2.1.18. | 1.2.1.8. |  |
| 1.2.1.19. | 1.2.1.10. |  |
| 1.2.1.20. | 1.2.1.9. 1.2.1.10. 1.2.1.11. |  |
| 1.2.1.21. | 1.2.1.12. |  |
|  |  | 1.2.1.13. |
|  |  | 1.2.1.14. |
| 1.2.2.1. deleted activity |  |  |
| 1.2.2.2. | 1.2.2.1 |  |
| 1.2.2.3. deleted activity |  |  |
| 1.2.2.4. deleted activity |  |  |
| 1.2.2.5. | 1.2.2.2. (slightly amended) |  |
| 1.2.2.6. | 1.2.2.3. |  |
| 1.2.2.7. | 1.2.2.4. |  |
| 1.2.2.8. | 1.2.2.5. |  |
| 1.2.2.9. | 1.2.2.6. (slightly amended) |  |
|  |  | 1.2.2.7. |
| 1.2.2.10. | 1.2.2.8. |  |
| 1.2.2.11. | 1.2.2.9. (уз допуну за Државно веће тужилаца) |  |
| 1.2.2.12. | 1.2.2.10. |  |
| 1.2.2.13. | 1.2.2.11. |  |
| 1.2.2.14. | 1.2.2.12. |  |
| 1.2.2.15. | 1.2.2.13. |  |
|  |  | 1.2.2.14. |
|  |  | 1.2.2.15. |
| 1.2.2.16. deleted activity |  |  |
| 1.2.2.17. | 1.2.2.16. |  |
| 1.2.2.18. | 1.2.2.17. |  |
| 1.2.2.19. | 1.2.2.18. |  |
| 1.2.2.20. | 1.2.2.19. |  |
| PROFESSIONALISM / EFFICIENCY |  |  |
| 1.3.1.1. deleted activity |  |  |
| 1.3.1.2. deleted activity |  |  |
| 1.3.1.3. deleted activity |  |  |
| 1.3.1.4. deleted activity |  |  |
| 1.3.1.5. | 1.3.1.4. |  |
| 1.3.1.6. | 1.3.1.1. 1.3.1.2. |  |
| 1.3.1.7. | 1.3.1.3. |  |
| 1.3.1.8. | 1.3.1.5. |  |
| 1.3.1.9. | 1.3.1.6. |  |
|  |  | 1.3.1.7. |
|  |  | 1.3.1.8. |
| 1.3.1.10. deleted activity |  |  |
| 1.3.1.11. | 1.3.1.9. |  |
| 1.3.2.1. | 1.3.2.1. |  |
| 1.3.2.2. | 1.3.2.2. |  |
| 1.3.2.3. | 1.3.2.3. (with appropriate interventions) |  |
| 1.3.2.4. | 1.3.2.4. (with appropriate interventions) |  |
| 1.3.3.1. | 1.3.3.1. (with appropriate interventions) |  |
|  |  | 1.3.3.2. |
|  |  | 1.3.3.3. |
| 1.3.3.2. | 1.3.3.4. |  |
| 1.3.3.3. deleted activity |  |  |
| 1.3.4.1. | 1.3.4.1. (with appropriate interventions) |  |
| 1.3.4.2. | 1.3.4.2. 1.3.4.3. |  |
| 1.3.4.3. | 1.3.4.4. |  |
|  |  | 1.3.4.5. |
| 1.3.5.1. | 1.3.5.1. |  |
| 1.3.5.2. | 1.3.5.2. |  |
| 1.3.6.1. | 1.3.6.1. (with appropriate interventions) |  |
| 1.3.6.2. | 1.3.6.2. (with appropriate interventions) |  |
| 1.3.6.3. deleted activity |  |  |
|  |  | 1.3.6.3. |
| 1.3.6.4. deleted activity |  |  |
| 1.3.6.5. deleted activity |  |  |
|  |  | 1.3.6.4. |
| 1.3.6.6. | 1.3.8.1. |  |
| 1.3.6.7. | 1.3.8.7. |  |
| 1.3.6.8. deleted activity |  |  |
| 1.3.6.9. deleted activity |  |  |
| 1.3.6.10. | 1.3.8.6. |  |
| 1.3.6.11. | 1.3.8.6. 1.3.8.9. |  |
| 1.3.6.12. |  |  |
| 1.3.6.13. | 1.3.6.5. |  |
| 1.3.6.14. | 1.3.6.6. |  |
|  |  | 1.3.6.7. |
| 1.3.6.15. | 1.3.8.7. |  |
| 1.3.6.16. deleted activity |  |  |
| 1.3.6.17. deleted activity |  |  |
| 1.3.6.18. deleted activity |  |  |
| 1.3.6.19. deleted activity |  |  |
| 1.3.6.20. | 1.3.6.8. |  |
| 1.3.6.21. | 1.3.6.9. |  |
| 1.3.6.22. | 1.3.6.10. |  |
| 1.3.6.23. deleted activity |  |  |
| 1.3.6.24. | 1.3.6.11. |  |
| 1.3.6.25. | 1.3.6.12. |  |
|  |  | 1.3.6.13. |
|  |  | 1.3.6.14. |
|  |  | 1.3.6.15. |
| 1.3.6.26. | 1.3.6.16. |  |
| 1.3.6.27. | 1.3.6.17. |  |
| 1.3.6.28. | 1.3.6.18. |  |
| 1.3.6.29. | 1.3.6.19. |  |
| 1.3.7.1. deleted activity |  |  |
|  |  | 1.3.7.1. |
| 1.3.7.2. | 1.3.7.2. |  |
| 1.3.7.3. deleted activity |  |  |
| 1.3.7.4. deleted activity |  |  |
| 1.3.7.5. deleted activity |  |  |
|  |  | 1.3.7.3. |
|  |  | 1.3.7.4. |
|  |  | 1.3.7.5. |
|  | ***only new activities should be regarded |  |
| 1.3.8. THIS WHOLE PART SHOULD NOT BE REGARDED. 1.3.8.1. 1.3.8.2. 1.3.8.3. 1.3.8.4. 1.3.8.5. 1.3.8.6. 1.3.8.7. 1.3.8.8. 1.3.8.9. 1.3.8.10. 1.3.8.11. | 1.3.8.1. (old act. 1.2.1.1.) |  |
|  | 1.3.8.2. (old act.1.2.1.2.) |  |
|  |  | 1.3.8.3. |
|  | 1.3.8.4. (old act.1.2.1.1.) |  |
|  | 1.3.8.5. (old act.1.2.1.1.) |  |
|  | 1.3.8.6. (old act.1.2.1.4. and 1.3.6.9.) |  |
|  | 1.3.8.7. (old act.1.2.1.2.) |  |
|  |  | 1.3.8.8. |
|  | 1.3.8.9. (old act.1.2.1.6., 1.2.1.7., 1.2.1.9., 1.3.6.11.) |  |
|  | 1.3.8.10. (old act.1.2.1.1.) |  |
|  |  | 1.3.8.11. |
|  | 1.3.8.12. (old act.1.2.1.9.) |  |
|  |  | 1.3.8.13. |
|  |  | 1.3.8.14. |
|  |  | 1.3.8.15. |
|  |  | 1.3.8.16. |
|  |  | 1.3.8.17. |
|  |  | 1.3.8.18. |
|  |  | 1.3.8.19. |
|  |  | 1.3.8.20. |
| 1.3.9.1. | 1.3.9.1. |  |
| 1.3.9.2. deleted activity |  |  |
| 1.3.9.3. | 1.3.9.2. |  |
| 1.3.9.4. | 1.3.9.3. (with appropriate interventions) |  |
| 1.3.9.5. | 1.3.9.4. |  |
|  |  | 1.3.9.5. |
|  |  | 1.3.9.6. |
| 1.3.10.1. deleted activity |  |  |
| 1.3.10.2. deleted activity |  |  |
| 1.3.10.3. deleted activity |  |  |
| 1.3.11.1. deleted activity |  |  |
| 1.3.11.2. deleted activity |  |  |
| 1.3.11.3. deleted activity |  | 1.3.10.1. |
|  |  | 1.3.10.2. |
| WAR CRIMES |  |  |
| 1.4.1.1. deleted activity |  |  |
| 1.4.1.2. deleted activity |  |  |
| 1.4.1.3. deleted activity |  |  |
| 1.4.1.4. deleted activity |  |  |
|  |  | 1.4.1.1. |
|  |  | 1.4.1.2. |
|  |  | 1.4.1.3. |
|  |  | 1.4.1.4. |
| 1.4.1.5. | 1.4.1.5. |  |
|  |  | 1.4.1.6. |
| 1.4.1.6. | 1.4.1.7. |  |
| 1.4.1.7. deleted activity |  |  |
| 1.4.1.8. deleted activity |  |  |
| 1.4.1.9. | 1.4.1.8. |  |
| 1.4.1.10. | 1.4.1.9. |  |
| 1.4.2.1. deleted activity |  |  |
|  |  | 1.4.2.1. |
| 1.4.2.2. deleted activity |  |  |
| 1.4.2.3. | 1.4.2.2. |  |
| 1.4.3.1. deleted activity |  | 1.4.3.1. |
| 1.4.3.2. deleted activity |  | 1.4.3.2. |
| 1.4.3.3. deleted activity |  | 1.4.3.3. |
| 1.4.3.4. deleted activity |  |  |
| 1.4.3.5. deleted activity |  |  |
| 1.4.4.1. deleted activity |  |  |
| 1.4.4.2. deleted activity |  |  |
| 1.4.4.3. | 1.4.4.1. |  |
| 1.4.4.4. | 1.4.4.3. |  |
| 1.4.4.5. | 1.4.4.2. |  |
| 1.4.4.6. | 1.4.4.4. |  |
| 1.4.4.7. | 1.4.4.5. |  |
|  |  | 1.4.4.6. |
|  |  | 1.4.4.7. |
|  |  | 1.4.4.8. |
|  |  | 1.4.4.9. |
| 1.4.5.1. | 1.4.5.1. |  |
| 1.4.5.2. | 1.4.5.2. |  |

Institutions and bodies represented in the Coordination Body shall be as follows: Ministry of Justice, Negotiation Group for Chapter 23, Ministry of European Integration, Ministry of Interior, Ministry of Public Administration and Local Self Government, Ministry of Finance, Office for the Human and Minority Rights, Supreme Court of Cassation, Republic Public Prosecutor’s Office, High Judicial Council, State Prosecutorial Council, Judicial Academy, War Crime Prosecutor’s Office, Anticorruption Agency, Ministry of Health, Ministry of Science, Education and Technology,  Ministry of Labour, Employment, Veteran and Social Affairs, Office for Cooperation with Civil Society, Chamber of Public Enforcement Officers, Chamber of Notaries, Commissioner of Public Importance and Personal Data Protection, Ombudsman, Commissioner for Gender Equality.

Reporters without borders: World Press Freedom Index https://rsf.org/en/ranking#

Freedom Houise, Freedom in the world: https://freedomhouse.org/report/freedom-world/2019/serbia

Reporters without borders: World Press Freedom Index https://rsf.org/en/ranking#

Freedom Houise, Freedom in the world: https://freedomhouse.org/report/freedom-world/2019/serbia

World Economic Forum, Global Gender Gap Report 2020, http://www3.weforum.org/docs/WEF_GGGR_2020.pdf (Regarding Index score higher is better)

Republic institute for social care: Report on the work of social protection institutions for adults and the elderly with mental, intellectual, Physical or sensory disorders for 2018 http://www.zavodsz.gov.rs/media/1877/izvestaj-o-radu-ustanova-za-odrasle-i-starije-sa-mentalnim-i-intelektualnim-teskocama-2018.pdf page 23

Situational Analysis of Children and Adolescents in Serbia 2019, UNICEF

Republic Institute for Social care, Work Report of the Centers for Social Work for 2018. http://www.zavodsz.gov.rs/sr/biblioteka/izve%C5%A1taji-iz-sistema/izve%C5%A1taji-iz-systema-2018/  published  in December 2019. p. 11

Republic Institute for Social care, Children in social care system 2018: http://www.zavodsz.gov.rs/media/1874/deca-u-sistemu-socijalne-zastite-2018.pdf published in August 2019, p 19.

Republic Institute for Social care, Children in social care system 2018: http://www.zavodsz.gov.rs/media/1874/deca-u-sistemu-socijalne-zastite-2018.pdfhttp://www.zavodsz.gov.rs/media/1874/deca-u-sistemu-socijalne-zastite-2018.pdf published in August 2019, p 18.

Republic Statistical Institute, BULLETIN, Juvenile offenders in the Republic of Serbia, 2017. -https://publikacije.stat.gov.rs/G2018/Pdf/G20185641.pdf

Source: Republic statistical institute, https://publikacije.stat.gov.rs/G2018/Pdf/G20185641.pdf

Zavod za statistiku Republike Srbije, ‘РЕПУБЛИКА’ СРБИЈА, <http://devinfo.stat.gov.rs/SerbiaProfileLauncher/files/profiles/sr/1/DI_Profil_Republika%20Srbija_EURSRB.pdf#page=6>, page visited 20 December 2019

Situational Analysis of Children and Adolescents in Serbia 2019, UNICEF

Information booklet of Commissioner for Information of Public Importance and Personal Data Protection https://www.poverenik.rs/en/information-booklet.html