### ACTION PLAN

### FOR IMPLEMENTATION OF THE

### NATIONAL STRATEGY ON THE RIGHTS OF VICTIMS AND WITNESSES OF CRIME IN THE REPUBLIC OF SERBIA

### FOR THE PERIOD 2020-2025

| Overall objective of the Strategy: Enhancing the status of victims and witnesses of crime in the criminal justice system of the Republic of Serbia in line with EU standards set out in the Directive 2019/29/EU (hereinafter: Directive). Impact indicator for the overall objective The rights of victims and witnesses of crime in the Republic of Serbia are enshrined in the legislative and institutional framework, as well as in good practices, in keeping with the standards guaranteed under the Directive. Baseline value in 2020: partially aligned; Target value in 2025: fully aligned; Verification source: EU Country Report. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Specific objective 1: Setting up a National Network of Victim and Witness Support Services in the Republic of Serbia (hereinafter: National Network). Setting up a sustainable National Network of Victim and Witness Support Services in the Republic of Serbia, while preserving and continually improving the achieved standard of quality and availability of support services. Outcome indicator for specific objective 1: The National Network of Victim and Witness Support Services in the Republic of Serbia has been made fully operational and has been providing assistance and support services in line with the standards set out in the Directive. Baseline value in 2020: There is no National Network in place; Target value in 2025: The National Network comprises 25 support services established at courts, as well as victim and witness support and assistance services at the High Court of Belgrade and the War Crimes Prosecutor’s Service, and services set up as part of civil society organisations; Verification source: Reports produced by the Coordination Body. |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 1.1 |  | Amendments to the legislative framework that governs the organization of the judiciary |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Regulatory |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team |  |  |  |
|  |  | Estimates of financial resources | Republic of Serbia’s Budget |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular budget funds–Chapter 23 – Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to Victims and Witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | Law on Organisation of Courts; Law on Ministries; Court Rules of Procedure; Rules on Administration in Public Prosecutor’s Offices; Rules on Internal Organisation and Job Classification adopted by High Courts; Rules on Internal Organisation and Job Classification at the War Crimes Prosecutor’s Office; Rules on Operation of Victim and Witness Support Services at High Courts in the Republic of Serbia; Rulebook on Internal Organisation and Job Classification at the Ministry of Justice; Rules on Treatment of Victims and Witnesses of Crime; Act on Internal Organisation and Job Classification of the MoI; Rules on Treatment of Victims and Witnesses of Crime; |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2020 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | The legislative framework that governs the organisation of the judiciary is able to identify and regulate in an adequate manner the process of setting up victim and witness support services and their operation. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  |  | Verification source: |  |
|  |  |  | 0% |  |  | 100% |  |  |  |  | Reports of the Coordination Body Annual Report of the Ministry of Justice Annual Report of the Ministry of Interior |  |
| Activity |  |  |  | Time frame | Implementing authority |  | Implementation indicator |  |  | Verification source |  | Budget |
| 1.1.1 | Forming and work of an expert group to produce models for necessary amendments to the set of judicial laws and related secondary legislation with respect to provisions concerning the establishment and operation of the National Network of Victim and Witness Support Services; submission of those model amendments to relevant working groups of the Ministry of Justice tasked with drafting amendments to the set of judicial laws in accordance with the Draft Amendments to the Constitution. |  |  | Fourth quarter of 2019 – third quarter of 2020 | Ministry of Justice in cooperation with OSCE-IPA 2016 Project Team |  | An expert group responsible for producing models for necessary amendments to the set of judicial laws and related secondary legislation with respect to provisions concerning the establishment and operation of the National Network of Victim and Witness Support Services has submitted draft amendments to relevant working groups of the Ministry of Justice. |  |  |  |  | RS Budget - regular budget funds, Programme Activity 0010 – Administration and management OSCE – EUR 3,000 in 2019 |
| 1.1.2 | Drawing up a Draft Law on Amendments to the Law on Organisation of Courts to provide for engagement of judicial assistants responsible for the provision of support and assistance to victims and witnesses of crime. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Organisation of Courts has been drawn up accordingly. |  |  | Annual Report of the Ministry of Justice |  | RS Budget - regular budget funds, Programme Activity 0010 – Administration and management |
| 1.1.3 | Amending the Court Rules of Procedure to regulate the operation of victim and witness support services and focal points for providing information at courts. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | The Court Rules of Procedure have been amended accordingly. |  |  | Annual Report of the Ministry of Justice |  | Budgeted under Activity 1.1.2 in 2020 (RS Budget –ruglar budget funds) |
| 1.1.4 | Amending the Rules on Administration in Public Prosecutor’s Offices to regulate the operation of victim and witnesses support services and the operation of focal points for provision of information at public prosecutor’s offices. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | The Rules on Administration in Public Prosecutor’s Offices have been amended accordingly. |  |  | Annual Report of the Ministry of Justice |  | Budgeted under Activity 1.1.2 in 2020 (RS Budget –regular budget funds) |
| 1.1.5 | Amending, where necessary, Rulebooks on Internal Organisation and Job Classification at High Courts to provide for the position of judicial assistant responsible for provision of support to victims and witnesses of crime. |  |  | Fourth quarter of 2019 – fourth quarter of 2020 | High Courts |  | Rulebooks on Internal Organisation and Job Classification at High Courts have been amended accordingly. |  |  | Report of the Coordination Body |  | RS Budget - regular budget funds, Programme Activity 0010 – Administration and management |
| 1.1.6 | Amending the Rulebook on Internal Organisation and Job Classification at the War Crimes Prosecutor’s Office to provide for the position of prosecutorial assistant for provision of support to victims and witnesses of crime. |  |  | Fourth quarter of 2020 | War Crimes Prosecutor’s Office |  | The Rulebook on Internal Organisation and Job Classification at the War Crimes Prosecutor’s Office has been amended accordingly. |  |  | Annual Report of the War Crimes Prosecutor’s Office |  | RS Budget– regular budget funds, Programme Activity 0010 – Administration and management |
| 1.1.7 | Adopting Rules on Operation of Victim and Witness Support Services at High Courts in the Republic of Serbia. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Rules on Operation of Victim and Witness Support Services at High Courts in the Republic of Serbia have been adopted accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Justice |  | Budgeted under Activity1.1.2 in 2020 (RS Budget– regular budget funds) |
| 1.1.8 | Preparing amendments and amending the Act on Internal Organisation and Job Classification of the MoI to include in the description of already existing duties of competent organisational units of the police (criminal investigation, traffic and general police) a duty to provide information to victims and injured parties affected by a criminal offence or misdemeanour about their rights and available support and assistance services both orally and in writing. |  |  | Fourth quarter of 2019 – fourth quarter of 2020 | Ministry of Interior |  | The Act on Internal Organisation and Job Classification of the Ministry of Interior has been amended accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Interior |  | RS Budget - regular budget funds, Programme Activity 0010 – Administration and management |
| 1.1.9 | Preliminary analysis of necessary amendments and drawing up a Draft Law on Amendments to the Law on Ministries to provide in Article 9 of said law that the Ministry of Justice shall be competent for establishing and coordinating the activities of victim support services. |  |  | Fourth quarter of 2019 – fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Ministries has been drawn up accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Justice |  | RS Budget - regular budget funds, Programme Activity 0010 – Administration and management |
| 1.1.10 | Preliminary analysis of necessary amendments and amending the Rulebook on Internal Organisation and Job Classification in the Ministry of Justice to introduce the position of the Victim and Witness Support Services Coordinator. |  |  | Third quarter of 2019 – Fourth quarter of 2020 | Ministry of Justice |  | The Rulebook on Internal Organisation and Job Classification in the Ministry of Justice has been amended accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Justice |  | RS Budget–RSD 25,530 2019 Programme Activity 0010 – Administration and management |
| 1.1.11 | Adopting Rules on Quality Standards for Victim and Witness Support Providers and their Accountability. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Rules on Quality Standards for Victim and Witness Support Providers and their Accountability have been adopted accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Justice |  | Budgeted under Activity 1.1.2 in 2020 (RS Budget –RSD 3,705,300 in 2020) |
| 1.1.12 | Adopting Rules on Treatment of Victims and Witnesses of Crime. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Rules on Treatment of Victims and Witnesses of Crime have been adopted accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Justice |  | Budgeted under Activity 1.1.2 in 2020 (regular budget funds) |
| 1.1.13 | Adopting an internal act governing the treatment of victims and witnesses of crime intended for police officers. |  |  | Fourth quarter of 2020 | Ministry of Interior |  | An internal act governing the treatment of victims and witnesses of crime intended for police officers has been adopted accordingly. |  |  | Report of the Coordination Body, Annual Report of the Ministry of Interior |  | RS Budget – regular budget funds, Programme Activity 0010 – Administration and management |
| Measure 1.2 |  | Establishment of support and assistance services for victims and witnesses of crime at High Courts in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Institutional, management and organisational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team High Courts |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management, Chapter 6. Courts, Heading 6.6. High Courts, Programme 1603 – Operation of Courts, Programme Activity 0014, Administrative support to conduct of High Court proceedings |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 1.1. |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Support and assistance services for victim and witness of crime have been established at 15 High Courts in the Republic of Serbia; administrative staff and office equipment have been duly provided. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  |  | Verification source: |  |
|  |  |  | 0 |  |  | Fifteen services have been established at High Courts. Fifteen judicial assistants responsible for providing support have taken up their duties. |  |  |  |  | Reports of the Coordination Body Annual Report of the Ministry of Justice |  |

|  | Activity |  | Time frame | Implementing authority |  | Implementation indicator |  |  |  | Verification source | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.2.1 | Establishment of victim and witness support services at the High Courts of: 1 Belgrade 2 Novi Sad 3 Kragujevac 4 Niš 5 Novi Pazar 6 Vranje |  | Second quarter of 2021 | Ministry of Justice in cooperation with High Courts |  | Victim and witness support services have been established at the High Courts of: 1 Belgrade 2 Novi Sad 3 Kragujevac 4 Niš 5 Novi Pazar 6 Vranje |  |  |  | Reports of the Coordination Body | RS Budget Programme Activity 0014, Administrative support to conduct of High Court proceedings – RSD 18,381,600 in total; of that amount, a sum of RSD 3,676,320 will be allocated in 2021, and a sum of RSD 14,705,280 will be allocated in 2022. |  |
| 1.2.2 | Establishment of victim and witness support services at the High Courts of: 1 Zrenjanin 2 Sombor 3 Požarevac 4 Užice 5 Zaječar |  | First quarter of 2022 | Ministry of Justice in cooperation with High Courts |  | Victim and witness support services have been established at the High Courts of: 1 Zrenjanin 2 Sombor 3 Požarevac 4 Užice 5 Zaječar |  |  |  | Reports of the Coordination Body | RS Budget, Programme Activity 0014, Administrative support to conduct of High Court proceedings, RSD 9,190,800 in total in 2022. |  |
| 1.2.3 | Establishment of victim and witness support services at the High Courts of: 1 Subotica 2 Šabac 3 Čačak 4 Kraljevo |  | Fourth quarter of 2022 | Ministry of Justice in cooperation with High Courts |  | Victim and witness support services have been established at the High Courts of: 1 Subotica 2 Šabac 3 Čačak 4 Kraljevo |  |  |  | Reports of the Coordination Body | RS Budget, Programme Activity 0014, Administrative support to conduct of High Court proceedings, RSD 2,450,880 in total in 2022 |  |
| 1.2.4 | Employing judicial assistants for provision of victim support at newly established support services at High Courts, according to the following schedule: - Six assistants in 2020 - Five assistants in 2021 - Four assistants in 2022 |  | Second quarter of 2021 - Fourth quarter of 2022 | Ministry of Justice in cooperation with High Courts |  | Support services at High Courts will have been adequately staffed by employing 15 judicial assistants to provide support by 2022. |  |  |  | Reports of the Coordination Body | RS Budget – budgeted under Activities 1.2.1, 1.2.2 and 1.2.3 (RS Budget – RSD 1,838,160 in total; of that amount, a sum of RSD 1,225,440 will be alocated in 2021 and RSD 612,720 will be allocated in 2022; RS Budget – RSD 1,021,200 in total; of that amount, a sum of RSD 510,600 will be allocated in 2021 and 2022 each; and RS Budget –RSD 408,480 In 2022) |  |
| 1.2.5 | Adapting special premises at High Courts to ensure unobstructed functioning of newly established support services. |  | Fourth quarter of 2020 - Second quarter of 2022 | Ministry of Justice in cooperation with High Courts, and OSCE/IPA 2016 Project Team |  | Premises necessary for the functioning of newly founded support services have been provided at High Courts. |  |  |  | Reports of the Coordination Body | OSCE: EUR 169,750 in 2020 |  |
| 1.2.6 | Developing and setting up a software package for a database to be used by the victim and witness support services in the Republic of Serbia. |  | Fourth quarter of 2020 - Second quarter of 2022 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | A single database on victims and witnesses who have been provided with support services has been set up. |  |  |  | Reports of the Coordination Body | Activity 1.2.5 (ОSCE: EUR 169,750 in 2020) |  |
| Measure 1.3 |  | Establishment of the National Network |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  | Institutional, management and organisational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  | Implementing partners |  |  | OSCE – IPA 2016 Project Team High Court of Belgrade War Crimes Prosecutor’s Office Civil society organisations Coordination Body High Judicial Council Ministry of Labour, Employment, Veteran and Social Affairs |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 -Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 1.1. |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | A National Network of Victim and Witness Support Services has been established in the Republic of Serbia. |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  | Target value: |  |  |  | Verification source: |  |  |
|  |  |  | 0 |  | The National Network has been put in place. The Service Coordinator has commenced work. |  |  |  | Reports of the Coordination Body Annual Report of the Ministry of Justice |  |  |

|  | Activity |  |  | Time frame | Implementing authority |  | Implementation indicator |  |  |  | Verification source | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.3.1 | Commencement of work of the Support Services Coordinator at the Ministry of Justice. |  |  | Third quarter of 2021 | Ministry of Justice |  | The Support Services Coordinator has commenced work at the Ministry of Justice. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | RS Budget, Programme Activity 0010 – Administration and management, RSD 2,430,456 in total; of that amount, a sum of RSD 1,225,440 will be allocated in 2021 and 2022 each. |
| 1.3.2 | Commencement of operation of the National Network of Victim and Witness Support Services in the Republic of Serbia. |  |  | Continuously, starting from the third quarter of 2022 | Ministry of Justice |  | The National Network of Victim and Witness Support Services has been founded. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | RS Budget – budgeted under Activities 1.2.1, 12.2 and 1.2.3 (RS Budget – RSD 1,838,160 in total; of that amount, a sum of RSD 612,720 will be allocated in 2021 and 2022 each; RS Budget – RSD 1,021,200 in total; of that amount, RSD 510,600 will be allocated in 2021 and 2022 each, and RS Budget – RSD 408,480 in 2022). |
| 1.3.3 | Standardising the operation of services that are already in place at the Organised Crime Special Department and War Crimes Department of the High Court of Belgrade as well as at the War Crimes Prosecutor’s Office so that they could join the National Network. |  |  | Continuously, starting from the second quarter of 2021 | Ministry of Justice, High Court of Belgrade, War Crimes Prosecutor’s Office |  | The operation of the Injured Party and Witness Support Service at the Organised Crime Special Department and the War Crimes Department of the High Court of Belgrade has been improved and the Service is functioning in line with the quality standards, operating procedures and accountability mechanisms laid down in the Strategy. |  |  |  | Reports of the Coordination Body; | RS Budget, covered by regular funds. |
| 1.3.4 | Standardising the operation of victim and witness support services in place at other institutions of the Republic of Serbia so that they could join the National Network. |  |  | Continuously, starting from the second quarter of 2021 | Ministry of Justice, Ministry of Labour, Employment, Veteran and Social Affairs |  | Quality standards, operating procedures and accountability mechanisms laid down in the Strategy are also being applied at victim and witness support services operating at other institutions of the Republic of Serbia. |  |  |  | Reports of the Coordination Body; | RS Budget, covered by regular funds. |
| 1.3.5 | Preparing and adopting Rules on membership of victim and witness support services set up as part of civil society organisations in the National Network of Support Services. |  |  | Fourth quarter of 2020 – third quarter of 2021 | Ministry of Justice |  | Rules on membership of victim and witness support services set up as part of civil society organisations in the National Network of Support Services have been adopted accordingly. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice. | Budgeted under Activity 1.1.2 in 2020 (RS Budget - regular budget funds) |
| 1.3.6. | Publication of open calls to victim and witness support services set up as part of civil society organisations to join the National Network of Support Services. |  |  | Periodically, starting from the second quarter of 2022 | Ministry of Justice |  | Open calls to victim and witness support services set up as part of civil society organisations to join the National Network of Support Services are published periodically. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | The cost of this activity is negligible - Regular funds of the Ministry of Justice |
| 1.3.7 | Continuous monitoring and preparation for carrying out evaluations of the operation of victim and witness support services set up as part of civil society organisations within the framework of the National Network of Support Services. |  |  | Periodically, starting from the fourth quarter of 2022 | Ministry of Justice |  | Continuous monitoring and preparation for evaluations of operation of victim and witness support services set up as part of civil society organisations are carried out periodically within the framework of the National Network of Support Services. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity.1.3.1 (RS Budget, RSD 2,430,456 in total; of that amount, a sum of RSD 1,225,440 will be allocated in 2021 and 2022 each) |
| 1.3.8 | Assessment of the costs of provision of victim and witness support services within the framework of the National Network. |  |  | Fourth quarter of 2021 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | An assessment of the costs of provision of victim and witness support services within the framework of the National Network has been carried out. |  |  |  | Reports of the Coordination Body | Not known at this point – will be known after the Ministry of Justice and the Project Team carry out a relevant analysis. |
| 1.3.9 | Mandatory allocation of funds required for financing support services provided to victims and witnesses within the framework of the National Network of Victim and Witness Support Services. |  |  | Periodically, starting from the third quarter of 2022 | Ministry of Justice, High Judicial Council |  | Periodic allocations of funds required for financing support services provided to victims and witnesses within the framework of the National Network of Victim and Witness Support Services have commenced. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice; Annual Report of the High Judicial Council. | Not known at this point – will be known in 2021. |
| 1.3.10 | Adopting Rules on overseeing the operation of victim and witness support services belonging to the National Network. |  |  | Fourth quarter of 2020 | Ministry of Justice |  |  |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | RS Budget, regular budget funds, Programme Activity 0010 – Administration and management |
| Measure 1.4 |  | Strengthening professionals capabilities of personnel working in the field of the rights of victims and witnesses of crime in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Informational and educational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice Ministry of Interior |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team High Judicial Council State Prosecutorial Council Judicial Academy Bar Association of Serbia |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management and Chapter 23.3 – Judicial Academy, Programme 1602 - Organisation and management in the system of the judiciary, Programme Activity 0009 – Professional development of future and incumbent judicial office holders |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 1.1. |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Victim and witness service providers, police officers, trial judges, public prosecutors and attorneys-at-law have received adequate training in the subject matter of victims’ rights. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |
|  |  |  | 0 |  |  | - A hundred and fifty providers of primary/general support from the National Network have received training in line with standards and training curricula that have been established in advance; - Sixty providers of specialist support from the National Network have received training in line with standards and training curricula that have been established in advance; - Fifty police officers/focal points have completed specialist training in the field of victims’ rights; - A thematic unit related to the rights of victims forms an integral part of initial and ongoing training at the Judicial Academy; - A thematic unit related to the rights of victims forms an integral part of ongoing training provided to police officers; - A thematic unit related to the rights of victims forms an integral part of initial and ongoing training at the Attorney Academy; |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice; Annual Report of the Ministry of Interior; Annual Report of the Judicial Academy; Annual training curricula intended for judges; Annual training curricula intended for public prosecutors; Annual training curricula intended for police officers. |  |  |

|  | Activity |  |  |  | Time frame | Implementing authority |  |  | Output indicator |  |  | Verification source | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.4.1 | Develop a training curriculum for primary/general support providers working at services that belong to the National Network. |  |  | Fourth quarter of 2019 – third quarter of 2020 |  | Ministry of Justice, Judicial Academy |  | A training curriculum intended for primary/general support providers working at services that belong to the National Network has been developed. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice; Annual Reports of the Judicial Academy | RS Budget – regular budget funds, Programme Activity 0009 – Professional development of future and incumbent judicial office holders |
| 1.4.2 | Implementing training programmes on the rights of victims of crime intended for providers of primary/general support working at services that belong to the National Network. |  |  | Continuously, starting from the first quarter of 2021 |  | Ministry of Justice, Judicial Academy |  | Training programmes on the rights of victims of crime intended for providers of primary/ general support working at services that belong to the National Network are implemented continuously. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice; Annual Reports of the Judicial Academy | RS Budget, Programme Activity 0009 – Professional development of future and incumbent judicial office holders, RSD 31,000,000 in total; of that amount, a sum of RSD 16,500,000 will be allocated in 2021 and RSD 14,500,000 will be allocated in 2022 OSCE: EUR 20,000 in total; of that amount, a sum of EUR 10,000 will be allocated in 2020 and 2021 each. |
| 1.4.3 | Develop and/or revise specialist-training curricula for providers of secondary support working at services that belong to the National Network. |  |  | Continuously, starting from the fist quarter of 2021 |  | Ministry of Justice, relevant ministries, Judicial Academy |  | Specialist-training curricula intended for providers of secondary support working at services that belong to the National Network have been developed and/or revised. |  |  |  | Reports of the Coordination Body | RS Budget, Programme Activity 0009 – Professional development of future and incumbent judicial office holders, RSD 560,280 in total; of that amount, a sum of RSD 151,800 will be allocated in 2021 and RSD 408,480 will be allocated in 2022. |
| 1.4.4 | Implementing specialist-training programmes for providers of secondary victims support working at services that belong to the National Network. |  |  | Continuously, starting from the first quarter of 2021 |  | Ministry of Justice, relevant ministries, Judicial Academy |  | Specialist-training programmes for providers of secondary victims support working at services that belong to the National Network are implemented continuously. |  |  |  | Reports of the Coordination Body; Annual Reports of the Judicial Academy | RS Budget, Programme Activity 0009 – Professional development of future and incumbent judicial office holders, RSD 594.000 in total; of that amount, a sum of RSD 118,800 will be allocated in 2021 and RSD 475,200 will be allocated in 2022. |
| 1.4.5 | Amend the Initial Training Curriculum implemented at the Judicial Academy to include training courses on the rights of crime victims. |  |  | Second quarter of 2020 |  | High Judicial Council, State Prosecutorial Council, Judicial Academy |  | The Initial Training Curriculum implemented at the Judicial Academy has been amended to include training courses on the rights of crime victims. |  |  |  | Annual Reports of the Judicial Academy; Annual initial training curricula | RS Budget – regular funds |
| 1.4.6 | Incorporate training courses on the rights of crime victims into ongoing training curricula for judicial office holders. |  |  | Fourth quarter of 2020 |  | High Judicial Council, State Prosecutorial Council, Judicial Academy |  | Training courses on the rights of crime victims have been incorporated into ongoing training curricula for judicial office holders. |  |  |  | Annual ongoing training curriculum for judges; Annual ongoing training curriculum for public prosecutors; Reports of the Coordination Body. | RS Budget – regular funds |
| 1.4.7 | Develop a training curriculum and training materials to provide training to judicial office holders and initial training attendees at the Judicial Academy. |  |  | Fourth quarter of 2019 – third quarter of 2020 |  | High Judicial Council, State Prosecutorial Council, Judicial Academy |  | A training curriculum and training materials have been developed to provide training to judicial office holders and initial training attendees at the Judicial Academy. |  |  |  | Annual ongoing training curriculum for judges; Annual ongoing training curriculum for public prosecutors; Reports of the Coordination Body. | RS Budget - regular funds |
| 1.4.8 | Provide judicial office holders with training in the rights of victims of crime. |  |  | Continuously, starting from the fourth quarter of 2020 |  | Judicial Academy |  | Training in the rights of victims of crime is continuously provided to judicial office holders. |  |  |  | Reports of the Coordination Body; Annual Reports of the Judicial Academy | RS Budget – budgeted under Activity 1.4.2 |
| 1.4.9 | Develop a training curriculum for the thematic unit “Rights of Victims” for Ministry of Interior police officers who perform the role of focal points. |  |  | Fourth quarter of 2020 |  | Ministry of Interior, Ministry of Justice, Judicial Academy, University of Criminal Investigation and Police Studies |  | A training curriculum for the thematic unit “Rights of Victims” has been developed to provide training to Ministry of Interior police officers who perform the role of focal points. |  |  |  | Reports of the Coordination Body; Annual Reports of the Ministry of Interior; Annual training curricula for police officer. | RS Budget – regular funds |
| 1.4.10 | Provide training to police officers who perform the role of focal points for providing information to victims and witnesses. |  |  | Continuously, starting from the fourth quarter of 2020 |  | Ministry of Interior, Ministry of Justice, Judicial Academy, University of Criminal Investigation and Police Studies |  | Police officers who perform the role of focal points for providing information to victims and witnesses are continuously provided with relevant training. |  |  |  | Reports of the Coordination Body; Annual Reports of the Ministry of Interior; Annual training curricula for police officers | RS Budget – regular funds |
| 1.4.11 | Incorporate the thematic unit “Rights of Victims” into the Ongoing Training Curricula for police officers. |  |  | Second quarter of 2021 |  | Ministry of Interior, University of Criminal Investigation and Police Studies |  | Thematic unit “Rights of Victims” has been incorporated into the Ongoing Training Curricula for police officers. |  |  |  | Reports of the Coordination Body; Annual Reports of the Ministry of Interior; Annual training curricula for police officers | RS Budget – regular funds |
| 1.4.12 | Provide police officers, including those working with the War Crimes Investigation Service, with training in the rights of victims of crime |  |  | Continuously, starting from the fourth quarter of 2021 |  | Ministry of Interior, University of Criminal Investigation and Police Studies |  | Training in the rights of victims of crime is continuously provided to police officers. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Interior; Annual training curricula for police officers | RS Budget – regular funds |
| 1.4.13 | Develop a training curriculum concerning the topic of victims’ rights for attorneys. |  |  | Fourth quarter of 2020 |  | Bar Association of Serbia, Attorney Academy, OSCE/IPA 2016 Project Team |  | A training curriculum concerning the topic of victims’ rights intended for attorneys has been developed. |  |  |  | Reports of the Coordination Body | Budget of the Bar Association and OSCE IPA 2016 |
| 1.4.14 | Provide attorneys with training in the rights of victims of crime. |  |  | Continuously, starting from the first quarter of 2021 |  | Bar Association of Serbia, Attorney Academy, OSCE/IPA 2016 Project Team |  | Attorneys are continuously provided with training in the rights of victims of crime. |  |  |  | Reports of the Coordination Body | Budget of the Bar Association and OSCE IPA 2016 |
| 1.4.15 | Develop and implement training curricula on the topic of dealing with victims intended for court guards. |  |  | Periodically, starting from the fourth quarter of 2020 |  | Ministry of Justice, OSCE/IPA 2016 Project Team, Judicial Academy |  | Training curricula on the topic of dealing with victims intended for court guards are implemented periodically. |  |  |  | Reports of the Coordination Body | RS Budget – regular funds |
| 1.4.16 | Prepare and organise a round table to define the needs for providing training in the educational, healthcare and social protection systems (to school psychologists, emergency physicians, gynaecologists, paediatricians and social workers). |  |  | Fourth quarter of 2020 – second quarter of 2021 |  | Ministry of Justice, OSCE/IPA 2016 Project Team |  | A round-table discussion has been held to define the needs for providing training in the educational, healthcare and social protection systems. |  |  |  | Reports of the Coordination Body | RS Budget – regular funds |
| Measure 1.5 |  | Improving the mechanism for decision-taking on the restitution claim in criminal proceedings |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  |  | Informational and educational Institutional, management and organisational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Supreme Court of Cassation |  |  |  | Implementing partners |  |  |  | OSCE - IPA 2016 Project Team Judicial Academy Ministry of Justice |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  |  |  | Foreign aid |  |  |  |
|  |  |  | Regular Budget funds – Chapter 23 – Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management, Chapter 6.1. – Supreme Court of Cassation, Programme 1603 – Operation of courts, Programme Activity 0004 – Administrative support to the conduct of judicial proceedings before the Supreme Court of Cassation, RSD 255,322,000; and Chapter 23.3 – Judicial Academy, Programme 1602 –Organisation and management in the system of the judiciary, Programme Activity 0009 – Professional development of future and incumbent judicial office holders |  |  |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |
|  |  | Regulations implementing the measure | Civil Procedure Code; Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings |  |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Judges presiding over criminal trials have received training in applying Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings adopted by the Supreme Court of Cassation and have been applying them accordingly; Restitution claims are filed using uniform claim forms and professionals working at support services assist victims with filling in those claim forms. |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  |  | Target value: |  |  |  |  | Verification source: |  |
|  |  |  | - Five percent of decisions on restitution claims are rendered in criminal proceedings; - No judges and public prosecutors have received training in applying the Guidelines |  |  |  | - Twenty-five percent of decisions on restitution claims are rendered in criminal proceedings; - Two hundred judges and public prosecutors have received training in applying the Guidelines. |  |  |  |  | Reports of the Coordination Body; Annual Report on the operation of all courts in the Republic of Serbia; Annual Report of the Ministry of Justice; Annual Report of the Judicial Academy. |  |

|  | Activity |  |  | Time frame | Implementing authority | Output indicator |  |  | Verification source | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.5.1 | Adopting Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings. |  |  | Third quarter of 2019 | Supreme Court of Cassation | Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings have been adopted accordingly. |  |  | Report of the Coordination Body | RS Budget -regular funds of the SCC, Programme Activity 0004 – Administrative support to the conduct of judicial proceedings before the Supreme Court of Cassation |
| 1.5.2 | Providing training to public prosecutors and judges handling or presiding over criminal cases who have been trained to apply the Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings adopted by the Supreme Court of Cassation. |  |  | Continuously, starting from the third quarter of 2020 | Supreme Court of Cassation, Judicial Academy | Courses of training are accordingly run for public prosecutors and judges handling or presiding over criminal cases who have been trained to apply the Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings adopted by the Supreme Court of Cassation. |  |  | Report of the Coordination Body; Annual Report of the Judicial Academy | RS Budget, regular funds |
| 1.5.3 | Developing a uniform claim form for filing restitution claims in criminal proceedings. |  |  | Third quarter of 2020 | Supreme Court of Cassation | A uniform claim form for filing restitution claims in criminal proceedings has been developed accordingly. |  |  | Report of the Coordination Body | RS Budget -regular funds of the SCC, Programme Activity 0004 – Administrative support to the conduct of judicial proceedings before the Supreme Court of Cassation |
| 1.5.4 | Continuous application of the Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings and monitoring of results of their application to define corrective measures when necessary. |  |  | Continuously, starting from the first quarter of 2020 | Supreme Court of Cassation, criminal courts of the Republic of Serbia | Application of the Guidelines for improving the case law with regard to procedure for compensation of damage to victims of serious crimes in criminal proceedings is continuously monitored. |  |  | Report of the Coordination Body | RS Budget -regular funds allocated to courts |
| 1.5.5 | Assisting victims with filling in restitution claim forms that are filed in criminal proceedings as part of the primary support programme. |  |  | Continuously, starting from the fourth quarter of 2021 | Support services belonging to the National Network | Restitution claims are filed using uniform claim forms and professionals from support services render assistance to victims with filling in those claim forms. |  |  | Report of the Coordination Body | Not known at this point – will be known in 2020 – reference to Activity 1.3.9 |
| 1.5.6 | Drawing up a Draft Law on Amendments to the Civil Procedure Code to enhance the status of victims in the process of pursuing restitution claims in civil litigation. |  |  | Fourth quarter of 2019 – fourth quarter of 2020 | Ministry of Justice, OSCE/IPA 2016 Project Team | A Draft Law on Amendments to the Civil Procedure Code has been drawn up to enhance the status of victims in the process of pursuing restitution claims in civil litigation. |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | RS Budget – regular budget funds, Programme Activity 0010 – Administration and management |
| Measure 1.6 |  | International cooperation and exchange of experiences in the field of provision of support and protection to victims and witnesses of crime |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Institutional, management and organisational |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners | OSCE - IPA 2016 Project Team Coordination Body |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 -Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 1.1. |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |
|  |  | Output indicator: | The National Network has been cooperating continuously with relevant international organisations and support services and recommendations made by the Coordination Body with a view to improving the operation of the National Network are based on concepts found in comparative law and best practice in the field of victim support. |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  | Verification source: |  |  |
|  |  |  | Membership of 0 international organisations and networks. |  |  | Application for membership of at least one international organisation has been filed. |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice |  |  |

|  | Activity |  |  | Time frame | Implementation authority |  | Output indicator |  |  |  | Verification source | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.6.1 | The Coordination Body, supported by the Coordinator, has been making constant efforts to join international organisations and organisation networks in the field of victim protection and support as well as to cooperate with them in other respects. |  |  | Continuously, starting from the first quarter of 2021 | Coordination Body, Ministry of Justice |  | Continuous communication and exchange of experiences between the Coordination Body and/or the Coordinator and relevant international organisations. |  |  |  | Reports of the Coordination Body | RS Budget - regular funds, Programme Activity 0010 – Administration and management |
| 1.6.2 | In developing recommendations for improvement of the operation of the National Network, the Coordination Body has been taking into account concepts found in comparative law and best practices in the field of victim support. |  |  | Continuously, starting from the first quarter of 2021 | Coordination Body, Ministry of Justice |  | Recommendations for improvement of the operation of the National Network developed by the Coordination Body are based on concepts found in comparative law and best practices in the field of victim support |  |  |  | Reports of the Coordination Body | RS Budget - regular funds, Programme Activity 0010 – Administration and management |
| 1.6.3 | Support services that belong to the National Network, supported by the Coordinator, have been continuously cooperating with victim and witness support services in the region. |  |  | Continuously, starting from the fourth quarter of 2022 | Support services belonging to the National Network, Ministry of Justice |  | Support services that belong to the National Network, supported by the Coordinator, have been continuously cooperating with victim and witness support services in the region. |  |  |  | Reports of the Coordination Body | RS Budget - regular funds, Programme Activity 0010 – Administration and management |
| Specific objective 2: Strengthening protection afforded to victims and witnesses Improving availability, quality and effectiveness of measures to protect victims and witnesses of crime in the Republic of Serbia, with special attention to be devoted to the protection of particularly vulnerable categories of victims and witnesses. Outcome indicator for specific objective 2: Effective and quality protection measures according to the standards established under the Directive have been made available to crime victims and witnesses, especially those belonging to particularly vulnerable categories. Baseline value in 2020: Improvements are required in legislative and institutional frameworks, as well as in practices; Target value in 2025: Legislative and institutional frameworks, as well as practices regarding treatment of victims and witnesses ensure the provision of adequate protection; Verification source: Reports produced by the Coordination Body. |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 2.1 |  | Amendments to the legislative framework governing the field of penal law in line with the provisions of the Directive |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Regulatory |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | Criminal Code; Criminal Procedure Code; Law on Juvenile Offenders and Criminal Protection of Juveniles; Law on Enforcement of Penal Sanctions; Law on Enforcement of Non-Custodial Sanctions and Measures; Law on Amendments to the Law on Special Measures to Prevent Sexual Offences against Juveniles |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2020 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Penal legislation of the Republic of Serbia is fully aligned with the provisions of the Directive |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |
|  |  |  | 0% |  |  | Necessary amendments to the legislative framework governing the field of penal law have been defined and drafted 100%. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice |  |  |

|  | Activity |  |  | Time frame | Implementing authority |  | Output indicator |  |  |  | Verification source | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1.1 | Forming and work of an expert group to produce necessary draft amendments to criminal laws and accompanying secondary legislation to ensure their alignment with the provisions of the Directive, as well as to provide for the establishment and operation of the National Network of Victim and Witness Support Services in the Republic of Serbia. |  |  | Fourth quarter of 2019 – fourth quarter of 2020 | Ministry of Justice in cooperation with the OSCE-IPA 2016 Project Team |  | The expert group has produced necessary draft amendments to criminal laws and accompanying secondary legislation to ensure their alignment with the provisions of the Directive. |  |  |  | Report prepared by the Expert Group | RS Budget – regular funds, Programme Activity 0010 – Administration and management and OSCE – EUR 6,000 in 2019 |
| 2.1.2 | Drawing up a Draft Law on Amendments to the Criminal Code to align the relevant provisions of the Code with the definition of the term “victim” as given in the Directive. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Criminal Code has been drawn up, aligning relevant provisions of the Code with the definition of the term “victim” as given in the Directive. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| 2.1.3 | Drawing up a Draft Law on Amendments to the Criminal Procedure Code to: - Align the relevant provisions of the Code with the definition of the term “victim” as given in the Directive; - Provide for the right of victims to be accompanied by a person of trust during evidentiary activities; - Ban cross-examination of particularly vulnerable victims and witnesses and asking them leading questions; - Enhance the rights of victims to receive relevant documents in criminal proceedings; - Enhance the right of victims to seek legal remedy in criminal proceedings; - Lay down the scope, accessibility and procedure for making use of information available from questionnaires used to assess victims’ individual needs in criminal proceedings; - Grant all juvenile witnesses the status of particularly vulnerable witness in all instances; - Provide for the conditions under which video conferencing may be used; - Provide for the conditions under which the public may be excluded from the main hearing; - Provide for the issue of data protection regarding particularly vulnerable witnesses; - Provide in greater detail for issues related to the use of language in criminal proceedings; - Lay down the competence and procedure for notifying victims of defendant’s release from detention. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Criminal Procedure Code has been drawn up accordingly. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| 2.1.4 | Drawing up a Draft Law on Amendments to the Law on Juvenile Offenders and Criminal Protection of Juveniles to align the relevant provisions of that law with the provisions of the Directive with regard to: - The extent to which an injured party can exercise their right to be represented by an attorney; - Limiting the number of times a juvenile injured party may be questioned; - Ban confrontation of juvenile injured parties who are under the age of 14 years with defendants. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Juvenile Offenders and Criminal Protection of Juveniles has been drawn up accordingly. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| 2.1.5 | Drawing up a Draft Law on Amendments to the Law on Special Measures to Prevent Sexual Offences against Juveniles with a view to harmonising said law with the Criminal Code. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Special Measures to Prevent Sexual Offences against Juveniles has been drawn up accordingly. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| 2.1.6 | Drawing up a Draft Law on Amendments to the Law on Enforcement of Penal Sanctions with regard to the mechanisms for notifying the victim about the release of the convicted person. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Enforcement of Penal Sanctions has been drawn up accordingly. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| 2.1.7 | Drawing up a Draft Law on Amendments to the Law on Enforcement of Non-Custodial Sanctions and Measures with regard to establishment of mechanisms for notifying the victim of the release of the convicted person. |  |  | Fourth quarter of 2020 | Ministry of Justice |  | Draft Law on Amendments to the Law on Enforcement of Non-Custodial Sanctions and Measures has been drawn up accordingly. |  |  |  | Report of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.1.1 (RS Budget - regular funds and OSCE –EUR 6,000 in 2019) |
| Measure 2.2 |  | Strengthening the system of procedural protection afforded to victims and witnesses by improving practices related to the treatment of victims and witnesses |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Institutional, management and organisational |  |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team Supreme Court of Cassation |  |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 2.1. |  |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2021 |  |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Improvements have been made with regard to implementing measures aimed at affording procedural protection to victims and witnesses of crime. |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |  |
|  |  |  | No instruments have been developed for monitoring the implementation of protection measures. |  |  | Mechanisms have been developed to monitor the implementation of measures aimed at affording procedural protection. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice |  |  |  |

|  | Activity |  |  | Time frame | Implementing authority |  | Output indicator |  |  |  | Verification source | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.2.1 | Carry out a review of the existing interviewing practices applied by authorities conducting proceedings and other participants therein with regard to questioning of vulnerable witnesses and make recommendations for improvements. |  |  | Fourth quarter of 2020 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | A review of the existing interviewing practices applied by authorities conducting proceedings and other participants therein has been carried out with respect to the questioning of vulnerable witnesses and recommendations for improvements have been defined accordingly. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | RS Budget – regular funds, Programme Activity 0010 – Administration and management |  |
| 2.2.2 | Carry out a review of the existing case law with regard to imposing sanction for acts that disrupt the court’s normal process, ordering measures of procedural protection of victims and witnesses, cautioning and fining defence attorneys and other participants in the proceedings who insult the witness or the injured party or threaten them or endanger their safety and make recommendations for improvements. |  |  | Fourth quarter of 2020 | Ministry of Justice, OSCE/IPA 2016 Project Team, Bar Association of Serbia |  | A review of the existing case law has been carried out in respect of imposing sanction for acts that disrupt the court’s normal process and ordering measures of procedural protection of victims and witnesses. |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice | Budgeted under Activity 2.2.1 (RS Budget – regular funds) |  |
| 2.2.3 | Continuously monitor practical implementation of measures aimed at providing procedural protection to victims and witnesses by means of a questionnaire especially designed for that purpose. |  |  | Continuously, starting from the fourth quarter of 2021 | Supreme Court of Cassation, Coordination Body |  | The Coordination Body has been continuously monitoring the implementation of measures aimed at providing procedural protection to victims and witnesses in the case law/ by means of a questionnaire especially designed for that purpose. |  |  |  | Reports of the Coordination Body | RS Budget – regular funds |  |
| Measure 2.3 |  | Strengthening the system of procedural protection afforded to victims and witnesses by improving infrastructure of courts and prosecutor’s offices |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Institutional, management and organisational Informational and educational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team Supreme Court of Cassation |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds- Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 2.1. |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | Judicial infrastructure has been improved in such a way that it ensures more appropriate treatment of victims and witnesses of crime. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |
|  |  |  | Judicial infrastructure is inadequate to allow provision of support and protection to victims and witnesses |  |  | Competent authorities have been implementing measures aimed at protecting victims and witnesses in line with the standards guaranteed under the Directive. |  |  |  | Reports of the Coordination Body Annual Report of the Ministry of Justice |  |  |

|  | Activity |  |  | Time frame | Implementing authority |  |  | Output indicator |  | Verification source |  | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.3.1 | Publish a catalogue of standards to be met by judicial infrastructure with respect to protection and support afforded to victims and witnesses and their ongoing implementation in the process of construction and renovation of buildings housing courts and public prosecutor’s officers (related Activity 1.2.5). |  |  | Continuously, starting from the fourth quarter of 2020 | Ministry of Justice, OSCE/IPA 2016 Project Team |  |  | A catalogue of standards to be met by judicial infrastructure with respect to protection and support afforded to victims and witnesses has been published and is applied accordingly. |  | Reports of the Coordination Body |  | RS Budget - regular funds, Programme Activity 0010 – Administration and management |
| 2.3.2 | Adopting a rulebook to provide for the use of video conferencing in criminal proceedings. |  |  | Fourth quarter of 2020 | Ministry of Justice, Supreme Court of Cassation |  |  | A rulebook providing for the use of video conferencing in criminal proceedings has been adopted accordingly. |  | Reports of the Coordination Body |  | Budgeted under Activity 2.3.1 (RS Budget - regular funds) |
| 2.3.3 | Procurement of IT equipment to allow broader use of the video conferencing tool for questioning witnesses (related activities 1.2.1-1.2.3). |  |  | Continuously, starting from the fourth quarter of 2019 | Ministry of Justice, OSCE/IPA 2016 Project Team |  |  | IT equipment for questioning witnesses via a video conferencing tool has been procured according to the schedule and timetable for setting up support services. |  | Reports of the Coordination Body |  | Budgeted under Activity 1.2.1 (RS Budget – RSD 18,381,600 in total; of that amount a sum of RSD 3,676,320 will be allocated in 2020, and a sum of RSD 7,352,640 will be allocated in 2021 and 2022 each.) |
| 2.3.4 | Developing a curriculum and providing training on how to use the video conferencing tool. |  |  | Continuously, starting from the fourth quarter of 2020 | Ministry of Justice, Supreme Court of Cassation, OSCE/IPA 2016 Project Team |  |  | Training in using the video conferencing tool is continuously implemented. |  | Reports of the Coordination Body |  | RS Budget – regular funds |
| Specific objective 3: Raising awareness of victims’ and witnesses’ rights Raising awareness of the rights afforded to victims and witnesses of crime in the legal system of the Republic of Serbia, while continually informing the general public with that aim in mind. Outcome indicator for specific objective 3: Victims and witnesses of crime can access easily comprehensible and systematised information about rights afforded to them in the criminal justice system of the Republic of Serbia. Baseline value in 2019: Information about the rights of victims and witnesses in the Republic of Serbia’s legal system is difficult to access and has not been systematised in any way; Sporadic and inadequate information about the rights of crime victims and witnesses has been provided to the general public; Target value in 2025: Information about the rights of victims and witnesses in the Republic of Serbia’s legal system is continuously systematised, updated and disseminated by means of brochures, through the media and a specialised web portal. Verification source: Reports prepared by the Coordination Body. |  |  |  |  |  |  |  |  |  |  |  |  |
| Measure 3.1 |  | Raising awareness among crime victims of their rights in criminal proceedings and support services made available to them in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Informational and educational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  | Foreign aid |  |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measures 1.1 and 1.2. |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | - Information about victims’ rights and available support and assistance services has been systematised and made available to the public via specialised and interlinked websites; - Information about victims’ rights and available support and assistance services has been systematised and made available to the public via multilingual brochures distributed to institutions such as the police, the judiciary, healthcare and social protection institutions. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  |  | Verification source: |  |
|  |  |  | 0 |  |  | - A specialised website has been created and launched; - Specialised brochures have been made easily available; - Initial media campaign has been conducted. |  |  |  |  | Reports of the Coordination Body; Annual Report of the Ministry of Justice https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php https://www.mpravde.gov.rs/ https://vss.sud.rs/sr http://www.dvt.jt.rs/ http://www.rjt.gov.rs/ci/ https://www.vk.sud.rs/ https://www.pars.rs/sr/ https://www.zdravlje.gov.rs/ https://www.minrzs.gov.rs/sr http://www.mpn.gov.rs/ http://www.mpn.gov.rs/ http://www.tuzilastvorz.org.rs/sr/ https://www.bg.vi.sud.rs/ |  |

|  | Activity |  |  | Time frame | Implementing authority |  | Output indicator |  |  |  | Verification source |  | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1.1 | Creating and launching a specialised website designed to inform victims and containing comprehensive and detailed information about victims’ rights and services and support and assistance made available to them. |  |  | Second quarter of 2019 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | A specialised website designed to provide information to victims has been created and launched, containing comprehensive and detailed information about victims’ rights and services and support and assistance made available to them. |  |  |  | https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php |  | RS Budget – regular funds, Programme Activity 0010 – Administration and management |  |
| 3.1.2 | Linking the specialised website to as many as possible Internet websites of government authorities and other institutions, civil society organisations and healthcare institutions. |  |  | Continuously, starting from the second quarter of 2019 | Ministry of Justice, Ministry of Interior, Ministry of Labour, Employment, Veteran and Social Affairs, Ministry of Health, Ministry of Science, Education and Technological Development, civil society organisations |  | The specialised website dedicated to victims of crime has been linked to many websites of government authorities and other institutions, civil society organisations and healthcare institutions. |  |  |  | https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php https://www.mpravde.gov.rs/ https://vss.sud.rs/sr http://www.dvt.jt.rs/ http://www.rjt.gov.rs/ci/ https://www.vk.sud.rs/ https://www.pars.rs/sr/ https://www.zdravlje.gov.rs/ https://www.minrzs.gov.rs/sr http://www.mpn.gov.rs/ http://www.tuzilastvorz.org.rs/sr/ https://www.bg.vi.sud.rs/ |  | RS Budget - regular funds |  |
| 3.1.3 | Producing, printing and distributing informational brochures for victims. |  |  | Continuously, starting from the fourth quarter of 2019 | Ministry of Justice, Ministry of Interior, High Judicial Council, State Prosecutorial Council, Ministry of Health, Ministry of Labour, Employment, Veteran and Social Affairs |  | Specialised, multilingual brochures have been produced and distributed to relevant institutions, such as the police, the judiciary, healthcare and social protection institutions. |  |  |  | Reports of the Coordination Body |  | RS Budget - regular funds |  |
| 3.1.4 | Producing a Feasibility Study for setting up a special call-centre for victims and witness of crime. |  |  | Fourth quarter of 2022 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | A Feasibility Study for setting up a special call-centre for victims and witness of crime has been produced accordingly. |  |  |  |  | Reports of the Coordination Body; Feasibility Study | RS Budget – regular funds, Programme Activity 0010 – Administration and management |  |
| Measure 3.2 |  | ## Improving the knowledge and skills of members of the media regarding the rights of crime victims in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Informational and educational |  |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team Coordination Body |  |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |  |
|  |  | Regulations implementing the measure | No special regulations are required to be adopted or amended in order to implement this measure. |  |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | The quality of reporting on topics relevant to victims’ rights has improved. |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |  |
|  |  |  | Poor understanding of victims’ rights and support services; Low standard of quality of reporting on this subject matter; Markedly sensationalist approach to this subject matter. |  |  | Knowledge of the subject matter has been improved; The quality of reporting has been raised; As a result of those efforts, the public has become sensitized to this topic |  |  |  | Reports of the Coordination Body A study on media coverage of victim-related topics |  |  |  |

|  | Activity |  |  | Time frame | Implementing authority |  | Output indicator |  |  |  | Verification source | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.2.1 | Organising workshops for members of the media with a focus on victims’ rights. |  |  | Continuously, starting from the second quarter of 2019 | Ministry of Justice, OSCE/IPA 2016 Project Team |  | Workshops focusing on victims’ rights are continuously organised for members of the media. |  |  |  | Reports of the Coordination Body | RS Budget - regular funds, Programme Activity 0010 – Administration and management and OSCE: EUR 3,200 in 2019 |  |
| 3.2.2 | Holding consultative meetings with the Regulatory Authority for Electronic Media and the Press Council to improve monitoring mechanisms in the area of reporting about victim-related topics. |  |  | Periodically, starting from the first quarter of 2021 | Ministry of Justice, OSCE/IPA 2016 Project Team, Coordination Body |  | Consultative meetings have been held with the Regulatory Authority for Electronic Media and the Press Council with the aim of improving monitoring mechanisms in the area of reporting about victim-related topics. |  |  |  | Reports of the Coordination Body | RS Budget - regular funds |  |
| Measure 3.3 |  | ## Raising awareness among the general population of the rights made available to victims of crime in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |
|  |  | Type of measure |  |  |  | Informational and educational |  |  |  |  |  |  |
|  |  | Institution responsible for implementing the measure | Ministry of Justice |  |  | Implementing partners |  |  | OSCE - IPA 2016 Project Team |  |  |  |
|  |  | Estimates of financial resources | Budget of the Republic of Serbia |  |  |  |  | Foreign aid |  |  |  |  |
|  |  |  | Regular Budget funds - Chapter 23 - Ministry of Justice, Programme 1602 Organisation and management in the system of the judiciary, Programme Activity 0010 – Administration and management |  |  |  |  | IPA 2016 – Support to victims and witnesses in Serbia implemented by the OSCE Mission to Serbia |  |  |  |  |
|  |  | Regulations implementing the measure | This measure shall be implemented through previously amended/adopted regulations listed under Measure 1.1. |  |  |  |  |  |  |  |  |  |
|  |  | Implementation deadline | 2022 |  |  |  |  |  |  |  |  |  |
|  |  | Output indicator: | The general public is better informed of the rights afforded to victims and witnesses in the legal system of the Republic of Serbia and mechanisms of protection and support made available to them. |  |  |  |  |  |  |  |  |  |
|  |  |  | Baseline value: |  |  | Target value: |  |  |  | Verification source: |  |  |
|  |  |  | The general public is inadequately informed of and sensitised to victims’ rights and support services. |  |  | The general public has been more adequately informed of and sensitised to victims’ rights and support services. |  |  |  | Reports of the Coordination Body A study on media coverage of victim-related topics https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php |  |  |

|  | Activity |  | Time frame |  | Implementing authority | Output indicator |  | Verification source |  |  | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.3.1 | Conducting an online campaign aimed to raise awareness of the rights of victims with a focus on social media. |  | Continuously, starting from the fourth quarter of 2020 |  | Ministry of Justice, OSCE/IPA 2016 Project Team | An ongoing online campaign aimed to raise awareness of the rights of victims with a focus on social media is continuously conducted. |  | Reports of the Coordination Body; https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php |  |  | RS Budget – regular funds, Programme Activity 0010 – Administration and management |
| 3.3.2 | Improving the proportion of information about victims’ rights circulated in the state-owned and commercial media. |  | Continuously, starting from the fourth quarter of 2019 |  | Ministry of Justice, OSCE/IPA 2016 Project Team | The proportion of information about victims’ rights circulated in the state-owned and commercial media has been improved. |  | Reports of the Coordination Body A study on media coverage of victim-related topics |  |  | RS Budget – regular funds, Programme Activity 0010 – Administration and management |
| 4 Activities that need to be implemented in order to ensure continuous monitoring and efficient coordination of the process of enhancing the status of victims of crime in the Republic of Serbia |  |  |  |  |  |  |  |  |  |  |  |
|  | Measure | Time frame |  | Implementing authority |  |  | Output indicator |  | Verification source | Budget |  |
| 4.1 | Setting up a Victim and Witness Support Coordination Body in the Republic of Serbia. | Third quarter of 2020 |  | Government of the Republic of Serbia on the initiative of the Ministry of Justice |  |  | A Victim and Witness Support Coordination Body has been set up. |  | Decision establishing the Coordination Body | RS Budget –regular funds |  |
| 4.2 | The Victim and Witness Support Coordination Body of the Republic of Serbia has been holding meetings every three months. | Continuously, starting from the third quarter of 2020 |  | Ministry of Justice |  |  | The Victim and Witness Support Coordination Body has been established and holds regular meetings. |  | Reports of the Coordination Body | RS Budget –regular funds |  |
| 4.3 | The Victim and Witness Support Coordination Body of the Republic of Serbia has been monitoring and reviewing measures aimed at enhancing the status of victims of crime, adopting reports and makes recommendations for improvements. | Continuously, starting from the first quarter of 2021 |  | Ministry of Justice |  |  | Reports and recommendations are regularly adopted based on continuous monitoring of implementation of planned measures. |  | Reports of the Coordination Body; https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php | RS Budget –regular funds |  |
| 4.4 | Strategy Implementation Reports are regularly produced, discussed, adopted and made available to the public via the websites of relevant institutions. | Continuously, starting from the fourth quarter of 2020 |  | Ministry of Justice, Ministry of Interior, High Judicial Council, State Prosecutorial Council |  |  | Strategy Implementation Reports are made available to the public via the websites of relevant institutions. |  | Reports of the Coordination Body; https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php | RS Budget –regular funds |  |
| 4.5 | The Coordination Body organises annual round tables to examine the progress made in the previous year in the field of protection and support afforded to victims and witnesses with regard to the measures set out in the National Strategy and the Action Plan that accompanies it. | Continuously, starting from the fourth quarter of 2020 |  | Coordination Body, Ministry of Justice, OSCE/IPA 2016 Project Team |  |  | Progress made in the previous year in the field of protection and support afforded to victims and witnesses in respect of the measures set out in the National Strategy and the Action Plan that accompanies it is analysed and discussed at annual round tables organised by the Coordination Body. |  | Reports of the Coordination Body; https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php | RS Budget –regular funds |  |
| 4.6 | The Coordination Body, supported by external experts, will prepare and adopt an assessment of the effects of implementation of the National Strategy and the accompanying Action Plan for the period 2020-2022, with recommendations on how to prepare the Action Plan for the period 2023-2025. | Third quarter of 2022 |  | Coordination Body, Ministry of Justice |  |  | An assessment of the effects of implementation of the National Strategy and the accompanying Action Plan for the period 2020-2022 has been prepared and adopted, featuring recommendations on how to prepare the Action Plan for the period 2023-2025 (an ex post assessment). |  | Reports of the Coordination Body; An assessment of the effects of implementation of the National Strategy and the accompanying Action Plan for the period 2020-2022, with recommendations on how to prepare the Action Plan for the period 2023-2025. https://www.podrskazrtvama.rs/pomoc-i-podrska/podrska-zrtvama.php | Engagement of two senior experts will be required for a period of 30 days each to carry out this activity – at this point, it is not certain who will finance this activity – will be known in 2021. |  |
| 4.7 | Preparation and adoption of the Action Plan to Implement the National Strategy on the Rights of Victims and Witnesses in the Republic of Serbia for the period 2023-2025. | Fourth quarter of 2022 |  | Ministry of Justice |  |  | Action Plan to Implement the National Strategy on the Rights of Victims and Witnesses has been adopted in a timely fashion. It /builds on the provisions of the National Strategy and results of its implementation during first three years. |  | Conclusion adopting an Action Plan to implement the National Strategy on the Rights of Victims and Witnesses of Crime in the Republic of Serbia for the period 2023-2025. | RS Budget –regular funds |  |