REPUBLIC OF SERBIA NEGOTIATION GROUP FOR CHAPTER 23 ACTION PLAN FOR CHAPTER 23 - Judiciary - June, 2019

3. Mechanisms for implementation of the Action Plan

3.1. Subjects responsible for monitoring the implementation of the Action Plan

The responsibility for monitoring the implementation of the activities envisaged in the Action Plan will be entrusted to the Coordination Body for implementation of the Action Plan for Chapter 23 (hereinafter: Coordination Body). Expert and administrative- technical support to the Coordination Body will be provided by the Secretariat of the Coordination Body for implementation of the Action Plan for Chapter 23 (hereinafter: Secretariat).

Government of the Republic of Serbia shall render the Decision on establishing of the Coordination Body together with the adoption of the revised Action Plan. Government shall appoint members of the Coordination Body among the highest rank public office holders/ heads of institutions in charge of the implementation of the main portion of the activities from the Action Plan. Every member of the Coordination Body shall be accompanied with deputy member. Minister of Justice shall be President of the Coordination Body. Detailed rules and procedures of work of the Coordination Body shall be arranged by the Rules of Procedure of the Coordination Body.

Coordination Body:

- Monitors implementation of the Action Plan;

- Analyses and discusses draft Reports on implementation of the Action Plan;

- Adopts Reports on implementation of the Action Plan;

- Reports to the European Commission, Government of the Republic of Serbia and the National Assembly on implementation of the Action Plan;

- Defines recommendation for improvements of the implementation of the Action Plan;

- Initiates an Early Warning Mechanism in case of delays or other problems in the implementation of the Action Plan;

Coordination Body semi-annually reports on the implementation of the Action Plan to:

- The European Commission through the Ministry of European Integration;

- The European Integration Chamber of the National Assembly;

- Government of the Republic of Serbia.

Reports on the implementation of the Action Plan shall be publicly available on the Ministry of Justice Webpage.

The Coordinating Body meets at least four times a year. The meetings of the Coordination Body are attended by representatives of the Secretariat. At the invitation of the Coordination Body, sessions may also be attended by representatives of other institutions and bodies responsible for the implementation of the Action Plan that do not have representatives in the membership of the Coordination Body, as well as representatives of other institutions and bodies whose presence is important for the more efficient work of the Coordinating Body.

The constituent session of the Coordination Body shall be held no later than 30 days after the establishment of the Coordination Body. The members of the Coordination Body are not compensated for their work.

The Secretariat of the Coordination Body for the implementation of the Action Plan for Chapter 23 is the expert body that provides expert and administrative-technical support to the Coordinating Body. Independent experts with proven experience in the field of Chapter 23 shall be appointed to the Secretariat.

The Secretariat provides expert support to the Coordinating Body by:

- Analysis of the collected and consolidated data on the implementation of the Action Plan;

- Conducting a preliminary evaluation of the results of the implementation of the Action Plan in accordance with the indicators and interim benchmarks;

- Establishing a list of critical points in the implementation of the Action Plan under the Early Warning Mechanism;

- Adoption and an effective implementation of the Methodology for monitoring and evaluating the results of the implementation of the Action Plan and the training of focal points in institutions responsible for implementation of the Action Plan;

- Needs Assessment and initiation of the updates and revision of the Action Plan;

The Secretariat provides administrative support to the Coordinating Body by:

- Initiating and coordination of the collection, unification and processing of data on the implementation of the Action Plan;

- Drafting reports on the implementation of the Action Plan, as well as draft decisions of the Coordination Body;

- Timely publishing reports and other relevant information related to the implementation of the Action Plan;

- Organisation of sessions of the Coordination Body, meetings of the Coordination Body with civil society organizations, as well as training of focal points.

The Secretariat begins its work within 30 days since the establishment of the Coordination Body. The funds for the work of the Secretariat shall be allocated from the donor projects and/or the Budget of the Republic of Serbia and the members of the Secretariat appointed accordingly.

3.2. The role of civil society in monitoring the implementation of the Action Plan

Bearing in mind that the mechanisms of cooperation with the civil society, created during the screening process, the preparation of the Action Plan and the monitoring of its implementation before the revision, resulted in significant progress in the field of transparency and inclusiveness, but also showed certain shortcomings, after the adoption of the revised Action Plan, an improved consultation mechanism with civil society in the process of monitoring the implementation of the Action Plan will be developed.

Not later than 30 days after the establishment of the Coordination Body, the Office for Cooperation with Civil Society will announce a public call for systematic, continuous and institutionalized inclusion of civil society organizations in the process of monitoring the implementation of the Action Plan for Chapter 23, which will include the establishment of an expert platform for continuous dialogue with the Coordination Body and institutions in charge of implementing the Action Plan. This will include, among others, at least semi-annual debates and round tables with representatives of relevant stakeholders to discuss reports on the implementation of the Action Plan and other relevant issues.

In addition to this, the Negotiating Group for Chapter 23, the Coordination Body and the Secretariat will continue to use consultative mechanisms that showed the great capacity and results in the previous period of the implementation of the Action Plan, including the announcement of public calls for submitting suggestions and comments on drafts of relevant documents.

3.3. The Early Warning Mechanism in case of delays and/or problems in implementation of the Action Plan

Within the scope of preparation of draft Reports on implementation of the Action Plan, the Secretariat prepares a dedicated report or appendix to the draft Report outlining critical points in implementing the Chapter 23 Action Plan. This document would inform and urge the Coordination Body’s actions under the early warning mechanism.

Where institutions (not represented in the Coordination Body) face difficulties in implementing activities envisaged in the Chapter 23 Action Plan, their representatives shall be invited to the Coordination Body’s sessions for further discussion of the shortcomings and necessary measures.

The Coordination Body shall establish the follow-up reporting procedure of measures taken to address the issues that triggered the early warning mechanism.

In cases where reports in accordance with the follow up reporting procedure show that there is no progress or progress is not satisfying the Coordination Body shall inform the Government outside of the regular reporting timeframe in order to initiate the Government intervention aimed at fostering implementation of the Action Plan.

3.4. Monitoring and evaluation mechanism: relationship between the Action Plan for Chapter 23 and the Judicial Development Strategy for the period 2019-2024

The process of drafting Judicial Development Strategy for the period 2019-2024 and the process of revision AP 23 are two parallel processes, and their content is as far as possible harmonized. This will help us avoid the earlier dualism of strategic documents in the sector of judiciary, which was highlighted as a problem in the previous analyzes and reports of domestic authorities and institutions.

Monitoring of the implementation of the measures from the Judicial Development Strategy for the period 2019-2024 will be placed under the responsibility

of the body charged with monitoring the implementation of the activities in the Action Plan for Chapter 23 and in accordance with the methodology provided for in this strategic document in order to avoid duplication of work and unnecessary burdens in reporting by the same institutions.

Such an approach should result in achieving the maximum efficiency of the mechanism for monitoring the development of the judiciary, providing objective reports and strengthening accountability for the results of development and implementation of reforms with the relevant stake holders.

The deadlines set by the AP23 will be the deadlines for implementing the measures in the Strategy. The same applies to the impact indicators at the level of the recommendation, and the transitional benchmark and the indicators of the results at the level of measure or activity. The results indicators are set in relation to each activity individually, so as to facilitate the way in which the implementation of the Action Plan is monitored, in quantitative and qualitative terms.

MONITORING & EVALUATION MECHANISM

RS GOVERNMENT

COORDINATION BODY FOR THE IMPLEMENTATION OF AP CH23

Discusses, adopts and submits reports on the AP CH 23 implementation

Stakeholders in charge of the implementation of AP CH23

Working bodies in charge of the monitoring of national strategic documents related to CH 23

quarterly

Semiannual

Semiannual

CSO POOL

NATIONAL ASSEMBLY- CHAMBER FOR EU INTEGRATIONS

EUROPEAN COMISSION

MINISTRY OF EUROPEAN INTEGRATION

Semiannual

Semiannual

quarterly

SECRETARIAT OF THE COORDINATION BODY FOR THE IMPLEMENTATION OF AP CH23

Analyses performance reports, prepares draft reports and decisions of the Coordination Body and conducts pre evaluation

INTRODUCTION JUDICIARY

CURRENT STATE OF PLAY

LEGISLATIVE AND INSTITUTIONAL FRAMEWORK

The legislative framework regulating judiciary in Serbia encompasses: National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 57/13); Action plan for the implementation of the National Judicial Reform Strategy for the period 2013-2018 ("Official Gazette of the RS", No. 71/13, 55/14 and 106/16); The Constitution of the Republic of Serbia ("Official Gazette of the RS", No. 98/06); Law on the Constitutional Court ("Official Gazette of the RS", No. 109/07, 99/11, 18/13 –Decision of the Constitutional Court, 40/15 and 103/15); Law on the High Judicial Council ("Official Gazette of the RS", No. 116/08, 101/10, 88/11 and 106/15); Law on Judges ("Official Gazette of the RS", No. 116/08, 58/09 – decision of the Constitutional court, 104/09, 101/10, 8/12 – decision of Constitutional court, 121/12 and 101/13, 106/15, 63/16- decision of the Constitutional court and 47/17); Law on Organization of Courts ("Official Gazette of the RS", No. 116/08, 104/09, 101/10, 31/11 – state law, 78/11 – state law, 101/11 and 101/13, 106/15, 40/15 –state law, 13/16, 108/16, 113/17 and 65/18 – decision of the Constitutional court); Law on the State Prosecutorial Council ("Official Gazette of the RS", No. 116/08, 101/10, 88/11 and 106/15); The Law on Public Prosecutor’s Office ("Official Gazette of RS", No. 116/08, 104/09, 101/10, 78/11 – state law, 101/11, 38/12 – decision of the Constitutional court, 121/12 and 101/13,  106/15 и 63/16 – decision of the Constitutional court); Law on the Seats and Territorial Jurisdictions of Courts and Public Prosecutors’ Offices ("Official Gazette of the RS", No. 101/13); Law on the Judicial Academy ("Official Gazette of RS", No. 104/09 and decision of Constitutional court No. 32/14 – decision of the Constitutional court and 106/15); Criminal Procedure Code ("Official Gazette of the RS", No. 72/11, 101/11, 121/12, 32/13, 45/13 and 55/14); Civil Procedure Law ("Official Gazette of the RS", No. 72/11 49/13 – decision of Constitutional court, 74/13 – decision of Constitutional court, 55/14); Law on Non-Contentious Proceedings ("Official Gazette of the RS", No. 25/82 and 48/88 and "Official Gazette of the RS", No. 46/95 – state law, 18/05 – state law, 85/12, 45/13 – state law and 55/14, 6/15 и 106/15 – state law); Law on Enforcement and Security ("Official Gazette of the RS", No.106/15, 106/16 – authentic interpretation and 113/17 – authentic interpretation); Law on Public Notaries ("Official Gazette of the RS", No. 31/11, 85/12, 19/13, 55/14 – state law and 106/15); Law on Mediation ("Official Gazette of the RS", No. 55/14); Law on the Bar Exam ("Official Gazette of the RS", No. 16/97); Law on Misdemeanors ("Official Gazette of the RS", No. 65/13, 13/16 and 98/16 – decision of Constitutional court); Law on the Public Attorney's Office ("Official Gazette of the RS", No. 55/14).

The institutional framework encompass: the High Judicial Council, the (High) State Prosecutorial Council, Ministry of Justice, Judicial Academy, Supreme Court of Cassation, four appellate courts, 25 higher courts, 66 basic courts with 29 court units, Misdemeanor court of appeal with three departments, 44 misdemeanor courts, Commercial Court of Appeal, 16 commercial courts, Administrative Court with three departments, the Republic Public Prosecutor’s Office, four appellate public prosecutors’ offices, 25 higher public prosecutors’ offices, 58 basic public prosecutors’ offices.

The judicial system in the Republic of Serbia, as of January 1st 2019, encompasses 2595 judges, 71 public prosecutors and 707 deputy public prosecutors.

National Assembly of the Republic of Serbia enacted the National Judicial Reform Strategy for the period 2013-2018 on July 1st 2013, which has determined priorities, strategic goals and strategic guidelines of reform measures. The Government of the Republic of Serbia adopted an Action plan for implementation of the Judicial Reform Strategy for the period 2013- 2018 on July 31st which envisaged concrete measures and activities for implementation of strategic objectives, defined the deadlines and competent authorities for its implementation and financial sources. Following adoption of the Action plan for Chapter 23, the Government passed the Conclusion on the adoption of the revised Action Plan for the implementation of the National Judicial Reform Strategy in December 2016.

The Strategy envisaged independence, impartiality, competence, accountability and efficiency of the judiciary, as five basic principles and defined priorities, strategic objectives and strategic guidelines of reform measures.

The National Judicial Reform Strategy for the period 2013-2018 stipulates implementation of measures aimed at improvement of impartiality, ethics and integrity of the judicial office holders as well as at the alignment and complete accessibility to the case law and the full realization of the right to the natural judge. The same strategic document also stipulates the establishment of a system of appointment and promotion of judges and public prosecutors according to clear, objective and criteria determined in advance. Following measures in the reform of Judicial Academy are set forth as the strategic approach: Improving initial and continuously training of judges’ and public prosecutors’ associates and assistants, and judicial office holders as well as of representatives of legal professions, along with the system of development of a comprehensive annual training programs and assessment of attendees. In order to achieve these objectives, a comprehensive analysis of the position and directions of the development of the Judicial Academy was conducted. In that purpose, the Judicial Academy adopted the Strategic Plan for the Development of the Judicial Academy for the period 2016-2020 which set four main goals: further strengthening the capacity of the Judicial Academy in order to achieve an effective training and research institution; development of sustainable training programs for the holders of judicial functions, both for initial and continuous training; supporting the development of a system of appointment and promotion of judges and public prosecutors according to clear, objective and criteria system; further networking and external strengthening of the cooperation with partners.

As the National Judicial Reform Strategy for the period 2013-2018 expired at the end of 2018, the assessment of its implementation has been done with the support of USAID Rule of Law Project.

Reform activities in the Republic of Serbia will continue to be based on the new Judicial Development Strategy for the period 2019-2024, which draft is in progress. Strategic goals from the JDS 2019-2024 should follow the determination of Serbia for full membership in the EU. Thus, in the next five-year period, the strengthening of the independence and autonomy, impartiality, efficiency, competence and accountability of the judiciary, as well as the strengthening the public confidence in the work of the judiciary, will be priority of all stakeholders. As the process of the revision of the Action plan for Chapter 23 and of drafting Judicial Development Strategy for the period 2019-2024 are being conducted simultaneously, a particular attention was given to obtain two strategic documents dealing with judiciary that will be complementary and harmonized among themselves. The highest level of coherence of the two strategic documents is important not only regarding envisaged key activities, but also in respect of monitoring and evaluation mechanism that will be established in order to facilitate the oversight of the implementation of the reform.

INDEPENDENCE

Concerning independence of judiciary, the National Judicial Reform Strategy for the period 2013-2018 has identified the need of amending the Constitution in the part which deals with the interference of legislative and executive powers in the process of appointment and dismissal of judges, court presidents, public prosecutors and deputy public prosecutors, elected members of the High Judicial Council and State Prosecutorial Council, and the need for précising the role and status of Judicial Academy, as mechanism for entry to judiciary.

Although due to various reasons deadlines concerning constitutional changes prescribed at the APCH23 have not been fully met, in previous years the Republic of Serbia has made substantial progress as regards the revision of its Constitution in order to strengthen the independence and accountability of the judiciary.

The base for the commencement of the process regarding the constitutional amendments was the Analysis of the Constitutional Framework on the Judiciary in the Republic of Serbia done by the Working Group consisted of the professors of Constitutional law. This Working group was esablished by the Commission for the Implementation of the National Justice Reform Strategy for the period 2013-2018 on which session the Analisis was presented and discussed. On 29 November 2016 the Supreme Court of Cassation organized the conference devoted to the presentation of the Analysis. The Conference was attended by the presidents of all courts in the Republic of Serbia, representatives of the Working Group, representatives of the MoJ, international organizations and institutions, professional associations and the non-governmental sector.

On 19 May 2017 the Ministry of Justice in cooperation with the Office for Cooperation with Civil Society issued a public invitation for the participation of civil society organizations in a consultative process inviting the non-governmental sector to submit its proposals for amending the Constitution in the part relating to the judiciary. In order to ensure full transparency the proposals were published in the websites of the Ministry of Justice and Office for Cooperation with Civil Society. All of the proposals regarding constitutional changes in judiciary were analysed, the offered solutions for the future amandements were compared and they were taken into account during a drafting of the working texts of the constitutional amendments. As a part of the Consultative Process the MоJ organized six roundtables in the period from July to November 2017. After a series of roundtables organized throughout Serbia where the most important topics related to the future amendments („The Competence of the Holders of the Judicial Functions: The Position and the Role of the Judicial Academy in the Appointment Process, The Continuos Trainig and the Appraisal of the Competence“, „The Composition of the High Judicial Council and the State Prosecutorial Council“, „Competences of the High Judicial Council and the State Prosecutorial Council“, „Sources of Law and Harmonization of Case-law“, „Appointment of Judges and Public Prosecutors“) were discussed and in consultation with the expert of the Council of Europe, the first Working Version of the Draft Amendments to the Constitution of the Republic of Serbia was drafted and published on the website of the Ministry of Justice on January 22, 2018. All interested stakeholders (as well as public in large) had been invited to submit their opinions and reasoned comments regarding the Working text and the new roundtable series was organized. In line with received comments and suggestions, and on the basis of the conclusions from the public debate, the Working text has been revised by the Ministry. The second version of the Draft Amendments to the Constitution was published on April 13, 2018 and sent to the Venice Commission on opinion. At the plenary session held on June 22, 2018, the Venice Commission adopted the opinion on the Working Draft Amendments to the Constitution of the Republic of Serbia in the field of judiciary.  Since the APCH23 clearly stipulates that constitutional changes have to be done in accordance with the European standards as promulgated by the Venice Commission, the recommendations given in the Opinion have been implemented in the revised working draft of the amendments and such a third text was published on September 11, 2018 by the MoJ. Taking into account the views and suggestions of representatives of relevant state authorities, professional associations and civil society at the round table held on September 18, as well as the conclusions from the Analysis of the Constitutional Framework on the Judiciary in the Republic of Serbia, the Ministry of Justice revised the third working text of the constitutional amendments and published the final fourth version on October 15, 2018.

The Venice Commission on 22nd October published the Secretariat Memorandum on the compatibility of the draft Amendments to the Constitutional Provisions on the Judiciary as submitted by the Ministry of Justice of Serbia on 12 October 2018 (CDL-REF(2018)053) with the Venice Commission’s Opinion on the draft Amendments to the Constitutional Provisions on the Judiciary (CDL-AD(2018)011). In the Memorandum the VC concluded that the recommendations formulated by the Venice Commission in its opinion were followed by Serbian authorities in the final draft Amendments to the Constitutional Provisions on the Judiciary.

Transparency and inclusiveness of all stakeholders including civil society and professional organizations were the guiding principles for the Ministry throughout the entire process of drafting the amendments as the basis for initiation of the official procedure that will be continued in the Parliament.

The official procedure commenced at the end of 2018. The Government has established on its 113th session held on 29 November 2018 the Proposal for Amendments to the Constitution of the Republic of Serbia and made a conclusion, pursuant to Article 203. Item 1 of the Constitution of the Republic of Serbia and Article 142 of the Rules of procedure of the National Assembly (RS Official Gazette no. 20/12 - corrigendum) to propose to the National Assembly amendments to the Constitution of the Republic of Serbia. The Government submitted a Proposal for Amending the Constitution of the Republic of Serbia to the National Assembly on 30 November 2018.

Having in mind the importance of the alignment of the subsequent judicial legislation with new constitutional provisions, the Ministry of Justice has already formed four Working groups (Working group for the preparation of the Draft Law on Judicial Academy; Working group for the preparation of the Draft Law on High Judicial Council, the Draft Law on Court Organization and Draft Law on Judges; Working group for the preparation of the Draft Law on High Prosecutorial Council and the Draft Law on Public Prosecution; Working group for the division of the competences between Ministry of Justice and judicial and prosecutorial councils) which have started to meet and work. Their task is, on the one hand, to harmonize the judicial legislation with the future amendments to the Constitution considering the Venice Commission Opinion No.921/2018, and, on the other hand, to improve current legislative solutions where it is recognized as necessary and welcoming. The Venice Commission will be consulted on this legislation and its opinion will be valuable for taking next steps.

During the period of the implementation of the APCH23 and the NJRS 2013-2018 the National Assembly appointed the remaining court presidents at the proposal of the High Judicial Council. Presently, the procedure for the nomination and the election of the candidates for the court presidents is being conducted regularly, according to law, without delay and with a clear selection procedure applied.

Improved rules for evaluating professional performance of judges and public prosecutors have been adopted and are being successfully applied. Through the legislative changes and new bylaws, clear, measurable and objective criteria were defined for appointment to the function and evaluation of work of judges and public prosecutors. Progress has also been made in terms of transparency in that field, primarily through the availability of information relevant to the process and evaluation results on the VSS and DVT websites. Since the adoption of the Rulebook on criteria, standards, procedures and authorities for the assessment of the work of judicial assistants by High Judicial Council in 2016, the position of the judicial assistants has been improved to some extent as well.

The greatest progress at general has been made related to the transparent functioning of the HJC and the SPC, as bodies guaranteeing the independence and autonomy of courts and judges, public prosecutors and deputy public prosecutors. Namely, through the amendments and supplements to laws and adoption of bylaws, the publicity and transparency of work of the Councils has been significantly improved, making the judiciary and its work seem more accessible to the professional, as well as the general public.

There is a continuous process of strengthening professional and analytical capacities of the HCC and the SPC. In light of the Constitutional Court decision from October 2018 and the final version of the Working Draft Amendments to the Constitution of the Republic of Serbia in the field of judiciary published on 15 October 152018 assessed by the Venice Commission, the Working group for the division of the competences between Ministry of Justice and Councils formed in January 2109 will propose the sustainable legislative solution regarding transfer of competences from the MoJ to the HJC and the SPC.

IMPARTIALITY AND ACCOUNTABILITY

For the purpose of the establishment of an effective mechanism allowing the Councils to react against political interferences, The High Judicial Council, at the session held on 25 October 2016, adopted amendments to the Rules of Procedure of the High Judicial Council that stipulates the procedures of public reactions of the High Judicial Council in cases of political interference in the judiciary. Also, the State Prosecutorial Council adopted the Regulation on work of the State Prosecutorial Council in March 2017, which established the institute of the Commissioner for autonomy, stipulated that this function will be performed by the Deputy President of State Prosecutorial Council and prescribed the procedure of the State Prosecutorial Council public reactions in cases of political influence to work of public prosecution office, regularly (once in a year) and extraordinary (if needed). The Deputy of the President of State Prosecutorial Council started to perform duties of the Commissioner for autonomy in April 2017 and is being very active since then. The Commissioner for autonomy proceeded in several cases, he has been filing reports to the State Prosecutorial Council and has been informing the public on cases of forbidden influence to work of the public prosecution office, where, in opinion of certain prosecutorial office holders, were endangered independence of the public prosecution office and professional integrity of prosecutorial position holders.

In order to raise awareness that reluctance of criticizing court decisions (in particular by politicians) is an important component of strengthening the full respect of court decisions, the Government has adopted the Conclusion for passing the Code of conduct for Members of the Government of the Republic of Serbia, which regulates commenting judicial decisions and procedures in January 2016. The National Assembly has adopted the Code of conduct for members of Parliament (MPs) relating to restrictions on commenting on judicial decisions and proceedings in July 2017. In accordance with the new Law on Police (Article 45, paragraph 3) on the proposal of the Ministry of Interior, the Government of the Republic of Serbia adopted a completely new Police Code of Ethics. In this regard, the new Code of Police Ethics contains the general norm "Protection of official information".

A system for monitoring and promoting processing of misdemeanor cases of public violations of presumption of innocence (art. 73 from Law Public information and Media) as well as tracking records concerning this type of proceedings provided by the Supreme Court of Cassation, in cooperation with the Misdemeanor Court of Appeal, has successfully been established.

Civil society and professional associations are continuously involved in defining future steps in the reform process, as well as in monitoring the implementation of reforms. From the very beginning of the current process of constitutional amendments, the Ministry of Justice, with the support of the Office for cooperation with civil society, has involved civil society organizations and professional associations in its work by means of public calls and a series of round tables organized throughout Serbia. Despite some disagreements during the public  debate caused by the significance and the delicacy of the topic, the civil society organizations and professional associations gave a great contribution in this process. The final version of the Working Draft Amendments to the Constitution of the Republic of Serbia in the field of judiciary published on October 15, 2018 was the result of the implementation of large number of suggestions made by the civil society organizations and professional associations.

Ethics Committee within High Judicial Council was established in April 2016. The High Judicial Council adopted the Rules of Procedure of the Ethics Committee in September 2018. Judges can find relevant information regarding violation of provisions of Code of Ethics on the internet site of the High Judicial Council, via decisions of High Judicial Council in this matter. All decisions are anonymized. The State Prosecutorial Council has established Ethics Committee in April 2014 and adopted the Rules of Procedure of the Ethics Committee in July 2018. At the same session the State Prosecutorial Council established the Working group for amendment of the Code of Ethics so drafting of the text is in course, and it will be followed by guidelines for its implementation. The next step is the transformation of Ethics committees into the permanent bodies within the Councils, which demands legislative changes.

The legal framework and transparency of its implementation have been improved to a certain degree during the implementation of the APCH23 and the NJRS 2013-2018 with regard to the work of disciplinary bodies within the Councils. Disciplinary bodies of the High Judicial Council file yearly report to the High Judicial Council regarding their work. These reports can be found on internet site of the High Judicial Council. The Disciplinary Prosecutor also yearly submits the annual reports to the State Prosecutorial Council. The proposal of the improvement of the legal framework on disciplinary responsibility for judges and public prosecutors, based on the analysis findings, will be one of the tasks of the formed Working groups for the alignment of the subsequent judicial legislation with new constitutional provisions.

Seminars on ethics are part of the regular program of continuous education conducted by the Judicial Academy, and within it, cycles of education are being conducted annually for judges, public prosecutors and deputy public prosecutors. Through these numerous trainings and the availability of relevant materials on the VSS and DVT websites, awareness of the rules of ethics and mechanisms of disciplinary responsibility is raised.

PROFESSIONALISM / COMPETENCE / EFFICIENCY

It is obvious that efficient justice system could not be managed without comprehensive case management system and that is why a much effort is given to finish roll-out of modern efficient system for courts of general jurisdiction (named SAPS) in close cooperation with EU. SAPS software enables management of cases that covers the entire course and life cycle of the case, from filing an initial act to final decision and archiving. SAPS is a centralized application that is installed and run from the SCC for all associated courts.

The Analysis of current ICT systems in terms of hardware and software has been completed in September 2017 as a part of EU funded project. As a previous step, the Guidelines has been adopted by the ICT Sectorial Council that includes representatives of all judicial stakeholders on its session held on April 13th 2016. Having in mind the importance of this field, continuous capacity building activities of the e-justice sector are being implemented.

In September 2017 Judicial Efficiency Improvement Project (JEP) expert’s team developed and proposed over 80 tickets for the AVP application to stop the bad and invalid data entry into the AVP database. The implementation of the developed methodology was fully realized in 2017 and 2018. These tickets concern various types of common mistakes during data entry, harmonization with current Court rules book and Criminal procedure code and missing registries in electronic form. During 2017, trainings were held and the validation of software on data entry forms was significantly improved, which in this way allowed to drastically reduce the number of incorrect data in the databases in the courts.

Through Judicial Efficiency Improvement Project (JEP), Ministry of Justice has successfully developed and implemented the formula for evaluating cases by weight in twenty higher and founding courts in Serbia. In order to distribute cases evenly in cases of criminal, civil and labour disputes, the formula has been successfully identified and specifically assigned to judges for cases requiring more work. List of implemented courts with formula for evaluating cases by weight: Basic court in Zrenjanin, Basic and Higher court in Novi Sad, Basic and Higher court in Kragujevac, Basic court in Valjevo, Basic court in Cacak, Basic court in Leskovac, Basic court in Kraljevo, Basic court in Sombor, Basic court in Vranje, Basic court in Sremska Mitrovica, Basic court in Pozarevac, Basic court in Sabac, Basic court in Negotin, Basic court in Uzice, Basic and Higher court in Nis, Third Basic court in Belgrade and Higher court in Subotica.

Functionality of electronic scheduling of the hearings and data collection on the adjournments and the reasons for them are developed and implemented within the AVP application for the basic courts, the higher courts, the commercial courts and Commercial Appellate Court.

Furthermore, it is developed and are in process of implementing modern centralized case management system for commercial courts (named SIPRIS – System of Commercial courts in Serbian – SIstem PRIvrednih Sudova ), due to belief that it is important to use every possible instrument to speed up solving commercial dispute cases. SIPRIS, case management software system for commercial courts, is investment in commercial courts worth of 235,000,000 RSD (2,000,000 EUR). Contract regarding implementation SIPRIS was signed in 2018 and currently central servers for applications were being installed in Data Center of the MoJ. Main characteristic of SIPRIS, being centralized system, is that it enables administrating case status search among different courts, etc. from one access point. Key new functionality is barcode technology for registering filings to court cases which enables speeding up scanning process and routing filings to court case. Also, linking first instance decisions with decision by appellate courts is automatic. SIPRIS comprises case law of commercial courts with universal descriptors and it is prepared for data exchange with The Jurisprudence portal. It also contains a calendar with automatic and customized notifications and can generate predefined but customized reports. In addition, it is linked with registers of other institutions for data exchange.

The main thing concerning efficiency relating to court data is that in June 2019 the project of Central Court Statistics Business Intelligence Solution based on Oracle Business Intelligence technology is being closing off. The project has been conducted in cooperation with all the relevant stakeholders within the judiciary. Project scope covered implementing advanced tool for managing court statistics with electronic system for keeping central records on court statistical data. Goal was to improve judicial efficiency in the process of collecting court reports and their analysis due to fact that the system obtains data fully automatically from court case management program - SAPS and AVP.

For the purpose of electronic data exchange between judicial bodies and other government institutions, Ministry of Justice developed and implemented the Judicial Information System. The Judicial Information System caused significant improvements regarding speed and cost of processes. Through the Judicial Information System, all courts, public prosecutors, notaries and public enforcement officers can electronically check data from the Central Registry for Compulsory Social Security (data on compulsory social insurance paid by the employer for a certain period of time); Misdemeanor records (convictions); Administration for the Enforcement of Criminal Sanctions (whether a person is serving a sentence in a prison); Ministry of Internal Affairs (data on residence and residence history); Birth registers (data from birth registers, deceased, married); Business Registry Agency (data on natural and legal persons associated with companies, and the history of their functions); The Republic Geodetic Authority (searching for data on whether a person owns a real estate on the territory of the RS); General jurisdiction courts (Register of persons deprived of parental right, Register of persons participants in proceedings); Pension and Disability Insurance Fund (Data on paid pensions, assistance and care benefits and physical impairment benefits); Register of real estate transactions containing data on notarial records and solemnization by contracts on real estate transactions, data on notaries public making records or confirming the deeds, data on courts performing verification of the entry into the Registry; National Bank of Serbia (Single Register of Accounts for Legal Persons and Entrepreneurs, Register of Received Decisions and Register of Enforcement Debtors). According to Ministry of Justice statistics, since the commencement of the system operation users made 1.243.180 electronic inquiries, thus replacing 2.486.360 memos and saving RSD 291.208.894,72 for budget (postal services, pecuniary value of engaged labor (average gross salary). It speeds up average court proceeding length for approximated period from 3 to 6 months.

During the implementation of the APCH23, significant efforts have been made to improve the competence of the holders of judicial functions. A great attention has been dedicated in trainings of the representatives of new judicial professions, such as public enforcement officers, public notaries, mediators, and of the other judicial staff as well. Judicial Academy adopted numerous acts that regulate the training dynamics and contribute to its quality. New programs of continuous training were established and the capacities of the Judicial Academy were significantly improved.

The National Assembly passed the Law on Amendments to the Law on the Judicial Academy in December 2015. Amendments to the Law on Judicial Academy provided as follows: the Judicial Academy would be able to implement the professional advanced studies programmes intended for the enforcement officers, public notaries, public notaries’ assistants and public notaries' junior clerks/trainees, based on the contract made with the Chamber of Enforcement Officers, i.e. Chamber of Public Notaries; Programme Council composition was extended by including the representative of the initial training users’; the final exam board composition was determined and the fee of mentors engaged in the initial training programme would be aligned to the fee paid to the mentors engaged in the programmes intended for judicial and prosecutorial assistants and trainees; it was provided that the  initial training attendance would be regarded as an experience in the legal field and it was determined in which cases the permanent training would be obligatory (shift in specialized training, major modification of regulations, introduction of new working methods, resolving inefficient performance of judges and the public prosecutor assistants discovered by evaluation of their work results).

The National Assembly passed the Law on Amendments to the Law on Judges in May 2015. By means of modifications and amendments to the Law on Judges the rules were prescribed on the basis of which the High Judicial Council would particularly evaluate the completed initial training at the Judicial Academy and determine the candidates’ competence and training for the first appointment to the judicial post in basic court and misdemeanor court verified in an exam organized by the High Judicial Council. The candidates who completed initial training with the Judicial Academy are exempted from the obligatory exam and the criteria for competence and qualification evaluation for judicial position is the final exam grade achieved in the basic training at the Academy.

The National Assembly passed the Law on Amendments to the Law on Public Prosecution, in December 2015. By means of modifications and amendments to the Law on Public Prosecution the rules were prescribed on the basis of which the State Council of Prosecutors would particularly evaluate the completed initial training at the Judicial Academy and determine the candidates’ competence and qualification for the first appointment to the post of the deputy public prosecutor, prescribing that the competence of the candidate running for the deputy public prosecutor post for the first time would be  verified in an exam organized by the  State Council of Prosecutors. The candidates who completed initial training with the Judicial Academy are exempted from the obligatory exam and the criteria for competence and qualification evaluation for judicial position is the final exam grade achieved in the basic training at the Academy.

In 2018 the ninth generation of beneficiaries of the initial training of the Judicial Academy has been enrolled. During the conduction of the last entrance exam, the Judicial Academy has for the first time applied live broadcasting during the whole entrance exam, including the written part. In the aim of transparency, this method of activity implementation has been realized firstly during the entrance exam for the judicial and prosecutorial trainees. Within USAID's Judicial Academy support program following systems have been developed during the period of the implementation of the APCH23: a system for the selection and improvement of mentors and lecturers and a system of new evaluations of mentors' work as well as initial training beneficiaries. A new web portal of the Judicial Academy was established and the Judicial Academy has created a database of decisions of the ECHR under the name e-JURIS / e-CASE which was formed as an e-ACADEMY module. Adequate building for permanent accommodation of the Judicial Academy was obtained on 9th April 2015 by Serbian Government decision and its renovation started in January 2019 with the support of EU funded projects. The new premises should fully correspond to the needs of the Judicial Academy.

Activity regarding the development of monitoring system concerning quality of initial, continuous and specialized training that implies bidirectional evaluation system that would allow the assessment of the results of training or degree of advancement of knowledge of the participants, as well as the assessment of the quality of the program and trainers has being successfully implemented. Cooperation with the Institute for quality assurance of education only asserted our belief that it is necessary to well determine strategic planning. Both initial and continuous educations are conducted at the Judicial Academy since its establishment. At initial education, candidates are evaluated by mentors and at the end of education they are passing the final exam, simulation of trial, evaluated by the commission. Continuous education is being evaluated through standard questionnaires, evaluating the following aspects, quality of lecturers and conditions of work.

The Academy Program Council determined priority topics for education annually based on, among other things, performance evaluation. The programs are regularly being submitted to the High Court Council and the State Prosecutorial Council for adoption, and they are also having in mind performance evaluations when approving the programs.

A significant step in dealing with the problem of large number of backlog cases was the adoption of the Unified Backlog Reduction Program in the Republic of Serbia in December 2013 and the Special Program of Measures for Reduction of Old Enforcement Cases in the Courts in the Republic of Serbia for the period from 2015-2018 in November 2014. Teams in charge of reduction of backlogged cases were established in all courts. After that, in August 2016, the President of the SCC passed the Amended Unified Backlog Reduction Program in the Republic of Serbia for the period 2016-2020. The fact that this is a recognized and acknowledged measure is reflected in the APCH23, since the Unified Backlog Reduction Program is considered a dynamic document, which is why it needs to be “amended and improved in accordance with the initial results of its application and based on the conclusions from the regular sessions of the Working Group for the implementation of the Unified Backlog Reduction Program”. In the following period, in cooperation with the Judicial Academy, a training program for judges’ skills should be further developed – case management and drafting of an individual judge’s plan for reduction of backlog cases. The Working Group for monitoring the application of the Amended Unified Backlog Reduction Program at the meeting held on 5 December 2018 noted that the trend of backlog reduction continued as at the beginning of the year in all courts in the Republic of Serbia there were 1,911,086 cases pending and on 30 November 2018 there were 1,459,442 cases pending. On the other hand, in almost all courts there was an increase in the number of cases received, which also affected the burden of judges. This trend can also be noticed in the basic courts (which act in the matter of enforcement): it was noted that on 1 January 2018 there were 1.095.108 cases pending, that 961.345 cases were resolved, that 847.333 new cases were received, and that on 30 November 2018  there were 981,096 cases pending.

Regarding efficiency and the relieving the burden off the courts, the significant step was made by introducing the system of bailiff/enforcement officers and the public notary system into the Serbian judiciary. As at 1 January 2019, a total of 199 public notaries and 217 public enforcement officers were appointed. The Chambers of Public Notaries and the Chamber of enforcement officer have also been established and since then they both have very active role in the promotion of these relatively new judicial professions in the Republic of Serbia. The Judicial Academy is in charge of the organization of the trainings for the representatives of public notaries and bailiffs on basis of the agreements signed between the Chambers and the Judicial Academy. Memorandum on Cooperation was signed between the Judicial Academy and the Chamber of Enforcement Agents for the purpose of training of enforcement agents on 21 March 2015. Memorandum on Cooperation was signed between the Judicial Academy and the Chambers of Public Notaries for the purpose of training of public notaries on 22 March 2015.

Implementation of the Law on Enforcement and Security which was enacted in 2016 of an EU funded RoLE project, is being closely monitored and further improvements to the Law are currently under way in order to address the needs of improving practice. The Working Group for amending the Law has relentlessly worked since its establishment in March 2018 addressing identified problems such as jurisdiction of the courts and enforcement agents in the enforcement procedure, costs and fees of the procedure, legal remedies, service of documents, the sale procedure of the movable and immovable property, as well as the proportionality in the enforcement proceedings. Particularly, when it comes to public auction it has been determined that this procedure has to be greatly improved in order to achieve a more transparent and fair procedure. Therefore, one of the main amendments of the Law will be the new public auction procedure that will be conducted electronically through an E – Auction platform. The E – auction, as such, save time, increases the number of buyers and provides the judicial system with a higher level of regularity. The public discussion has commenced in May 2019. It is expected the mentioned amendment to the Law to be adopted by the end of the 2nd quarter of 2019.

For the purpose of application of provisions of the competences of notaries to act as a trustee of the court, the Ministry of Justice, Supreme Court of Cassation and High Judicial Council have enacted on 13 May 2016 “Instructions for the Implementation of Provisions of Arts. 30a and 110a of the Law on Non-Contentious Procedure and Art. 98 of the Law on Notary System”, enabling the extension of notary competences to inheritance proceedings, thereby alleviating courts of this non-contentious judicial workload.

The Ministry of Justice continuously monitor and analyse judicial statistics related to the entrusting of the implementation of inheritance proceedings and undertaking of actions in non-contentious proceedings. Regarding the transferal of non-judicial non-contentious cases to notaries, it can be concluded that the positive trend is continuous, having in mind that in the period from 1 July 2018 to 31 December 2018, almost 69.317 cases have been transferred to notaries, while in the period from 1 January 2018 to 30 June 2018, 68.947 cases have been transferred to notaries.

Following the analysis of appropriate solutions for improving the registration process in the real estate cadastre, i.e. for the improvement of the legal framework for cooperation of notaries, courts and enforcement officers with the Republic Geodetic Authority, the National Assembly has adopted the Law on procedure of registration with the Cadaster and Leads („Official Gazette RS“ number 41/18) dated on 31 May 2018. Based on the mentined law, the Government of the Republic of Serbia has adopted the Regulation on the mechanisms for delivery of documents in the procedure of registration with the Cadaster and the mechanisms of issuing of the Cadaster extract electronically (“Official Gazette RS number: 50/18”) dated on 29 June 2018.

According to the Law on Certification of Signatures, Manuscripts and Transcripts ("Official Gazette of RS", No. 93/14, 22/15 and 87/2018) since March 1st 2017 the public notaries have taken over new responsibilities and duties.

During the period of the implementation remaining by-laws and Chamber regulations have been adopted and the harmonization with the valid provisions of the Law on Public Notaries has been completed.

On 17 December 2018, by virtue of Article 119 of the Law on Notaries and of Article 15 of the Programme of Training of Notaries, the Executive Board of the Chamber adopted the Plan of Implementation of the Programme of Training of Notaries for 2019, all for the purpose of establishing of the continuous professional improvement of notaries, notary assistants, associates, and notary interns and the standardization of the notary practice.

The Supreme Court of Cassation in December 2016 adopted Rulebook on the replacement and omission (pseudonymization and anonymization) of data in court decisions. Rules governing the method of substitution and omission of information in judicial decisions of the Supreme Court of Cassation, including the method and techniques of anonymization / pseudonymisation in decisions in electronic and written form are defined by this document. The regulations in relation to the rules of anonymity of court decisions were adopted at the level of all appellate courts as well.

The activities of the Supreme Court of Cassation regarding the improvement of the consistency of the jurisprudence have been continued. Having in mind that the final version of the Working Draft Amendments to the Constitution of the Republic of Serbia gives a special place to this topic, the Working groups for the alignment of the subsequent judicial legislation with new constitutional provisions, will develop a proposal for more detailed regulation of this issue.

A steady increase of mediation referrals and mediation proceedings has been noted since the enacting of the Law on Mediation in Dispute Resolution (“Official Gazette of RS” no. 55/2014) and, in particular, since the issuing of the Joint Guidelines for the Improvement of Mediation in the Republic of Serbia on June 28th, 2017 by the Supreme Court of Cassation, the High Judicial Council and the Ministry of Justice. The issuing of the Joint Guidelines has been followed by various promotional activities by the Ministry of Justice and the Judicial Academy, and notable efforts by certain courts, such as the Second Basic Court in Belgrade and Basic Court in Kragujevac, within the framework of the Mediation Week, organised in October 2017 and the Basic and Higher Courts in Niš. Nonetheless, the statistics show that greater demand for mediation must be made in order to achieve the objective of the 2008 Mediation Directive. Various protocols have been concluded following the Joint Guidelines, such at the Protocol on Cooperation between the Higher and Basic Courts in Niš, on the one hand, and the Public Utility Company JKP Niš; Protocol on Cooperation to Enhance the Use of Commercial Mediation between the Serbian Chamber of Commerce and the Commercial Court of Appeal; Guidelines for the Promotion of the Procedure for Concluding and Implementing Out-of-Court Settlement in Procedures for the Protection of the Right to Trial in a Reasonable Time, etc.

By 17 May 2019, 965 mediators have been registered by the Ministry of Justice, out of which almost a third is from Belgrade (366), followed by Niš (128). There are 2016 lawyer-mediators (1/4th of all mediators), 27 judges, 7 judicial assistants and over 650 various other legal professionals. By 17 May 2019, 15 organizations have received licenses for conducting mediators’ training, but up to now, only 12 organizations conducted the various accredited training, with a total number of participants being 2,393. No proposals for revoking of licenses of mediators have been submitted to date to the Ministry of Justice Commission for Revocation of Mediation Licenses.

With respect to legislative changes, the Law on Amendments to the Law on Peaceful Labor Dispute Resolution, enacted in June 28th, 2018, significantly expanded the scope of the Republic Agency for Peaceful Settlement of Labor Disputes in accordance with its acquired experiences and practices.The competence for individual labor disputes was also expanded to include the disputes arising from: payment of salaries/wages, allowance of salaries/wages in accordance with the law, payment of severance pays during retirement, working hours and exercising rights to annual leave. An important novelty in the Law is the precise wording that the arbitrator should in the course of the proceedings indicate to the parties in  the dispute the possibility of an amicable settlement of the dispute.

Moreover, the Law on Amendments and Supplements to the Law on Court Fees ("Official Gazette of RS", no. 95/2018), applicable from 1 January 2019, further encourages parties to resolve their disputes by amicable means, through mediation, negotiated settlement, court settlement or any other amicable way. These amendments postpone the collection of court fees in order to leave the parties the opportunity to once again consider the amicable resolution of the dispute, once the court proceedings have been initiated. Through these provisions, which have been drafted by the Ministry of Justice, the state offers financial incentives to the parties to consider other viable dispute resolution options early in the court proceedings by exempting them from paying all relevant court fees if they achieve a settlement by the time of the first hearing.

Recognising the need for coordinated, joint, continued multi-annual efforts to establish a viable and sustainable mediation system, the Ministry of Justice has initiated a strategic approach to improving the use of mediation in August 2018 by addressing other institutions, such as the National Bank of Serbia and the Agency for Amicable Dispute Resolution, so as to seek to together find best ways to improve the use and quality of mediation in the fields of their respective competences. Moreover, the Working Group for drafting of amendments to the Law on Mediation in Dispute Resolution and accompanying bylaws has since January 2019 worked intensively on a new legal framework, likewise supported by EU funded projects, with the main objectives of improving the availability and quality of mediators, and increasing the number of mediations, i.e. finding modalities which would allow for achieving the objective of the 2008 Mediation Directive.

The implementation of the Criminal Procedure Code from 2011 has been successfully monitored, particularly within the work of the Commission for the Implementation of the NSRP 2013-2018. The quarterly reports on the implementation of the new Criminal Procedure Code elaborated by the RPPO have been widely discussed at the meetings of the Commission for the Implementation of the NSRP 2013-2018. The introduction of the prosecutorial investigation and the institutes of the deferring criminal prosecution and the plea agreement have made a criminal system much more efficient.  At this point in time, the working group will be formed to do fine tuning of the provisions and propose corrective measures where needed.

WAR CRIMES

The legal framework in Serbia encompass: Law on Organization and Competence of Government Authorities in War Crimes Proceedings („Official Gazette of the RS“ No. 67/03, 104/2009, 101/11- state law 6/15) established an institutional framework for the prosecution of war crimes; Criminal Code (“Official Gazette of RS”, No 121/12, 104/13, 108/14 and 94/16 ); Criminal Procedure Code (“Official Gazette of RS” No. 72/11, 101/11, 121/12, 32/13,45/13 and 55/14); Law on Mutual Legal Assistance in Criminal Matters (“Official Gazette of RS” No.20/2009); Law on Protection program for participants in Criminal Proceedings („Official Gazette of the RS“ No. 85/2005); Law on Cooperation with the ICTY („Official Gazette of the SRJ“ No. 18/2002, and “Official Gazette of SCG” No. 16/2003); Law on Migration Management („Official Gazette of the RS“ No. 107/2012); Decision on Establishing the Commission for Missing Persons of the Government of the Republic of Serbia („Official Gazette of the RS“ No. 49/06, 73/06, 116/06, 53/10 and 108/12); Memorandums on cooperation concluded between the state authorities of the Republic of Serbia with the competent authorities of the countries of the region (Croatia, Bosnia and Herzegovina, Montenegro) and Protocol on cooperation with EULEX, with the purpose of direct cooperation, and more efficient exchange of information regarding war crimes and perpetrators. Jurisdiction for War Crimes in Serbia: 1) Criminal offences from art. 370 through 386 of the Criminal Code; 2) Serious violations of International Humanitarian Law committed in the territory of the former Yugoslavia since January 1st 1991 stipulated in the Statute of the International Criminal Tribunal for the Former Yugoslavia; 3) Criminal offence from Art. 333 of the Criminal Code - assistance to the perpetrator after the commission of crime, if committed in relation to criminal offences from point 1) and 2) of this Article. Institutional framework: War Crimes Prosecutor’s Office; Higher Court, War Crime Department; Ministry of the Interior: War Crimes Investigation Service, Witness protection unit; Victims and Witnesses assistance and support Section.

The Government of the Republic of Serbia was of the opinion that it is necessary to adopt a strategy to prosecute war crimes at the national level, whose objectives and activities would provide a comprehensive and clear strategic framework for improving all areas where problems have been identified, as a clear reflection of the undeniable commitment of the Republic of Serbia to the effective punishment of war crimes. On February 20th 2016, the Government of the Republic of Serbia has adopted the National Strategy for Prosecution of War Crimes expressing its full support to all local judicial and executive bodies involved in the process of investigating, raising indictments for the war crimes, as well as all international and local organizations that monitor and report on these proceedings as independent observers.

In order of monitoring of the National Strategy, on August 26th 2017 by the decision of the Government of the Republic of Serbia, the Working body for Monitoring of the Implementation of the National Strategy was established. The members of the Working body are representatives of all institutions relevant for the implementation of the National Strategy. The working body develops conclusions and recommendations to competent institutions and it submits its reports on the implementation of the Strategy on a quarterly basis to the Secretariat for the Implementation of the Action Plan for Chapter 23 and to the Government of the Republic of Serbia. Five reports were adopted so far, covering the period until December 2018. It is expected that the 6th report that will be referred to the period starting from January 1st 2019 until March 30th 2019 will be adopted by the end of May 2019. The reports are published on the web page of the Ministry of Justice.

The draft version of the Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023 was presented at the expert meeting that was held on March 12th  2018 at the premises of the Office of the War Crime Prosecutor in Belgrade. The meeting was attended by the judges, prosecutors, lawyers, representatives of all state bodies involved in prosecution of war crimes, as well as representatives of the OSCE Mission to Serbia. Additionally the Office of the prosecutor of the Mechanism for International Criminal Tribunals gave its full support to the working version of the Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023. The Prosecutorial Strategy for War Crimes Investigation and Processing 2018 – 2023 was adopted at the Office of the War Crimes Prosecutor management board meeting of 04 April 2018.

New War Crime Prosecutor was elected by the National Assembly of Republic of Serbian on 15 May 2017 after what she took over the duty of the War Crime Prosecutor on 31 May 2017. The OWCP team currently consists of nine deputy war crimes prosecutors. Additionally, since 01 November 2018, a military analyst has been engaged as part of the OWCP team. The capacity building of the War Crimes Prosecutor's Office is constantly in progress.

Research into the ICTY/MICT archives – including the databases of the ICTY/MICT Prosecutor's Office – continued throughout the period of the implementation of the APCH23. The OWCP Liaison Officer is responsible for the the identification of evidentiary items and other relevant documents, their verification for use in cases handled by the OWCP and their timely delivery to this Office.

The cooperation between the Prosecutor's Office and the War Crime Investigation Service has been improved. The War Crimes Prosecutor's Office formed joint investigation teams with members of the War Crime Investigation Service, having introduced a new methodology in the work. The joint teams hold regular meetings for the purpose of efficient operational treatment. The Prosecutor's Office established working procedures between the War Crimes Prosecutor's Office and the Service, which are necessary for the purpose of harmonizing activities during the procedure in each case.

The strengthening institutional and administrative capacities of the War Crime Investigation Service within the Ministry of Interior Affairs by receiving adequate accommodation facilities - more working premises and adequate space for storing files in the physical form as well as new official vehicles, improved the efficiency of the Service.

The Government of the Republic of Serbia issued a decision on forming a Commission for the consideration of facts that have arisen during investigations conducted on the occasion of murder of journalists, including murders that were committed during the armed conflict in former Yugoslavia in the period from 1991 until 1995, and murders that were committed in the territory of Kosovo and Metohija in the period from 01 January 1998 until 31 December 2000.

The form and contents of the OWCP web presentation have been improved in order to update the public on the ongoing OWCP activities related to particular cases, on the implementation of relevant strategic documents and on other developments of importance for the work of this Office. Due to its multiple advantages, the OWCP web page – with its continuous improvements – is the major source of information and a reliable instrument for the presentation of data relevant to the OWCP performance, free and accessible at any time. In order to check if all war crimes reports have been properlly addressed, the OWCP prepared a report on its overall performance further to the crime reports received since 2003. The report was presented at the OWCP official website and thus made available to the public.

The Supreme Court of Cassation regularly publishes decisions on war crimes cases on its website. Also, a review of the criminal policy in war crimes proceedings for 2015, 2016 and 2017 is published on the website of the High Court in Belgrade.

The Witness Protection Unit has been granted a status of a special unit of police by the Decree on Special and Special Police Units ("Official Gazette of RS" No. 47/18 of 20.06.2018 and 59/18 of 31.07.2018) and reorganization of the WPU was carried out.

In compliance with the Act on Personal Data Protection, the OWCP has taken measures for the protection of data against unauthorized access, publishing or any other abuse. All members of the OWCP staff have signed the statement on the preservation of secret and confidential data within the meaning of the Data Secrecy Act and other legal / by-legal documents. A binding instruction on the protection and preservation of secret / confidential information, which is included in this statement, has been handed in to all employees. The instruction includes the overview of the applicable substantive regulations concerning the handling of secret / confidential data, obligation of the protection / preservation of such data, and the list of the criminal law provisions concerning the conduct of elected, appointed and employed staff members in contravention of their legally prescribed obligations.

Two important regional conferences considering, inter alia, the topic of sentencing policy of the war crimes were held during the period of the implementation of the APCH23. First expert meeting has been held on December 11th, 2015 where the representatives of all relevant institutions in the area of war crimes investigation and proceeding from region and ICTY took part in the discussion. Second regional conference on the subject "Cooperation, criteria and standards in the persecution of perpetrators of war crimes" has been held from 20th to 22nd May 2019 in Belgrade. The High Delegations of the Prosecutor's Offices of Bosnia and Herzegovina, the Federation of BiH, the Brčko District, the Una-Sana Canton, the State Attorney's Office and the Special Prosecutorial Offices of the Republic of Croatia, the Special Prosecution Office of Montenegro, the War Crimes Prosecutor's Office of the Republic of Serbia and the Prosecutor's Office of the Mechanism have participated at this Regional Conference. The conference was organized by the War Crimes Prosecutor's Office of the Republic of Serbia  and UNDP in cooperation with the United Kingdom and Italy. The Conference participants gave the following joint statement on the main conclusions and commitments which has been published in the website of the War Crime Prosecutor Office. The participants agreed that there is still a need for more war crimes proceedings in the conflicts on the territory of the former Yugoslavia and that cooperation between their prosecutors is crucial for achieving this goal. In a desire to significantly improve existing cooperation, the participants agreed to identify specific cases that would be suitable for transfer between their prosecutors' offices, and to start the necessary conversations in this regard. It was also concluded that it is necessary to raise the level of confidence of victims in regional cooperation. To this end, the Prosecution of the MICT will, if necessary, assist the Regional Prosecutor's Offices in the work on the taken cases. The Prosecutor's Offices from Bosnia and Herzegovina, Montenegro and Serbia expect the Prosecution of the MICT to continuously assist in strengthening their capacities and support in the exercise of the mandates entrusted to them. Finally, the participants emphasized the importance of regular communication between their prosecutors. One of the conclusions also was that it is necessary to organize periodicaly  regional trainings of public  prosecutors on which the regulations and jurisprudence from all countries will be presented, and which will be the opportunity to exchange opinions and remove the decisions that make the problem in practice, as proposed by the representative of the Prosecutor's Office of Bosnia and Herzegovina. In parallel, the War Crimes Prosecutor's Office of the Republic of Serbia adopted its conclusions related particularly to the question of proportionality of sentences and a sentencing policy. It is noted that one of the challenges that must be overcome is the equalization of the jurisprudence regarding the punishment of war crimes perpetrators, in the ICTY (MRMKS) and in the countries in the region, and overcoming the problems that have arisen in connection with this issue.

| 1.1. INDEPENDENCE |  |  |
| --- | --- | --- |
| RECOMMENDATION FROM THE SCREENING REPORT | OVERALL RESULT | IMPACT INDICATOR |
| 1.1.1. With the support of external experts, Serbia should make a thorough analysis of the existing solutions/possible amendments to the Constitution bearing in mind the Venice Commission recommendations and European standards, ensuring independence and accountability of the judiciary. Changes should include, inter alia, the following points: - The system for the recruitment, selection, appointment, transfer and termination of judge’s office, presidents of Courts, and prosecutors should be independent of political influence and remain of the responsibility of the High Judicial and Prosecutorial Councils. Entry in the judiciary shall be based on merit-based objective criteria, fair in selection procedures, open to all suitably qualified candidates and transparent in terms of public scrutiny. The High Judicial Council and the Prosecutorial Council should be empowered with leadership and the power to manage the judicial system, including when it comes to immunities. They should have a pluralistic composition, without involvement of the National Assembly (unless solely declaratory), with at least 50% of members stemming from the judiciary, representing different levels of jurisdiction. Their elected members should be selected by their peers; - Legal or executive authorities should not have the power to supervise or monitor operations of the judiciary; - Reconsider the probation period of three years for candidate judges and deputy prosecutors; - Clarify the grounds for the dismissal of judges; - Clarify the rules for terminating the mandate of Judges of the Constitutional Court; IBM: Serbia adopts new Constitutional provisions bearing in mind the Venice Commission recommendations, in line with European standards and based on a wide and inclusive consultation process. Serbia subsequently amends and implements the Laws on the Organisation of Courts, on Seats and Territorial Jurisdiction of Courts and Public Prosecutors’ Offices, on Judges, on Public Prosecutor’s Office, on the High Judicial Council and on the State Prosecutorial Council as well as the Law on Judicial Academy | Adopted new Constitution and judicial laws aligned with new Constitution in a process in which the representatives of the judiciary and the profession were actively and equally involved,, taking into account the recommendations of the Venice Commission and European standards, ensures the independence of the judiciary from political influence, maximally restricting influence of legislative and executive powers in the process of recruitment, selection, appointment, transfer and termination of the judge’s office, presidents of the courts, and (deputy) public prosecutors, and which must be based on precise criteria. Constitution and judicial laws guarantee, to all candidates, without discrimination, entrance in the judiciary based on merit-based objective criteria, fair in selection procedures, open to all suitably qualified candidates and transparent in terms of professional and public scrutiny. The role of the High Judicial Council and the State Prosecutorial Council in terms of the management of the judiciary, as well as in the supervision and control of the judiciary has been strengthened; their composition encompasses at least 50% of members from the ranks of judges and public prosecutors; Elected members of the High Judicial Council and the State Prosecutorial Council are elected by their peers and represent different levels of jurisdiction | - The judiciary in the Republic of Serbia is completely independent which is confirmed in the positive opinion of the Venice Commission on the new Constitution and the legal provisions relating to the judiciary; - Judges and prosecutors are elected on the basis of their expertise and merit, which has an overall positive impact on the quality and efficiency of the judiciary; - The High Judicial Council and the State Prosecutorial Council successfully manage the judiciary with adequate financial resources, competent and professional personnel elected with necessary competences, selected based on clear criteria, while respecting the principles of transparency and accountability; - All of the above is confirmed in the positive Annual report of the European Commission's on the progress of the Republic of Serbia, including the improvement of the provisions of the Constitution. |

| ACTIVITIES |  | RESPONSIBLE AUTHORITY |  |  | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1.1.1. | Conducting procedure for Constitutional amendments in the area of judiciary (Article 203 Constitution of RS and Art. 142-149 Rules of Procedure of the National Assembly), which implies the following steps: - Submitting proposal for the amendments to the Constitution, with an explanation of the proposal by an authorized proposer (Article 142 par.2 of the Rules of Procedure) - Determination of the competent committee that the proposal for the amendments to the Constitution is submitted by a proposer authorized by the Constitution and in a prescribed form (Article 142 par.2 of the Rules of Procedure) - Debating in the National Assembly the submitted proposal at its sitting (Article 143 par.1 of the Rules of Procedure) - Decision of the National Assembly on the proposal for the amendment to the Constitution (Article 143 par.3 of the Rules of Procedure) - Determination of the authorized committee of the draft proposal of an act on the amendments to the Constitution, with explanation, and a draft constitutional law for its implementation (Article 144 par.1 of the Rules of Procedure) - Decision of the authorized committee on organizing public hearings on proposed acts and notification of the Speaker of the Parliament on the decision to hold public hearings (Art. 83 and 84 of the Rules of Procedure) - Harmonization of the draft amendments to the Constitution and the proposal of the constitutional law for its implementation after held public hearings - Submitting a proposal for the amendments to the Constitution, and the draft of the constitutional law for its implementation to the Speaker of the National Assembly (Article 145, paraf.1 of the Rules of Procedure) - Discussion and a decision-making on the proposal for the amendments to the Constitution and on the proposal of the constitutional law for its implementation by a two-third majority of the total number of deputies of the National Assembly (Article 203 par.5 of the Constitution and Article 146 of the Rules of Procedure) - Conducting a referendum in order to confirm the acts, in accordance with the Law on Referendum and People's Initiative - Decision of the National Assembly on promulgation of the act amending the Constitution and a decision on promulgation of the constitutional law for implementation of the amendments to the Constitution (Article 148 of the Rules of Procedure) | Government of the Republic of Serbia (authorized representatives from the ministry in charge of judiciary) National Assembly (Authorized committee on constitutional and legislative issues) National Assembly (Sitting of the Assembly) |  |  | II quarter 2020 | Budget RS | The Act on the amendment of the Constitution and Constitutional Law promulgated and in line with the Venice Commission opinion |
| 1.1.1.2. | Work on harmonization of a set of judicial laws with new constitutional solutions, preparation of working texts on changes and supplements to the Law on Organization of Courts, Law on Seats and territorial Jurisdiction of Courts and Public Prosecutors’ Offices, Law on Judges, Law on Public Prosecutor’s Office, Law on High Judicial Council, Law on State Prosecutorial and Law on Judicial Academy and drafting set of judicial laws, which specifically implies: - Formation of working groups for drafting working texts of changes to the set of judicial laws - drafting of judicial laws and organizing public hearings in order to make remarks on drafts - harmonization of working texts of the set of judicial laws with remarks after holding public hearings - submitting a draft judicial legislation to the Venice Commission for the opinion - Further harmonization of draft laws with the opinion of the Venice Commission - Acceptance of the draft laws and determining a draft law by the Government for the submission to the National Assembly | Working groups formed by the Ministry of Justice, comprising of all relevant representatives from the Ministry, HJC, SPC, Supreme Court of Cassation, Public Prosecutor`s Office, Judicial Academy and professors of law universities, representatives from civil society and professional associations -Government of the Republic of Serbia |  |  | III and IV quarter 2020 | Budget of the Republic of Serbia and TAIEX IPA 2015 EU for Justice Support for Chapter 23 USAID Project “Rule of Law” | Formation of the working groups Working texts of relevant legislation elaborated and public hearings held in accordance with regular procedure (Law on Planning System) Working texts of relevant legislation harmonized with the conclusions from public debates Draft proposal elaborated and set of legislation sent to the Venice Commission for its opinion Venice Commission opinion obtained Proposal of the relevant legislation elaborated in accordance with the Venice Commission opinion |
| 1.1.1.3. | Passing new set of legislation in the National Assembly in accordance with the new Constitutional solutions and with the Venice Commission opinion: - Law on Organization of Courts - Law on Seats and territorial Jurisdiction of Courts and Public Prosecutors’ Offices - Law on Judges - Law on Public Prosecutors Office - Law on High Judicial Council - Law on State Prosecutorial Council - Law on Judicial Academy | National Assembly |  |  | IV quarter 2020 | Budget of the Republic of Serbia | Set of legislation adopted in accordance with the new constitutional solutions and with the opinion of the Venice Commission, through a transparent process, with a broadly established consultative process and organized public hearings |
| 1.1.1.4. | Election of new composition of the High Judicial Council and State Prosecutorial Council, in accordance with the new constitutional and legal solutions and by-laws adopted | High Judicial Council State Prosecutorial Council National Assembly |  |  | III quarter 2021 | Budget of the Republic of Serbia | New composition of the High Judicial Council and State Prosecutorial Council in place |
| 1.1.1.5. | Alignment of by-laws with new constitutional and legal solutions:, referring, but not limited, to : - Rules of Procedure of the High Judicial Council - Rules of Procedure of the State Prosecutorial Council - Rulebooks on the bodies and procedure for evaluating the work of judges and (deputy) public prosecutors - Regulations on the work of the permanent working bodies of the High Judicial Council and the State Council of Prosecutors, (disciplinary bodies, ethics committees, election commissions, appeal commissions, evaluation performance commissions of judges and prosecutors) - Rules on Procedure of Managing Board and Program Council of the Judicial Academy | - Ministry of Justice -High Judicial Council -State Prosecutorial Council -Supreme Court of Cassation -Republic Public Prosecutor’s Office -Judicial Academy |  |  | III quarter of 2021. | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” USAID Project “Rule of Law” | By-laws in the field of judiciary aligned with the new constitutional and legal solutions |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  | OWERALL RESULT |  | IMPACT INDICATOR |
| 1.1.2. A fair and transparent system of promotion of judges and prosecutors needs to be established, together with a periodical professional assessment of judges and prosecutors' performance. A system to monitor and evaluate the application of those standards in practice should be established. The Councils should bear the responsibility for taking decisions on promotion, demotion or dismissal; IBM: Serbia establishes an initial track record of implementing a fair and transparent system based on merit for the management of the careers of judges and prosecutors including recruiting, evaluating and promoting judges and prosecutors based on periodic, professional performance assessment (including at senior level). |  |  |  |  | Established fair and transparent system, in which both Councils are accountable for decision making for promotion, deployment and dismissal of judges and public prosecutors functions, based on periodical professional assessment of judges’ and public prosecutors’ performance. A system of monitoring and evaluation of the application of adopted standards in practice established. |  | 1. Serbia has a comprehensive career advancement system for judges and public prosecutors, including the election and dismissal of judges, performance evaluation, promotion, disciplinary responsibility, demotion, dismissal, etc.in a way that guarantees the independence (internal and external) and the impartiality of the entire judicial system; 2. Evaluation of the work of judges, public prosecutors, as well as judicial and prosecutorial assistants is regularly conducted, and promotion is based on competence and merit, which has an overall positive effect on the quality and efficiency of justice which is confirmed in the positive evaluation issued by European Commission in Annual Progress Report on Serbia; 3. Positive evaluation stated in the Report of High Judicial Council for monitoring results of judicial laws’ implementation; 4. Positive evaluation stated in the Report of State Prosecutorial Council for monitoring results of judicial laws’ implementation. |
| ACTIVITIES |  |  | RESPONSIBLE AUTHORITY |  | TIMEFRAME/ DEAD LINE | FINANCIAL RESOURCES | RESULT |

| 1.1.2.1. | Adoption of by-laws on criteria and measurement for the election of judges and court presidents, for promotion and termination of judicial function and the function of the court president, in accordance with the new constitutional and legal solutions and their publication on the website of the High Judicial Council | High Judicial Council | III quarter 2021 | Budget of the Republic of Serbia IPA 2017 Project “Support to the HJC” | Adopted by-laws on criteria and criteria for the election of judges and court presidents, for promotion and termination of judicial function and function of the president of court, in accordance with new constitutional and legal solutions Acts published on the website of the High Judicial Council and accessible to the public |
| --- | --- | --- | --- | --- | --- |
| 1.1.2.2. | The High Judicial Council makes decisions on the election, promotion and termination of judicial function and the function of the court presidents, by applying new legislative solutions and by-laws on the election, promotion and termination of judicial function and the function of the court presidents | High Judicial Council | Continuously, commencing from III quarter 2021 | Budget of the Republic of Serbia | The High Judicial Council makes decisions on the election, promotion and termination of the judicial function and the function of the president of the court in accordance with the new legal and subordinate solutions The reasoned decisions of the High Judicial Council on the election, promotion and termination of the judicial function and the function of the president of the court published on the website of the Council |
| 1.1.2.3. | Adoption of by-laws on criteria and measurement for the election of the holders of public prosecutors offices, for their promotion and termination of the prosecutorial function, in accordance with the new constitutional and legal solutions and their publication on the website of the State Prosecutorial Council | State Prosecutorial Council | III quarter 2021 | Budget of the Republic of Serbia IPA 2018 Project “Support to the SPC” | Adopted by-laws on criteria and measurement for election to the public prosecutor's office, for promotion and termination of the public prosecutor's office, in accordance with the new constitutional and legal solutions Acts published on the website of the State Prosecutorial Council and accessible to the public |
| 1.1.2.4. | The State Prosecutorial Council makes decisions on the election, promotion and termination of prosecutorial function, by applying new legislative solutions and by-laws on the election, promotion and termination of prosecutorial function | State Prosecutorial Council | Continuously, commencing from III quarter 2021 | Budget of the Republic of Serbia | The State Prosecutorial Council makes decisions on the election, promotion and termination of the public prosecutor's office in accordance with the new legal and sub-legal provisions The reasoned decisions of the State Prosecutorial Council on the election, promotion and termination of the public prosecutor's office published on the website of the Council |
| 1.1.2.5. | The High Judicial Council is publishing detailed information on its website and by forwarding it to all courts, promotes the importance of performance evaluation and its impact on career development. | High Judicial Council | Continuously, commencing from III quarter 2021 | Budget of the Republic of Serbia USAID Project “Rule of Law” | Information on the significance of evaluating their work and its impact on career progression are available to the judges on the website of the High Judicial Council and the courts. |
| 1.1.2.6. | The State Prosecutorial Council is publishing detailed information on its website and by forwarding it to all public prosecutors’ offices, promotes the importance of evaluation of the work of public prosecutors and deputy public prosecutors and its impact on career development. | State Prosecutorial Council | Continuously, commencing from III quarter 2021 | Budget of the Republic of Serbia | Information on the significance of evaluating their work and its impact on career progression are available to the holders of the public prosecutor's office on the website of the State Prosecutorial Council and Public Prosecutor's Offices |
| 1.1.2.7. | The High Judicial Council, within the scope of its competence, monitors the effects of the implementation of judicial laws that are currently in the force as well as future judicial laws that are going to be adopted after constitutional changes. | -High Judicial Council | Continuously | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | -The High Judicial Council efficiently and continuously monitors the effects of implementation of judicial laws; -Number of analyses which were conducted by High Judicial Council: -Number of initiatives submitted to competent ministry for law amendments and supplements. |
| 1.1.2.8.. | , State Prosecutorial Council, within the scope of its competence, monitors the the effects of the implementation of the judicial laws that are currently in the force as well as future judicial laws that are going to be adopted after constitutional changes. | - State Prosecutorial Council | Continuously, | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | -The State Prosecutorial Council efficiently and continuously monitors the effects of implementation of judicial laws; -Number of analyses which were conducted by State Prosecutorial Council: -Number of initiatives submitted to competent ministry for law amendments and supplements. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.1.3. Sufficient administrative capacities and financial authority over their own budget needs to be ensured to allow the High Judicial and Prosecutorial Councils to effectively perform their tasks. Their work should be governed by transparency and institutional accountability; IBM: Serbia provides an adequate administrative capacity to the Judicial and Prosecutorial Councils and provides them with their own budget. |  |  | The High Judicial Council and the State Prosecutorial Council successfully manage the judiciary with adequate financial resources and personnel elected with a clear mandate, while respecting the principles of transparency and accountability. |  | - Increased structure and number of employees in Administrative office of High Judicial Council according to new systematization especially based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with the new constitutional and legal solutions; - Increased structure and number of employees in Administrative office of the State Prosecutorial Council according to new systematization, especially based on the needs of strengthening the analytical, statistical and managerial capacities in accordance with the new constitutional and legal solutions; - High Judicial Council independently proposes and executes its own budget; - State Prosecutorial Council independently proposes and executes its own budget; - Sessions of High Judicial Council and State Prosecutorial Council are, as a rule, open to the public; - Decisions of High Judicial Council and State Prosecutorial Council are reasoned; - Reports on work of High Judicial Council and State Prosecutorial Council are published at the websites of these bodies; - Clear procedures for institutional responsibility of High Judicial Council and State Prosecutorial Council are established. |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.1.3.1. | Adoption of the Law on the High Judicial Council which improves the еlection procedure of its members and introduces mechanisms of its institutional accountability, in accordance with the new constitutional solutions, especially in the part of: - determining conditions and improving procedure of the election of High Judicial Council’s members from the rank of judges in the context of strengthening judicial independence, - determining clear conditions for the election of Council`s members from the rank of prominent lawyers - prescribing the responsibility of the members of the High Judicial Council for its work and establishing an institutional accountability mechanism | -Ministry of Justice High Judicial Council -Government of the Republic of Serbia -National Assembly | IV quarter 2020 | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | The Law on High Judicial Council adopted The mechanisms for institutional accountability introduced and in place Clear and transparent system of the election of all members of the HJC |
| 1.1.3.2. | Adoption of the Law on the State Prosecutorial Council which improves the еlection procedure of its members and introduces mechanisms of its institutional accountability, in accordance with the new constitutional and legal solutions, especially in the part of: : - determining conditions and improving procedure of the election of State Prosecutorial Council’s members from the rank of (deputy) public prosecutors, all in the context of strengthening prosecutorial autonomy . - determining conditions for the election of Council`s members from the rank of prominent lawyers - prescribing the responsibility of the members of the SPC for its work and establishing an institutional accountability mechanism | -Ministry of Justice State Prosecutorial Council -Government of the republic of Serbia -National Assembly | IV quarter 2020 | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | The Law on State Prosecutorial Council adopted The mechanism for institutional accountability introduced and in place Clear and transparent system of the election of all members of the State Prosecutorial Council |
| 1.1.3.3. | Changes to the Law on High Judicial Council, the Law on Organization of Courts and the Law on Ministries, with the aim to delineate and specify the competences between the High Judicial Council and the Ministry in charge of judicial affairs in order to strengthen the judicial independence in organizational and budgetary performance, in accordance with the new constitutional solutions and the decision of the Constitutional Court number: IUo-34/2016 of 25 October 2018, | Ministry of Justice High Judicial Council National Assembly | IV quarter 2020 | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” USAID Project “Rule of Law” | The Law on High Judicial Council, the Law on Organization of Courts and the Law on Ministries changed |
| 1.1.3.4. | Changes to the Law on State Prosecutorial Council, the Law on Public Prosecutors Office and the Law on Ministries, with the aim to delineate and specify the competences between the State Prosecutorial Council and the Ministry in charge of judicial affairs in order to strengthen the prosecution autonomy in organizational and budgetary performance, in accordance with the new constitutional solutions and considering the decision of the Constitutional Court number: IUo-34/2016 of 25 October 2018 | Ministry of Justice State Prosecutorial Council National Assembly | IV quarter 2020 | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) USAID Project “Rule of Law” | The Law on State Prosecutorial Council, the Law on Public Prosecutors Office and the Law on Ministries changed |
| 1.1.3.5. | Strengthening the capacities of Administrative office of the High Judicial Council, in line with a new systematization act, and especially in the field of the analytical, statistical and managerial capacities, in accordance with new constitutional and legal solutions. | -High Judicial Council | Continuously | Budget of the Republic of Serbia USAID Project “Rule of Law” | Capacities of Administrative Office of High Judicial Council strengthened, , in line with a new systematization act, especially in the field of the analytical, statistical and managerial capacities in accordance with new constitutional and legal solutions |
| 1.1.3.6. | Strengthening the capacities of Administrative office of the State Prosecutorial Council, in line with the new systematization act, especially in the field of analytical, statistical and managerial capacities, in accordance with new constitutional and legal solutions | State Prosecutorial Council | Continuously | (-Budget of the Republic of Serbia | Capacities of Administrative office of the State Prosecutorial Council strengthened, in line with new systematization act, especially in the field of the analytical, statistical and managerial capacities in accordance with new constitutional and legal solutions. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.1.4. Establish a clear procedure for both Councils to react publicly in cases of political interference in the judiciary and prosecution; IBM: Serbia establishes an effective mechanism allowing the Councils to react against political interferences and establishes an initial track record of fully respecting judicial decisions and refraining from public comments on the work of courts by officials and politicians. |  |  | High Judicial Council and State Prosecutorial Council react according to clear and in-advance established procedures in case of political interference in the judiciary. |  | - Essentially reduced perception of political interference in the work of judicial instances, both among judicial officers and the citizens; - Improved transparency of the High Judicial Council and the State Prosecutorial Council and their cooperation with the media. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.1.4.1. | Amending Rules of Procedure of High Judicial Council to define clear procedure for public reacting and introducing an effective mechanism in keeping track record on cases of political interference in the judiciary | High Judicial Council | III quarter of 2021. | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | High Judicial Council acts in line with amended Rules of procedure which stipulate clear procedures for public reacting in cases of political interference in the justice. |
| 1.1.4.2. | Amending Rules of Procedure of State Prosecutorial Council to define clear procedure for public reacting and introducing an effective mechanism in keeping track record on in cases of political interference in the operation of public prosecutor’s office . | State Prosecutorial Council | III quarter of 2021. | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | State Prosecutorial Council acts in line with amended Rules of procedure which stipulates clear procedures for public reacting in cases of political interference in operation of public prosecutor’s office. |
| 1.1.4.3. | Regular and periodic reporting and extraordinary addressing of the High Judicial Council to public, regarding the possible existence of political interference on the work of the judiciary | High Judicial Council | Continuously, starting from III quarter of 2021 | Budget of the Republic of Serbia | Report on the HJC actions regarding the possible existence of a political influence on the work of the judiciary |
| 1.1.4.4. | Regular and periodic reporting and extraordinary addressing of the State Prosecutorial Council of the public, regarding the possible existence of political influence on the work of the prosecution | State Prosecutorial Council | Continuously, starting from III quarter of 2021 | Budget of the Republic of Serbia | Report on the SPC actions regarding the possible existence of a political influence on the work of the judiciary |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |
| 1.1.5. Ensure the full respect of court decisions including by raising the awareness that criticizing decisions, in particular by politicians puts the independence at risk; IBM: Serbia establishes an effective mechanism allowing the Councils to react against political interferences and establishes an initial track record of fully respecting judicial decisions and refraining from public comments on the work of courts by officials and politicians. |  |  | Judicial decisions are fully respected,whereas awareness, that criticizing decisions puts the independence at risk, has been improved. |  | - Increased percentage of members of executive and legislative branch who claim that are knowledgeable of European standards concerning restrictions of criticizing judicial decisions; - Increased percentage of judges and public prosecutors who claim that are knowledgeable of European standards concerning restrictions of criticizing judicial decisions; - Increased percentage of journalists who claim that are knowledgeable of European standards and internal norms concerning reporting on court proceedings; - Decreased percentage of judges and public prosecutors who consider that their independence has been put at risk by public criticizing judicial decisions; - Number of petitions for initiating misdemeanor proceedings concerning violation of the presumption of innocence and the unauthorized disclosure of information in relation to criminal proceedings; - Number and structure of decisions finalizing misdemeanor proceedings concerning violation of the presumption of innocence and the unauthorized disclosure of information in relation to criminal proceedings. |  |

| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| --- | --- | --- | --- | --- | --- |
| 1.1.5.1. | Establish a monitoring mechanism for full respect of judicial decisions and refraining from public comments on the work of courts by officials and politicians of judicial decisions through holding of periodic joint meetings and, always when appropriate, between representatives of the High Judicial Council, State Prosecutorial Council, National Assembly and the Government of the Republic of Serbia | High Judicial Council State Prosecutorial Council National Assembly Government of the Republic of Serbia | Continuously | Budget of the Republic of Serbia | Periodic joint meetings scheduled |
| 1.1.5.2. | Drawing up electronic brochure on the limits of permissible commenting judicial decisions and procedures for political office holders and its publication on the web pages of the National Assembly and the Government of the Republic of Serbia. | - Ministry of Justice and National Assembly (Republic Secretariat for Legislation), with the support of the High Judicial Council and the State Prosecutorial Council | IV quarter 2019 | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | Drawn up electronic brochure on the limits of permissible commenting judicial decisions and procedures for political office holders and publicized on the web pages of the National Assembly and the Government of the Republic of Serbia. Number of visits to the link with electronic brochures Number of documents downloaded from the links |
| 1.1.5.3. | Introduction of European standards relating to respect of judicial decisions and limits of permissible critique of judicial decisions and procedures in the context of respect of judiciary’s independence in the program of the Judicial Academy and the implementation of such training program in this area. | - Judicial Academy -High Judicial Council -State Prosecutorial Council -Partners (associations of journalists and civil society organizations) | Continuously, Donor support (Council of Europe) | Projects Council of Europe | European standards related to the limits of the permissibility of criticizing judicial decisions and proceedings in the process of respecting the independence of the judicial system are included in the Annual Curriculum of the Judicial Academy Periodically organized training on European standards relating to respect of judicial decisions and limits of permissible critique of judicial decisions and procedures in the context of respect of judiciary’s independence. Number of trainings held Number of participants trained |
| 1.1.5.4. | Organizing workshops for journalists in order to adopt European standards and national regulations concerning respect for judicial decisions and concerning respect of reporting on court proceedings. | -High Judicial Council - State Prosecutorial Council - Press Council in the Ministry of Information -Partners (associations of journalists and civil society organizations) | Continuously, | IPA 2016 Project “Support to the HJC” IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) USAID Project “Rule of Law” | Organized workshops for journalists in order to adopt European standards and national regulation concerning respect for judicial decisions and limits of permissible critique of judicial decisions and procedures in the context of respecting judiciary’s independence. Number of trainings / round tables for journalists held Number of journalists trained |
|  |  |  |  |  | Supreme Court of Cassation |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.1.6. Ensure the involvement of civil society and professional organizations in defining further steps in the reform process and in monitoring the implementation of the action plans; IBM: Serbia fully recognises and exploits the benefits of civil society expertise and therefore engages in a real and systematic dialogue with civil society |  |  | Civil society and professional organizations are involved in defining the further steps in the reform process and in monitoring the implementation of action plans. |  | Suggestions and comments of civil society and professional associations related to defining the further steps in the reform process are regularly discussed at meetings of the body responsible for monitoring the implementation of action plan for Chapter 23. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.1.6.1. | Publication of public call to civil society and professional associations to submit suggestions and comments for defining further steps in the reform process and performing supervision over the implementation of the reform steps | - Ministry of Justice in cooperation with the Office for Cooperation with civil society | Continuously, commencing from | Budget of the Republic of Serbia | Number of received and published comments and proposals by civil society and professional associations Number of adopted comments and proposals by civil society and professional associations |
| 1.1.6.2. | Submitting, publishing and consideration of reports on submitted comments and suggestions of civil society organizations on defining further steps in reform process. | - Ministry of Justice -Council for monitoring of the AP Ch. 23 implementation - | Continuously, commencing from | Budget of the Republic of Serbia | Number of received and published comments and proposals by civil society and professional associations Number of adopted comments and proposals by civil society and professional associations |
| 1.1.6.3. | Organizing roundtables to discuss achieved goals, shortcomings and possibilities of improving cooperation in creating and implementing reform steps, following the good practice of providing the motivated feedback on CSOs’ suggestions. | -Ministry of Justice - Negotiating Group for Chapter 23 -Office for Cooperation with Civil Society | Twice a year, commencing from | Budget of the Republic of Serbia | Number of round tables held Number of participants in civil society organizations |
| 1.1.6.4. | Improving other types of cooperation with civil society (jointly organized workshops, common publications, researches and raising awareness campaigns) in the process of defining reform steps, in accordance with: a) Guidelines (prepared with the support of experts from TAIEX) for cooperation between institutions which participate in Chapter 23 and civil society and b) Guidelines for inclusion of civil society in legislative process. | -Ministry of Justice - Negotiating Group for Chapter 23 -Office for Cooperation with Civil Society | Continuously, commencing from | Budget of the Republic of Serbia | Number of jointly organized and held workshops, joint publications, research and campaigns made to raise awareness Number of participants in the above events, research and campaigns |

| 1.2. IMPARTIALITY AND ACCOUNTABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |
| 1.2.1. Clarify and implement the rules for random allocation of cases, including through finding technical solutions to avoid circumventing the system. Ensure that the system is not open to manipulation and make it subject to regular inspection by the body authorized for monitoring within the High Judicial Council and the State Prosecutorial Council; IMB: Serbia puts in place a coherent procedural framework and the necessary ICT tools ensuring random allocation of cases in all courts and prosecution offices. Serbia ensures that the Judicial and Prosecutorial Council have tools to monitor the random allocation of cases. |  |  | Rules for random allocation of cases are clarified and are implemented consistently; regular inspection on their implementation is carried out by Inspectorate of High Judicial Council and State Prosecutorial Council. |  | - All cases are randomly allocated in courts on an automatized principle of allocation of cases; - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases, from report of supervisory body in the High Judicial Council; - Number of defined and removed irregularities concerning implementation of rules on random allocation of cases, from report of supervisory body in the State Prosecutorial Council - Cases are randomly allocated in prosecutors’ offices, on an automatized principle of allocation of cases, in line with the restrictions prescribed by laws and bylaws and considering the specific organization of the prosecution |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES |  | RESULT |
| 1.2.1.1. | Organization of focused training of end-users of existing platforms for the use of methodological instructions for "cleaning" the data, the implementation of "cleaning" and addition to the information in the ICT system. | Judicial Academy Ministry of Justice (E-justice) | Continuously | Budget of the Republic of Serbia |  | Clean data in ICT system. |
| 1.2.1.2. | Drawing up protocol on input and exchange of data in ICT system (and scanning of documents) with the purpose of unification of conduct in entire judicial system and training programs for staff in the judiciary with the aim of improving the quality of the existing ICT platforms. | Ministry of Justice (E-justice) Sector Council for ICT |  | Budget of the Republic of Serbia |  | Protocol on input and exchange of data in ICT system drafted Defined training programs for staff in the judiciary |

| 1.2.1.3. | Conducting trainings under the program of activities 1.2.1.2. with the aim to initiate uniform acting in input and exchange of data in ICT system. Uniform acting is periodically verified pursuant to institutional solutions related to ICT management system | Sector Council for ICT Ministry of Justice (E-justice) | Continuously, commencing from | Budget of the Republic of Serbia | After conducted trainings, input and exchange of data in ICT system is carried out in accordance with the Protocol. Protocol is being periodically assessed. |
| --- | --- | --- | --- | --- | --- |
| 1.2.1.4. | Further improvement of ICT systems through considerable investments in infrastructure, software and improvement of human resources, with the aim of establishing unique ICT system throughout the entire judicial system, and in accordance with the Guidelines that define the directions of development (conceptual model) of ICT system in the justice system of the Republic of Serbia. | Ministry of Justice (E-justice) | Continuously, commencing from | Budget of the Republic of Serbia | Measures aimed at establishing a unified ICT system in the entire judicial system of the Republic of Serbia are constantly being implemented through considerable investment in infrastructure, improvement of software and human resources development. Uniformed and centralized case management system established.in justice system |
|  | weighting weighting |  |  |  | weighting |

| 1.2.1.5. | Amendments to the Law on Judges in part which deals with random allocation of cases, aiming at implementation of Program for weighting of cases. | -Ministry of Justice -Government of the republic of Serbia -National Assembly | IV quarter of 2020 | Budget of the Republic of Serbia | Amended Law on judges in part which deals with allocation of cases by chance, aiming at implementation of Program for weighting of cases. |
| --- | --- | --- | --- | --- | --- |
| 1.2.1.64. | Adopt amendments to the Court Rules of Procedure in order to clarify rules concerning random allocation of cases (by chance), which will take into account complexity of cases as one of criteria for case allocation (in line with Program for weighting of cases that provides gradually approach in the introduction of case weighting system as one of the criteria for its allocation- Activity 1.2.1.7.) | Ministry of Justice -High Judicial Council | III quarter 2021 |  | Rules concerning random allocation of cases have been clarified upon adoption of amendments to the Court Rules of Procedure. |
| 1.2.1.7. | Application of the Program – case weighting methodology in all courts | Ministry of Justice High Judicial Council |  | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | Program implemented in all court, regardless of the size of the court |
| 1.2.1.8. | Developing a methodology for case weighting in public prosecutors' offices, taking into account the specialization of deputy public prosecutors and their uniform burden with cases | Ministry of Justice State Prosecutorial Council |  | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | Methodology for evaluating cases by weight in public prosecutors' offices developed |
| 1.2.1.9. | Adopt amendments to the Rules on administration in public prosecutors offices in order to clarify rules of random allocation of cases, which will take into account complexity of cases as one of criteria for case assignment (in line with Program for weighting of cases that provides gradually approach in the introduction of case weighting system as one of the criteria for its allocation- Activity 1.2.1.8.). | Ministry of Justice Republic Public Prosecutors Office State Prosecutorial Council |  | Budget of the Republic of Serbia | Rules concerning random allocation of cases have been clarified upon adoption of amendments to the Rules on administration in public prosecution. |
| 1.2.1.10. | Application of the Program – case weighting methodology in all public prosecutors offices | Ministry of Justice State Prosecutorial Council |  | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | Program implemented in all PPO, regardless of the size of the PPO |
| 1.2.1.11. | Establishing preparatory departments in courts, which are in charge of, inter alia, weighting of cases and tracking their work. | -High Judicial Council All court (court presidents) |  | Budget of the Republic of Serbia IPA 2016 Project “Support to the HJC” | Preparatory departments in courts have been established. Reports on the work of preparatory departments |
| 1.2.1.12. | Establishing preparatory departments in public prosecutors’ offices, which are in charge of, inter alia, weighting of cases and tracking their work. | -State Prosecutorial Council All public prosecutors offices |  | Budget of the Republic of Serbia IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | Preparatory departments in public prosecutors’ offices have been established. Reports on the work of preparatory departments |
| 1.2.1.13. | Preparing the program of training for work in preparatory departments on case weighting methodology and carrying out training of judicial and prosecutorial assistants for its implementationweighting . | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from | Budget of the Republic of Serbia USAID Project “Rule of Law” | Conducted training of judicial and prosecutorial assistants for work in preparatory departments of courts and public prosecutors’ offices. |

| 1.2.1.14. | Delineation and specifying jurisdictions between the Ministry of Justice and the High Judicial Council / State Prosecutorial Council in the performance of judicial administration in the field of supervision over the work and results of the work of the courts / public prosecutor's offices, including the field of collecting and analyzing statistical data | -Ministry of Justice -High Judicial Council State Prosecutorial Council Supreme Court of Cassation Republic Public Prosecutor Office | IV quarter 2020 | Budget of the Republic of Serbia IPA 2016 Project “Support to HJC” | Passing the Law on Organisation of Courts The implementation of the provisions of the Law on the Organization of Courts that regulate the issue of jurisdiction for the performance of judicial administration in the field of supervision over the work and effect of courts, including the field of collecting and analyzing statistical data, |
| --- | --- | --- | --- | --- | --- |
| 1.2.1.15. | Coherent implementation of amended rules on random allocation of cases in courts with regular supervision /inspection of their implementation by the High Judicial Council. | -all courts -High Judicial Council | Continuously, commencing from | Budget of the Republic of Serbia | Rules on random allocation of cases in courts are coherently implemented and regular supervision / inspection of their implementation is carried out by the High Judicial Council. |
| 1.2.1.16. | Coherent implementation of amended rules on random allocation of cases in public prosecutors’ offices with regular supervision / inspection of their implementation by the State Prosecutorial Council, having in mind the specific organization of prosecution | -all Public Prosecutor’s Office -State Prosecutorial Council | Continuously, commencing from | Budget of the Republic of Serbia | Rules on random allocation of cases in public prosecutors offices are consistently implemented and regular supervision / inspection of their implementation is carried out by the State Prosecutorial Council, having in mind the specific organisation of prosecution. |
| 1.2.1.17. | Establishment of a permanent working body of the High Judicial Council and State Prosecutorial Council in order to monitor the proper distribution of cases in the courts and public prosecutor's offices and their reporting on visits and conducted controls, in accordance with the program | High Judicial Council State Prosecutorial Council | III – IV quarter 2021 | Budget of the Republic of Serbia | Shortcomings remedied in the distribution of court cases Number of on-the-spot inspections carried out in courts and public prosecutors' offices Number of recommendations given to eliminate possible shortcomings The number of irregularities removed based on the report of the permanent working body of the High Judicial Council and the State Prosecutorial Council in charge of monitoring the correct implementation of the random allocation of cases |

| RECOMMENDATION FROM THE SCREENING REPORT | OVERALL RESULT | IMPACT INDICATOR |
| --- | --- | --- |
| 1.2.2. Strengthen the accountability of judges and prosecutors through a strict application of all legal and disciplinary means, including through : - Ensuring the effective implementation of "conflict of interest" rules and amending them if need be; - Ensuring the effective verification of asset declarations and cross- checking with other relevant information; - Effective monitoring of compliance with the code of ethics and carrying out further evaluation activities and training of judges and prosecutors in ethical behavior; - Review where necessary and effectively implement rules on disciplinary and dismissal procedures; - Re-assessing the system of functional immunity ensuring full accountability of judges and prosecutors under criminal law. - IBM: Serbia ensures that magistrates are fully accountable providing an initial track record of using the system of asset declarations as an effective means to detect inexplicable wealth, raising awareness on and the strict application of conflict of interest rules, promoting and controlling the respect of codes of ethics, avoiding that the concept of functional immunity is abused, ensuring regular inspections by an independent inspection body of the work of judges and prosecutors. | The accountability of judges and public prosecutors strengthened through a strict application of all legal and disciplinary means, including through the effective implementation of "conflict of interest" rules; effective verification and cross-checking of asset declarations; effective monitoring of compliance with the code of ethics and carrying out trainings for judges and public prosecutors in the field of ethics; effective implementation of rules on disciplinary accountability, functional immunity, dismissal procedures and accountability of judges and public prosecutors. The respective Councils have both an inspection capacity based on clear rules and bestowed with powers allowing them to act ex officio or on signals from citizens, state bodies or other legal entities related to inter alia questions of integrity or professional failure. | - Regular opinion polls confirm that there has been a decrease in the perception of corruption among citizens regarding the manner in which judges and public prosecutors respect the rules of ethics and values, which is confirmed in the positive assessment positive evaluation by European Commission concerning the system of accountability of judges and public prosecutors stated in the Annual Progress Report on Serbia; - The system of asset declaration and verification is actively used as a tool for the prevention and detection of illicit enrichment of judges and public prosecutors; - Increased number of judges and prosecutors who are covered by training in the field of ethics, results in raising awareness of the need to respect ethical values; - Results of the evaluation of judges and public prosecutors included in ethics training; - Positive evaluation on the degree of compliance with the code of ethics from the reports of ethics committees of the High Judicial Council and State Prosecutorial Council; - Data on the number of disciplinary charges and disciplinary proceedings against judges and public prosecutors from the reports of the disciplinary bodies of the High Judicial Council and State Prosecutorial Council; 7. Data on criminal charges and criminal proceedings against judges and public prosecutors. |

| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| --- | --- | --- | --- | --- | --- |
| 1.2.2.1. | Regular notification by institutions to the Anti-Corruption Agency concerning taking the judicial office and concerning termination of the judicial offices in order to, in more efficient manner, check the existence of conflict of interests. | - Сourt presidents and public prosecutors -Anti-Corruption Agency | Continuously, commencing from | Budget of the Republic of Serbia | Courts and Public Prosecutors offices regularly submit notifications concerning taking the judicial offices and their termination that enables ACA regularly updating lists of judicial offices holders. |
| 1.2.2.2. | Improvement of cooperation between High Judicial Council and the State Prosecutorial Council on the one side and Anti-Corruption Agency on the other side through the regular meetings and consideration of problems in order to coherently and timely implement duties of submitting reports on assets and incomes (assets declaration) of judicial office holders | High Judicial Council State Prosecutorial Council Anti-Corruption Agenc | Continuously, commencing from |  | Improved cooperation between the High Judicial Council , State Prosecutorial Council and Anti-Corruption Agency. Judicial office holders regularly submit assets declaration to the Anti-Corruption Agency. |
| 1.2.2.3. | Amendments to the normative framework which regulates: - requirements for dismissal of judges with the aim of specifying the requirements; - assessment of the professionalism of judges; - competence for conducting disciplinary proceedings and making decisions - statute of limitations for disciplinary misdemeanor; - sanctioning regime and practice | - -Ministry of Justice -Government of the Republic of Serbia -National Assembly | IV quarter of 2020- | Budget of the Republic of Serbia | Analysis of the normative framework, with recommendations drafted to regulate these issues Requirements for dismissal of judges are specified; provisions that regulate jurisdiction of Disciplinary commission and statute of limitations for disciplinary misdemeanor are specified and redefined. |
| 1.2.2.4. | Amendments to the normative framework which regulates: - requirements for dismissal of public prosecutor’s office holders with the aim of specifying the requirements; - assessment of the professionalism of public prosecutors and deputy public prosecutors; - competence for conducting disciplinary proceedings and making decisions - jurisdiction for conducting disciplinary procedure and decision making, - statute of limitations for disciplinary misdemeanor; - sanctioning regime and practice. | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | IV quarter of 2020 | Budget RS | Analysis of the normative framework, with recommendations drafted to regulate these issues Pursuant to the results of the analysis, requirements for dismissal of public prosecutors are specified to the determined extent; provisions that regulate jurisdiction of Disciplinary commission and statute of limitations for disciplinary misdemeanor are specified and redefined. |

| 1.2.2.5. | Amendments to the Law on Judges and the Law on the High Judicial Council in order to: - prescribing the Ethics Committee as a permanent working body of the HJC - prescribing the competencies of the HJC for the adoption of the Rules of Procedure of the Ethics Committee - prescribing the obligation to draft a report on the work of the HJC Ethics Committee on compliance with the provisions of the Code of Ethics | Ministry of Justice Government National Assembly | IV quarter of 2020 | Budget of the Republic of Serbia | Established the Ethics Committee of the High Judicial Council, in accordance with the new legal solutions and established a mechanism for monitoring its implementation |
| --- | --- | --- | --- | --- | --- |
| 1.2.2.6. | Analysis and in case the results of the analysis indicate the need, amending Code of Ethics for Judges, in line with the Opinion No. 3 of the Consultative Council of European Judges (SSJE), the Bangalore Principles of Judicial Conduct and Recommendation CM / Rec (2010) 12 of the Committee of Ministers to member states on independence, efficiency and accountability in the judiciary . | -High Judicial Council | III quarter of 2021 |  | An analysis, with recommendations performed Amendments to the Code of Ethics for Judges in accordance with the recommendations |
| 1.2.2.7. | Amendments to the Law on Prosecution and the Law on State Prosecutorial Council in order to: - prescribing the Ethics Committee as a permanent working body of the State Prosecutorial Council - prescribing the competencies of the State Prosecutorial Council for the adoption of the Rules of Procedure of the Ethics Committee - prescribing the obligation to draft a report on the work of the State Prosecutorial Council Ethics Committee on compliance with the provisions of the Code of Ethics | Ministry of Justice Government of the Republic of Serbia National Assembly | III quarter of 2021 | Budget of the Republic of Serbia | Amendments to the Law on Public Prosecutors Office and the Law on State Prosecutorial Council adopted |
| 1.2.2.8. | Analysis and in case the results of the analysis indicate the need, amending Code of Ethics for public prosecutors and deputy public prosecutors in accordance with the standards of the International Association of Prosecutors (1999) and the European Guidelines on Ethics and Behavior of Public Prosecutors (Guidelines from Budapest) adopted by the Conference of Supreme Prosecutors of Europe on May 31, 2005 | - State Prosecutorial Council | IV quarter of 2020 | Budget of the Republic of Serbia | An analysis, with recommendations performed Amendments to the Code of Ethics for Public Prosecutors in accordance with the recommendations |
| 1.2.2.9. | Adoption of Rules of Procedure of Board of Ethics of High Judicial Council and State Prosecutorial Council which regulate monitoring of compliance with Code of Ethics for Judges and public prosecutors and deputy public prosecutors conducting activities of evaluation and training of judges and public prosecutors and deputy public prosecutors on ethics. | -High Judicial Council State Prosecutorial Council | III quarter of 2021 | Budget of the Republic of Serbia IPA 2017 Project “Support to the HJC” IPA 2017 Project “Support to the SPC and RPPO in performing their competences related to prosecutorial governance and coordination (programming in progress) | Rules of Procedure of Board of Ethics of High Judicial Council adopted Rules of Procedure of Board of Ethics of State Prosecutorial Council adopted . |
| 1.2.2.10. | Organizing seminars for judicial office holders on integrity rules and ethics. | -Judicial Academy -High Judicial Council -State Prosecutorial Council | Continuously, commencing from |  | Seminars for judicial office holders on integrity rules and ethics are regularly organized. Number of seminars planned Number of seminars held Number of participants to the seminars held |
| 1.2.2.11. | Drawing up and publication of an updated brochure for judges for increasing awareness on ethics’ rules, containing examples of permissible / impermissible conduct, and which encompasses examples from practice. Publishing the brochure on the website of the High Judicial Council. | -High Judicial Council | III quarter 2021 | Budget of the Republic of Serbia | Brochure encompassing ethics’ rules and containing examples of permissible / impermissible conduct is drawn up and available on the website of High Judicial Council. |

| 1.2.2.12. | Drawing up and publication of an updated brochure for public prosecutors for increasing awareness on rules of ethics containing examples of permissible / impermissible conduct from practice. Publishing brochure on the website of the State Prosecutorial Council. | -State Prosecutorial Council | III quarter 2021 | Budget of the Republic of Serbia | Brochure encompassing ethics’ rules containing examples of permissible/impermissible conduct is drawn up and available on the website of the State Prosecutorial Council . |
| --- | --- | --- | --- | --- | --- |
| 1.2.2.13. | Proactive approach of judges and High judicial council in creation and monitoring of Code of Ethics for Judges, through the promotion of ethical principles and professional behavior rules. | -High Judicial Council | Continuously | Budget of the Republic of Serbia | Judges and members of High Judicial Council proactive participate in creating and monitoring of Ethics for Judges, through a series of seminar, round tables, workshops etc. in order to present permissible/impermissible conduct from practice |
| 1.2.2.14. | Amendments to the Law on Judges in the part concerning the disciplinary responsibility of judges, especially in parts of: - Differences between light, moderate and serious disciplinary offenses - respecting the principle of proportionality between disciplinary offenses and disciplinary sanctions - Clear definition of the disciplinary procedure and jurisdiction for conducting the disciplinary procedure and the procedure for dismissal - the role of the Disciplinary Commission - establishing a database of disciplinary proceedings against judges and their outcome | Ministry of Justice Government National Assembly | IV quarter 2020 | Budget RS | The Law on Judges adopted |
| 1.2.2.15. | Amendments to the Law on Public Prosecution in the part referring to the disciplinary responsibility of public prosecutors, especially in parts of: - Differences between light, moderate and serious disciplinary offenses - respecting the principle of proportionality between disciplinary offenses and disciplinary sanctions - Clear definition of disciplinary procedure and jurisdiction for conducting disciplinary procedure and dismissal procedure - the role of the Disciplinary Commission - establishing a database of disciplinary proceedings initiated against prosecutors and their outcome | Ministry of Justice Government National Assembly | IV quarter 2020 | Budget RS | The Law on Public Prosecution adopted |
| 1.2.2.16. | Effective implementation of Rules of Procedure on disciplinary proceedings and disciplinary liability of judges. | -High Judicial Council, disciplinary bodies | Continuously | Budget of the Republic of Serbia | Disciplinary bodies of High Judicial Council effectively implement Rules of Procedure on disciplinary proceedings and disciplinary liability of judges. Number of applications submitted Number of initiated procedures Number of cases completed by the determination of the judge's responsibility Statistics on the type of sanctions imposed |
| 1.2.2.17. | Effective implementation of Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors. | -State Prosecutorial Council, disciplinary bodies | Continuously | Budget of the Republic of Serbia | Disciplinary bodies of the State Prosecutorial Council effectively implement Rules of Procedure on disciplinary proceedings and disciplinary liability of public prosecutors and deputy public prosecutors. Number of applications submitted Number of initiated procedures Number of cases completed by the determination of the judge's responsibility Statistics on the type of sanctions imposed |
| 1.2.2.18. | Conduct analysis of provisions that regulate functional immunity of judicial office holders. | Minister of Justice, High Judicial Council State Prosecutorial Council | II quarter of 2020. | Budget of the Republic of Serbia | Conducted analysis of provisions that regulate functional immunity of judicial office holders. |
| 1.2.2.19. | Implementation of measures in accordance with conducted analysis from the activity 1.2.2.18. | -Ministry of Justice -High Judicial Council -State Prosecutorial Council | III and IV quarter of 2020. | Budget of the Republic of Serbia | Implemented measures in accordance with conducted analysis. |
| 1.3. PROFESSIONALISM/COMPETENCE/EFFICIENCY: |  |  |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.1. Develop the Judicial Academy as a center for continuously and initial training of judges and prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the public prosecution and the Judicial Academy, including through: - introducing a yearly curriculum covering all areas of law, including EU law; - allocating sufficient resources and introduce a quality control system for initial and specialized training; - IBM: - – Serbia ensures that the Judicial Academy adopts a multi-annual work programme, covering human and financial resources and a further development of its training programme. - Serbia also provides a sustainable and long term solution for financing the Judicial Academy applies a quality control mechanism and regularly and effectively assesses the impact of the training. |  |  | The Judicial Academy has been improved as a center for continuous and initial training of judges and public prosecutors in line with the rulings of the Constitutional Court on the provisions of the laws on the Public prosecutor’s Office and the Judicial Academy. Trainings are held according to annual curriculum covering all areas of law, including EU law and are subject to regular control. |  | - Improved quality of continuous and initial training that is implemented on the basis of the annual training program; - Judicial Academy operates with adequate infrastructure, equipment and staff in relation to training needs; - Programs of continuous, specialized and initial trainings are subject to regular control of quality and are improved according to the results of control; - Needs for training and education for judicial office holders are determined as part of their annual evaluation, and in accordance with the real needs of the system. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |

| 1.3.1.1. | Implementation of measures for improvement of programs of Judicial Academy in accordance with new constitutional and legal solutions, as well as with the Development Strategy of the Judicial Academy, and with the results of Functional Analyses of Judicial Academy needs such as: - Improvement of the entrance exam for initial training participants (two-year training) and development of multiple models of exams for participants in specific training programs, in accordance with the transitional solution of several entrance "gates" for candidates depending on work experience, practice and career path after passing the bar exam ; - Improvement of initial and continuous training programs and development of specific training programs through drawing up and adoption of annual curriculum of training that covers all areas of law (including EU law and human rights, ethics and integrity) and skills necessary for work in judiciary, which include the practical skills, along with all areas of law, depending on the category of the specific student and in particular usage of ICT system, legal analysis, methodology and method of decision drafting. Annual training curriculum has to encompass education in the field of management intended for court managers, court presidents and public prosecutors; - Improving continuous training through a wider range of participants, potentially through prescribing the minimum number of training days per holder of judicial office annually, whereby the training must include not only judicial officials but also presidents, secretaries and managers, judicial and prosecutorial assistants, administrative staff and persons engaged in judicial professions; - Improvement of transparency of elections of trainers; - Improvement of methods of teaching through workshops, simulations and the introduction of distance learning; - Improvement of the final exam for all categories of participants; | -Judicial Academy -Ministry of Justice -High Judicial Council -State Prosecutorial Council | Continuously, commencing from | Budget of the Republic of Serbia- | Program of Judicial Academy is significantly improved in line with the results of Functional Analyses of Judicial Academy needs. |
| --- | --- | --- | --- | --- | --- |
| 1.3.1.2. | Development of monitoring system concerning quality of initial, continuous and specialized training that implies bidirectional evaluation system that would allow the assessment of the results of training or degree of advancement of knowledge of the participants, as well as the assessment of the quality of the program and trainers in cooperation with the Institute for quality assurance of education and with Faculty of Philosophy – Department for pedagogy and andragogy. The system assumes that initial training candidates are evaluated by mentors and at the end of education they are passing the final exam, simulation of trial, evaluated by the commission. Continuous education is being evaluated through standard questionnaires, evaluating the following aspects, quality of lecturers and conditions of work. The further monitoring and evaluation enhancement shall be achieved through introduction of e-learning system, enabling more precise and complex measurement of different aspects of education process. | -Judicial Academy -High Judicial Council --State Prosecutorial Council | Continuously, commencing from | Budget of the Republic of Serbia- | Bidirectional system for monitoring of quality of initial, continuous and specialized training that allows the assessment of the results of training or degree of advancement of knowledge of the participants, as well as the assessment of the quality of the program and trainers has been developed and being implemented. |
| 1.3.1.3. | The number of initial training participants is determined in accordance with the Human Resources Management Plan of the High Judicial Council and the State Prosecutorial Council and the objectives of the Human Resources Strategy for the Judiciary | High Judicial Council -State Prosecutorial Council | III quarter of 2021 | Budget of the Republic of Serbia | Number of initial training participants determined in line with the Human Resources Strategy and Human resources management plan |
| 1.3.1.4. | Implementation of measures for improvement organization of work of Judicial Academy in accordance with the results of Functional analyses of Judicial Academy needs such as: - Further development of the Center for Documentation and research - Adoption of a new act on systematization of jobs and strengthening of professional and administrative capacities, in accordance with planned program-organizational changes, based on new constitutional and legal solutions | -Judicial Academy | Continuously, commencing from | Budget of the Republic of Serbia- – | The organization of work of the Judicial Academy as well as its administrative capacities are improved in accordance with the results of Functional analyses of Judicial Academy needs. |
| 1.3.1.5. | Ensuring adequate infrastructural preconditions for the work of the Judicial Academy with increased capacities, through the adaptation and equipping of the adequate building in line with the decision of the Republic of Serbia Government, from the session held on April 9, 2015 on allocation of the building that is located in centre of Belgrade and has 2800 m2 | -Judicial Academy -Ministry of Justice | II quarter 2020 | Apply for IPA 2015 (for improvement of Judicial Academy infrastructure) From its own budget resources, the Judicial Academy has taken responsibility to finance design of the Preliminary project design, which was finished on May 2, 2015. The Preliminary project design was submitted for procedure of obtaining necessary permits and licenses in line with the Republic of Serbia law. The Academy has taken responsibility to finance from its own budget resources expenses related to drafting final project, conducted upon adoption of the Preliminary project design, expenses of permits and appliances for utilities (water, electricity, heating, etc.). These expenses are estimated to 180.000 €. By October, the Academy shall have all necessary permits and projects for initiation of works. During the first half of May 2015 the Preliminary project design, estimation and preliminary estimate of costs of works will be submitted to the EU Delegation in order to provide resources from the IPA 2015 funds. | Judicial Academy is properly placed and equipped. |
| 1.3.1.6. | Further development of the cooperation of the Judicial Academy with its EU counterparts in the European Judicial Training Network (EJTN) and ensure participation of judges and prosecutors in EJTN's activities: - by inserting the financial support of these activities in the annual national IPA programme and - by preparing the adoption of a Memorandum of understanding with DG Justice to take part in the Justice programme (and enable the costs of participation in EJTN's activities to be covered by the operating grant that the EJTN receives from DG Justice) | - Judicial Academy - Ministry of Justice | Continuously, |  | The Judicial Academy takes part in EJTN activities. Judges and prosecutors take part in training seminars and exchanges of the EJTN and its members. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.2. Develop a system that allows assessing training needs as part of the overall evaluation of performance of judges and prosecutors; IBM: Serbia ensures that training needs are evaluated as part of the performance assessments of judges and prosecutors. |  |  | The assessment of training needs is part of the performance appraisal of judges and public prosecutors. |  | 1. High Judicial Council and the State Prosecutorial Council refer judges and public prosecutors to continuous training based on the results of their performance appraisal, and based on the results of the evaluations from previous trainings; 2. Annual curriculums of trainings for judges and public prosecutors are proposed and adopted taking also into account performance appraisal results of judges and public prosecutors. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.2.1. | Defining criteria for referring judges to additional training based on the performance appraisal results, and based on the results of the evaluations from previous trainings and referring judges to additional training according to the results of performance appraisal; implementation of training. | -High Judicial Council -Judicial Academy | Defining criteria: IV quarter 2020 Referring : Continuously, commencing from III quarter 2020 | Budget of the Republic of Serbia | An amended legislative framework concerning the criteria and criteria for additional training of judges The prescribed criteria for additional training High Judicial Council refers judges to additional trainings (which are implemented by Judicial Academy), according to criteria set in advance in accordance to the performance appraisal results and in accordance to the results from the evaluations from previous trainings. |
| 1.3.2.2. | Defining criteria for referring public prosecutor’s office holders to additional trainings based on performance appraisal results, and based on the results of evaluations from previous trainings and referring public prosecutor’s office holders to additional trainings. | - State Prosecutorial Council -Judicial Academy | Defining criteria: IV quarter 2020 Referring: Continuously, commencing from III quarter 2020 | Budget of the Republic of Serbia | An amended legal framework concerning the criteria and criteria for additional training of public prosecutors The prescribed criteria for additional training The State Prosecutorial Council refers public prosecutor’s office holders to additional trainings which are implemented by Judicial Academy based on the criteria for referring public prosecutor’s office holders to additional training based on performance appraisal results, and based on the results of evaluations from previous trainings defined. |
| 1.3.2.3. | Annual curriculums for training for judges are proposed and adopted taking also into account performance appraisal results of judges and evaluation of trainings performed | -High Judicial Council -Judicial Academy | Continuously, commencing from | Budget of the Republic of Serbia | Annual curriculums for training for judges are proposed and adopted taking also into account performance appraisal results of judges. |
| 1.3.2.4. | Annual curriculums for trainings for public prosecutor’s office holders are proposed and adopted taking also into account performance appraisal results of public prosecutors or deputy public prosecutors and evaluation of trainings performed | - State Prosecutorial Council -Judicial Academy | Continuously, commencing from | Budget of the Republic of Serbia | Annual curriculums for trainings for public prosecutor’s office holders are proposed and adopted taking also into account performance appraisal results of public prosecutor’s office holders. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.3. Conduct a comprehensive analysis prior to taking further steps in the reform of the court network, including in terms of cost, efficiency and access to justice; IBM: Serbia conducts a comprehensive assessment of its court and prosecution network with a focus on costs and allocated resources, efficiency, workload and access to justice prior to taking any further steps in the development of the court and prosecution network. |  |  | Comprehensive analysis of the costs, efficiency and access to justice as the foundation for considering whether further steps are needed in the reform of the court network. |  | 1. Regular monitoring of data using clear, previously defined methodology: - number of courts and public prosecutors offices per 100 000 inhabitants; - number of judges and public prosecutors per 100 000 inhabitants; - average and maximum distances of courts and public prosecutors offices from settlements on the territory of that court or public prosecutor’s office; - the conditions and scope of the exercise of the right to free legal aid; - the conditions and scope of the exercise of the right to a legal remedy; -the amount of court fees; - the number of cases per court and public prosecutor’s office; - the number of cases per judge and per public prosecutor; - the costs of operation of the judicial network; - duration of court proceedings (according to the matter) on average; - number of backlogged cases; - number of old cases; - -number of admitted applications before the European Court of Human Rights relating to the violation of the right to trial within a reasonable time. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.3.1. | Production of a mid-term situation assessment taking into account conclusions and recommendations from Functional review, on the following: - analysis of judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice, which includes an analysis of the jurisdiction of the courts in relation to subject matter, in particular between the first instance courts and between the second instance courts and the impact of the division of jurisdiction on the (un) even burden of courts and judges; - needs and scope of workload analysis; workload of judges and public prosecutors especially taking into account human, financial and technical resources and possible further changes in structure of courts, recruitment and education of staff. (The same activity 1.3.4.1. and 1.3.5.1.) | Ministry of Justice |  | Budget of the Republic of Serbia | Mid-term situation assessment produced taking into account conclusions and recommendations from Functional review on the following: |

| 1.3.3.2. | Establishing a new network of administrative courts (the multidimensionality of the administrative judiciary) and strengthening the capacity of the administrative judiciary in terms of selecting a sufficient number of judges and court staff | Ministry of Justice of the Republic of Serbia High Judicial Council |  | Budget of the Republic of Serbia GIZ Project “Support to the Administrative Court” | Multidimensionality of administrative court network established A sufficient number of judges elected A sufficient number of court staff selected |
| --- | --- | --- | --- | --- | --- |
| 1.3.3.3. | Further improving of the infrastructure judicial network, improvement of infrastructure and internal procedures, according to results of mid-term assessment from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1. | -Ministry of Justice -High Judicial Council -State Prosecutorial Council - Supreme Court of Cassation -Republic Public Prosecutor’s Office | Continuously, commencing from | Budget of the Republic of Serbia, | Undertaken reform steps on correction of infrastructure of the judicial network, improvement of infrastructure and internal procedures, according to results of assessment of judicial network. |
| 1.3.3.4. | Comprehensive analysis of implementation of reform of judiciary with a view to examine the impact of the reforms implemented after Functional Review of 2014. and adoption of recommendations for further development | Ministry of Justice, with the support of: High Judicial Council State Prosecutorial Council Judicial Academy, Supreme Court of Cassation and Republic Public Prosecutor’s Office. |  |  | Through a comprehensive analysis of the reform of judiciary the impact of the reforms implemented after the 2014 Functional review assessed. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.4. Establish and implement a medium-term human resource strategy for the judiciary, based on an analysis of needs and workload, and bearing in mind possible further changes in the structure of courts, recruitment and training; IBM: Serbia adopts and implements a human resources strategy for the entire judiciary, leading to a measurable improvement in the workload spread, efficiency and effectiveness of the justice system. |  |  | A mid-term human resource strategy for the judiciary, based on an analysis of needs and workload, and bearing in mind possible further changes in the structure of courts, recruitment and training adopted and implemented. |  | Clear staffing situation in the reformed judiciary established, the needs are defined and adequately provided and it is taken care to the greatest extent possible, that the workload is evenly distributed through the system. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.4.1. | Production of a medium-term situation assessment taking into account conclusions and recommendations from Functional review on the following: - analysis of judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice, which includes an analysis of the jurisdiction of the courts in relation to subject matter, in particular between the first instance courts and between the second instance courts and the impact of the division of jurisdiction on the (un) even burden of courts and judges; - needs and scope of workload analysis; workload of judges and public prosecutors especially taking into account human, financial and technical resources and possible further changes in structure of courts, election and education of staff. (The same activity 1.3.3.1. and 1.3.5.1.) | Ministry of Justice |  |  | Mid-term situation assessment produced taking into account conclusions and recommendations from Functional review on the following: - judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; - needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. |

| 1.3.4.2. | Finalization of the drafting of the medium-term Human Resources Strategy for the judiciary, in accordance with the results of the assessment from the activities 1.3.3.1, 1.3.4.1. and 1.3.5.1., which will, inter alia, address the following questions: - adopting a rulebook on the criteria for determining the required number of holders of judicial functions, taking into account the working conditions, the number of cases, the structure and complexity of the cases in which the court is performing; - adoption of rules on criteria for determining the required number and structure of judicial and prosecutorial assistants; - adoption of rules on criteria for determining the required number and professional structure of administrative staff in the judiciary | Ministry of Justice High Judicial Council State Prosecutorial Council |  | Budget of the Republic of Serbia | Midterm Strategy on human resources in judiciary prepared and adopted addressing inter alia, the following questions: - The number and structure of judges and prosecutors; - Status, number and structure of judicial assistants and prosecutorial assistants; - Management, number and professional structure of administrative staff in the judiciary. |
| --- | --- | --- | --- | --- | --- |
| 1.3.4.3. | Implementation of mid-term Strategy on human resources in judiciary in order to achieve more effective / more optimal planning, recruitment, deployment, motivation and promotion within the judiciary | -Ministry of Justice -High Judicial Council - State Prosecutorial Council | Continuously | Budget of the Republic of Serbia IPA 2017 Project “Support to the HJC” | Efficient implementation of midterm Strategy on human resources in judiciary. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.5. Ensure herewith a sustainable solution for workload imbalances; |  |  | Established efficient system for balancing the workload for judges and public prosecutors. |  | - Number of cases per court; - Number of cases per public prosecutor’s office; - Number of cases per judge; - Number of cases per public prosecutor or deputy public prosecutor. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.5.1. | Production of a mid-term situation assessment taking into account conclusions and recommendations from Functional review, on the following: - analysis of judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice, which includes an analysis of the jurisdiction of the courts in relation to subject matter, in particular between the first instance courts and between the second instance courts and the impact of the division of jurisdiction on the (un) even burden of courts and judges; - needs and scope of workload analysis; workload of judges and public prosecutors especially taking into account human, financial, technical resources and possible further changes in structure of courts, selection and education of staff. (The same activity 1.3.3.1. and 1.3.4.1.) | Ministry of Justice High Judicial Council State Prosecutorial Council |  |  | Mid-term situation assessment produced taking into account conclusions and recommendations from Functional review on the following: - judicial network in terms of costs, current state of play of infrastructure, efficiency and access to justice; - needs and scope of workload; workload of judges and public prosecutors especially taking into account human, material, technical resources and possible further changes in structure of courts, election and education of staff. |

| 1.3.5.2. | Based on the assessment and analysis from activity 1.3.5.1. defining measures to establish a sustainable solution to the problem of unequal workload of judges and public prosecutors with the number of cases: - periodic monitoring of the required number of judges and public prosecutors for each court / public prosecutor - transfer of judges / public prosecutors according to established criteria and criteria - Delegation ("overflow") of cases in accordance with the statutory criteria | High Judicial Council State Prosecutorial Council Ministry of Justice |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1.3.5.3. | Monitoring the implementation of measures from activities 1.3.4.2. and 1.3.4.3. which contribute to the functioning of an efficient system for equalizing the burden on judges and public prosecutors with the number of cases | High Judicial Council State Prosecutorial Council Ministry of Justice |  | Budget of the Republic of Serbia | Measures for unification of number of cases per judge / public prosecutor / deputy public prosecutor performed in line with the analysis and its results |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
|  |  |  |  |  | 1. Sustainable trend of reducing the average duration of court proceedings (per matter); |
| 1.3.6. Implement the backlog reduction program, including introducing alternative dispute resolution tools; |  |  | Coherent implementation of the backlog reduction program and efficiently introduced alternative dispute resolution tools. |  | - Sustainable trend of reducing the total number of backlogged (in particular old) cases; - Number of disputes resolved before mediator in one year; |
| IBM: Serbia implements its national backlog reduction programme - including through promoting the use of various alternative dispute resolution mechanisms - and establishes an initial track record of a sustainable decrease in the backlog of court cases. |  |  |  |  | 4. Number of transactions concluded via public notaries. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.6.1. | Amending а Civil Procedure Code in order to improve efficiency particularly in part which deals with: service of documents, hearing recording and discipline during the proceedings, particularly taking into account EU standards and practices of the ECtHR and the Constitutional Court | -Ministry of Justice -Supreme Court of Cassation | IV quarter 2020 | Budget of the Republic of Serbia USAID Project “Rule of Law” | Amending а Civil Procedure Code, whose provisions encourage efficiency, and particularly in the part relating to service of documents, recording of hearings and procedural discipline,, aligned with EU standards and practices of the ECtHR and the Constitutional Court. Supreme Court of Cassation |
| 1.3.6.2. | Amending Criminal Procedure Code in order to improve efficiency of the proceedings in particular in part dealing with service of documents, trial recording and discipline during the proceedings taking into account EU standards, jurisprudence of the ECtHR and the Constitutional Court | -Ministry of Justice -Supreme Court of Cassation -Republic Public Prosecutor’s Office | IV quarter 2020 | Budget of the Republic of Serbia USAID Project “Rule of Law” | Adopted new Criminal Procedure Code, which provisions improve efficiency, particularly in part dealing with service of documents, trial recording and discipline during the proceedings aligned with EU standards, jurisprudence of the ECtHR and the Constitutional Court |
| 1.3.6.3. | Amending Law on Enforcement and Security in order tofind the most effective solution: - for enforcement proceedings in which "small claims" are forcibly imposed; - which will prevent an increase in the number of enforcement proceedings initiated to settle claims that could be settled in the same executive proceeding. | -Ministry of Justice -Supreme Court of Cassation | IV quarter of 2019 | Budget of the Republic of Serbia- USAID Project “Rule of Law” | Law on Enforcement and Security adopted in order to improve efficiency of enforcement procedure in accordance with a comprehensive analysis of the enforcement system in the Republic of Serbia. Supreme Court of Cassation |
|  |  | -Ministry of Justice -Supreme Court of Cassation |  |  |  |
| 1.3.6.4. | Monitoring the implementation of the Uniform backlog reduction program through holding regular meetings of the Working Group for the implementation of the Uniform Backlog Reduction Program. | Supreme Court of Cassation Ministry of Justice | Continuously | Budget of the Republic of Serbia | Number of meetings of the Working Group for the implementation of the Uniform Backlog Reduction Program held Number of interventions proposed and implemented |

|  |  |  |  | Supreme Court of Cassation |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | - Supreme Court of Cassation |  |  |  |
| 1.3.6.5. | Amending Rules of Procedure on internal organization and systematization of jobs in Ministry of Justice and employment of IT experts in accordance with new systematization. |  |  | -Ministry of Justice | Continuously | Budget of the Republic of Serbia | Rules of Procedure on internal organization and systematization of jobs in Ministry of Justice amended and IT experts employed in accordance with new systematization. |
| 1.3.6.6. | Amending Rules of Procedure on internal organization and systematization of jobs in Supreme Court of Cassation and employment of IT experts in accordance with new systematization. |  |  | -Supreme Court of Cassation | Continuously | Budget of the Republic of Serbia | Rules of Procedure on internal organization and systematization of jobs in Supreme Court of Cassation adopted and IT experts employed in accordance with new systematization. |
| 1.3.6.7. | Analyses and, if necessary adopt amendments to Law on Notaries and the set of accompanying laws, in accordance with EU standards, with the support of experts and based on the results of implementation. |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | Periodically, commencing from | Budget of the Republic of Serbia | Competences of notaries are periodically refined and amended, in line with results of analyses; Quality control system is improved. |
| 1.3.6.8. | Drawing up and adopting remaining by-laws and Chamber regulations envisaged in Law on Notaries such as: - The act of the Minister in charge of the judiciary referred to in Article 70 of the Law on Public Notary on the electronic format and conditions that the notary public document, which is made in electronic form, and which has not been printed on the paper, must fulfill it in order to be considered a public notary - Public Notary Rules and other acts that enable the digitization of notaries |  |  | -Minister of Justice -Chamber of Public Notaries |  | Budget of the Republic of Serbia | By-laws and Chamber of Notaries regulations envisaged in Law on Notaries adopted. |
| 1.3.6.9. | Conducting of notary state exam and appointment of additional number of notaries, in accordance with the Law on the Notaries and rulebook on the number of notaries’ positions and the official seats of notaries. |  |  | - Ministry of Justice -Chamber of Public Notaries | Continuously | Budget of the Republic of Serbia | - Number of candidates for notaries increased; - Increased number of notaries. - Notaries for the territory of all basic courts appointed; |
| 1.3.6.10. | Strengthening the capacity of the Ministry of Justice department in charge of supervision of notary system. |  |  | -Ministry of Justice | Continuously | Budget of the Republic of Serbia | Capacities of the Ministry of Justice department in charge of supervision of work of notary system strengthened: |
| 1.3.6.11. | Promotion of public notary system |  |  | -Ministry of Justice | Continuously | Budget of the Republic of Serbia - | Benefits of notary system and results of work of notaries periodically presented. |
|  |  |  |  | -Chamber of Public Notaries |  |  |  |
| 1.3.6.12. | Regular implementation of trainings for public notaries. |  |  | -Judicial Academy -Chamber of Public Notaries | Continuously | Budget of the Republic of Serbia | Trainings for notaries are organized regularly. Number of trainings held increased Number of participants increased |
| 1.3.6.13. | Drafting and adoption of a strategic framework for improving the application of mediation |  |  | Ministry of Justice Supreme Court of Cassation |  |  | Strategy and Action Plan for improving the application of mediation drafted and published |
| 1.3.6.14. | Implementation of a strategic framework for improving the application of mediation and monitoring its effective implementation |  |  | Ministry of Justice Supreme Court of Cassation |  |  | Periodical reports on the implementation of the strategic framework developed and published. |
| 1.3.6.15. | Creation and adoption of laws regulating mediation, mediation conditions, rights and duties of mediators, and training program for mediators (mediators) |  |  | Ministry of Justice Government National Assembly |  | Budget of the Republic of Serbia | The law was adopted in accordance with the standards of mediation contained in the acts of the United Nations, the European Union and the Council of Europe and in line with the objective of Directive 2008/52 / EC on certain aspects of mediation in civil and commercial matters ("establishing a balance between the number of court proceedings and the number of mediations "). |
| 1.3.6.16. | Adoption of program for initial and continuous training of mediators and its implementation. |  |  | -Ministry of Justice -Judicial Academy -Other accredited organizations and institutions | Continuously, commencing from | Budget of the Republic of Serbia | Programs for specialised training of mediators adopted by relevant organisations. Basic and specialised training of mediators regularly conducted. Ministry of Justice keeps updated records of all issued certificates on completed training. |
| 1.3.6.17. | Continuous updating of Registry of Mediators and improvement of access to information on licensed mediators and аccredited training institutions, organisations and legal entities which are vested with the license to educated mediators. |  |  | -Ministry of Justice | Continuously, commencing from | Budget of the Republic of Serbia | Registry of Mediators established and continuously improvement of access to information on licensed mediators and accredited training institutions (state bodies, organizations and legal entities). |
| 1.3.6.18. | Sistematization of an appropriate number of positions in the Ministry of Justice for conducting professional and administrative tasks within the Commission for the revocation of the license for mediation to conduct the procedure for revocation of licenses, , as well as keep of the Register of Mediators and monitor over the implementation of the training programs. |  |  | -Ministry of Justice |  | Budget of the Republic of Serbia- | systematization of an adequate number of jobs in the Ministry of Justice performed. |
| 1.3.6.19. | Further improvement and promotion of alternative dispute resolution through the activities such as: - Publishing information on the website; - Publication of informative brochures and public service announcements; - Informing the media; - Designing infographics; - Organizing round tables and workshops |  |  | -Ministry of Justice, Public Relations Service | Continuously, commencing from | Budget of the Republic of Serbia USAID Project “Rule of Law” | Information on mediation system is easily and widely accessible to public |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.7. Strengthen the enforcement of judgments, in particular in civil cases; IBM: – Serbia adopts and implements the new Law on Enforcement and Security and establishes an initial track record of an improved clearance and recovery rate of enforcement proceedings in civil and commercial cases. Serbia monitors the enforcement system and develops further measures where relevant |  |  |  |  | Improved efficiency of enforcement of judgments in particular in civil law cases. |  | - Trend of reduction of the number of backlogged cases in enforcement; - Reduced average duration of enforcement proceedings. |
| ACTIVITIES |  |  |  | RESPONSIBLE AUTHORITY | TIMEFRAME/ DEAD L INE | FINANCIAL RESOURCES | RESULT |
| 1.3.7.1. | Amendments to the Law on Enforcement and Security in order to improve the effective elimination of the observed shortcomings in practice, , in particular: - revision of prescribed remedies; - introduction of an electronic real estate sales platform to ensure transparency of the procedure - introduction of compulsory initial training as a condition for appointment for executors |  |  | -Ministry of Justice -Government of the Republic of Serbia -National Assembly | IV quarter of 2019 | Budget of the Republic of Serbia USAID Project “Rule of Law” | Law on Enforcement and Security adopted, considering recommendations contained in the RoLE Assessment Report, in particular: - Scope of competences of enforcement officers broadened; - Old utility cases transferred into competence of enforcement officers; - Mandatory initial training for enforcement officer candidates introduced. |
| 1.3.7.2. | Enacting of by-laws and Chamber regulations necessary for implementation of |  |  | - Ministry of Justice, | IV quarter of 2019 | Budget of the Republic of Serbia- | Necessary by-laws and Chamber regulations enacted; |

|  | Law on Enforcement and Security, in particular for: - Establishing clearly defined professional standards and reporting criteria (substantive and financial), professional ethics, disciplinary proceedings, and system of monitoring and control by the Ministry of Justice and the Chamber, for a functional and transparent system of accountability of enforcement officers; | - Chamber of Enforcement Officers - Judicial Academy |  | USAID Project “Rule of Law” | Initial and continuous training programs and materials enacted. |
| --- | --- | --- | --- | --- | --- |
|  | - Conducting initial and continuous training programs. |  |  |  |  |
| 1.3.7.3. | Regular monitoring and control of the implementation of the system of enforcement officers by the Chamber of Enforcement Officers and Ministry of Justice, as prescribed by the Law on Enforcement and Security and relevant by-laws; Regular reporting to Strategy Implementation Commission and undertaking of necessary measures in order to solve problems and improve quality of work and efficiency. | -Ministry of Justice -Chamber of bailiffs -Strategy Implementation Commission | Continuously, commencing from | Budget of the Republic of Serbia USAID Project “Rule of Law” | Regular monitoring of the quality and efficiency of the system through: - Statistical reports on work of enforcement officers; - Regular reports by the Chamber of Enforcement Officers; - Number of performed inspections in enforcement officers’ offices; - Number of disciplinary proceedings initiated and completed, including number of imposed sanctions. Necessary measures undertaken, when necessary. |
| 1.3.7.4. | Changing the public service tariff in order to achieve a higher predictability of calculating and collecting labor remuneration and compensation for the costs of public enforcement officers | Ministry of Justice | IV quarter of 2019 | Budget of the Republic of Serbia USAID Project “Rule of Law” | Calculation and collecting labor |
| 1.3.7.5. | Monitoring the implementation of the amendments to the Law on Enforcement and Security, in particular with the implementation of the provisions related to the "E-auction" and the Public Executing Tariff | Ministry of Justice | Continuously | Budget of the Republic of Serbia USAID Project “Rule of Law” | - - Regular monitoring of the quality and efficiency - Statistical reports on work of enforcement officers; - Regular reports by the Chamber of Enforcement Officers related to the E-auction |
| 1.3.7.6. | Improving the capacities of the Ministry of Justice to carry out supervision over the work of public enforcement officers | Ministry of Justice | Continuously | Budget of the Republic of Serbia | Number of trainings held Number of people trained Evaluation of the trainings performed with respect to the performance assessment of the employees in the Ministry of Justice |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
|  |  |  |  |  | 1. Increased number of statistical parameters of efficiency of judiciary that can be monitored by means of Information and Communication Technology; |
| 1.3.8. Gradually develop an e-Justice system as a means to improve the efficiency, transparency and consistency of the judicial process, building on the existing automated case management system. Ensure the visibility of reliable and consistent judicial statistics and introduce a system to monitor the length of trials; IBM: – Serbia develops and rolls out a coherent e-Justice system allowing systematic automated information exchange across the court system and prosecution offices, the electronic assignment of cases and the development and use of a sound statistical capacity (in line with CEPEJ guidelines on judicial statistics) to allow inter alia the measurement of the average duration of court proceedings. Serbia ensures sufficient training for the users of the system |  |  | Developed an e-Justice system as a means to improve the efficiency, transparency and consistency of the judicial process, building on the existing automated case management system. Ensured the visibility of reliable and consistent judicial statistics and introduced a system to monitor the length of trials. |  | - Possibility of actual monitoring of length of court proceedings by introducing the uniform case number; - Perception of transparency of the court proceedings through availability of data via Information and Communication Technology (judicial office holders, attorneys, citizens); 4. Perception of data transparency, in relation to the efficiency of the judiciary, through availability of data via Information and Communication Technology (judicial office holders, attorneys, citizens). |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.8.1. | Analysis Roll out applications for the automatic case management system in courts, prosecutors' offices and Institute for the Execution of Criminal Sanctions (SAPS, SAPA and SAPO) and development of strategic guidelines based on the analysis made | Ministry of Justice |  |  | Analysis with strategic guidelines performed |
| 1.3.8.2. | Implementation of the strategic guidelines from 1.3.8.1. for implementation within the entire judicial system | Ministry of Justice |  |  | Strategic guidelines implemented Uniformed and centralized case management system is established |
|  |  | а |  |  |  |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.3.9. Improve consistency of jurisprudence through judicial means (consider simplification of the court system by abolishing courts of mixed jurisdiction and possibility to file an appeal before the Supreme Court of Cassation based on legal grounds against any final decision) and by ensuring complete electronic access to court decisions and motivations and their publication within a reasonable amount of time; IBM: Serbia ensures a qualitative improvement of the consistency of jurisprudence, including by ensuring easy access to jurisprudence for all courts through an electronic database and their publication within a reasonable amount of time |  |  | Improved consistency of jurisprudence in all areas of law; judicial decisions and judicial motivations are timely published in all available electronic data bases. |  | 1. Established uniform and comprehensive electronic database of jurisprudence available to everyone, which is in compliance with regulations governing data confidentiality and protection of personal data resulting in a greater uniformity of jurisprudence; - Number of accepted applications against Republic of Serbia because violation of Article 6 paragraph 1 European Convention for Human Rights before ECHR;. - Number of accepted Constitutional complaint because violation of Article 32 of Constitution of thr Republic of Serbia before Constitutional Court of Republic of Serbia based on inconsistent jurisprudence; 4. Positive opinion from European Commission, stated in Annual Progress Report on Serbia, concerning progress achieved in the field of uniformity and availability of jurisprudence. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.9.1. | Conduct analysis of the normative framework which regulates: the issue of taking into account of jurisprudence, right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning taking into account new constitutional solutions and the views of the Venice Commission. | Ministry of Justice Supreme Court of Cassation | II and III quarter of 2020 | Budget of the Republic of Serbia | Conducted analysis of normative framework which regulates: the issue of binding of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning taking into account new constitutional solutions and the views of the Venice Commission. |
| 1.3.9.2. | Amending normative framework, in line with the analysis performed under activity 1.3.9.1., which regulates: - the issue of binding of jurisprudence; - right to legal remedy and jurisdiction for deciding on legal remedy; - publishing judicial decisions and judicial reasoning. | -Supreme Court of Cassation -Ministry of Justice -Government of the Republic of Serbia -National Assembly | IV quarter 2020 | Budget of the Republic of Serbia | Normative framework which regulates: the issue of binding of jurisprudence; right to legal remedy and jurisdiction for deciding on legal remedy; publishing judicial decisions and judicial reasoning is in line with EU standards and the best practice. |
| 1.3.9.3. | Improving access to regulations and case law, through establishment and promotion of comprehensive and widely available electronic databases of legislation and case law, with respect to the provisions governing data confidentiality and personal data protection, and bearing in mind the provisions of the Law on publishing laws and other regulations, the Law on Judicial Academy and the Law on Courts. | -Public Enterprise “Official Gazette” -Supreme Court of Cassation - Judicial academy | Continuously | Budget of the Republic of Serbia | Comprehensive electronic databases and widely available electronic databases of legislation and case law, with respect to the provisions governing data confidentiality and personal data protection, and bearing in mind the provisions of the Law on publishing laws and other regulations, the Law on Judicial Academy and the Law on Courts established and regularly updated and improved. |
| 1.3.9.4. | Capacity strengthening and improvement of efficiency of operation of departments for jurisprudence in Supreme Court of Cassation , courts on Republic level and appellate courts.. | -Supreme Court of Cassation -Administrative Court -Commercial Appellate Court -Misdemenaur Appellate Court -Appellate courts of general jurisdiction | Continuously | Budget of the Republic of Serbia | Capacities and efficiency of operation of department for jurisprudence in the Supreme Court of Cassation, courts on Republic level and appellate courts. are continuously improved. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
|  |  |  |  |  | 1. Data from analysis of mid-term results of implementation of reform in 2015; |
| 1.3.10. Conduct a mid-term review at the end of 2015 as well as an impact assessment in 2018 of the results generated by the 2013 Strategy and its revised action plan. Define on that basis and where needed measures to cover the remaining period up until accession. |  |  | A mid-term review assessed the impact of the reform of judiciary for period up until 2018 and an impact assessment on that basis served to define measures for period after 2018 up until accession. |  | - Data from impact assessment for the period up until 2018; - Measures planned for period from 2018 up until accession, based on an analysis of the mid-term results and projection for period until 2018. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.3.10.1. | Based on an assessment of the impact of the implementation of the National Strategy for Judicial Reform for the period 2013-2018. and the Action Plan for its implementation, propose measures for the period until full accession. | -Ministry of Justice | Through 2019 | Budget of the Republic of Serbia TAIEX | The analysis on the implementation of the National Strategy for the Judiciary Reform for the period from 2013 to 2018 |
| 1.3.10.2. | Adoption of a new strategy for the judiciary sector for the period of 2019-2024, with the proposed measures, until accession | Ministry of Justice Government National Assembly | IV quarter 2019 | Budget of the Republic of Serbia USAID project Rule of Law | New Strategy for justice sector adopted for the period of 2019-2024 with measures until accession |

|  |  | State Prosecutorial Council |  |  |  |
| --- | --- | --- | --- | --- | --- |

| 1.4. WAR CRIMES |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |  |
|  |  |  |  |  | 1. New prioritized and serious allegations prosecuted in line with prosecutorial strategy; 2. Number of proceedings completed with final judgment; - Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; - Positive reports from other relevant governmental and non-governmental organizations; 5. Public Opinion Survey on citizens’ perceptions whether the suspects for war crimes are properly investigated and punished; 6. Duration of the proceedings (efficient investigative and pre-investigative actions); 7. Quality of proceedings and judgments for war crimes in comparison to international standards. |
| 1.4.1 Ensure that all allegations are properly investigated and subsequently prosecuted and tried; |  |  | All priority and serious allegations in accordance with prosecutorial strategy have been properly investigated and all trials for war crimes have been completed, with full and accurate implementation of international standards concerning the support of victims and witnesses and their protection. |  |  |
| IBM: Serbia effectively demonstrates adequate investigations of allegations and equal treatment of suspects avoiding giving the impression that anyone is above the law, regardless of their nationality or ethnicity or that of the victims; |  |  |  |  |  |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.4.1.1. | Monitoring the effective implementation of the National Strategy for prosecution of war crimes (2016-2020). | -Working group of the Government of Serbia -Experts and civil society | Continuously | Budget of the Republic of Serbia | National Strategy for prosecution of war crimes adopted and being effectively implemented. Number of defined conclusions and recommendations of the Government Working Group Report to the body responsible for the implementation of the Action Plan for Chapter 23 and the Government of the RS Maintaining regular meetings of the working body of the Government of the Republic of Serbia for monitoring the implementation of the Strategy with representatives of all the entities involved in the processing of war crimes |
|  |  | - Government of the Republic of Serbia |  |  |  |

| 1.4.1.2. | Complete insight and research of International Criminal Tribunal for former Yugoslavia (ICTY) and Residual Mechanism (MICT) archives (about war crimes on the territory of former Yugoslavia including documents not only from Serbia but also from BiH and RH, as well as general and specific allegations already investigated by independent prosecutors of ICTY), analysis of the discovered documents through the established liaison officers based on EU project that will ensure that all priority and serious allegations or war crimes are properly | -War Crime Prosecutor Office | Continuously | Budget of the Republic of Serbia | Complete research of the ICTY and MICT archives. Evidence transfer completed. Knowledge and experience of the ICTY is applied in investigation and prosecution of war crimes in Serbia. Strategy related to concrete cases developed and implemented. |
| --- | --- | --- | --- | --- | --- |

|  | investigated and subsequently prosecuted and tried in line with prosecutorial strategy. -Identifying ICTY/MICT materials and evidence which are relevant to the cases identified as a priority under activity 1.4.1.3 above and transfer of identified documents and evidence from the ICTY and MICT to the War Crime Prosecutor Office (support obtained and memorandum of understanding signed). -Transferring the ICTY know-how through: - Cooperation of the WCP with the ICTY/MICT on concrete cases in which the evidence was transferred in order to also obtain general and case specific knowledge, expertise and strategies from the ICTY and MICT investigators/prosecutors (transparency is ensured as information and expertise are obtained from independent experts) Cooperation of the WCP with the ICTY/MICT on concrete cases in which the evidence was transferred in order to share the strategy and transfer knowledge and practice on jurisprudence relating to crimes and types of responsibility that will be used as allegation in concrete cases (transparency is ensured as information and expertise are obtained from independent experts) - Ad hoc presence of the WCP advisor in the ICTY and MICT prosecutor’s office on ad hoc basis related to concrete national cases, analyzing ICTY prosecutor’s case files and developing a strategy for concrete cases that will be prosecuted by the WCP before the High Court in Belgrade. |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1.4.1.3. | Establishing a system of training and education in the field of international criminal law for the related group of judges and prosecutors: | -Judicial Academy -War Crime Prosecutor’s Office | Continuously | Budget of the Republic of Serbia | Trainings in the field of international criminal law are held continuously according to previously adopted program for other judges and prosecutors on as needed basis. The established curriculum (curriculum) for initial training in the above areas for newly elected and new employees in war crimes cases |

|  | - initial training for the newly appointed members of state bodies dealing with war crimes; - continuous education training for judges and prosecutors in line with National strategy and prosecutorial strategy (ensuring that the latest IHL developments are included). | -Supreme Court of Cassation -Higher Court in Belgrade -Appellate Court in Belgrade -High Judicial Council -State Prosecutorial Council |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1.4.1.4. | Continuous enhancement and regular updating of the WCP web-site to enable the public to monitor what activities and when have been performed by the WCP in relation to specific criminal charges. | -War Crime Prosecutor Office -Ministry of Justice | Continuously | Budget of the Republic of Serbia | Enhanced WCP website which provides an opportunity for the public to monitor which activities have been performed by the WCP in relation to specific criminal charges. |
| 1.4.1.5. | Preparation of a report by the War Crimes Prosecutor’s Office, in line with the established methodology of reporting, which will be available to the public indicating what has been done in respect of all criminal charges since 2005, to determine and to represent whether all allegations of war crimes are investigated appropriately. (the same activity 1.4.3.5.) | -War Crimes Prosecutor’s Office | Once a year | Budget of the Republic of Serbia- | Report of War Crimes Prosecutor’s Office published, including activities related to all criminal charges since 2005, focusing on cases of highly ranked officers. Annual reporting of WCP with regard to all criminal charges in the reporting period, in accordance with the established methodology of reporting Presentation of the Annual WCP report at the press conference |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.4.2. Ensure proportionality of sentences; IBM: Serbia ensures proportionality of sentences and a sentencing policy in line with international criminal law standards |  |  | Imposed sentences are proportional to criminal offence in accordance with the international standards. |  | - Level of sentences imposed in comparison to the jurisprudence of international tribunals; - Positive evaluation from analysis and reports of international and non-governmental organizations concerning proportionality of sentences; - Implementation of international criteria (including aggravating and mitigating circumstances) in imposition of sentences in war crimes cases. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |

| 1.4.2.1. | Publishing and follow up the conclusions from conferences organized in the region with reference to proportionality of sentences and a sentencing policy in line with international criminal law standards | -Higher Court in Belgrade, War Crime Chamber -Appellate Court in Belgrade -Supreme Court of Cassation - Wаr Crime Prosecutors Office -Ministry of Justice |  | Budget of the Republic of Serbia | Published and implemented conclusions from the Conference. |
| --- | --- | --- | --- | --- | --- |
| 1.4.2.2. | Publication and dissemination of reports on the Higher, Appellate Court and Supreme Court of Cassation case law on sentencing policies in war crime proceedings for judges’ prosecutors and lawyers. | -Higher Court in Belgrade, War Crime Chamber -Appellate Court in Belgrade - Supreme Court of Cassation -Ministry of Justice | Continuous, yearly and when needed | Budget of the Republic of Serbia- | Printed and disseminated reporta of the Higher Appellate Court and Supreme Court of Cassation jurisprudence on sentencing in war crime proceedings for judges’ prosecutors and lawyers. |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |

| 1.4.3. Ensure equal treatment of suspects, including in cases of high level officers allegedly involved in war crimes; IBM: Serbia provides an initial track record of investigation, prosecution and adjudication of a higher number of cases including against high level suspects as well as of cases transferred from ICTY to Serbia |  |  | Suspects – irrespective of their (former) rank or grade or current occupancy - are treated equally before the court both in terms of sentencing as well as in terms of the speed of bringing their cases forward. |  | - The number of new cases against high level officials; - The number of resolved cases against high level officials; - Positive evaluation in the report of the ICTY Chief Prosecutor and President to the Security Council; - Positive evaluation in the reports from relevant international and non-governmental organizations. |
| --- | --- | --- | --- | --- | --- |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.4.3.1. | Monitoring the effective implementation of the National Strategy prosecution of war crimes (2016-2020). | -Working group established by the Government of Serbia, comprised of representatives of the institutions with jurisdiction in war crimes and academic community -Experts and civil society - Government of the Republic of Serbia | Continuously | Budget of the Republic of Serbia | Number of quarterly made reports on the implementation of the National Strategy for prosecution of war crimes Number of recommendations for improving the procedure on war crimes Positively assessed findings from the Report by the EU and CSOs that prepare alternative reports |
| 1.4.3.2. | Establishment of the working group and elaboration of an analysis of the results achieved and defining further steps in the processing of war crimes | Working group of the Ministry of Justice | I quarter of 2021 | Budget of the Republic of Serbia | Working group established An analysis of the achieved results in the implementation of the National Strategy for the Prosecution of War Crimes and defining further steps |
| 1.4.3.3. | Monitoring the Implementation of the Prosecutorial Strategy for the Investigation and Prosecution of War Crimes in the Republic of Serbia 2018 - 2023 | Prosecutor for war crimes Collegium War Crimes Prosecutors Office | Quarterly | Budget of the Republic of Serbia | Analysis made for quarterly evaluations of the Prosecutorial Strategy Republic Public Prosecutor Office Annual Reports on the Application of the Prosecutorial Strategy |

| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| --- | --- | --- | --- | --- | --- |
| 1.4.4. Step up security of witnesses and informants and improve witness and informant support services; IBM: Serbia strengthens its investigative, prosecutorial and judicial bodies including ensuring a more proactive approach and the confidentiality of investigations, providing for training for new and current staff members, improving its witness protection and victim support system and ensuring victims' rights and access to justice without discrimination |  |  | Security of witnesses and informants has been stepped up and support services for witnesses and informants have been improved. |  | - The number of witnesses in witness protection program and increased number of witnesses willing to appear in the war crime cases without protection; - Positive Annual progress report on the Republic of Serbia issued by the European Commission concerning the level of security of witnesses and informants and concerning functioning of support services for witnesses and informants; - Decreasing number of instances were witnesses status and information about them is put in jeopardy or publicly revealed; - Positive evaluation in the reports from relevant international and nongovernmental organizations. |
| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| 1.4.4.1. | Analysis of current practice in the implementation of Article 102, paragraph 5 of the Criminal Procedure Code in order to identify existing needs for amending the Article and better protection of witnesses. and analysis on the implementation and results achieved of the Law on Protection Programme for Participants in Criminal Proceedings with conclusions and recommendations for possible changes to the Law in order to improve protection system | Sector working group established by the Minister of Justice, which encompass representatives of following institutions: Ministry of Justice, War crimes Prosecutor’s Office, Higher Court in Belgrade - WPU, Ministry of Interior-Unit for Witness Protection |  | Budget of the Republic of Serbia | Prepared analysis of current practice in the implementation of Article 102, paragraph 5 of the Criminal Procedure Code in order to identify existing needs for amending Article and better protection of witnesses. Prepared analysis on the implementation and results achieved of the Law on Protection Programme for Participants in Criminal Proceedings with conclusions and recommendations for possible changes to the Law in order to improve protection system |
| 1.4.4.2. | Activities aimed at establishing and improvement of the service for the support and assistance to witnesses and victims national wide network, based on results of the previous analyses, and taking into account already established services for the support and assistance to victims in courts and public prosecutor’s offices. (AP Ch. 24: 6.2.11.8, 6.2.11.10. and AP Ch: 23: 3.7.1.21.) | -Ministry of Justice -High Judicial Council -State Prosecutorial Council - Courts - PPO | Continuously, | Budget of the Republic of Serbia- | The service for the support and assistance to witnesses and victims national wide network, established and being improved, based on results of the previous analyses, and taking into account already established services for the support and assistance to witnesses and victims in courts and public prosecutor’s offices. |
| 1.4.4.3 | Adopt adequate implementing laws to effectively implement the change of identity as protective measure for witnesses | - Ministry of Justice and all relevant state organs that have any jurisdiction over the issue - War Crimes Prosecutor’s Office In cooperation with the Service for the support to victims and witnesses |  |  | Relevant laws needed to implement the change of identity as a witness protection measure amended. |
| 1.4.4.4. | Further capacity development and filling in the positions of psychologists in the WCP to deal with victims and witnesses when there is a need, in accordance with the implementation of the Prosecutorial Strategy for the Investigation and Prosecution of War Crimes in the RS | WCP |  |  | Working positions of psychologists filled in |
| 1.4.4.5. | Improving administrative capacities of the Ministry of Interior’s Witness Protection Unit through training. (Link with activity Chapter 24. 6..2.11.5). | - Ministry of Interior Witness Protection Unit, through ) through EU Project on Cooperation in Criminal Justice: Witness protection in the fight against serious crime and corruption (WINPRO II) implemented with NI-CO (Northern Ireland) -Ministry of Interior Administration for | Continuous | Budget of Republic of Serbia | Improved administrative capacities of the Ministry of Interior’s Witness Protection Unit through training. |

|  |  | education, training, specialisation and science for continuous training -War Crimes Prosecutor’s Office -Ministry of Justice -Higher Court in Belgrade, War Crime Chamber |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1.4.4.6. | On the basis of previously performed analysis, amend the Rulebook on internal systematization and job classification in the Ministry of Interior which refers to the activities and organization of the Unit for witness protection and implement measures in line with the amended Rulebook. (Link with activity Chapter 24. 6.2.11.3.) | -Ministry of Interior |  | Budget of the Republic of Serbia | Amended Rulebook on internal systematization and job classification in the Ministry of Interior which refers to the activities and organization of the Protection Unit and measures effectively implemented.. |
| 1.4.4.7. | Adoption of the National Strategy for the Promotion of Victims' Rights and Witnesses with the accompanying Action Plan | Ministry of Justice Ministry of Interior High Judicial Council State Prosecutorial Council Supreme Court of Cassation RPPO |  | Budget of the Republic of Serbia | National Strategy and the related Action Plan adopted |
| 1.4.4.8. | Full implementation and regular monitoring of the implementation of the National Strategy for the Promotion of Victims' Rights and Witnesses with the accompanying Action Plan, especially strong procedural guarantees for victims of war crimes | Ministry of Justice Ministry of Interior High Judicial Council An amended legal framework concerning the criteria and criteria for additional training of public prosecutors The prescribed criteria for additional training Supreme Court of Cassation RPPO | Continuously | Budget of the Republic of Serbia | The Coordinating Body for Victims and Witnesses support has been established and regularly meets. Reports on the implementation of the Strategy and the Action Plan are periodically drafted. |
| 1.4.4.9. | Establishing a network of services nationwide to support victims, witnesses and injured parties in the investigation and all stages of the criminal proceedings. | Ministry of Justice Ministry of Interior Supreme Court of Cassation RPPO High Judicial Council State Prosecutorial Council |  | Budget of the Republic of Serbia | A network of support and assistance services for witnesses and victims established at the national level. |
| 1.4.4.10.. | Conduct training of judges, public prosecutors and police officers on the application of minimum standards on the rights, support and protection of victims in accordance with Article 25 of Directive 2012/29 / EU | Judicial Academy | Continuously | Budget of the Republic of Serbia | Conduct regular trainings of judges, public prosecutors and police officers Number of trainings planned Number of trainings held Number of participants - trained persons |
| RECOMMENDATION FROM THE SCREENING REPORT |  |  | OVERALL RESULT |  | IMPACT INDICATOR |
| 1.4.5. Ensure confidentiality of the investigation including witness and informant testimony. IBM: Serbia strengthens its investigative, prosecutorial and judicial bodies including ensuring a more proactive approach and the confidentiality of investigations, providing for training for new and current staff members, improving its witness protection and victim support system and ensuring victims' rights and access to justice without discrimination |  |  | Investigations are confidential including witness and informant testimony. |  | 1. Positive reports to the Security Council submitted by the Chief Prosecutor and President of the International Tribunal for the Prosecution of Persons Responsible for Serious Violations of International Humanitarian Law Committed in the Territory of the Former Yugoslavia since 1991; 2. Positive evaluation issued in Annual progress report on the Republic of Serbia by European Commission concerning improvement of Constitution’s provisions |

| ACTIVITIES |  | RESPONSIBLE AUTHORITY | TIMEFRAME/DEADL INE | FINANCIAL RESOURCES | RESULT |
| --- | --- | --- | --- | --- | --- |
| 1.4.5.1. | Organizing round tables and lectures for the members of Ministry of Interior (War Crime investigative Service and Witness protection Unit) on the subject of „Basic communication with media“. | -War Crimes Prosecutor’s Office -Ministry of Interior | Continuously | Budget of the Republic of Serbia | Round tables organized and lectures delivered. |
| 1.4.5.2. | In line with the provisions of the National Strategy (activity 1.4.1.1.) assess confidentiality rules and their respect within relevant institutions, amend them where needed and strengthen control over implementation | -War Crimes Prosecutor’s Office | Continuously | Budget of the Republic of Serbia | Confidentiality rules and control over their implementation improved in line with the provisions of the National Strategy from activity 1.4.1.1. |

Institutions and bodies represented in the Coordination Body shall be as follows: Ministry of Justice, Negotiation Group for Chapter 23, Ministry of European Integration, Ministry of Interior, Ministry of Public Administration and Local Self Government, Ministry of Finance, Office for the Human and Minority Rights, Supreme Court of Cassation, Republic Public Prosecutor’s Office, High Judicial Council, State Prosecutorial Council, Judicial Academy, War Crime Prosecutor’s Office, Anticorruption Agency, Ministry of Health, Ministry of Science, Education and Technology,  Ministry of Labour, Employment, Veteran and Social Affairs, Office for Cooperation with Civil Society, Chamber of Public Enforcement Officers, Chamber of Notaries, Commissioner of Public Importance and Personal Data Protection, Ombudsman, Commissioner for Gender Equality.